## Schedule of Works
Item | Work Required | Quantity | Unit | Rate | Tender | Contract | VALUATION 01 |  | VALUATION 02 |  | VALUATION 03 |  | VALUATION 04 |  | VALUATION 05 |  | VALUATION 06 |  | VALUATION 07 |  | FINAL ACCOUNT
[7 empty] | 23.04.2018 |  | 21.05.2018 |  | 18.06.2018 |  | 16.07.2018 |  | 13.08.2018 |  | 17.09.2018 |  | 10.10.2018 |  | 26.11.2018
| SECTION 3 - SCHEDULE OF WORKS | [5 empty] | % | £ | % | £ | % | £ | % | £ | % | £ | % | £ | % | £ | % | £
1 | GENERAL
Tender Submission Allowances
1.01 | The following schedule of works is to be read in conjunction with all other sections and appendices of the main contract specification of works and all reports, drawings, product data sheets and schedules provided. |  | Item |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
1.02 | The Contractor should allow for including the whole of the works in one phase, in accordance with best building practices, guidance and regulations and to the full satisfaction of the Employer/Contract Administrator, where specifically described in the scope or not. |  | Item |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
1.03 | The Contractor shall enter a lump sum price against each of the items within the Schedule of works. Such sum shall include for all Builders Works In Connection (BWIC) with the works including but not limited to; cutting away, making good, joining new to existing and other labours, plugging, preparation of surfaces/substrates and supplying and fixing of all sundry items. |  | Item |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
1.04 | The contractor shall make all provisions within their individual pricing for assessing the working areas. No extra costs will be entertained by the employer for failure to do so. |  | Item |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
1.05 | Provisional Sums (PS) or Provisional Quantities (PQ) have been provided against some items throughout the schedule of works. These are only intended as a guide to the tenderer when pricing the particular items. Such quantities will not form part of the contract and will only be adjusted where the item is marked provisional or the quantity noted as a provisional quantity and shall not be executed without prior written agreement from the Contract Administrator. |  | Item |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
1.06 | Design
1.07 | The structural Engineering design and installation for this project is detailed and provided within section 4 'John Plumber Partnership structural Engineering Calculations' document. The contractor is to provide all required structural technical design submittals to the Contract Administrator and the consulting Structural Engineer for approval prior to installation. |  | Item
1.08 | The mechanical and electrical design and installation for this project forms part of the Contractors Design portion (CDP) under the JCT Contract. The CDP for all the M&E items of work are detailed and provided within section 5 'Building Services Consultants Design Specification Overview' document. The contractor is to provide all required M&E technical design submittals to the Contract Administrator and the consulting Mechanical and Electrical Engineer for approval prior to installation. The contractor is required to refer to the relevant Mechanical and Electrical sections within this specification for pricing. |  | Item |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
1.09 | Contractor to provide the following JCT collateral warranties for the works as part of the JCT Intermediate Contract with Contractors Design 2016. |  | Item
Samples
1.1 | The Contractor shall provide sample pallets of all paint colours and any other material products / finishes for approval as may reasonably be required by the Contract Administrator, prior to the any expenditure of any monies. |  | Item |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
Site Management
1.11 | The Contractor is to employ a full time and qualified site foreman / manager with a working mobile telephone during the course of the works. The foreman will be responsible for the smooth running of the works. The site manager should be based on site during normal working hours and must be contactable at all times. |  | Item |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
1.12 | Whilst the premises will not be occupied for the duration of the works, it should be noted that works will be carried out in close proximity to the general public. A high level of workmanship and overall method undertaking these works is expected at all times together with an exceptional level of behaviour and noise. No smoking is permitted on site and at anytime. |  | Item |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
Site Access & Security
1.13 | The Contractor shall allow for gaining all necessary Licences in respect of scaffolding, storing skips, gaining access etc., for the works and shall provide the Contract Administrator with copies of the relevant approvals prior to commencement of the works. This includes the submission of any required applications to the Local Authority / Highways Agency. |  | Item |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
1.14 | The Contractor shall allow for ensuring safe and adequate escape from the building, via the fire escape routes, at all times throughout the works. |  | Item |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
1.15 | The Contractor is to include for supplying plant and other equipment necessary to facilitate access for the complete and proper execution of the works. |  | Item |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
1.16 | Allow to put in place and maintain security provisions to the existing property to ensure that any unauthorised access is not gained to the site. The existing property is to be left safe and secure at the end of each working day. Provide Heras fencing, barriers or screens to the site perimeter where required to prevent unauthorised access and to maintain escape routes at all times. |  | Item |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
Scaffolding / Mobile Access Towers
1.17 | The contractor is to price here for designing, providing, erecting maintaining and, removing on completion, any scaffolding system required and necessary for the proper execution of the works. Scaffolding should be suitable for carrying out inspections of all specified and provisional work, including work by contractors, sub contractors and any other persons employed on or administering the works. All access systems are to comply with all statutory requirements and adhere to the relevant standards (BSEN) as well as any other safe access method as determined suitable by the Contractor to allow for the full and proper execution of the works. Attention is drawn to the following which are to be allowed for and included for within the price: |  | Item |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
● | The contractor is to investigate and undertake any necessary works in relation to shoring or temporary reinforcement of the pavement lights and vaults. If temporary shoring is impractical, the contactor is to include alternative measures within their scaffold design. |  | Item |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
● | The Contractor will be required to provide all sketches drawings and calculations for the proposed scaffold designs to the Principal Designer / Contract Administrator no later than 2 weeks from commencement o the works for approval prior to installation. |  | Item |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
● | Any required scaffolding required to complete the works is to be designed and erected so as to be independent from the building. Fixing directly into the building fabric is not permitted under any circumstances and tying to the exterior through open windows, is to be agreed withe Contract Administrator prior to any works commencing on site. |  | Item |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
● | Prior to erecting the scaffold, the contractor is to provide a Schedule of Condition and inform the CA of any existing damage to elevations and basement areas. Any damage not recorded and picked up will be the contractors liability to remedy at their cost. |  | Item |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
● | If required, the contractor is to utilise Hilti resin fixing rods for fixing scaffolding to the building facade or similar approved universal fixing method so fixing points can reused in the future to minimise damage to the brickwork and cladding. Upon striking of scaffold, the contractor is to remove rod and the resin anchor can stay in place for future use. Holes are to be capped off at completion of work with a stone coloured plastic cap fitting into the permanent fixing or cover cladding panels. CA to approve cap samples prior to contractor placing orders. |  | Item |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
● | It is essential that the number of scaffolding standards are kept to a minimum and are positioned such that no doors and windows are obstructed in any way. |  | Item |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
● | Protection of all substrates upon which the scaffolding standards and loading points bare on to with use of protective sole / floor plates. |  | Item |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
● | All scaffolding is to be fully enclosed with debris netting / monoflex. Allow to provide new branded monoflex sheeting to the scaffolding for all lifts of scaffolding (approximately at the top middle and bottom of the elevation). The contractor will be expected to keep the scaffold sheeting in a good condition ensuring that it is clean and in tension at all times. |  | Item |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
● | Protection to all floors, pavement lights especially where open and susceptible to water ingress, signs, lighting and any other fixings of fixings services especially when striking and erecting the scaffolding. Include for making good all damaged caused due to the scaffolding. The contractor should note that the scaffolding cannot be fixed in a destructive method and other suitable restraining methods are to be adopted. |  | Item |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
● | Protection of all existing public, private and emergency routes. Access equipment must not hinder access or egress from the building. |  | Item |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
● | Physical protection from any falling debris or run-off of liquids over doorways and entrances and along the length of scaffold. |  | Item |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
● | Scaffold shall be enclosed and have securely fixed fans as appropriate to protect persons and property from falling debris. |  | Item |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
● | When scaffolding is being erected, altered or dismantled, below passers and general public must be excluded from the vicinity by hoardings or other barriers. Banks men must be deployed at ground level to ensure that such passers by are safely directed away from the area whiles such works are in progress. Signs must be in place at pavement level warning that works are in progress above. |  | Item |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
● | Standing scaffolding shall be left in position until no longer required. The Contract Administrator shall be given notice in writing of not less than one week of the removal of any scaffold. |  | Item |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
● | The Contractor will be required to make good any damage caused by the erection and dismantling of the scaffolding. Ensure that all roof lights are fully protected prior to the erection or dismantling of scaffolding. |  | Item |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
● | The Contractor shall allow for providing adequate “wet paint” signage at all ground floor, pedestrian areas and for providing security and pedestrian lighting and painted plywood timber casings securely fixed to the vertical standards up to a minimum of 3 m above ground floor level, where scaffold is provided. All hoarding is to be constructed from external quality ply and to incorporate a skirting and capping detail. Hoarding is to be fully prepared for painting and painted in one coat of undercoat and 2 no coats of Dulux external grade topcoat. |  | Item |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
● | Include for undertaking all scaffolding in full accordance with the Local Authority and County Council requirements. The contractor is to obtain necessary road closure consents and scaffold licences from the Local Authority in respect of any scaffolding over and affecting the Highway and/or Highway footpath. |  | Item |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
● | On completion of each section of scaffolding and prior to the works commencing on that scaffold, the CA must be provided with a copy of a recognised and valid suitability and handover Certificate. |  | Item |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
1.18 | The Contractor is reminded of their statutory duty of care to scaffold users, and other persons who may foreseeably be affected by the scaffolding during its erection, use or dismantling. The scaffolding shall comply in all respects with the relevant statutory requirements, including: a) The Factories Act 1961 b) Health & Safety at Work Act 1974 c) BS 5973 (Scaffolding) d) The Construction (Health, Safety and Welfare) Regulations 1996. |  | Item |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
2.19 | The scaffolding must not be struck or be moved until the CA has approved the works and in the event of this being so, the Contractor shall re-erect the scaffolding at its own expense. |  | Item |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
● | Please note that your chosen sub contractor must be able to demonstrate competency and experience of working on projects in similar environments to this project i.e. Listed buildings and busy high streets and must have an excellent health and safety track record. The scaffolding sub contractors must be members of the National Access and Scaffolding Confederation (NASC) and evidence of membership must be submitted with the Principal Contractor’s tender return documents. All scaffolding sub contractors will be required to meet the core criteria for demonstration of competence in accordance with the Construction (Design and Management) Regulations 2015 Approved Code of Practice. Including demonstrating its competency to the Principal Designer / CA that they meet the above criteria in full. Please advise on the name of your chosen scaffolding sub contractor and demonstrate previous experience: Scaffolding Sub Contractor: Tel: Address: |  | Item
Temporary Services & Supply
1.2 | The contractor is to make safe all services as required prior to starting on site. The Contractor is to provide and maintain all necessary temporary services required to undertake the works. |  | Item |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
1.21 | Mains water may will be available for use on site although the contractor is entitled to use the mains water supply if available. Where a separate water supply is required the contractor is to make all arrangements and applications for connections. |  | Item |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
1.22 | Mains electric will be directly available on site although the contractor is entitled to use the main electricity supply if available. Where a separate power supply is required the contractor is to provide their own generator(s), temporary supply, where necessary and make all arrangements and applications for connections. |  | Item |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
1.23 | The mains gas supply is being isolated by the client ahead of the works.
Health, Safety & Welfare
1.24 | The contractor is to comply with and fulfil their duties as a designer under the Construction (Design and Management) Regulations 2015 at all times during the project. |  | Item |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
1.25 | The Contractor is to allow to provide a detailed construction phase health and safety plan, keep all necessary site registers and other H&S information on site throughout the course of the works, and provide the Principal Designer / Contract Administrator with a detailed operation and maintenance manual for the works upon completion. |  | Item |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
1.26 | The Contractor is to prepare and provide specific risk assessments and method statements (RAMS) in connection with the below works to the Principal Designer / Contract Administrator prior to commencement of works on site. All RAMS and safe working practices in relation to COVID-19 must also be included within the contractors RAMS. |  | Item |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
1.27 | The contractor is to make all due allowances to comply with the building's house rules if required, including arranging any permits to work, adhering to any noisy working hours, use permitted access routes during business hours, and access pass requirements. |  | Item |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
1.28 | The Contractor is to allow for welfare facilities offsite and must allow for their own accommodation and welfare facility provisions. All proposals for welfare facilities must be submitted to the Principal Designer / Contract Administrator at least 1 week prior to the commencement of works on site and detailed within the construction phase health and safety plan. |  | Item |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
1.29 | The contractor is not to store any materials, tools or equipment on site without prior approval from the Contract Administrator. Should this be required, all materials, tools and equipment must be kept in a secure location with any flammable material stored within a secure fireproof box. The contractor is to confirm any storage location with the Principle Designer / Contract Administrator prior to works commencing on site. |  | Item |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
1.3 | The contractor is to provide copies of all current insurance certificates and safe contractor scheme certificates as part of their tender return submission. |  | Item |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
Deleterious Materials
1.31 | The contractor is required to review the Demolition and Refurbishment Asbestos Survey report and Asbestos Register provided within the Pre-Construction information pack and to act in accordance with the Control of Asbestos Regulations 2012 in relation to the works on site. |  | Item |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
1.32 | Allow to remove, encapsulate and professionally clean all identified asbestos containing materials (ACM'S) within the property as identified and recommended within Demolition and Refurbishment Asbestos survey report. All works are to be undertaken using an appropriately qualified and licensed Asbestos removal contractor. Allow for replacement for all items with modern equivalent as maybe required. Contractor to provide all asbestos waste disposal certificates. |  | Item |  |  | 5000 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 5000
1.33 | If any suspected deleterious materials are found, the contractor must follow safety procedures, cease work and inform the Client & Contract Administrator immediately. |  | Item |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
Temporary Protection
1.34 | Whilst the work proceeds the Contractor shall allow for providing, and maintaining as necessary, temporary protection to all existing internal and external surfaces, components, fixings and fittings within the building. The Contractor shall allow for all temporary screens, dust sheets, tarpaulins and other measures necessary to protect the building and its features. This includes but is not limited to providing adequate protection to all ceiling and wall plasterwork, windows, doors, paintings, fire places, balustrades, floor boards/stones and all other items of special architectural interest or value. |  | Item |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
Site Clearance & Waste Management
1.35 | The Contractor is to ensure that the site is cleared on a regular basis as the work proceeds. The contractor is to allow for all required waste removal and skip hire and undertake a full and thorough professional clean of site following completion of the works. |  | Item |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
1.36 | The Contractor is to provide waste consignment certificates for the disposal of all waste material removed from site. These are to be submitted to the Contract Administrator at Practical Completion. All waste is to be disposed at licensed waste sites and dealt with in accordance with statutory requirements. |  | Item |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
Limitations
1.37 | The Contractor will be required to comply fully with any specific limitations on the working sequence determined by the Principal Designer / Contract Administrator. It is suggested that the Contractor discuss the requirements with the Principal Designer / Contract Administrator as part of the Tender process. |  | Item |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
Snagging / Completion
1.38 | In order to avoid the property being handed over prematurely, the contractor shall carry out an internal snag of the works and rectify any defective work. Works to all external and internal areas are to be completed and cleaned (i.e. ready for handover) before they are offered to the Contract Administrator for inspection. This inspection is required at least one week prior to the proposed practical completion and formal handover of the site. |  | Item |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
1.39 | The Contract Administrator and/or employer's representative shall make one inspection of the works prior to Practical Completion to compile a list of incomplete or defective work which the contractor will be in attendance for. Any outstanding works will be provided to the contractor and are to be completed prior to Practical Completion. |  | Item |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
Contingency
1.4 | Provisional Sum: Allow the contingency sum of Fifty Thousand Pounds (£50,000.00) for additional unforeseen works. Sum only to be expended upon formal written instructions from the Contract Administrator via a contract instruction. | 1 | PS | 50000 | 50000 | 20000 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 20000
2 | DEMOLITION / STRIP OUT
2.01 | Carefully isolate all supplies, strip out and cart away from site including associated fixings, fittings and service media back to source to the following; |  | Item |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
● | Existing dumb waiter to the basement. |  | Item
● | Existing keg pump and associated fixings and fittings to the basement. |  | Item
● | Existing timber staircase to the basement including all associated fixings and fittings. |  | Item
● | Existing internal and external surface mounted loose, defective and redundant service media conduits, fixings and fittings (to include all roof areas and elevations throughout). |  | Item |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
● | Existing external and internal walls as per Drawing 8341,B04A - Existing Building Demolition Plan |  | Item |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
● | Existing external and internal doors as per Drawing 8341,B04A - Existing Building Demolition Plan |  | Item |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
● | Existing ground floor fire place's to the Dining area 2 and Kitchen including all associated fixings and fittings. |  | Item |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
● | Existing internal and external fixed and loose chattels including but not limited to furniture, equipment, surface mounted fixings and fittings, signage, mirrors, racking, shelving, redundant fire fighting equipment etc. Contractor to ensure the building is clear and ready to commence works. |  | Item |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
● | Remove existing wall tiles finish back to substrate throughout the ground and first floor including all associated fixings and fittings. |  | Item |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
● | Remove existing WC fittings to the ground and first floor including all associated fixings and fittings. |  | Item |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
● | All existing windows as per Drawing 8341,B04A - Existing Building Demolition Plan with reference to the 'Window Key' |  | Item |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
● | Existing pitches roof covering back to roof structure including all coverings, battens, felts, flashing and fixtures and fittings. |  | Item
● | Existing flat roof and dormer coverings |  | Item |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
● | Existing guttering, downpipes and hoppers throughout all elevations.
● | Existing facia and sofit boards throughout all elevations. |  | Item |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
● | Existing stone copping stones to parapet wall.
● | Existing damaged boundary fence |  | Item |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
● | Existing chattels, fixings and structures to the rear courtyard. |  | Item |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
● | Existing external joinery & metal work including but not limited to bollards, furniture, concrete steps. |  | Item
● | Existing Mechanical Services installations and service media back to source in accordance with 'Building Services Consultant' M&E Design specification Overview' Document. |  | Item |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
● | Existing Electrical installations and service media back to source in accordance with Building Services Consultant' M&E Design specification Overview' Document. |  | Item |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
3 | SUB-STRUCTURE AND SUPER STRUCTURE
Generally
3.01 | To all new and existing sub-structure and super structure works: Contractor to supply and install all required structural works strictly in accordance with the 'John Plumber Partnership Structural Engineering Calculations and Details' Document (Issue B2). Should the Contractor have any specific queries in relation to the structural design and specification they should seek guidance from the Structural Engineer prior to undertaking any works. Contractor to provide cost breakdown for each structural element below. For the avoidance of doubt the below structural works cost summary schedule is for cost collection and pricing purposes only. |  | Item
3.02 | STRUCTURAL ENGINEERING STATEMENT(B2) |  | Item
3.03 | TEMPORARY STABILITY(B2) |  | Item
3.04 | PERMENANT STABILITY |  | Item
3.05 | DISPROPORTIONATE COLLAPSE |  | Item
3.06 | CONSTRUCTION DESIGN & MANAGEMENT (CDM) REGULATIONS |  | Item
3.07 | CONTRACTOR DESIGN ELEMENTS |  | Item
3.08 | INFORMATION UPON WHICH THE DESIGN IS BASED |  | Item
3.09 | ANALYSIS AND DESIGN COMPUTER PROGRAMMES |  | Item
3.1 | REFERENCES |  | Item
3.11 | ASSUMPTIONS |  | Item
3.12 | DIMENSIONS |  | Item
3.13 | SEQUENCE OF CONSTRUCTION (B2) |  | Item
3.14 | STRUCTURAL STEELWORK SPECIFICATION |  | Item
3.15 | MASONRY AND ANCILLARY COMPONENTS SPECIFICATION |  | Item
3.16 | STRUCTURAL (LOOSE CUT) TIMBER SPECIFICATION |  | Item
3.17 | GROUND BEARING GROUND FLOOR SLAB SPECIFICATION |  | Item
3.18 | CONCRETE SPECIFICATION(B2) |  | Item
3.19 | FOUNDATION SPECIFICATION |  | Item
3.2 | REINFORCEMENT SPECIFICATION |  | Item
3.21 | APPENDIX A - JOHN PLUMBER PARTERNSHIP DRAWINGS |  | Item
3.22 | APPENDIX B - CLIENT SUPPLIED INFORMATION |  | Item
3.23 | SPPENDIX C - STRUCTURAL ENGINEERING DESIGN CALCULATIONS |  | Item
3.24 | Provisional Sum: Allow Provisional Sum of Ten Thousand Pounds (£10,000.00) for additional unforeseen foundation excavation & installation works. Sum only to be expended upon formal written instructions from the Contract Administrator via a contract instruction. | 1 | PS |  | 10000
4 | ROOF
| Existing Roof | [5 empty] | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
4.01 | To the existing timber roof structure: Allow to undertake woodworm treatment survey and instruct suitable woodworm treatment as recommended by the treatment survey. Contractor is to ensure all presence of wood worms have been effectively treated and all necessary certification and documentation is forwarded to the Contract Administrator. |  | Item
4.02 | To the existing pitched roof: Remove all existing roof coverings, battens and underfelts taking the roof back to timber structure, setting aside all clay tiles to be reused where possible. Supply and install new insulation boards (Kingspan Kooltherm K107) between rafters with eaves ventilation strips (Sandtoft Eaves Vent 10mm or similar approved) installed to provide a minimum of 50mm ventilation gap over insulation. Install breathable membrane underfelt (Kingspan Nilvent or similar approved) over the rafters with tanalised sawn timber battens to BS5534 fixed vertically and then counter battened horizontally at no more than 600mm apart. Install clay tiles (previously set aside) with ridge tiles (half round Marley ridge tiles) mechanically fixed with twice nailed mechanical H fixings installed between each ridge tile. Include for galvanised hip irons to all external corners. Clay tiles to be fixed using two nails to secure each plain tile in at least every fifth course complete with suitable mortar mix to secure ridge and hip tiles including all associated mortars (1:3 cement: sand, with plasticizing admixtures) fixings and fittings. Where tiles are damaged they are to be replaced like for like to match existing. All specified products to be installed in accordance with the manufacturers recommendations including all associated fixings and fittings. |  | Item
4.03 | The Contractor is to allow for replacing 25% of clay tiles here. |  | Item
4.04 | To all roofs: Allow for providing temporary weatherproofing to the existing structure with tarpaulins or similar to be suitably fixed to the retained roof structure whilst the roof area is stripped in order to ensure minimal water ingress occurs to the existing retained structure. Arrange for Contract Administrator/Structural Engineer to undertake full inspection of exposed roof timbers to identify any repairs required to the roof structure prior to new works. |  | Item
4.05 | To the existing roof voids and eaves: Supply and install mineral wool insulation (ROCKWOOL Roll, Twin roll and Roolbatt) as per the manufacturers recommendations including all associated fixings and fittings. Insulation to be installed between ceiling joists then cross laid in 100mm layers to achieve a total thickness off 400mm. Care should be taken not to block any ventilation grills along the eaves. Upon completion of works the Contractor is to allow for carrying out all tests and provide certification to confirm that the loft insulation achieves a U-value rating of 0.11(W/m2K). |  | M2
[7 empty] | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
Extension Roof
4.06 | To the new extension roof primary steelwork. Supply and install new cold-rolled galvanised Z-purlins (Kingspan multibeam or similar approved) as per the manufacturers recommendations. The span direction, size and type and spacing of the Z-purlins is to be in accordance with 'John Plumber Partnership Structural Engineering Calculations and Details' Document. All specified products to be installed in accordance with the manufacturers recommendations including all associated fixings and fittings. Should the Contractor have any specific queries in relation to the structural design and specification they should seek guidance from the Structural Engineer prior to undertaking any works. |  | M2
[7 empty] | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
4.07 | To the new extension primary steel work: Further to the installation of the z-purlins supply and install new trapezoidal composite roof panels (Kingspan KS1000RW 135mm). Roof panels to be fixed to z-purlins as per the manufacturers recommendation including all associated trims, fixtures and fittings. All works to be in accordance with the 'John Plumber Partnership Structural Engineering Calculations and Details' Document. Should the Contractor have any specific queries in relation to the structural design and specification they should seek guidance from the Structural Engineer prior to undertaking any works. |  | M2
4.08 | To the proposed extension roof lights: Supply and install new powder coated (colour Traffic Grey RAL 7043) aluminium framed doubled glazed (toughened outer glass and laminated inner safety glass) Velux commercial roof lights (Velux Modular Rooflights - Linear light) complete with Rain sensor (WLA 331), Control unit (WCC103, WCC 310/320), Control switch (WSK102/103), blinds (Colour RMR 8805), Blind control wall switch (KLI 312) and prefabricated insulated timber upstands including all associated ironmongery, operating mechanisms, sealants, adhesives and fixings and fittings. All specified products to be installed in accordance with the manufacturers recommendations including all associated fixings and fittings. All works to be in accordance with drawing '8341,B05C - Proposed Site Layout Plan'. |  | Item
Flat Roof
4.09 | To the new flat roof: Further to the remove all of all existing coverings and timber joists supply and install Sika - Sarnafil, single ply PVC membrane in Lead grey (Sika colour No.9500) new flat roof complete with timber joists (47x 220mm C24 timber at 400 mm centres) notched and packed tight into the proposed steel work and hung from timber wall plate (47X220mm C24 Timber fixed to the existing masonry wall with H10 chemical anchors at every 200mm) on joist hangers with 22mm marine plywood decking (screwed to every joist at a maximum of 150mm centres around the perimeter of each board/300mm centres internal within each board) with a suitable vapour control barrier laid on the ply decking followed by a minimum of 130mm insulation (Kingspan Theraroof or similar approved) including all associated sealants, adhesives fixings and fittings. Contractor to allow for a minimum of 200mm upstand. All specified products to be installed in accordance with the manufacturers recommendations including all associated fixings and fittings. All works are to be in accordance with the 'John Plumber Partnership Structural Engineering Calculations and Details' Document. |  | M2 |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0
4.1 | To the existing bay window and dormer window flat roofs: Strip flat roof back to timber structure and supply and install new warm deck flat roof with Sika - Sarnafil, single ply PVC membrane in Lead grey (Sika colour No.9500) with 22mm marine plywood decking (screwed to every joist at a maximum of 150mm centres around the perimeter of each board/300mm centres internal within each board) with a suitable vapour control barrier laid on the ply decking followed by a minimum of 130mm insulation (Kingspan Theraroof or similar approved) including all associated sealants, adhesives, fixings and fittings. Contractor to allow for a minimum of 200mm upstand as per drawing and for PVC membrane to be dressed over parapet wall as per drawing. All specified products to be installed in accordance with the manufacturers recommendations including all associated fixings and fittings. All works to be in accordance with drawing '8341 - B06 - Proposed Ground and Basement Floor Plans'. |  | Item |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0
4.11 | To the existing painted timber facias and soffits: Further to the removal of the existing timber facias and soffits supply and install new white UPVC facias boards (Eurocell standard facia board) fixed directly to the rafter ends with timber fillets for additional support using 65mm fixings pins and white UPVC vented soffits (Eurocell 25mm Airspace Eurosoffit Board) including all associated trims, ends caps, panel joints, fixings and fittings. All specified products to be installed in accordance with the manufacturers recommendations including all associated fixings and fittings. |  | M2
4.12 | To all new and existing roofs: Supply and install new code 4 lead flashing to all new roof tile joints, ridge tiles and chimneys. All work to be carried out in accordance with the Lead Sheet Association best working practises and including all required and associated fixings and fittings. All specified products to be installed in accordance with the manufacturers recommendations including all associated fixings and fittings. |  | Lm
4.13 | To all new flat roofs: Contractor to allow for detailing flat roof covering to all upstands, Rainwater goods, drips, parapet walls and render as per drawings: - DT01 - FLAT ROOF UPSTAND DETAIL - DT02 - GUTTER DETAIL - DT03 - DRIP DETAIL - DT04 - PARAPIT WALL DETAIL - DT05 - RENDER DETAIL All specified products to be installed in accordance with the manufacturers recommendations including all associated fixings and fittings. |  | Item
[7 empty] | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0
Rainwater Goods
4.14 | To the next extension roof: Supply and install a new hidden ppc rainwater system in goosewing grey (Kingspan Industrial Highline Gutter) including but not limited to gutters, internal and external corners, stop ends, overflows, downpipes,, brackets, swan necks, elbows, shoes, collars and adapters including all associated fixings and fittings. All specified products to be installed in accordance with the manufacturers recommendations including all associated fixings and fittings. |  | Lm |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
4.15 | To the existing pitched roof and new flat roof: Supply and install new PVC-U deep flow rainwater system in black (Marley Plumbing & Drainage Solutions) including but not limited to gutters, internal and external corners, stop ends, overflows, downpipes,, brackets, swan necks, elbows, shoes, collars and adapters including all associated fixings and fittings. Contractor to allow for connecting all new RWG into existing underground drainage. All specified products to be installed in accordance with the manufacturers recommendations including all associated fixings and fittings. |  | Lm |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0
4.16 | To all rainwater goods and surface drainage services: Thoroughly clean, rod and jet wash all gutters, downpipes liner slot drains and gulley's and ensure running clear. Ensure that gutter joints are adequately sealed and water tight and free flowing upon completion of the works. |  | Item |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
5 | ELEVATIONS
5.01 | To all brickwork elevations throughout the property: Remove any debris undertake a professional deep clean to soiled facing brickwork ensuring all vegetation/moss growth and staining is removed from facing brickwork. |  | M2 |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
5.02 | Provisional Quantity: To the existing brickwork walls: Undertake localised repairs to remove damaged bricks and replace & repoint with new brick work to match existing including all associated fixings and fittings. Contractor to price for 30m2 of brickwork repairs here: ......................... Contractor to price for 30m2 of repointing here: .......................... |  | PQ
5.03 | To all new connections between existing old and new masonry walls throughout: Supply and install wall starters (Ancon Staifix Universal Wall Starter System) fixed to the existing masonry wall using the wall plugs, washers and screws provided in accordance with the manufacturers recommendations including all associated fixings and fittings. Wall starters are to be used for each individual skin of a masonry wall. |  | Item
5.04 | To all door and window openings: Supply and install new cavity closers (Kooltherm Cavity Closer or similar approved) cavity closers to be cut precisely to the opening width with the jambs overhanging the bottom of the closers by a minimum of 50mm including all associated fixings and fittings. All specified products to be installed in accordance with the manufacturerrs recommendations including all associated fixings and fittings. |  | Lm
5.05 | To the existing Window openings: Further to the removal of the existing windows supply and install new cavity wall infill with 100mm low density concrete blockwork (Thomas Armstrong - Insulite Concrete Block) inner and outer leaf with 75mm insulation board (Kingspan Kooltherm K108 Cavity Insulation board) fixed to the internal leaf with wall tie retaining clips ensuring a 25mm cavity void is left between insulation board and outer leaf including all associated mortar, 225mmcavity ties (Ancon Staifix RT2 - Type 2 fixed at no less than 2.5 per meter square 900mm horizontal x 450mm vertical centres) , fixings and fittings. New Infill must achieve improvement u-value of 0.3. As per the Building Regulations Part L. All specified products to be installed in accordance with the manufacturers recommendations including all associated fixings and fittings. All works to be in accordance with drawing '8241 - B10 - Ground Floor Wall Specification Plan'. |  | M2
5.06 | To the proposed extension: Supply and install new cavity wall with 100mm splitface concrete blockwork outer leaf and 100mm Medium density concrete blockwork (Thomas Armstrong - Insulite Concrete Block) inner leaf with 100mm cavity insulation (Kingspan Kooltherm K108 Cavity Insulation board) fixed to the inner leaf and 50mm cavity void between insulation board and outer leaf and including all associated mortar, cavity ties, fixings and fittings. New wall must achieve improvement u-value of 0.26. As per the Building Regulations Part L The contractor is to ensure the new cavity wall is tied to the steel columns using anco SDB Ties at maximum 225 vertical centres and tired in with the existing masonry wall using wall starters at a maximum of 225 vertical centres. All specified products to be installed in accordance with the manufacturers recommendations including all associated fixings and fittings. All works are to be in accordance with 'John Plumber Partnership Structural Engineering Calculations and Details' Document. |  | M2
5.07 | To the existing dormer window cheeks: Strip dormer cheeks back to structural timber stud. Remove existing tiling, trims, boarding, battens/counter battens and internal finishes. Supply and install 50mm (minimum) - 75mm insulation between existing timber studs (insulation to be install along the full length of dormer walls) and single layer of felt breather membrane on 18mm marine quality plywood complete with Accoya wood horizontal cladding with translucent finish on the vertical supporting battens and trims in accordance with the manufacturers recommendations including all associated fixtures and fittings. All specified products to be installed in accordance with the manufactures recommendations including all associated fixings and fittings. All works to be in accordance with drawing '8341 - B11 - First Floor Wall Specification Plan'. |  | M2
6 | EXTERNAL WINDOWS
6.01 | To the existing dormer windows: Undertake condition survey of all dormer window timber openings and strengthen existing timber frames where required to support new proposed aluminium framed windows including all associated fixings and fittings. |  | Item
6.02 | Provisional Sum: Allow provisional sum of £300.00 per dormer window for timber strengthening works including all associated fixtures and fittings as recommended by condition survey. | 4 | PS | 300 | 1200
6.03 | To window openings 1 -17: Supply and install new top hung vent aluminium framed polyester powder coated (colour RAL 9011)double glazed casement windows (AluK C70S Open Out Thermally Broken Window System) complete with trickle vents including all associated ironmongery, operating mechanisms, trims, sealants and fixings and fittings. All specified products to be installed in accordance with the manufacturers recommendations including all associated fixings and fittings. All works to be in accordance with drawing '8341,B20A - Window Schedule' & '8341,B06 - Proposed Ground and Basement Floor plans' 8341,B07 - Proposed First Floor Plan' On completion of the works the Contractor is to provide a 10 year insurance backed product and workmanship guarantee for the new windows including profiles, hardware and accessories. | 17 | No.
6.04 | To the existing dormer windows: Supply and install new code 4 lead flashing to the dormer window edges. All work to be carried out in accordance with the Lead Sheet Association best working practises and including all required and associated fixings and fittings. All specified products to be installed in accordance with the manufacturers recommendations including all associated fixings and fittings. |  | Lm
7 | EXTERNAL DOORS
7.01 | To all new doors: All door closers should be capable of operating with an opening force of no more than 30N, for the first 30° of opening, and 22.5° for remainder of swing. Ensure that all existing and relocated doors meet currently Building Regulations requirements in terms of fire-rating and suitability of ironmongery. Consideration must be made when selecting door frame colours to ensure contrasting effect in line with Equality Act requirements. |  | Item
7.02 | To door openings 1, 10 and 25 (Door Type 8) : Supply and install new 44mm thick 926x2060mm polyester powder coated (Colour RAL 9011) aluminium framed solid FD 30 door sets. Allow for fire rated(FR to match door) double glazed vision panel in accordance with The building Regulations 2010 - Approved Document K4/K5. Doors to be hung on 3 no. heavy duty single axix door hinges complete with fire and smoke seals including all associated fixings and fittings. All specified products to be installed in accordance with the manufacturers recommendations including all associated fixings and fittings. All doors to be installed in accordance with drawing '8341,B18 - Door Schedule'. | 3 | No.
7.03 | To door opening 2 (Door Type 9) : Supply and install new 44mm thick 926x2060mm polyester powder coated (Colour RAL 9011) aluminium framed FD 30 glazed door. Allow for fire rated (FR to match door) double glazed clear glazing in accordance with The building Regulations 2010 - Approved Document K4/K5. Door to be hung as per the manufacturers recommendations complete with fire and smoke seals including all associated fixings and fittings. All specified products to be installed in accordance with the manufactures recommendations including all associated fixings and fittings. All doors to be installed in accordance with drawing '8341,B18 - Door Schedule'. | 1 | No.
7.04 | To door opening 11 (Door Type 10) : Supply and install new leaf and a half 44mm thick 826/434x2060mm polyester powder coated (Colour RAL 9011) aluminium framed solid FD30 fire exit door. Allow for fire rated emergency exit push bar with shoot bolts in accordance with BS EN 179:2008. Doors to be hung as per then manufacturers recommendations and be complete with fire and smoke seals including all associated fixings and fittings. All specified products to be installed in accordance with the manufactures recommendations including all associated fixings and fittings. All doors to be installed in accordance with drawing '8341,B18 - Door Schedule'. | 1 | No.
7.05 | To door opening 2 (Type 9): Supply and install manifestation to glazed door in accordance with The Building Regulations 2010 - Approved Document K5.2 Section 7: Manifestation of Glazing including all associated fixings and fittings | 1 | No.
7.06 | To all external doors throughout: Supply and install ironmongery and signage to all doors including but not limited to push plates, pull handles, kick plates, overhead closers, door stops, door holders, door mounted coat hooks, mortice cylinder key locks, thumb turn operation to mortice cylinder on internal side, thumb turn privacy indicators and surface mounted signage including all associated fixings and fittings. All specified products to be installed in accordance with the manufactures recommendations including all associated fixings and fittings. All door ironmongery, signage and finishes are to be in accordance with drawing 'B341,B19 - Ironmongery Schedule'. The Contractor is to ensure that before any orders are place a sample board containing labelled samples of ironmongery and signage showing methods of fixing is provided to the Contract Administrator for approval. | 1 | Item
7.07 | To all lockable external doors throughout all elevations: supply 3no. sets of keys to all locks for all security and access doors to the property. | 4 | No. |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
8 | EXTERNAL AREAS
Hardstanding's
8.01 | To the tarmac car park areas and concrete hardstanding's throughout the site: Remove rubbish and debris and thoroughly brush clean down surface. |  | M2 |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
8.02 | To the front entrance of the building: Supply and install subframe on pad supports at 450mm centres with noggins. Supply and fit new Millboard lasta-grip anti slip composite decking in golden oak finish raised decking complete balustrades, handrails, stepped and ramped access in accordance with The Building Regulations - Approved documents K and M. Allow for all necessary supports and subframe recommended by the manufacture including all associated fixtures and fittings. Contractor to allow for access hatch for beer hatch below proposed decking. All works to be in accordance with drawing '8341,B05C - Proposed Sit Layout Plan'. |  | M2 |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
8.03 | To the proposed car park area: Remove existing tarmac layer back to existing sub-base and supply and install new 190mm toping course to new carpark. Allow for any adjustments to existing manholes, gullies as necessary to ensure correct fall to rainwater gullies. The proposed build up of the car park is as follows: 40mm Thick close graded asphalt concrete 60mm Thick dense binder course (20mm coarse aggregate) 90mm Thick dense base Existing sub-base All works to be in accordance with drawing '8341,B05C - Proposed Sit Layout Plan'. |  | M2 |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
8.04 | To the proposed car park area: Thoroughly prepare and apply new thermoplastic lining. Allow for White line marking to standard car parking bays and yellow line marking to accessible parking spaces including wheel chair symbol and hatched areas. All works to be in accordance with drawing '8341,B05C - Proposed Sit Layout Plan' |  | Lm |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
8.05 | To all new soakaways: Allow to excavate as necessary and form new soakaway, minimum size 2m x 2m x 1m and to be positioned a minimum 5m from the existing building or new extension and other adjacent buildings. Positions to be approx. as detailed on the drawings. Allow to connect all new surface water drainage into new soakaways. New soakaways to be formed Wavin Aquacell Eco Modular units. These units to be wrapped with geotextile membrane. Base of the soakaway is to be covered with pea gravel to a depth of approx. 100mm and hole to be back filled with similar pea gravel to a minimum depth of 150mm. Ensure all relevant connections made to soakaway and back fill with top soil to bring levels back to match existing. All works to be in accordance with drawing '8341,B05C - Proposed Sit Layout Plan' |  | Lm
8.06 | To all new and existing below surface drainage: Allow for all necessary excavation and provide and install complete below ground foul and surface water drainage system to the layout shown on the drawings and as detailed. The below ground drainage installation to include for all new inspection chambers, suitable covers, frames, gullies, linear drainage channels and pipework etc. to complete the installation. All new drainage installation to be strictly in accordance with current Building Regulations. All works to be in accordance with drawing '8341,B05C - Proposed Sit Layout Plan' |  | Lm
8.07 | To all new and existing below and surface drainage: Allow for cleaning out and rodding through existing and new surface water and foul water drainage on completion of the works and ensure that all pipework is clear and free running. |  | Item
8.08 | To all new below ground M&E services installations: Contractor to allow for all BWIC with the installation of all new below ground drainage, soakaways, manholes, connections, electrical and data runs including all associated fixings and fittings. All works to be in accordance with drawing '8341,B05C - Proposed Sit Layout Plan' |  | Item |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
Boundaries, Fences and Gates
8.09 | To the NE & SE boundary fence: Supply and install new 1800mm high timber boundary fence. Allow for concrete posts with concrete gravel boards and timber vertical timber feather board fence. |  | Lm |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
8.1 | To the proposed perimeter fence: Supply and install new 1200mm high bow top metal fence with coated black finish and 2no. sliding entrance gates including all associated fixings and fittings. Contractor to present proposed fence to Contract Administrator for approval prior to placing any orders. All works to be in accordance with drawing '8341,B05C - Proposed Sit Layout Plan' |  | Lm
8.11 | To the air source heat pump: Supply and install new 1800mm timber slat double leaf gates into 100x100mm timber weathered top gate posts. Allow for slide latch within the gate frame including all associated fixings and fittings. | 3 | Lm
8.12 | To the Air source heat pump: Supply and install new 200mm thick reinforced concrete base for the proposed air source heat pump. All works to be in accordance with drawing '8341,B05C - Proposed Sit Layout Plan' |  | m2
Out Buildings, Sheds and Shelters
8.13 | To the left hand side of the building: Supply and install new Steel framed 'Bi-store' open end clear thermoplastic (RG665) cycle shelter with 5no. galvanised steel cycle rings including all associated fixtures and fittings. All specified products to be installed in accordance with the manufacturers recommendations including all associated fixings and fittings. | 1 | Item |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
8.14 | To the bin store: Supply and install new bin store with 100x100 timber gate posts and timber chevron slates. Contractor to all for 2no. Timber framed gates with chevron slats. All works to be in accordance with drawing '8341,B05C - Proposed Sit Layout Plan' |  | Lm
9 | CEILINGS
9.01 | To all ceilings throughout: Fix boards to ceilings before installing dry lined walls and partitions. Boards are to be fixed with bound edges at right angles to supports and with ends staggered in adjacent rows. Where two layers of boarding is required stagger joints between layers. |  | Item
9.02 | Provisional Quantity: To the existing plasterboard ceilings Undertake patch repairs to damaged and damp stained sections of plasterboard ceiling cutting out defective sections and replacing with new sections of plasterboard to match existing including all associated fillers, fixings and fittings. Contractor to price for 10m2 of Plasterboard repairs here: ......................... Where ceiling is beyond economical repair the contractor is to price to replacing the ceiling with new to match existing including all associated trims, tapes, fixtures and fittings. Contractor to price for 10m2 of new plasterboard ceiling here: ......................... |  | PQ
9.03 | To the ceiling voids throughout: Allow to upgrade and install new fire stopping between compartments where required to comply with Part B of The Building Regulations. This includes but is not limited to fire boarding as part of finishes, intumescent seals to building fabric joints and junctions and fire stopping to services penetrations etc. The contractor is to ensure the CA and Approved Inspector for the project are notified prior to voids being closed up so that all required inspections in relation to statutory compliance can be undertaken. All works to be in accordance with drawings ' 8241,B10 - Ground Floor Wall Specification Plan and 8241 - B11 - First Floor Wall Specification Plan'. | 1 | M2
9.04 | To the areas receiving new MF ceilings as per the reflected ceiling plan: Supply and install new metal frame ceiling (British Gypsum Casoline MF Ceiling System) with 12.5mm plasterboard layer (British Gypsum Gyproc Wallboard) complete with 3mm plaster skim coat including all associated beads, trims, tapes, fixings and fittings. All specified products to be installed in accordance with the manufacturers recommendations including all associated fixings and fittings. All works are to be in accordance with drawing '8341,B12 - Reflected Ceiling Plans'. | 167.1 | M2
9.05 | To the areas receiving new overboard ceilings as per the reflected ceiling plan: Supply and install 12.5mm (British Gypsum Gyproc) finish with 3mm plaster skim coat including all associated beads, trims, tapes, fixings and fittings. All specified products to be installed in accordance with the manufacturers recommendations including all associated fixings and fittings. All works are to be in accordance with drawing '8341,B12 - Reflected Ceiling Plans'. | 198.3 | M2
9.06 | To the areas receiving new moisture resistant MF ceilings as per the reflected ceiling plan: Supply and install new metal frame ceiling (British Gypsum Casoline MF Ceiling System) with 12.5mm plasterboard layer (British Gypsum Gyproc Moisture Resistant Plasterboard) complete with 3mm plaster skim coat including all associated beads, trims, tapes, fixings and fittings. All specified products to be installed in accordance with the manufacturers recommendations including all associated fixings and fittings. All works are to be in accordance with drawing '8341,B12 - Reflected Ceiling Plans'. | 23.3 | M2
9.07 | To the areas receiving new moisture resistant overboard as per the reflected ceiling plan: Supply and install 12.5mm plasterboard layer (British Gypsum Gyproc Moisture Resistant Plasterboard) complete with 3mm plaster skim coat including all associated beads, trims, tapes, fixings and fittings. All specified products to be installed in accordance with the manufacturers recommendations including all associated fixings and fittings. All works are to be in accordance with drawing '8341,B12 - Reflected Ceiling Plans'. | 25.4 | M2
9.08 | To the community hall ceiling: Supply and install new suspended ceiling system (Gyproc - MF Gypceiling) with ceiling sections at 600mm centres (British Gypsum Gypframe MF5), primary supports at 400mm centres (British Gypsum Gypframe MF7), steel angles (British Gypsum Gypframe MFEA1) and 150mm of mineral wool insulation(Isover Acoustic Partition Roll) complete with Supawood Supaslat 3 timber slat feature ceiling (Colour Supacolour - Black SF) including all associated fixings and fittings. All specified products to be installed in accordance with the manufacturers recommendations including all associated fixings and fittings. Allow for lighting, emergency lighting, electrical fittings and all service media to be set between the timber slats. Service void to be adjusted to suit proposed M&E services. Suspended ceiling system to be fixed to the primary steelwork. Roof purlins with feature timber ceiling installed between primary and secondary steel beams as per the manufactures recommendations. All works are to be in accordance with drawings '8341,B12 - Reflected Ceiling Plans' and '8341, B21 - Proposed sections A-A & B-B' | 129.5 | M2
10 | WALLS
10.01 | Provisional Quantity: To all existing internal partitions: Undertake localised repairs to internal walls raking out defective sections of plaster and replacing with new plaster skim including all associated beads, joints, tapes, fixings and fittings. Contractor to price for 20m2 of Plaster repairs here: ......................... |  | PQ
10.02 | To the existing ground floor partitions: Supply and install new 100mm low density concrete blockwork (Thomas Armstrong Ultralite Concrete Block) partitions complete with 12.5mm plasterboard (British Gypsum Gyproc Wallboard and Moisture Resistant Plasterboard) fixed to either side using adhesive dabs and 3mm plaster skim including all associated adhesives, beads, joints, tapes, fixings and fittings. Contractor to use Gyproc moisture resistant plasterboard for all WC partitions. All specified products to be installed in accordance with the manufacturers recommendations including all associated fixings and fittings. All works to be in accordance with drawing '8241,B10 - Ground Floor Wall Specification Plan'. |  | M2
10.03 | To the existing internal ground floor partitions: Supply and install new 100mm low density concrete blockwork (Thomas Armstrong Ultralite Concrete Block) wall infill with 100mm cavity void complete with 12.5mm plasterboard (BritishGypsum Gyproc Wallboard) fixed to either side using adhesive dabs and 3mm plaster skim including all associated adhesives, beads, joints, tapes, fixings and fittings. All specified products to be installed in accordance with the manufacturers recommendations including all associated fixings and fittings. All works to be in accordance with drawing '8241,B10 - Ground Floor Wall Specification Plan'. |  | M2
10.04 | To the community hall high level internal wall lining: Supply and install new cold-rolled Z-purlins (Kingspan multibeam or similar approved) with 48mm metal stud (British Gypsum Gypframe C Stud) between steel bracing and 50mm mineral wool cavity fill (Isover acoustic insulation) finished with 12.5 plaster board (BritishGypsum Gyproc Wallboard) and 3mm plaster skim including all associated adhesives, beads, joints, tapes, fixings and fittings. The span direction, size and type and spacing of the Z-purlins is to be in accordance with 'John Plumber Partnership Structural Engineering Calculations and Details' Document. All specified products to be installed in accordance with the manufacturers recommendations including all associated fixings and fittings. Should the Contractor have any specific queries in relation to the structural design and specification they should seek guidance from the Structural Engineer prior to undertaking any works. |  | M2
10.05 | To the first floor new internal partitions: Supply and install new 130mm metal stud partitions (British GypsumGywall single frame) at 600mm centres with 50mm cavity insulation roll (Isover Acoustic Partition roll APR 1200) finished with two layers of 12.5mm plasterboard (BritishGypsum Gyproc Wallboard) with staggered joints and 3mm plaster skim including all associated adhesives, beads, joints, tapes, fixings and fittings. All specified products to be installed in accordance with the manufacturers recommendations including all associated fixings and fittings. |  | M2
10.06 | To the basement: Supply and install new floor to ceiling store rooms with 100x50mm preservative treated timber stud walls installed at 600mm centres with suitable noggins finished with chain link fencing to one side. Door to be structural timber frame with cross bracing with chain link fence including all associated fixings and fittings. |  | Lm
10.07 | To all new and proposed partitions throughout: Allow to upgrade and install new fire stopping between compartments where required to comply with Part B of The Building Regulations. This includes but is not limited to fire boarding as part of finishes, intumescent seals to building fabric joints and junctions and fire stopping to services penetrations etc. The contractor is to ensure the CA and Approved Inspector for the project are notified prior to voids being closed up so that all required inspections in relation to statutory compliance can be undertaken. All specified products to be installed in accordance with the manufacturers recommendations including all associated fixings and fittings. All works to be in accordance with drawing '8241,B10 - Ground Floor Wall Specification Plan'. |  | M2
11 | INTERNAL WINDOWS
N/A
12 | INTERNAL DOORS
12.01 | All door closers should be capable of operating with an opening force of not more than 30N, for the first 30° of opening, and 22.5° for remainder of swing. Ensure that all existing and relocated doors meet requirements in terms of fire-rating and suitability of ironmongery. Consideration must be made when selecting door frame colours to ensure contrasting effect in line with Equality Act requirements. |  | Item
12.02 | To door openings 8 & 24 (Door Type 1) : Supply and hang new 54mm thick 926x2060mm polyrey HPL laminate chene bastude C129(Natural woods, Oak) solid FD 60 door sets. Allow for 180mm fire rated (FR to match door) double glazed vision panel in accordance with The building Regulations 2010 - Approved Document K4/K5. Doors to be hung on 3 no. Heavy duty single axix door hinges complete with fire and smoke seals including all associated fixings and fittings. All doors to be installed in accordance with drawing '8341,B18 - Door Schedule'. | 2 | No.
[7 empty] | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
12.03 | To door openings 6, 7, 13, 14 and 16 (Door Type 2) : Supply and hang new 44mm thick 826x2060mm polyrey HPL laminate chene bastude C129(Natural woods, Oak) solid FD 30 door sets. Allow for 180mm clear fire rated (FR to match door) double glazed vision panel in accordance with The building Regulations 2010 - Approved Document K4/K5. Doors to be hung on 3 no. Heavy duty single axix door hinges complete with fire and smoke seals including all associated fixings and fittings. All doors to be installed in accordance with drawing '8341,B18 - Door Schedule'. | 5 | No.
[7 empty] | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
12.04 | To door openings 3, 17, 22, 23, 26, 27, 29, 32, 34 and 35 (Door Type 3) : Supply and hang new 44mm thick 826x2060mm polyrey HPL laminate chene bastude C129(Natural woods, Oak) solid FD 30 door sets. Doors to be hung on 3 duty single axix door hinges complete with fire and smoke seals including all associated fixings and fittings. All doors to be installed in accordance with drawing '8341,B18 - Door Schedule'. | 10 | No.
[7 empty] | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
12.05 | To door openings 5, 20 and 28 (Door Type 4) : Supply and hang new 44mm thick 726x2060mm polyrey HPL laminate chene bastude C129(Natural woods, Oak) solid FD 30 door sets. Doors to be hung on 3 duty single axix door hinges complete with fire and smoke seals including all associated fixings and fittings. All doors to be installed in accordance with drawing '8341,B18 - Door Schedule'. | 3 | No.
[7 empty] | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
12.06 | To door openings 4, 9, 18, 19, 21, 30 and 31 (Door Type 5) : Supply and hang new 44mm thick 1050 x2060mm polyrey HPL laminate chene bastude C129(Natural woods, Oak) solid FD 30 door sets. Doors to be hung on 3 duty single axix door hinges complete with fire and smoke seals including all associated fixings and fittings. All doors to be installed in accordance with drawing '8341,B18 - Door Schedule'. | 7 | No.
[7 empty] | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
12.07 | To door opening 15 (Door Type 6) : Supply and hang new leaf and a half 44mm thick 826/434 x2060mm polyrey HPL laminate chene bastude C129(Natural woods, Oak) solid FD 30 door set. Doors to be hung on 3 duty single axix door hinges complete with fire and smoke seals including all associated fixings and fittings. All doors to be installed in accordance with drawing '8341,B18 - Door Schedule'. | 1 | No.
[7 empty] | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
12.08 | To door opening 12 (Door Type 7) : Supply and hang new 54mm thick 626x2060mm polyrey HPL laminate chene bastude C129(Natural woods, Oak) solid FD 60 door sets. Doors to be hung on 3 duty single axix door hinges complete with fire and smoke seals including all associated fixings and fittings. All doors to be installed in accordance with drawing '8341,B18 - Door Schedule'. | 1 | No. |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
[7 empty] | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
12.09 | To all internal doors throughout: Supply and install ironmongery and signage to all doors including but not limited to push plates, pull handles, kick plates, overhead closers, door stops, door holders, door mounted coat hooks, mortice cylinder key locks, thumb turn operation to mortice cylinder on internal side, thumb turn privacy indicators and surface mounted signage including all associated fixings and fittings. All door ironmongery, signage and finishes are to be in accordance with drawing 'B341,B19 - Ironmongery Schedule'. The Contractor is to ensure that before any orders are place a sample board containing labelled samples of ironmongery and signage showing methods of fixing is provided to the Contract Administrator for approval. | 29 | No.
12.1 | To all new fire doors throughout: where new fire doors sets have been fitted the Contractor is to provide certification of compliance with the Building Regulations Part B. | 1 | Item
[7 empty] | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
13 | JOINERY
13.01 | To all walls and internal partitions thought: Supply and install new 100mm softwood bullnose skirting securely fixed with mitred corners including all associated fixings and fittings. |  | Lm |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
13.02 | To all door openings throughout: Supply and install new 75mm softwood bullnose architraves securely fixed with mitred corners including all associated fixings and fittings. |  | Lm |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
13.03 | To all the new window openings: Supply and install new 25mm softwood windows cills with profiled edges to match existing like for like including all associated fixings and fittings. |  | Lm,
13.04 | Provisional Quantity: To all exposed pipework and services throughout the WC's: Supply and instal new 10mm ply boxing to all exposed services and pipe work leaving all surfaces ready to receive decoration including all associated fixing and fittings. Contractor to price for 50m2 of new ply boxing here: .............................. | 50 | PQ
13.05 | To the basement: Supply and install new timber staircase from the basement to the ground floor. Staircase is to be constructed from treated softwood and ply with closed risers and strings. Staircase to comply with Buildings Regulations Part K in respect to hand rail heights, widths, goings and risers, etc. Staircase to allow for a quatre landing and anti slip strips on all goinings with aluminium noggings. |  | Item
WC's
13.06 | To the first floor WC's: Supply and install new 1250x597x12 marine pattress board (Smartply Pattress Plus or similar approved) within the metal stud frame including all associated fixings and fittings. All specified products to be installed in accordance with the manufacturers recommendations including all associated fixings and fittings. |  | M2
13.07 | To all WC's throughout: Supply and install new close coupled toilets (white glazed fireclay pan, vitreous china cistern and plastic seat and cover) with dual flush including all associated pipework, fixings and fittings. All works to be in accordance with drawing '8341,B16 - Proposed WC Details' | 9 | No. |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
13.08 | To all WC's throughout: Supply and install: Supply and install washbasins (Armitage shanks - HBN - 00-10-HTM65[LB G M] Contour 21+ 50cm back outlet basin) complete with chrome thermostatic basin mixer taps (Sanceram Sequential TMV3 mixer tap) and chrome waste trap including all associated pipework, fixings and fittings. All works to be in accordance with drawing '8341,B16 - Proposed WC Details' | 9 | No. |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
13.09 | To all WC's throughout: Supply and install new highly polished stainless steel 700x450mm 6mm thick mirrors with bevelled edges including all associated fixings and fittings. All works to be in accordance with drawing '8341,B16 - Proposed WC Details' | 12 | No. |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
13.1 | To all WC's throughout: Supply and instal new wall mounted paper towel dispensers (Tork Xpress® Multifold Hand Towel Dispenser 552000) including all associated fixings and fittings. All works to be in accordance with drawing '8341,B16 - Proposed WC Details' | 12 | No. |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
13.11 | To all WC's throughout: Supply and install new wall mounted soap dispensers (Tork Liquid and Spray Soap Dispenser 560000) including all associated fixings and fittings. All works to be in accordance with drawing '8341,B16 - Proposed WC Details' | 12 | No. |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
13.12 | To all WC's throughout: Supply and install new free standing white plastic brissled toilet brushed including all associated fixings and fittings. | 12 | No.
13.13 | To all accessible WC's throughout: Supply and install new Doc M assessable WC equipment packages (Armitage Shanks contour 21+ close coupled WC Doc M pack Stock Code: S0683AC) including all associated fixings and fittings. All accessible WC installations are to be in accordance with The Building Regulations - Approved Document M - Access and use of Buildings and Drawing '8341,B16 - Proposed WC Details'. | 3 | No.
Tea point
13.14 | To Tea point A (Room Hire A): Supply and install new tea point complete with all associated base units, worktops, sinks, waste, traps, end panels, plinths, metal edging strips, sealants, adhesives, fixings and fittings. Tea point to include(Unit Colours to be confirmed): - Greenwich Gloss 575mm integrated undercounter fridge housing unit - Greenwich Gloss 425mm Pullout Bin unit (including bin) - Greeneich Gloss 900mm Double Base unit - Greenwich Gloss 900mm Double Base unit with 450mm soft close drawer - Howdens T Bar Brushed Stainless Steel Effect Classic Cupboard Handle 230mm - Howdens Franke Bell 1.5 Bowl Inset Stainless Steel Sink - Howdens Franke Bell Polished Chrome Swan Neck Mixer Tap with chrome pop up waste - HPL Bonded Laminate Chene Bastude C129 (Natural woods, Oak) worktop All works to be in accordance with drawing '8341,B17 - Tea point Details' | 1 | Item
13.15 | To Tea point B (Community Hall): Supply and install new tea point complete with all associated base units, worktops, sinks, waste, traps, end panels, plinths, metal edging strips, sealants, adhesives, fixings and fittings. Tea point to Include (unit Colours to be confirmed): - Greenwich Gloss 575mm integrated undercounter fridge housing unit - Greenwich Gloss 425mm Pullout Bin unit (including bin) - Greenwich Gloss 900mm Double Base unit with 450mm soft close drawer - Howdens T Bar Brushed Stainless Steel Effect Classic Cupboard Handle 230mm - Howdens Franke Bell 1.5 Bowl Inset Stainless Steel Sink - Howdens Franke Bell Polished Chrome Swan Neck Mixer Tap with chrome pop up waste - HPL Bonded Laminate Chene Bastude C129 (Natural woods, Oak) worktop - 2.no 18x300mm White laminate floating shelves at 300mm centres (length to match tea point) All works to be in accordance with drawing '8341,B17 - Tea point Detail | 1 | Item
13.16 | To Tea point C (Room hire B): Supply and install new tea point complete with all associated base units, worktops, sinks, waste, traps, end panels, plinths, metal edging strips, sealants, adhesives, fixings and fittings. Tea point to include(Unit Colours to be confirmed): - Greenwich Gloss 575mm integrated undercounter fridge housing unit - Greenwich Gloss 425mm Pullout Bin unit (including bin) - Greenwich Gloss 900mm Double Base unit with 450mm soft close drawer - Howdens T Bar Brushed Stainless Steel Effect Classic Cupboard Handle 230mm - 2.no 18x600mm White Laminate open shelving at 300mm centres (Cut to fit flush against angle of the wall) - Howdens Franke Bell 1.5 Bowl Inset Stainless Steel Sink - Howdens Franke Bell Polished Chrome Swan Neck Mixer Tap with chrome pop up waste - HPL Bonded Laminate Chene Bastude C129 (Natural woods, Oak) worktop - Altro Whitrock 2.5x610mm splash back (White W103/W104) Length to match tea point All works to be in accordance with drawing '8341,B17 - Tea point Details' | 1 | Item
13.17 | To Tea point D (Offices): Supply and install new tea point complete with all associated base units, worktops, sinks, waste, traps, end panels, plinths, metal edging strips, sealants, adhesives, fixings and fittings. Tea point to include(Unit Colours to be confirmed): - Greenwich Gloss 575mm integrated undercounter fridge housing unit - Greenwich Gloss 425mm Pullout Bin unit (including bin) - Greeneich Gloss 900mm Double Base unit - Greenwich Gloss 900mm Double Base unit with 450mm soft close drawer - Howdens T Bar Brushed Stainless Steel Effect Classic Cupboard Handle 230mm - Howdens Franke Bell 1.5 Bowl Inset Stainless Steel Sink - Howdens Franke Bell Polished Chrome Swan Neck Mixer Tap with chrome pop up waste - HPL Bonded Laminate Chene Bastude C129 (Natural woods, Oak) worktop All works to be in accordance with drawing '8341,B17 - Tea point Details' | 1 | Item
13.18 | To all the new tea points: Supply and install new integrated undercounter fridge (Lamona LAM6000 Integrated White Larder Fridge) including all associated service media, fixings and fittings. | 4 | Item
13.19 | To Tea point D (Offices): supply and install new freestanding solo microwave (Russle Hobbs RHM20765 Solo Microwave - Silver) including all associated service media, fixings and fittings. | 1 | Item
13.2 | To all WC's, Tea points & the Community Space: Supply and install new Altro Whitrock -Rigid PVC Wall Sheeting echo satin (White W103/W104) with 150mm coving to all WC's, cleaners stores and tea points with aluminium skirting cap including all associated trims, fixings and fittings in accordance with the manufacturer's recommendations. WC's - Full wall height Tea points - 610mm above worktops All specified products to be installed in accordance with the manufacturers recommendations including all associated fixings and fittings. All works to be in accordance with drawing '8341,B15 - Proposed Finishes Plan' |  | M2
14 | METALWORK
[7 empty] | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
15 | FLOORS
15.01 | To all floors through the ground floor: Prepare existing substrate by removing dust and debris and Supply and install new self levelling screed (Sikafloor Level-30) in accordance with the manufactures recommendations. Contractor to ensure even floor finish throughout the ground floor and that adequate curing time in line with the manufactures recommendations is allowed for before floor finishes are laid. | 218 | M2
15.02 | To the Community hall, Room Hire A, Room Hire B and Frist Floor lobbies: Supply and instal new hardwearing entrance flooring (Forbo Coral Classic 4751 Silver Grey) including all required threshold strips, fixings and fittings. All works to be in accordance with drawing '8341,B15 - Proposed Finishes Plan' | 3 | M2
15.03 | To the first floor offices 1, 2 & 3: Prepare existing timbe board flooring (ply sheet overboard if required) and supply and install new carpet tile floor covering (500x500.6,7mm Forbo, Tessera Infused Carpet Tile 4500 Magic Mood (Grey) including all associated threshold strips, fixings and fittings in accordance with the manufactures recommendations. All works to be in accordance with drawing '8341,B15 - Proposed Finishes Plan' | 175 | M2
15.04 | To room hire A WC's & Lobbies, Store Rooms and Tea points throughout: Supply and install new sheet vinyl floor covering (Forbo Laguna Surestep - 181922 Concrete) with 150mm height coving to all vinyl floor finishes with aluminium skirting cap including all associated threshold strips, jointing trims, fixings and fittings in accordance with the manufactures recommendations. All works to be in accordance with drawing '8341,B15 - Proposed Finishes Plan' | 84 | M2
15.05 | To the Community space and Room hires A & B: Supply and install new sheet vinyl floor covering (Forbo - Surestep wood - 18952 Dark Grey Oak) including all associated threshold strips, jointing trims, fixings and fittings in accordance with the manufactures recommendations. All works to be in accordance with drawing '8341,B15 - Proposed Finishes Plan' | 7 | M2
15.06 | To the community hall: Supply and install new sprung timber floor (Boen Boflex Olympia Timber Floor - Beech Finish) with 5mm foam insulation (Evazote) including all associated threshold strips, trims, adhesives, fixings and fittings in accordance with the manufacturers recommendations. All works to be in accordance with drawing '8341,B15 - Proposed Finishes Plan' | 124 | M2
16 | MECHANICAL AND ELECTRICAL
16.01 | The design and installation of the mechanical & electrical works form part of the contractors design portion of the contract works. All mechanical & electrical works are to be designed and completed in accordance with 'Building Services Consultants Design Specification Overview' and all relevant and current statutory requirements, regulations, guidance and in line with the best practices. Contractor to ensure all new mechanical & electrical installations are to be chased into the existing substrate with no exposed or surface mounted conduits. Final setting out positions for all new face plates, fixtures and fittings are to be agreed with the CA prior to installation. Contractor to all for all design & installation of all above ground drainage in accordance with IoP, CIBSE and Building Regulations Approved Documents. |  | Item
16.02 | Carryout full validation measurements of existing building performance. Including but not limited to:- • Water tests • Electrical tests |  | Item
16.03 | New MVHR Ventilation Systems |  | Item
16.04 | New Intermittent Extract Ventilation Systems |  | Item
16.05 | New Split Type air to air heat pump heating and cooling systems |  | Item
16.06 | New direct electric radiant space heating system |  | Item
16.07 | New ASHP and VLTHW to Community Hall Underfloor heating system |  | Item
16.08 | New hot and cold water systems |  | Item
16.09 | New above ground drainage wastewater disposal systems |  | Item
16.1 | New Building Management Control Systems |  | Item
16.11 | New LV Distribution Systems |  | Item
16.12 | New Small Power Distribution system |  | Item
16.13 | New data and AV cabling systems |  | Item
16.14 | New general and emergency internal lighting systems |  | Item
16.15 | New Lightening Protection System |  | Item
16.16 | New fire alarm systems |  | Item
16.17 | New CCTV Systems |  | Item
16.18 | New security and access control system |  | Item
16.19 | New hand driers |  | Item
16.2 | New call systems (acc. WC’s) |  | Item
16.21 | Induction loop systems |  | Item
16.22 | New Roof mounted Photovoltaic (PV) Systems |  | Item
16.23 | New electric vehicle charging points |  | Item
16.24 | AV Equipment (supply and install) |  | Item
16.25 | Commissioning |  | Item
16.26 | Legionella Risk Assessment |  | Item
16.27 | 12 Months Maintenance in accordance with maintenance specification SFG20 and manufacturers recommendations |  | Item
17 | DECORATIONS
17.01 | All previously decorated finishes and new finishes are to have full redecoration throughout. Refer to drawing '8341,B15 - Proposed Finishes Plan' for colours and paint finishes. Contractor to allow for 1no. mist coats to all new plastered surfaces prior to applying finishing coats. |  | M2
17.02 | To all ceilings and walls throughout: Prepare surfaces and decorate with 2no. coats of Dulux Trade Diamond Emulsion in White cotton (off white) in accordance with the manufacturer's recommendations. All decorations to be in accordance with drawing '8341,B15 - Proposed Finishes Plan' |  | M2
17.03 | To the canteen, Room Hire A lobby, Room Hire B & Community Hall walls: Prepare surfaces and decorate with 2no. coats of Dulux Trade Emulsion Green - 40GY-371 in accordance with the manufacturer's recommendations. All decorations to be in accordance with drawing '8341,B15 - Proposed Finishes Plan' |  | M2
17.04 | To all WC's, Tea points & Cleaners stores walls: Prepare surfaces and decorate with 2no. coats of Dulux Trade Diamond Egg shell White cotton in accordance with the manufacturer's recommendations. All decorations to be in accordance with drawing '8341,B15 - Proposed Finishes Plan' |  | M2
17.05 | To all skirtings and architraves throughout: Prepare surfaces and decorate with 2no. coats of Dulux Trade Diamond Satinwood Almost Black 09BB/008 in accordance with the manufacturer's recommendations. All decorations to be in accordance with drawing '8341,B15 - Proposed Finishes Plan' |  | M2
17.06 | Provisional Quantity: To all new internal boxings : Thoroughly prepare and decorate with 2no. coats of Dulux Trade Diamond Satin Paint in accordance with the manufacturer's recommendations. Contractor to price for 50m2 of decorations to boxing here: .............................. | 50 | PQ
17.07 | To the new timber staircase : Thoroughly prepare and decorate with 2no. coats of Dulux Trade Diamond Satin Paint in accordance with the manufacturer's recommendations. | 1 | M2
18 | CLEANING
18.02 | To all windows and doors throughout: thoroughly clean all internal and external glazing panes upon completion of the works. |  | Item |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
18.03 | To all external hard standing areas: Remove all rubbish, vegetation and undertake a full builders clean and jet wash all floor coverings upon completion of the works. |  | Item |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
18.04 | To all internal areas and surfaces throughout the entire building: remove all rubbish and debris upon completion of the works and thoroughly clean all surfaces, finishes fixings and finishes throughout ready to the hand the building over to the employer upon completion of the project works. |  | Item
19 | HANDOVER INFORMATION
19.01 | Upon completion the contractor is to provide a full health and safety file in relation to the works inclusive of all test certificates, product data sheets, warranties and operation and maintenance manuals. |  | Item |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
19.02 | Upon completion the contractor is to provide as built drawings in electronic and hardcopy format for works which form part of the Contractors design portion of the contract works |  | Item
SECTION 4 - COLLECTION
WORKS COST SUMMARY
1 | Preliminaries |  |  |  | 50000 | 25000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25000
2 | Demolition / Strip Out |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
3 | Sub-Structure & Superstructure |  |  |  | 10000 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
4 | Roof |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
5 | Elevations |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
6 | External Windows |  |  |  | 1200 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
7 | External Doors |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
8 | External Areas |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
9 | Ceilings |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
10 | Walls |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
11 | Internal Windows |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
12 | Internal Doors |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
13 | Joinery |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
14 | Metalwork |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
15 | Floors |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
16 | Mechanical & Electrical |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
17 | Decorations |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
18 | Cleaning |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
19 | Handover |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Total Works Cost | - | Sum |  | 61200 | 25000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25000
VALUATION - 00 - 00.00.000
FINANCIAL ANALYSIS SUMMARY
| CONTRACT SUM |  |  |  |  | 25000
| VAULATION SUM | [6 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25000
| CAI | [6 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| GROSS VALUATION | [6 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25000
| RETENTION (5% / 2.5%) | [6 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 625
| NET VALUATION | [6 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 24375
| PREVIOUSLY CERTIFIED | [6 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 666969.52
| PAYMMENT DUE | [6 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | -642594.52
| VAT AT 20 % | [6 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | -128518.904
| FINAL PAYMENT DUE | [6 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | -771113.424

## Variation Scheudle of Works
Item | Work Required | Quantity | Unit | Rate | OH&P | Quote | Cost | CAI
10%
VARIATION SCHEDULE OF WORK
V1.00 | GENERAL
V1.01 |  | 1 | Item | 0 | 0 | 0 | 0
V2.00 | DEMOLITION / STRIP OUT
V2.01 | Remove Wall. | 1 | Item | 0 | 0 | 0 | 0
V3.00 | ROOF
Coverings
V3.01 | - | 1 | Item | 0 | 0 | 0 | 0
Rainwater Goods
V3.02 | - | 1 | Item | 0 | 0 | 0 | 0
Pest Control
V3.03 | - | 1 | Item | 0 | 0 | 0 | 0
V4.00 | ELEVATIONS
V4.01 | - | 1 | Item | 0 | 0 | 0 | 0
V5.00 | EXTERNAL WINDOWS
V5.01 | - | 1 | Item | 0 | 0 | 0 | 0
V6.00 | EXTERNAL DOORS
V6.01 | - | 1 | Item | 0 | 0 | 0 | 0
V7.00 | EXTERNAL AREAS
V7.01 | - | 1 | Item | 0 | 0 | 0 | 0
V8.00 | CEILINGS
V8.01 | - | 1 | Item | 0 | 0 | 0 | 0
V9.00 | WALLS
V9.01 | - | 1 | Item | 0 | 0 | 0 | 0
V10.00 | INTERNAL WINDOWS
V10.01 | - | 1 | Item | 0 | 0 | 0 | 0
V11.00 | INTERNAL DOORS
V11.01 | - | 1 | Item | 0 | 0 | 0 | 0
V12.00 | JOINERY
V12.01 | - | 1 | Item | 0 | 0 | 0 | 0
V13.00 | METALWORK
V13.01 | - | 1 | Item | 0 | 0 | 0 | 0
V14.00 | FLOORS
V14.01 | Intall new carpets to office . | 1 | Item | 0 | 0 | 0 | 0
V15.00 | ELECTRICAL
V15.01 | Small Power
V15.01.01 | - | 1 | Item | 0 | 0 | 0 | 0
V15.02 | Lighting & Emergency Lighting
V15.02.01 | - | 1 | Item | 0 | 0 | 0 | 0
V15.03 | Fire Alarm
V15.03.01 | - | 1 | Item | 0 | 0 | 0 | 0
V15.04 | Data & Telecommunications
V15.04.01 | - | 1 | Item | 0 | 0 | 0 | 0
V15.05 | Security, Access & CCTV | 1 | Item | 0 | 0 | 0 | 0
V15.05.01 | - | 1 | Item | 0 | 0 | 0 | 0
V15.06 | Lightening Protection
V15.06.01 | - | 1 | Item | 0 | 0 | 0 | 0
V16.00 | MECHANICAL
V16.01 | Cold Water
V16.01.01 | - | 1 | Item | 0 | 0 | 0 | 0
V16.02 | Hot Water
V16.02.01 | - | 1 | Item | 0 | 0 | 0 | 0
V16.03 | Lightening Protection
V16.03.01 | - | 1 | Item | 0 | 0 | 0 | 0
V16.04 | Ventilation & Extraction
V16.04.01 | - | 1 | Item | 0 | 0 | 0 | 0
V16.05 | Drainage / Public Health
V16.05.01 | - | 1 | Item | 0 | 0 | 0 | 0
V16.06 | Gas
V16.06.01 | - | 1 | Item | 0 | 0 | 0 | 0
V16.07 | Mechanical Access / Lifts
V16.06.01 | - | 1 | Item | 0 | 0 | 0 | 0
V17.00 | DECORATIONS
V17.01 | - | 1 | Item | 0 | 0 | 0 | 0
V18.00 | CLEANING
V18.01 | - | 1 | Item | 0 | 0 | 0 | 0
V19.00 | HANDOVER INFORMATION
Investigations / Testing / Commissioning
V19.01 | - | 1 | Item | 0 | 0 | 0 | 0
| Sub Total |  |  |  |  | 0 | 0
0

## CAI
CAI | ADD/OMIT | DESCRIPTION | ADD | OMIT | VALUATION 01 |  | VALUATION 02 |  | VALUATION 03 |  | VALUATION 04 |  | VALUATION 05 |  | VALUATION 06 |  | VALUATION 07 |  | FINAL ACCOUNT
[5 empty] | % | £ | % | £ | % | £ | % | £ | % | £ | % | £ | % | £ | % | £
CONTRACT ADMINISTRATOR'S INSTRUCTIONS
CAI - 1
CAI - 1.1 | ADD | Item V1.01: |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
CAI - 2
CAI - 2.1 | OMIT | Item V1.01: |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0
CAI - 3
CAI - 3.1 | ADD | Item V1.01: |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0
CAI - 4
CAI - 4.01 | ADD | Item V1.01: |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0
CAI - 5
CAI - 5.1 | ADD | Item V1.01: |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0
|  | TOTAL CAI SUM | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | APPROXIMATE ADJUSTED CONTRACT SUM | 578139.64 |  | 578139.64 |  | 578139.64 |  | 578139.64 |  | 578139.64 |  | 578139.64 |  | 578139.64 |  | 578139.64 |  | 578139.64
NB: All figures are exclusive of VAT