| CHANGE CONTROL NOTICE (CCN) |  |  |  |
| --- | --- | --- | --- |
| Contract Title: | Contract for the Provision of Civil Service Employee Policy Benchmarking Salary Survey 2020 (The Contract) |  |  |
| Contract Reference: | CCMK20A03 | Contract Change Number: | CCMK20A03-1 |
| Date CCN issued: | 12th September 2022 | Date Change Effective from: | 16th September 2022 |
| Between: The Cabinet Office (The Customer) and REDACTED TEXT under FOIA Section 40, Personal Information (The Supplier) - The Contract is varied as follows: - Customer has requested a three (3) months extension to the original contract - The Customer has obtained additional budgetary approval to cover the increase in value. - The Contract Value will now be £40,875.00 Ex VAT, including the possible extensions (Original Total Contract Value £36,000.00 Ex VAT). - Words and expressions in this Change Control Notice shall have the meanings given to them in the Contract. - The Contract, including any previous Contract changes, authorised in writing by both Parties, shall remain effective and unaltered except as amended by this Change Control Notice. |  |  |  |
| Change authorised to proceed by: (Customer’s representative): 15th September 2022 REDACTED TEXT under FOIA Section 40, Personal Information REDACTED TEXT under FOIA Section 40, Personal Information Signature Print Name and Job Title Date |  |  |  |
| 15th September 2022 REDACTED TEXT under FOIA Section 40, Personal Information REDACTED TEXT under FOIA Section 40, Personal Information Authorised for and on behalf of the Supplier: Signature Print Name and Job Title Date |  |  |  |
| 12/09/2022 REDACTED TEXT under FOIA Section 40, Personal Information REDACTED TEXT under FOIA Section 40, Personal Information Authorised for and on behalf of the Customer: Signature Print Name and Job Title Date |  |  |  |