# Annex A

| Title of Project | CEND0119 Offshore Brighton Epibenthic Imagery Analysis |
| --- | --- |
| Date and Time for Return of Bids | Tuesday 13 December 2022 at 16:00 hours |
| Contract Reference Number | C22-0427-1702 |
| Address for Bid Submission | 1 electronic copy to be sent to TenderResponse@jncc.gov.uk or QuotationResponse@jncc.gov.uk or FrameworkResponse@jncc.gov.uk (please only pick one address) PLEASE DO NOT SEND BIDS DIRECTLY TO JOSH TATE OR SHARON JOYCE VIA THEIR WORK EMAIL ADDRESSES AS THIS WILL INVALIDATE YOUR BID. Bids must be less than 10 MB in size. On receipt of your bid, you will receive an automated e-mail to confirm receipt by the JNCC Support Co. If you do not receive this automated email, please contact the number below; (00 44 1733 866 988) |
| Contacts for Technical Information relating to this Project Specification | Joint Nature Conservation Committee Name: Josh Tate Email: josh.tate@jncc.gov.uk Telephone: 01733 866906 OR Joint Nature Conservation Committee Name: David Reynolds Email: david.reynolds@jncc.gov.uk Telephone: 01733 943167 |
| Contact for Queries Regarding the Procurement Procedure | Finance and Planning Team Joint Nature Conservation Committee Email: @jncc.gov.uk or contractqueries@jncc.gov.uk Telephone: 01733 866894 |
| Proposed Start Date | 03/01/23 |
| Proposed End Date | 15/03/23 |

Title of Project - CEND0119 Offshore Brighton Epibenthic Imagery Analysis

Contents

1.	Joint Nature Conservation Committee	3

2.	Project Aims	3

3.	Project Background	3

4.	Project Objectives	3

5.	Project Objectives: Detailed Tasks	3

6.	Potential Follow-On Work	3

7.	Outputs	4

8.	Dissemination	4

9.	Timescale	4

10.	Health and Safety	4

11.	Product Specification	4

12.	Project Management	5

13.	Instructions for Bid Submission	5

14.	Evaluation Criteria	6

15.	Payment	7

16.	Additional Requirements	7

17.	References	7

## Joint Nature Conservation Committee

The Joint Nature Conservation Committee (JNCC) is the statutory adviser to the UK Government and devolved administrations on UK and international nature conservation

Our role is to provide scientific evidence, information, and advice to inform decisions to  protect the natural environment. Our specific role is to work on nature conservation issues that affect the UK as a whole and internationally, by:

advising Government on the development and implementation of policies for, or affecting, nature conservation in the UK and internationally.

providing advice and disseminating knowledge on nature conservation issues affecting the UK and internationally.

establishing common standards throughout the UK for nature conservation, including monitoring, research, and the analysis of results; and

commissioning or supporting research which it deems relevant to these functions.

Background to JNCC can be found on JNCC’s website at: https://jncc.gov.uk/about-jncc/

## Project Aims

JNCC wishes to commission a contract to undertake the analysis of a subset of seabed imagery (still images only) collected during the CEND0119 survey at Offshore Brighton MCZ.

Still images from 84 stations will be analysed; tenderers should provide quotes outlined in table 1.

More detailed metadata will be provided along with information from the logs and survey report.

Please note: The image subset is still undergoing filtering at this point and as such we are asking tenderers to quote for the analysis of up to 1527 still images, however this number may reduce when the filtering process is complete.

Access to a BIIGLE project containing images from the survey can be provided for tenderers to view upon request. (Please note this could be the images from the subset previously analysed if the images for this analysis are not finalised for BIIGLE upload, but will be representative of all stations)

## Project Background

Cefas and JNCC undertook a survey of the Offshore Brighton Marine Conservation Zone (MCZ) between 03 January and 25 January 2019, cruise code CEND0119.

Video observations were made with a drop camera (DC) system. The DC was equipped with a high-definition video camera and a separate still image camera unit, in a planar (downwards facing) orientation inside the frame. The stills camera was fitted with a four-spot (green) laser-scaling device forming a 21 cm x 21 cm square

The primary survey objective, related to seabed imagery, was to acquire video and still images from both sites for the purposes of MPA feature monitoring (at Offshore Brighton these monitoring stations were separated into those targeting rock and those targeting sedimentary habitats).

The secondary objective was to increase replication at a subset of monitoring stations in order to understand within station variability in habitats and epifaunal communities.

The third priority was to acquire video and still images for groundtruthing purposes, in order to improve the quality of habitat maps of the site.

To address these survey objectives three different methods were used.

- Camera stations for monitoring (based on a regular grid survey design - 5 minute transects)

- Camera stations for monitoring (increased replication at a subset of regular grid stations)

- Camera stations for groundtruthing (known as “GT” stations – 15 minute transects)

Camera stations for monitoring were positioned using a triangular grid. 1 x 5 minute transects were collected at each of these stations. A separate grid was used for the rock and sedimentary habitats.

At a subset of the camera stations for monitoring, replication was increased and a further 4 x 5 minute transects were collected.

Additional camera stations for groundtruthing target features identified from bathymetry data. 1 x 15 minute transects were collected at each of these stations.

Still images have been selected and pre-processed using a protocol developed by Cefas and a subset of 1831 Still images from OBRG were analysed in 2020 along with all acquired video data.

JNCC would now like to commission a contract to analyse the remaining ~1427 images acquired from this survey, as well as 100 images previously analysed in order to aid in calibration of the two datasets, totalling 1527 images. Maps of the camera stations sampled Offshore Brighton are shown in Figure 1.

More detailed metadata is provided in Appendix B.

Table 1. Imagery collected on CEND0119 survey to be analysed

| Location | Method | No. of stations | No. of still images (raw and jpeg) |
| --- | --- | --- | --- |
| Offshore Brighton | Drop Down Video | 84 | 1527 |

Figure 1. Camera stations sampled during CEND0119 at Offshore Brighton and broadscale habitats at the site. Camera stations for monitoring (green squares), camera stations for monitoring (increased replication) (blue squares), and camera stations for groundtruthing (red circles) are shown.

Please note the following documents will be supplied to the successful contractor:

Survey programme

Associated metadata

Cruise Report

MEDIN compliant MS Excel proforma spreadsheets

## Project Objectives

To meet the overall aims of this project (Section 2), the objectives are:

JNCC wishes to commission a contract to undertake the analysis of remaining seabed imagery (still images) collected on the CEND0119 survey.

- The Tenderers are to provide a quote for:

  - Still images from all 84 stations (Up to 1527 images from 84 stations)

- The successful contractor will undertake the analysis as set out below and adhering to the NMBAQC Epibiota interpretation guidelines (Turner et al, 20161).

- High level review of imagery should be conducted as outlined in Section 3.1 of Turner et. al., 2016.

- The successful contractor will use BIIGLE to annotate still images as described in Appendix A. A start-up meeting will be arranged with JNCC to provide limited training in use of BIIGLE in MPA projects.

- Substrate and taxonomic image reference collections are required

- The successful contactor should ensure that still image references used in analysis outputs are identical to those used in the naming of the original media, to enable future reconciliation between data and media. If identical naming is not possible, a suitable alternative should be sought with JNCC (e.g. a lookup table, or closely similar naming).

Any deviation from this methodology should be approved in writing by the project officer.

## Project Objectives: Detailed Tasks

## High level review of stills data

High level review of imagery should be conducted as outlined in Section 3.1 of Turner et. al., 2016.

If an image quality level of zero is given, then no further review of seabed substrate or fauna is required.

b.	Analysis of stills data

As described in Appendix A, the analysis of still images using BIIGLE is conducted in two parts; Tier 1 (whole image labels for metadata such as substrate, relief, image quality etc.) and Tier 2 (faunal annotations) for enumerating identified fauna within each image.

Whilst almost all of the required outputs (for both the Proforma and faunal abundance and percentage cover matrices) will be exported from the BIIGLE reports at the end of the project, certain information should be added to the proforma at the time of analysis. For each still image being analysed, use the proforma spreadsheet provided to note the following:

- Record image quality categories

- Provide a brief habitat description (BHD) for each still image

- Define the substrate present (as outlined in Appendix 3 of Parry (2015))

- Any comments from the analyst which are considered of importance

Note that some of the above information will also be captured in the Tier 1 whole image label BIIGLE process.

Tier 1 – Whole Image Labelling for Metadata

The Tier 1 image labelling process will result in each image being tagged with labels providing information on the following:

Note: Many of these annotations can be recorded directly into the stills analysis proforma spreadsheet if the analyst prefers as this is often quicker (with the exception of Still image field of view etc which are automatically calculated by BIIGLE).

- Still image field of view (calculated automatically in BIIGLE, provided laser points are annotated correctly.

- Substrate categories are provided in BIIGLE label tree, these categories are to the nearest 10 percentile.

- Bedforms (MPA Label Hierarchy provides for classifying ripples)

- Relief

- Image Quality

- Broadscale habitat Type (EUNIS level 3)

- MNCR biotope assigned by the analyst

- Presence of any Annex I habitats

- Presence of any habitat FOCI

- Presence of any OSPAR habitat

- Record the presence of litter using the categories listed in Annex 5.1 of the Joint Research Centres Guidance on Monitoring of Marine Litter in European Seas.

- Presence of Non-native Invasive species (NIS) (these individuals will be annotated in Tier 2, but a Tier 1 label is of great use in processing the data).

- Record the presence of any other visible impacts or other modifiers, such as trawl marks, visible physical damage, evidence of strong currents.

- Percentage of “Faunal Turf” present in image (to nearest 10 percentile).

- Percentage of Sabellaria present in image (to nearest 10 percentile)

- Percentage coverage of brittlestars present in image (to nearest 10 percentile)

- Percentage cover of serpulid tubeworms present in image (to nearest 10 percentile)

Tier 2 – Annotation of fauna within still images

For each still image being analysed, please identify, and quantify all:

a.	Solitary and/or erect epifaunal species present as far as possible (to the lowest taxonomic level) using counts (I.e. individual point annotation on BIIGLE). With the exception of those in Tier 1 above (i.e. brittlestars)

b.	Colonial and/or encrusting epifaunal species present as far as possible (to the lowest taxonomic level) using percentage cover (achieved by using the Polygon tools within BIIGLE). With the exception of those in Tier 1 above (i.e. Sabellaria, serpulids, faunal turf).

N.B –Use the magic wand tool for quick polygon creation – for high % cover taxa within an image, complete accuracy is not essential. i.e. for an image with lots of disparate, small macroalgal fronds we do not require every frond annotated, simply a few larger polygons which, as accurately as possible, convey the general % cover of the taxa within the image.

This should be a quick process

c. 	Encrusting abundant solitary taxa such as serpulid worms (i.e. Salmacina spp. and Spirobranchus spp.) and barnacles should be tagged at the Tier 1 level with a SACFOR % annotation (see user guide)

Where accurate determination to species/ genus level is not obvious, please use morphotype species (examples within the BIIGLE MPA label hierarchy) to distinguish between different types of easily confused species (E.g. cf. Urticina sp. for robust Actiniaria where the columns are not visible and counting tentacles is not possible due to resolution). However, please note these names will then not be suitable for entry in to Marine Recorder and will have to all be grouped together into Actiniaria in the final stages.  In this circumstance, please group into broader taxonomic groups but retain the finer distinctions by using a qualifier to differentiate. Merging the taxa later for Marine Recorder is not a problem as with the use of qualifiers any issues can be resolved and aggregated where necessary.

Please also annotate individual occurrences of MCZ species Features of Conservation Importance.

## Quality Assurance

Following award of the contract, and dependent on the evaluation scores they achieve, unsuccessful bidders may be invited to undertake the independent external QA aspects of this project. Please indicate in your tender if you do not wish to be considered for this work.

Note external QA analysis may be undertaken at same time as primary analysis if preferred by successful contractor and suitable process is agreed with JNCC at start-up meeting.

Internal Quality Assurance process for imagery analysis

A minimum of 10% of still images analysed are to be subject to an internal QA process.

Tenderers must demonstrate their internal Quality Control (QC) system, which includes routine checks of data and analysis.

QC of data and analysis is where data are re-checked and compared against the original and compared to an expected standard/ limit of error/ deviation from the original.  It is also where electronic records (in spreadsheets or databases) are checked against the data on the original field/laboratory datasheets.  This measures the repeatability of the method of analysis and data entry, and highlights factors such as inter-worker variability.  QC must also include details of remedial action in cases where expected standards/limits are not met.

Internal QC must be undertaken by a staff member other than the staff member who conducted the original analysis.

External Quality Assurance process for still images

Ten percent of still images analysed are to be subject to an independent external QA process.

The following steps will be adhered to:

- Images to be quality assured will be selected by JNCC

- The auditing analysts receive the imagery data from JNCC and project level identifications (i.e. substrate and taxonomic image reference collections) from the original analyst. Abundance data are not provided to the auditing analysts, to ensure auditing analyst enumeration is undertaken blind

- The auditing analysts complete the image analysis for selected images as described above

- The results are sent to JNCC and original analysts

- The auditing analysts complete the JNCC image analysis comparison proforma spreadsheet

- JNCC, the original and the auditing analysts meet to resolve any discrepancies in taxa identification and enumeration to the satisfaction of all parties.

Any remedial action required following the QA process must be completed within an agreed timeframe at no extra cost to the project.

All remedial action taken, and associated rationale, are to be recorded and provided as outputs of this contract. The contract shall not be deemed complete until this external Quality Assurance step has been completed successfully

| Party | To provide | Format |
| --- | --- | --- |
| JNCC | Image analysis comparison proforma spreadsheet template and review of completed image analysis comparison proforma spreadsheet | MS Excel spreadsheet MS Word Document |
| Original analyst | Results of audit and review of completed image analysis comparison proforma spreadsheet and summary of all remedial action taken, and associated rationale | MS Excel spreadsheet MS Word Document |
| Auditing analyst | Completed image analysis comparison proforma spreadsheet, review of completed image analysis comparison proforma spreadsheet | MS Excel spreadsheet MS Word Document |

## Outputs

Any products or outputs submitted to JNCC [for publication] should adhere to JNCC’s house-style and should be produced in an accessible format (see product specification for more information).

JNCC require the successful contractor to provide analysis results in the MEDIN compliant MS Excel proforma spreadsheets which will be provided.

Locations of still images should be provided as ArcGIS & QGIS compatible point shapefiles with the substrate assigned to each image included as an attribute for each point.

Please note the Final Report must adhere to the JNCC report template and house style which will be provided to the successful contractor at the start-up meeting.

The report should be no longer than 14,000 words including all tables and appendices.

The report should be provided electronically via email as a Microsoft Word document, and will include the following sections:

Methodology

Results

Details of all QA work undertaken, and any remedial action deemed necessary.

| Output/deliverable | Format |
| --- | --- |
| Imagery analysis results | Completed MS Excel spreadsheets (JNCC Proformas) BIIGLE CSV reports: Image Label report, “Full” Annotation Report” “Annotation Area Report” |
| Comparison of analysis and independent analysis and reconciliation | Excel spreadsheet |
| Point shapefile representing still image locations and substrate assigned to each still image. Shapefile should be ArcGIS & QGIS compatible, imbedded with MEDIN compliant metadata (INSPIRE metadata template available in ArcGIS) and fully georeferenced in a defined coordinate system | ArcGIS & QGIS compatible point shapefile |
| Reference collection of images for each substrate type and taxon identified and metadata spreadsheet. Taxa to be highlighted in image (e.g. using a boundary box) | Still image files labelled with StnCode and substrate type/taxon they represent |
| Final Report | DOC |

## Product Specification

JNCC is committed to making its publicly available resources and documents accessible, in accordance with the Public Sector Bodies (Websites and Mobile Applications) (No. 2) Accessibility Regulations 2018.

Making material accessible means making sure it can be used by as many people as possible.  This includes those with:

- impaired vision

- motor difficulties

- cognitive impairments or learning disabilities

- deafness or impaired hearing

The outputs and material that JNCC publishes should be compliant with the Web Content Accessibility Guidelines version 2.1 AA standard.

To meet this standard, all reports and other documentation which are to be made publicly available must adhere to JNCC’s house-style (to be provided) and be produced using a JNCC template (to be provided), unless otherwise stated. All reports (draft and final) should be provided electronically via email both as a Microsoft Word document and an Adobe PDF.

Copies of documentation associated with case studies should be provided in electronic format with an associated reference catalogue.

For any other outputs or products which are to be made publicly available through JNCC, evidence regarding how the accessibility standard will be reached should be included.

## Dissemination (delete if non-applicable)

The products/outputs produced under this contract will be a JNCC product and shall not be published or disseminated without the written permission of JNCC. Outputs may at some point be published on the JNCC website and all material supplied as part of this contract shall remain copyright of JNCC. The findings from this contract will also be made available to staff within JNCC), Defra and Cefas.

## Timescale

Provisional dates for delivery of the contact outputs are set out below. Exact dates are to be agreed at the start-up meeting based on Contractor and JNCC staff availability.

| Output | Provisional Date |
| --- | --- |
| Start-up meeting (UK) | TBC |
| Interim meeting to discuss any issues or resolve questions, after the analysis of ~10 camera stations has been completed. | WC 09/01/2023 |
| Completion of analysis and reporting, provision of draft deliverables to JNCC and external QA samples to external QA analyst(s) | 01/03/2023 |
| Completion of external QA and remedial action if necessary | 15/03/2023 |
| Wash-up meeting | 20/03/2023 |

In agreeing exact dates, please note that the potential for work under this contract to be funded into 2022/23 is subject to availability of funds.

## Health and Safety

The successful bidder is expected to follow appropriate Health & Safety procedures including adhering to JNCC’s policy on safeguarding. For further information  https://jncc.gov.uk/about-jncc/corporate-information/safeguarding/ and to be able to undertake appropriate risk assessments, evidence of which should be supplied to JNCC. (NB under no circumstances should any work or service commence prior to the receipt of written approval of the risk assessment by the JNCC H&S Advisor).

Any incidents occurring within the contract period should be immediately reported to JNCC.

## Project Management

The successful Contractor shall nominate a project manager who shall be responsible for ensuring the project is completed satisfactorily and who shall be the main contact point for JNCC.

JNCC’s main contact points will be:

Name: Josh Tate

Email: josh.tate@jncc.gov.uk

Telephone: +44 (0)1733 866906

Name: David Reynolds

Email:  david.reynolds@jncc.gov.uk

Telephone: +44 (0)1733 943167

## Instructions for Bid Submission

The bid submission should include the following:

A brief summary of the bidder’s experience in relation to the requirements of this contract;

A proposed approach for achieving the objectives of the contract and delivering the detailed tasks identified within each objective. This should be sufficiently detailed to allow assessment against the evaluation criteria (Section 14);

A detailed project plan (including Gantt chart) with proposed work programme and an estimate of time required to achieve each objective;

A draft Table of Contents for the final report;

Details of Quality Control procedures to be followed

Details of the bidder’s own internal Quality Management System;

Details of the Project Team including their roles and experience, an estimate of their time input into each task and CVs of all personnel who will be involved in the contract/project; please ensure all CVs MUST be attached as a separate PDF documentation from the proposal, so that we can meet our JNCC GDPR retention policy requirements.

Availability of the Project Team for a start-up meeting via Microsoft Teams

Overall quote for the contract to include:

  - Day rates for all members of the Project Team;

  - Costs and time allocation should be clearly allocated to specific tasks within this contract/project; and

  - VAT if applicable. The contractor is to specify whether VAT at the prevailing rate would be applicable to this project and if so, provide their VAT registration number.

The following documentation:

  - Copies of health and safety policy statements where available or a note regarding such items as lone working, emergency procedures and accident reporting;

  - Copies of current public and employer liability insurance certificates;

  - Copies of any appropriate risk assessments; and

  - Copies of any environmental policies should you have them.

In addition, note that the bid submission should provide sufficient information to allow assessment against the evaluation criteria outlined in Section 14.

## Evaluation Criteria (Note to Project Managers evaluation table below is a guide and can be adapted to suit individual project requirements) delete brackets once Annex A finalised

JNCC is not bound to accept the lowest priced or any bid. Having the technical expertise and experience to complete the work to a high standard and being able to complete it within the timescale are of the essence for this contract.

The bid evaluation may be undertaken by a panel consisting of JNCC staff only

For information on how we handle personal data please see our Privacy Notice at https://jncc.gov.uk/about-jncc/corporate-information/privacy-statement/

Bids will be evaluated using the following criteria:

|  | EVALUATION CRITERIA | Maximum Score | Score |
| --- | --- | --- | --- |
| 1. Quality of Bid (50% of the total for the three assessment categories) |  |  |  |
|  | Clarity of proposal particularly work programme and deliverables | 10 |  |
|  | Understanding of, and relevance to, the requirements in particular the adequacy of outputs and understanding of any….name any particular knowledge/skill/understanding expected) | 10 |  |
|  | Soundness and logicality of methods | 5 |  |
|  | Realism and measurability of outputs | 5 |  |
|  | Evidence provided of how accessibility standards will be met | 5 |  |
|  | Identification and proposed solutions to potential risks/issues | 5 |  |
|  | Serious weaknesses which threaten success | 5 |  |
|  | Probability of success | 5 |  |
|  | Sub Total | 50 |  |
| 2. Details of Contractor (20% of the total for the three assessment categories) |  |  |  |
|  | Expertise, experience, and balance of team | 9 |  |
|  | Risks if important team members drop out | 5 |  |
|  | Adequacy of subcontractors if any | 6 |  |
|  | Sub Total | 20 |  |
| 3. Cost (30% of the total for the three assessment categories) |  |  |  |
|  | Transparency and correctness of presentation what does presentation mean here in relation to cost? | 10 |  |
|  | Fairness/reasonableness for the level of work and expertise required | 6 |  |
|  | Appropriateness of ratio of senior to junior staff time | 6 |  |
|  | Clarity of each team member’s contribution and value added | 8 |  |
|  | Sub Total | 30 |  |
| Total Score |  | 100 |  |

## Payment

Unless a payment schedule is stated in your submission and agreed by JNCC project manager. Payment will be made on completion of the objectives following the submission of invoice(s) and based on the satisfactory undertaking of the contractual elements to the agreed standard of the JNCC Project Officer.

## Additional Requirements

All bidders are requested to carefully read the Terms and Conditions applying to this contract. Payment will only be made upon delivery of key outputs.

It is assumed that all costs associated with the production of figures, reproduction of photographs and the final report are accounted for within the rates/fees given.

The bidder is expected to supply all necessary equipment, software, licences, etc. to carry out the obligations required under the contract.

## References

1http://www.nmbaqcs.org/media/1643/nmbaqc_epibiota_interpretation_guidelines_final.pdf & http://www.nmbaqcs.org/scheme-components/epibiota/epibiota-quality-assurance-framework-and-documents/

2 https://www.biigle.de/

3 Copy-Paste from the original material is preferred, to avoid typos. Note if changes are made a lookup table is essential, as it takes a lot of time to write and check the code for matching strings when combining attributes from different files.

4 https://mhc.jncc.gov.uk/

5 https://mcc.jrc.ec.europa.eu/documents/201702074014.pdf

6 Parry, M.E.V. 2015. Guidance on Assigning Benthic Biotopes using EUNIS or the Marine Habitat Classification of Britain and Ireland JNCC report No. 546 JNCC

7 Please note that a mixture of point and area annotations should not be used for a single taxon. i.e. if Alcyonium digitatum is considered colonial it should be labelled as such in all cases.

8 http://www.nmbaqcs.org/scheme-components/epibiota/epibiota-quality-assurance-framework-and-documents/

9 http://randd.defra.gov.uk/Document.aspx?Document=13892_ME5215Objective2-Monitoring.pdf

10 https://hub.jncc.gov.uk/assets/1684dd5e-36e3-4969-852f-4541c82240eb

11 EQA Policy https://jncc.gov.uk/about-jncc/corporate-information/evidence-quality-assurance/

## Appendix A: BIIGLE protocol (adapted from Cefas BIIGLE protocol)

- A BIIGLE account (with editor privileges) will be created for the successful contractor, if one does not already exist, which will allow for annotations to be added to each image.

- Images will be stored on a remote volume which JNCC, MSS and the successful contractor will have access to.

- The contractor will not have access to the volume following completion of the contract.

### Stills Annotation

The Label Tree

The BIIGLE annotation process for stills imagery is split into two parts; Tier 1 (whole image labels – used for metadata such as image quality, relief, habitat etc.)  and Tier 2 (faunal annotation).

An MPA label tree has been created within the BIIGLE project, which provide for all the relevant metadata labels, and a “Biota” sub tree. The Biota sub tree is a work in progress, and is based upon the CATAMI system, enabling us to “nest” higher resolution taxonomies within morphological “classes”. This tree also includes some specific, commonly encountered UK taxa).

The Annotation Process (Tier 1 - Whole Image Labelling for Metadata)

Whole image labels (what we refer to as “Tier 1” labels) are annotations that apply to the whole image, not just to one specific point within the image. As such, these are very useful in annotating for the typical “metadata” that an analyst provides alongside the faunal abundance / percentage cover matrices.

The whole image label annotations should be added at the same time as the Tier 2 faunal annotations, i.e. by using the annotation tool (accessed by clicking on an individual image in the volume overview) for both sections of analysis.

To attach whole image labels using the annotation tool, select the label from the MPA Imagery Analysis Hierarchy (see user guide) and Select the “Image Labels” tab from the side menu:

Figure 1 Showing the “Image Label” tab

Once the “Image Label” tab is open, and the correct label is selected (I.e. Image Quality: Excellent in the above example) then click the “+” symbol in the top right of the “Image Label” tab to append this label to the whole image. Please ensure that a Tier 1 label is appended for every category stated in the RFQ / protocol. Note that no label is required for certain categories (such as Annex I habitats, NIS, OSPAR habitats etc.) where no such habitat / feature is present.

The Annotation Process (Tier 2 – Faunal Annotation)

Once you have navigated to the image (and are therefore in the “Annotation tool”), select the biota label of choice (this could be a morphological label, if ID to genus or species level is impossible) , and then use the “Set Point A” button on the bottom toolbar, and click with the mouse over the first random point

  - This will create the first point “Annotation” of the image.

  - Where it is possible to identify any specific taxa (to family, genus or species level), add these specific taxa to the label tree, nesting them under the most appropriate morphological class.

N.B JNCC require regular updates about taxa which have been added to the MPA label tree

  - It is recommended that you annotate all individuals of the same taxa within the image at the same time, as this is more efficient.

- If the individual / colony you are annotating is a ground-cover taxon, this can be done using the “Draw Polygon” or “Magic wand” tools.  The “Magic Wand” tool is an image analysis and prediction tool for rapid drawing of highly detailed polygons, again select the biota label of choice, and then hover over the Draw Polygon tool on the tool bar - you will then see a second tool appear above, this is the “Magic wand” button. Click this tool, then place the curser over the centre of the individual /colony you are annotating, press and hold the middle mouse button and slowly move the cursor out. Release the button when the polygon has best matched the individual / colony outline.

- Repeat this process until all taxa within the field of view have been classified.

- If the Magic Wand tool does not work, please use the basic Draw Polygon Tool.

Any deviation from this methodology should be approved in writing by JNCC.

Please note there are some specific taxa (i.e. ophiruoids) which should be annotated as Tier 1 percentage cover for this project, outlined in the project background and objectives. This is to tie in with methodology that was used in the initial analysis.

### Report downloading

BIIGLE allows admin users to download “Annotation Reports”. These are CSV documents which contain, line by line the: image ID, file name, annotation tag labels, exact tag position within the image (pixel x and y), BIIGLE user ID.

- It is from these reports that the final dataset will be compiled.

- The contractor can request a report to be generated as required for data management tracking purposes.

## Appendix B: Non-indigenous species (after Curtis et al, 2020)

Taxa listed as non-indigenous species (present and horizon) which have been selected for

assessment of Good Environmental Status in GB waters under MSFD Descriptor 2 (Stebbing et al.

2014)10.

Additional taxa listed as non-indigenous species in the JNCC ‘Non-native marine species in British waters: a review and directory’ report by Eno et al. (1997)11 which have not been selected for assessment of Good Environmental Status in GB waters under MSFD.

https://www.biigle.de/

http://archive.jncc.gov.uk/pdf/Report_546_web.pdf

https://mcc.jrc.ec.europa.eu/documents/201702074014.pdf