Invitation to Quote (ITQ)

Contract STA-0128-03 Provision of Item Writing for Key Stage 1 Mathematics

Contract STA-0128-04 Provision of Item Writing for Key Stage 2 Mathematics

| Tenderer: |  |
| --- | --- |

TABLE OF CONTENTS

1	INTRODUCTION	3

Purpose	3

Structure	3

Disclaimer and Conditions	3

Freedom of Information and Transparency	3

2	INSTRUCTIONS TO TENDERERS	5

Tender Validity	5

Proposed Contract	5

Procurement Timescales	6

Clarification Questions	6

Preparation of Tender	6

STA Point of Contact	7

Confidentiality	7

Conflict of Interest	7

Value Added Tax	7

Submission of Tenders	7

Right to Reject/Disqualify	8

Debriefing	8

3	EVALUATION METHODOLOGY	9

Basis of Award Decision	9

Evaluation Process	9

Award Decision	9

4	SPECIFICATION OF REQUIREMENTS (SoR)	11

Background	11

Revised national curriculum	11

Test Frameworks	11

Project Deliverables/Outputs and Critical Steps	12

Functional Requirements	19

5	Tenderer's Response	30

Key Stage 1 Mathematics	30

Key stage 2 Mathematics	36

6	Annexes	42

Annex A – Test Frameworks	42

Annex B – Item Classification Spreadsheet	42

Annex C – Cost Breakdown	42

Annex D – Copyright permission letter template	42

Annex E – Test Development External Suppliers Security Policy	42

Annex F – National curriculum Test Design Specification	42

# INTRODUCTION

## Purpose

  - This ITQ has been issued by the Standards and Testing Agency (STA) for the purpose of securing items for tests in

- key stage 1 mathematics

- key stage 2 mathematics

- (collectively “the Item Writing Services”).

  - The delivery of the Item Writing Services will be governed by the Department for Education’s (DfE) standard Contract for Item Writing Services which will be let in accordance with, and subject to, English law.

## Structure

  - This ITQ:

Outlines the planned procurement process;

Sets out the context for the required services and details of the STA’s requirements; and

Contains a tender response section to evaluate the Tenderer's proposed solution to the STA requirements ("Tender").

## Disclaimer and Conditions

  - No information contained in this ITQ or in any communication made between STA and any Tenderer shall be relied upon as constituting a contract, agreement or representation that any contract will be offered.

  - STA reserves the right, subject to compliance with the Public Contracts Regulations 2006 (as amended), ("the Procurement Regulations"), to change without notice the basis of, or the procedures for, this ITQ or to terminate the ITQ at any time. Under no circumstances shall STA incur any liability in respect of this ITQ or any supporting documentation and STA will not reimburse any costs incurred by Tenderers or potential Tenderers in connection with preparation and/or submission of their Tenders.

  - The information contained within this document is confidential and should not be disclosed except for purposes related to the completion of the Tender.

  - STA is responsible for developing the national curriculum assessments on behalf of DfE and must ensure that all contracted agencies and consultants are aware of, and comply with, the relevant sections of the current Ofqual Regulatory Framework.

To reference please refer to the Regulatory Framework for National Assessments: National curriculum and Early Years Foundation Stage https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/481558/2011-regulatory-framework-for-national-assessments.pdf

## Freedom of Information and Transparency

  - As the executive agency of a public authority, STA is committed to open government and to meeting its legal responsibilities under the Freedom of Information Act 2000 (“FOIA”). Accordingly, Tenderers should be aware that all information submitted to a public authority may need to be disclosed by the public authority in response to a request under the FOIA and that, in addition, DfE may also decide to include certain information in the publication scheme, which it maintains under FOIA.

  - STA participates fully in the Government’s transparency arrangements. As such, Tenderers should be aware that:

- any contracts or agreements resulting from its procurement exercises may be published in full, subject to limited redactions in line with FOIA exemptions; and

- financial transactions in relation to any contracted goods or services will be published and so cannot be deemed commercially sensitive (see over).

  - If a Tenderer considers that any of the information included in its Tender is commercially sensitive, it should identify this information in the table below and explain a) what harm may result from disclosure if a request is received, and b) the time period applicable to that sensitivity. Tenderers should be aware that, even where they have indicated that information is commercially sensitive, STA may be required to disclose in response to a request under FOIA or as part of the Government's transparency arrangements. For example, the value of a contract must be made publicly available so this information cannot be deemed commercially sensitive.

| - Section | - Commercial Sensitivity | - Time Period |
| --- | --- | --- |

# INSTRUCTIONS TO TENDERERS

  - Tenderers should read these instructions carefully before completing their Tenders.

  - These instructions are designed to ensure that all Tenderers are given equal and fair consideration. It is important therefore that you provide all the information asked for in the format and order specified.

  - The Tenderer shall not make contact with any other employee, agent or consultant of STA who is in any way connected with this ITQ exercise during the period of this ITQ exercise, unless instructed otherwise by the Test Development Procurement Manager Rashida Akbar.

  - All material issued in connection with this ITQ shall remain the property of STA and shall be used only for the purpose of this ITQ exercise. Any confidential STA Information shall either be returned to STA or securely destroyed by the Tenderer (at STA’s option) at the conclusion of the exercise.

  - The Tenderer shall ensure that each and every proposed sub-contractor, consortium member and adviser abides by the terms of these instructions.

  - STA shall not be committed to any course of action as a result of:

Issuing this ITQ or any invitation to participate in this ITQ exercise;

Communicating with a Tenderer or a Tenderer’s representatives or agents in respect of this ITQ exercise; or

Any other communication between STA (whether directly or by its agents or representatives) and any other party.

  - Tenderers shall accept and acknowledge that, by issuing this ITQ, STA shall not be bound to accept any Tender and reserves the right not to conclude a contract for the services for which Tenders are invited.

  - STA reserves the right to amend, add to, or withdraw all or any part of this ITQ at any time during the ITQ exercise.

## Tender Validity

  - Your Tender should remain valid for a period of 30 days from the submission date.

## Proposed Contract

  - Contracts for the provision of Item Writing Services will be let under the STA’s standard Contract for the Provision of Item Writing Services. Contract numbers for each subject are provided in the table below:

| - Subject | - Contract Number |
| --- | --- |
| - Key stage 1 Mathematics | - STA-0128-03 |
| - Key stage 2 Mathematics | - STA-0128-04 |

## Procurement Timescales

  - The proposed timetable for the ITQ exercise is set out below. STA reserves the right to change this if it becomes operationally necessary so to do.

| DATE | STAGE |
| --- | --- |
| 31 October 2016 | ITQ issued to Suppliers |
| 12:00hrs, 14 November 2016 | Deadline for submission of Clarification Questions by Tenderers |
| 12:00hrs, 29 November 2016 | Closing Date for receipt by STA of Tenders |
| 15/16 December 2016 | Notification of Award Decision |
| KS1: Between 9 and 13 January 2017 KS2: Between 16 and 20 January 2017 | Proposed contract Commencement and Start-Up Meeting |

## Clarification Questions

  - Clarification Questions should be submitted by e-mail only to testdevelopment.sta@education.gov.uk and cc’d to rashida.akbar@education.gov.uk. No further requests for clarifications will be accepted after the date shown in the table above. All communications should be clearly headed "Provision of Item Writing "and should include the subject and contract number which the question refers to. The name, contact details and position of the person making the communication should also be included.

  - STA will endeavour to answer all questions as quickly as possible, but cannot guarantee a minimum response time.

  - In order to ensure equality of treatment of Tenderers, STA intends to publish the questions and clarifications raised by Tenderers, together with STA’s responses (but not the source of the questions), to all participants on a regular basis via email.

  - Tenderers should indicate if a query is of a commercially sensitive nature – where disclosure of such query and the answer would or would be likely to prejudice its commercial interests. However, if STA at its sole discretion either does not consider the query to be of a commercially confidential nature, or considers the query to be one which all Tenderers would potentially benefit from seeing, then STA will either:

Invite the Tenderer submitting the query to either declassify the query and allow the query, along with the STA’s response, to be circulated to all Tenderers; or

Request the Tenderer, if it still considers the query to be of a commercially confidential nature, to withdraw the query.

  - STA reserves the right not to respond to a Clarification Question or to circulate such a Question where it considers that the answer to that Question would be likely to prejudice its own commercial interests.

## Preparation of Tender

  - Tenderers are solely responsible for their costs and expenses incurred in connection with the preparation and submission of their Tender. Under no circumstances will STA, or any of its advisers, be liable for any costs or expenses borne by Tenderers, sub-contractors, suppliers or advisers in this process.

  - Tenderers are required to complete and provide all information required by STA. Failure to comply with the ITQ requirements may lead STA to reject a Tender.

  - STA relies on Tenderers' own analysis and review of information provided. Consequently, Tenderers are solely responsible for obtaining the information which they consider is necessary in order to make decisions regarding the content of their Tenders and to undertake any investigations they consider necessary in order to verify any information provided to them by STA during the procurement process.

## STA Point of Contact

  - Unless stated otherwise in these instructions or in writing from STA, all communications from Tenderers (including their sub-contractors, consortium members, consultants and advisers) during the period of this procurement exercise must be directed to the contact identified in paragraph 3.12.

  - All communications should be clearly headed "Provision of Item Writing "and should include the subject and contract number which the question refers to. The name, contact details and position of the person making the communication should also be included.

## Confidentiality

  - All information supplied by STA to you must be treated in confidence and not disclosed to third parties except insofar as this is necessary to obtain sureties or quotations for the purposes of submitting the Tender.

  - All information supplied by Tenderers to STA will similarly be treated in confidence except for the disclosure of such information as may be required in accordance with the requirements of UK government policy on the disclosure of information relating to government contracts including the Freedom of Information Act and forthcoming transparency procedures.

## Conflict of Interest

  - Any known conflicts of interest, or any potential conflicts of interest that may be reasonably foreseen, should be declared in the Tender.

## Value Added Tax

  - STA is VAT registered. It is also an “eligible body” as classified in VAT Notice 701/30 "Education and Vocational Training". Proposals must therefore include VAT where applicable. Where any doubt exists, Tenderers are expected to have sought clarification from HM Customs and Excise. Prices in the Tender will be accepted on this basis.

  - Tenderers are requested to set out their understanding of the VAT status of the contract based on the services to be provided and the status of STA. There will be no adjustment to the contract sum if VAT is subsequently found to be payable.

## Submission of Tenders

  - The Tender must be submitted in the form specified by completing the Tenderer's Response using Arial 11 font and in English and using pounds sterling. Where applicable, word limits must be adhered to and material in excess of these limits will not be evaluated.

  - Tenderers must submit their responses by email to TendersTD.STA@education.gov.uk cc’d to rashida.akbar@education.gov.uk in the following format:

One complete and signed electronic version in MS Word 2010 (or compatible) format labelled 'priced' of their Tender and with their organisation name in the document title for each subject tendered; and

One electronic version in MS Word 2010 format (or compatible) labelled 'not priced' of their Tender excluding the pricing information and with their organisation name in the document title for each subject tendered.

  - Any example test materials and supporting documents submitted in response to Question 3 of the Tenderer’s Response should be merged into a single file per subject and either embedded into your response document, or provided as a separate document. Any passwords should be provided separate to your bid.

  - Tenders must be received by 12:00 noon on 29 November 2016.

  - Tenders will be accepted at any time up to this deadline but will not be opened or evaluated until the deadline has passed.

  - Any Tender received after the deadline may be rejected unless the Tenderer can provide irrefutable evidence that the Tender was capable of being received by the due date and time and that delivery failure was beyond their reasonable control.

## Right to Reject/Disqualify

  - STA reserves the right to reject or disqualify a Tenderer where:

The Tenderer fails to comply fully with the requirements of this ITQ, including proper completion of the format for response, or is guilty of a serious misrepresentation in supplying any information required in this document; or

There is a change in identity, control, financial standing or other factor relating to the Tenderer that impacts on the selection and/or evaluation process.

## Debriefing

  - Following the conclusion of the ITQ exercise, all unsuccessful Tenderers will have the opportunity of a debriefing. Unsuccessful Tenderers should notify STA by email that they wish to be debriefed. STA will aim to debrief unsuccessful Tenderers within 10 working days of receiving such a request.

# EVALUATION METHODOLOGY

## Basis of Award Decision

Technical Evaluation		70%

Commercial Evaluation		30%

## Evaluation Process

  - Tenders will be formally logged upon receipt - any Tender that is received after the deadline for submission will be rejected.

  - Following the deadline for submission, a compliance check will then be conducted on all Tenders that are received on time to determine whether they correspond to the tender requirements. STA may reject any Tender that does not comply with these tender requirements.

  - Tender evaluation will then comprise three stages:

(1) Legal evaluation – confirmation of acceptance of the terms and conditions of the standard Contract for Item Writing Services according to the Declaration by Tenderer.

(2) Technical evaluation – scoring of the un-priced technical responses required in the Tender by an independent evaluation panel using the scores per criterion set out in that section and with the technical criteria weighted according to the table below:

| Technical Criterion | Weighting |
| --- | --- |
| Expertise in item development and design (see question 1) | 35% |
| Project Management (see question 2) | 10% |
| Example test materials (see question 3) | 35% |
| Item Management (see question 4) | 10% |
| Informal trialling (see question 5) | 10% |

(3) Commercial evaluation – assessment of the price for the services as set out in the pricing schedule

## Award Decision

  - The technical and commercial evaluation scores will then be combined using the following methodology:

Technical Score = 100 x (Tenderer's technical score / Best technical score)

Price Score = 100 x (Lowest price / Tenderer's price)

Combined Score = (70% x Technical Score) + (30% x Price Score)

Quality Threshold: Tenderers scoring over 66% for their technical score will then be considered for award. STA reserves the right to amend this threshold in the event only one supplier scores higher – we will notify all parties if this occurs.

  - Each key stage submitted will be evaluated separately.

  - Each Work Package will be evaluated separately and they will be awarded to the Tenderer with the highest combined score in each case, with the intention of awarding to two different suppliers per key stage. STA reserves the right to award all work packages to a single supplier in the event only one supplier scores higher than the Quality Threshold.

  - STA reserves the right to withhold awarding Work Packages for a particular subject if no suppliers pass the Technical Score or costs exceed the approved budget.

For key stage 1 there will be two Work Packages : One Work Package  will be awarded to the Tenderer with the highest score which exceeds the technical threshold. The other Work Package will be awarded to the Tenderer with the second highest combined score, assuming the technical threshold has been exceeded.

For key stage 2 there will be two Work Packages: One Work Package  will be awarded to the Tenderer with the highest score which exceeds the technical threshold. The other Work Package will be awarded to the Tenderer with the second highest combined score, assuming the technical threshold has been exceeded.

  - Following evaluation, a summary of the relative quality score and relative price score will be fed back to all bidders. An example of the level of information provided for each work package is given below:

|  | Technical threshold result | Relative Quality Score | Relative Price Score | Weighted Combined Score | Rank for Compliant Bidders |
| --- | --- | --- | --- | --- | --- |
|  |  | 70% | 30% |  |  |
| Tenderer A | PASS | 0.73 | 0.12 | 0.55 | 3 |
| WINNER 1 | PASS | 0.93 | 1.00 | 0.95 | 1 |
| Tenderer C | PASS | 0.67 | 0.23 | 0.54 | 4 |
| WINNER 2 | PASS | 1.00 | 0.57 | 0.87 | 2 |

# SPECIFICATION OF REQUIREMENTS (SoR)

Background

Section 4 of this ITQ sets out the Specification of Requirements (SoR) with respect to the items and mark schemes for the tests.

Unless indicated otherwise, it should be assumed that each requirement applies to key stage 1 and key stage 2.

STA reserves the right to award a contract for a whole subject and/or key stage to a single supplier in the event that only one suitable Tender is received.

All work packages are to assess the range of cognitive demand, question styles and content domain of the test framework in the relevant subject area as specified in section 5.9.  Finalised test frameworks are available to download using the link in section 5.9 below. Please note that in some instances numbers of marks to be developed by item writing agencies will differ in proportion from those detailed in the test framework to address areas of shortfall in existing items. Further details are included later in this ITQ with additional clarification to be provided at start-up meetings.

Please note that the STA uses an item banking approach for test development. The item bank will be reviewed on a regular basis to identify areas where there are insufficient questions, meaning that at the point of project start-up, agencies will be provided with a more specific question writing brief to help address any areas of shortfall.

Revised National Curriculum

On 11 September 2013 the Secretary of State for Education published the new national curriculum framework following a series of public consultations. The Government wants the new national curriculum for primary English, mathematics and science to set out the very highest expectations for all pupils and to be on a par with the highest-performing education jurisdictions in the world.

The new Programmes of Study are available to download: https://www.gov.uk/government/publications/national-curriculum-in-england-primary-curriculum

The documents are very specific about the content to be covered, given the fundamental importance of these subjects as a foundation for further study and as the basis for our system of school accountability.

Test Frameworks

Test frameworks for key stage 1 and key stage 2 are based on the new national curriculum published in September 2013. Each framework defines what is assessed, via the content and cognitive domains and sets out the criteria for test construction in the test specification. https://www.gov.uk/government/collections/national-curriculum-assessments-test-frameworks

Sample materials have been published based on the frameworks. https://www.gov.uk/government/collections/national-curriculum-assessments-2016-sample-materials

The 2016 key stage 1 mathematics test can be found here: https://www.gov.uk/government/publications/key-stage-1-tests-2016-mathematics-test-materials.

The 2016 key stage 2 Mathematics test can be found here:  https://www.gov.uk/government/publications/key-stage-2-tests-2016-mathematics-test-materials

## Project Deliverables/Outputs and Critical Steps

The Project deliverables/outputs are provided in the table below, and individual deliverables or outputs are indicated as Critical Steps where appropriate. All deliverables and outputs are categorised as mandatory and it is essential that you confirm that you can meet them in full. Unless indicated below, all dates are negotiable with STA. Failure to provide confirmation in your proposal documents may result in your proposal being rejected.

The specific date for all Requirements 1 – 11 must be included within the project plan in the response to the Technical Evaluation.

| No | Deliverables/Outputs | Acceptance Criteria | Due Date |
| --- | --- | --- | --- |
| 1 | Start-Up Meeting – FIXED DATE RANGE Supplier will provide: - Detailed plan for item and mark scheme production for review and joint sign-off - Detailed plan for when checkpoints will be held for review and joint sign-off - Detailed project risk and issue log (Risk Log) for review and joint sign-off - Project Initiation Document (PID) STA will provide: - Clarification of any item writing requirements | Project Director / Project manager (or equivalent) attend the Start-Up Meeting and provision of listed documents by agreed date. | KS1: 9 to 13 January 2017 KS2: 16 to 20 January 2017 |
| 2 | Checkpoint Meetings and Management Information To attend regular Checkpoint meetings at least once a month, although they may need to be more frequent as some stages of the project. These meetings may be held as telephone conference calls. Checkpoint reports to be submitted to STA two working days in advance of each Checkpoint meeting. | Project manager (or equivalent) attends each Checkpoint meeting on agreed date and submission of Checkpoint report two working days in advance of each checkpoint meeting. | To be agreed at start-up meeting |
| 3 | Interim Handover – Critical Step Please refer to functional requirements section for full details of the materials to be handed over. | 100% of drafts of all materials required for completion of work package(s) received electronically by agreed date and to criteria specified in section 4.5. All items informally trialled and being considered for Final Handover have received positive feedback from teachers and / or pupils; or are submitted with amendments and supporting evidence from trialling for those amendments. | No later than 10 working days before date of interim review meeting. |
| 4 | Interim Review Meeting Please refer to functional requirements section for full details of purpose and scope of the meeting. | Project Manager / Lead Item Writer attend Interim Review meeting on agreed date. | Key stage 1: week beginning 3 April 2017 Key stage 2: week beginning 27 March 2017 |
| 5 | Informal Trialling – Critical Step Informal trialling should be completed before the end of the summer term (in the UK). Please refer to functional requirements section for details regarding informal trialling. | Required amendments completed before trialling. Volumes of informal trialling and variation to cost agreed. 100% of agreed items trialled with specified number of schools and pupils. STA are notified of possible trialling locations two weeks before the start of the trial and are consulted re dates of visits to allow dates to be agreed that enable STA staff to attend some visits. | Complete in sufficient time to allow for completion of required activities before post-trial handover. |
| 6 | Post-Trial Handover – Critical Step Please refer to functional requirements section for full details of the materials to be handed over. | All items informally trialled and being considered for Final Handover have either received positive feedback from teachers and / or pupils; or are submitted with amendments and supporting evidence from trialling for those amendments. All items requiring significant amendment following interim review are submitted with appropriate amendments and nay required new items are accepted following review. | No later than 5 working days before date of post-trial meeting, |
| 7 | Post-Trial Meeting Please refer to functional requirements section for full details of purpose and scope of the meeting. | Project manager (or equivalent) attends meeting on agreed date and is able to talk through rationale behind all proposed amendments to items. | Key stage 1: No later than week beginning 26 June 2017 Key stage 2: No later than week beginning 19 June 2017 |
| 8 | Final Handover – Critical Step Please refer to functional requirements section for full details of the materials to be handed over. The handover will take place via secure means as agreed with STA; e.g. courier for hardcopy materials and STA’s portal/EGRESS for electronic materials. A meeting is only required at this stage, if the need is identified at interim review. | 100% of specified hard copy materials received at STA by agreed date and materials are of appropriate quality as listed under Performance Requirements. Receipt of electronic materials specified and attendance at Final Handover meeting on agreed date (“Final Handover Date”) | Key stage 1: No later than week beginning 31 July 2017 Key stage 2: No later than week beginning 24 July 2017 |
| 9 | Acceptance of Final Handover materials – Critical Step Please refer to functional requirements section for details. STA will notify Suppliers once all Acceptance Criteria have been met. | 100% of specified materials with STA no later than two weeks after Final Handover Date. All materials to be error free. | No later than two weeks after Final Handover Date |
| 10 | Lessons learnt meeting To take place after completion of final acceptance if both STA and the Supplier are in agreement that this would be beneficial. | N/A | To be agreed between STA and Supplier following final handover. |

## Functional Requirements

| Functional Requirements |  |
| --- | --- |
| Assessment type: | National Curriculum Assessment – for pupils at the end of key stage 1 and key stage 2 |
| Item Development and Design: | The number of marks stated for each work package outlined below is the total number of marks which must be provided at final handover. Suppliers will need to ensure sufficient items are created to allow for any losses during the process. All items developed for this contract are required to be provided at the final handover stage. For items not comprising the final submission, these should be provided in the most recent version that they reached before being removed from the final question selection. |
| Item Writing requirements for each key stage: | Key stage 1 Mathematics |
|  | The items are destined for tests which assess the new National Curriculum programme of study for key stage 1 mathematics. Final test format The test will have 60 marks and will be comprised of two test papers: paper 1 (25 marks) will test children’s written arithmetic and will be produced internally by STA; paper 2 (35 marks) will test the whole range of the mathematics curriculum and will include questions involving mathematical fluency, solving problems and reasoning. The work packages apply to paper 2 only. No straightforward calculation items will be included in this paper as this is only tested in paper 1. The content domain from chapter four of the test framework details the statutory elements of the National Curriculum for mathematics, but items will need to be written that reflect the ‘flavour’ of the curriculum and this should be taken from the full National Curriculum for mathematics. Paper 2 will begin with five aural questions to introduce children to the test. The remaining 30 marks will be written questions. Work Packages 1 and 2 STA requires 140 marks of new and acceptable mathematics items at key stage 1. The items should be written to match the cognitive demand ratings as described in the new test framework for 2016 for complexity and item response. Work Packages 1 and 2 both contain 70 marks each. For each work package, the items should be distributed as follows: Number: 40 marks (+/- 2 marks) Measures, geometry and statistics: 30 marks (+/- 2 marks) Year 1: 12 marks (+/- 5 marks) Year 2: 58 marks (+/- 5 marks) 10 aural marks (n.b. for these questions please include the aural script on the same page as the pupils response space. Although questions will not be presented in this way in a final test, this format supports the accurate review of questions.) 60 written marks Context: 25 out of the 70 marks to be in context (+/- 5 marks) The following table reflects the ranges of mark for curriculum areas that is broadly similar to those used by STA for test construction. Further clarification on ranges required for each work package will be provided at the start-up meeting, since the ranges listed below may need to be adjusted to compensate for any imbalance in curriculum areas in STA’s item bank. Number Calculations Fractions Measures Geometry Position Statistics; 4-16 20-40 4-10 6-14 4-12 2-4 2-4. The test will need to include items of sufficient challenge to stretch the most able in the cohort and the bid should reflect this. Each item will need to be assigned a rating of 1 to 4 on each row of the cognitive demand table below, in the approximate proportions indicated: - Cognitive domain strand; - 1 Low; - 2; - 3; - 4 High; - Total marks. - Depth of understanding; 5-10; 15-30; - 20-30; 10-20; - 70. - Computational complexity; 15-25; 10-35; - 10-30; 5-10; - 70. - Spatial reasoning and data interpretation; 40-55; 5-10; - 5-10; 5-10; - 70. - Response strategy; 10-20; 10-20; - 20-30; 10-20; - 70. Chapter 4 of the mathematics test framework details the statutory requirements of the national curriculum. Items should be written that cover the breadth of the curriculum. Some additional requirements for each work package are as follows: - 6 two-mark ‘show your working’ questions per work package (+/- 1 question) - maximum of 15 marks of selected items. Additional requirements for specific national curriculum references to be tested will be made available at or before the start-up meeting for the successful supplier(s). |
|  | Key stage 2 Mathematics |
|  | The items are destined for tests which assess the new National Curriculum programme of study for key stage 2 mathematics. Final test format The test will have 110 marks and will be comprised of three test papers: paper 1 (40 marks) will test children’s written arithmetic and will be produced internally by STA; papers 2 and 3 (35 marks per paper) will test the whole range of the mathematics curriculum and will include questions involving mathematical fluency, solving problems and reasoning. The work packages apply to papers 2 and 3 only. No straightforward calculation items will be included in this paper as this is only tested in paper 1. The content domain from chapter four of the test framework details the statutory elements of the National Curriculum for mathematics, but items will need to be written that reflect the ‘flavour’ of the curriculum and this should be taken from the full National Curriculum for mathematics. Work Packages 1 and 2 STA requires 280 marks of new and acceptable mathematics items at key stage 2. The items should be written to match the cognitive demand ratings as described in the new test framework for 2016 for complexity and item response. Work Packages 1 and 2 both contain 140 marks each. For each work package, the items should be distributed as follows: Number: 90 marks (+/- 5 marks) Measures, geometry and statistics: 50 marks (+/- 5 marks) Upper KS2: 100 marks (+/- 5 marks) Lower KS2: 40 marks (+/- 2 marks) Context: 50 marks to be in context (+/- 10 marks) The following table reflects the ranges of mark for curriculum areas that is broadly similar to those used by STA for test construction. Further clarification on ranges required for each work package will be provided at the start-up meeting, since the ranges listed below may need to be adjusted to compensate for any imbalance in curriculum areas in STA’s item bank. Number Calculations Fractions, decimals, percentages Ratio Algebra Measures Geometry Position Statistics; lower 6-8 8-12 3-7 N/A N/A 5-9 2-6 2-4 2-6; upper 8-12 14-22 15-17 11-15 8-14 10-16 7-11 4-8 5-9. Each item will need to be assigned a rating of 1 to 4 on each row of the cognitive demand table below, in the approximate proportions indicated: - Cognitive domain strand; - 1 - Low; - 2; - 3; - 4 - High; - Total marks. - Depth of understanding; - 10-30; - 35-50; - 35-50; - 25-45; - 140. - Computational complexity; - 10-20; - 40-60; - 40-60; - 20-30; - 140. - Spatial reasoning and data interpretation; - 60-95; - 15-35; - 15-35; - 5-20; - 140. - Response strategy; - 15-75; - 20-40; - 40-60; - 10-20; - 140. Some additional requirements for each work package are as follows: - 4 or 5 three-mark ‘show your method’ questions per work package (these should all have computational complexity ratings of 4 n.b. these questions are required to include either a long division or long multiplication calculation along with one or more additional steps) - 16 two-mark ‘show your method’ questions per work package (+/- 2 questions) - 12 explain questions per work package (unless these can be answered using a straightforward counter example, they should have a response strategy of 4) (+/- 2 questions) - maximum of 25 marks of selected items: (multiple choice style questions should have a response strategy of 1, matching questions should have a response strategy of 2) Additional requirements for specific national curriculum references to be tested will be made available at or before the start-up meeting for the successful supplier(s). |
| Mark schemes/coding Frames for all subjects | Mark schemes must be developed for all items. For each key stage, please use wording from the mark schemes for the 2016 test and mark schemes as a guide to standard mark scheme wording. STA will also aim to provide additional guidance on standard wording for commonly occurring question types at the start-up meeting, along with the new general guidance section of the 2017 mark scheme. The mark schemes must provide sufficient and clear guidance for teachers and markers to: - allow marks to be allocated reliably, with consistency and accuracy - enable marking to be manageable - enable the marking of the tests to be effectively standardised - have a principle to define what is correct - include examples of responses that illustrate the range of correct responses and possible incorrect or insufficient responses. Ideally, mark scheme exemplars should be drawn from informal trialling, where the items have been trialled. The mark schemes should: - Clearly and succinctly communicate the marking principles for creditworthy and possible non-creditworthy responses to each item - Be straightforward to apply and recognise and reward pupils' responses appropriately |
| Item and mark scheme design | Prior to Interim Handover, items can be created in Adobe InDesign or Microsoft Word as preferred by the agency with the understanding that large amendments are likely to be required after the interim review meeting and before informal trialling. Mark schemes should be presented in Microsoft Word (or equivalent). For Final Handover, all items must be designed, using Adobe InDesign (STA currently uses Adobe Indesign CC, 2015.3 release), such that they match as closely as possible the style of the supplied key stage 1 and key stage 2 tests in relation to all design elements including font, font size, spacing, diagram style and illustration style. Templates and the requirements of the Design Specification will be provided to all winning bidders in Feb. 2017. Mark schemes should be submitted in Microsoft Word 2010 (or compatible subject to prior agreement) at Interim and Final Handover (see below). There is no requirement to create Adobe InDesign versions of the mark schemes. All content in mark schemes handed over to STA should be fully editable in Microsoft Word 2010 (or compatible subject to prior agreement) with the exception of any complex artwork or diagrams which should be embedded in the appropriate place in the document. The mark schemes should also match the style and layout of the 2016 mark schemes for the appropriate key stage as far as possible. |
| Artwork, texts and other external materials | Written test item texts, artwork or data All graphics that are fundamental to the questions and mark schemes (e.g. data sources, diagrams, photographs) must be produced and supplied at Final Handover. Where texts, artwork or data have been commissioned, please include the original material, contact details for the creator of the material, and a statement confirming assignment of the intellectual property rights (“IPR”) in the material from the creator to DfE. The formal assignment of the relevant IPR in the commissioned work must be completed by the Final Handover Date, using the templates provided in Annex D. Where there is a third party owner of any materials, it should be referenced as described below. Referencing source materials and artwork Any materials using externally sourced texts, artwork or data need to be fully referenced; including title, name of copyright owner, name of the author/editor/creator, details of the edition, publisher and page/location of the material within the source. If sourced from the web, a print out of the original website, showing the relevant artwork or data must be included. |
| Item classification | The Supplier must classify all items according to the fields on the item classification spreadsheet, and present the item information on the spreadsheet template supplied. Please note that a generic template is used for all subjects and key stages, with columns hidden for each project where they don’t apply. An example spreadsheet is provided in Annex B, which shows the columns for KS2. A final version for the relevant key stage(s) will be provided to successful supplier(s) at or before the start-up meeting This spreadsheet should be included with the materials presented at Final Handover (see below). Please note that on the question tab of the item classification spreadsheet there should be one row per question, while in the item tab each item (e.g. question part) should be presented on a separate row. |
| Interim Handover | Interim Handover must occur no later than week beginning 20 March 2017 for key stage 1 and week beginning 13 March 2017 for key stage 2. To provide copies of all materials, including amendments following review by any external consultants that the item writing agency may be working with. Where final versions are not available, a sketched outline or layout of any proposed illustrations or graphics should be provided, or a suitable placeholder graphic. The following materials must be sent to STA: - Combined PDF file of all items – the PDF of items should also be compiled into one file containing all test items/questions. Items should be ordered within the file according to National Curriculum strand. For KS1, all aural items should be presented first, followed by the written questions. - Collated file of all mark schemes, can either be in Word (or compatible) subject to prior agreement) or pdf. Order of mark schemes to match order of questions. - Draft item classification spreadsheet(s) in Excel 2010 format (or compatible). The order that questions appear in the item classification spreadsheet must match the order in the collated question file. - Summary table demonstrating the coverage of the interim handover materials against the number of marks, response types, content and cognitive domains specified in this ITQ and in the additional information provided during the start-up meeting. - InDesign files (STA currently uses Adobe Indesign CC, 2015.3 release) of at least 10% of the total marks required at the interim handover stage in order for STA to check that the materials comply with the Design Specification (see Annex G) and software compatibility. For this purpose, the files need to be submitted according to the specification and the template (to be provided in February 2017) but do not need to be the latest or final versions of the files. The remaining items to be handed over in InDesign or MS Word (or compatible) format. |
| Interim Review | STA will review the materials submitted at Interim Handover. A meeting will be held between STA and the item writers to review those materials. One of STA’s independent curriculum advisors will also attend this meeting. Any further changes to materials will be agreed at this meeting. The Supplier will complete these and any other agreed amendments prior to informal trialling (for items included in the trial) and final handover (for all items not included in the trial). Feedback will be provided at the Interim Review meeting on adherence to the Design Specification for those items submitted in InDesign format. Where possible a member of STA’s design team will attend part of the interim review meeting, to enable to Supplier to discuss any queries relating specifically to the house style template in InDesign. As a result of this feedback, the Supplier may be required to provide an additional set of all materials prior to final handover to ensure compliance with the Design Specification. An additional purpose of this meeting is to agree which items need to be informally trialled, and which do not, within the Supplier’s available resource. It will also be used to determine any amendments which need to be carried out to those items being trialled before they are presented to pupils. The final decision as to which items are trialled will lie with STA. Suppliers must ensure that sufficient materials are presented to STA prior to this meeting to ensure that the agreed number of items and/or marks as defined for each subject are available for handover at the end of the contract. The meeting will also be used to agree the format and content of the informal trialling report. The outcome of this meeting will determine the final cost for informal trialling. Should any items require significant amendments following interim review (where amendments are not agreed within the meeting), or the need for additional items is identified, these items will be required to be submitted for review by STA at the post-trial meeting, even if not included in the informal trial. The meeting will be chaired by STA and take place in STA offices in Coventry or London. |
| Informal Trialling | The primary aim of informal trialling is to aid development of mature items and mark scheme. Suppliers must ensure that as far as possible those individuals, or the key individual, who have devised the items (the Item Writer) conduct trialling personally so they get first hand feedback on the language and layout being used, area being assessed, and the interpretation and understanding of the items by pupils and teachers. Whether or not a pupil answers correctly is of secondary concern, rather that they understand what is being asked of them regardless of their answer. Established item types or those where pupil behaviours can be accurately or reasonably predicted should not be trialled. Each item should be trialled with at least 15 pupils, and those pupils should have been taught the particular curriculum area / topic area the item is assessing, or have been taught an equivalent programme of study. Pupils should be of an appropriate age and overall should show the range of abilities expected at the end of key stage 1 or 2. The items should be discussed with pupils in small groups of 4-6 pupils. It is not expected that trialling samples will be representative. Suppliers should provide details of the volume of items they will be able to trial with their Item Writers conducting the trialling and any interviews, and provide detail of their trialling model to ensure items and mark schemes are improved or validated as a result of the trial. Suppliers should also provide the following costs: - Informal trialling – fixed costs - Informal trialling – variable costs based on trialling 100% of the items written for this contract. There is no requirement to collect quantitative data as a result of this trial as the nature of the samples will not be representative. Any feedback from the trial should comprise summary details of when trialling took place, types of schools uses and details of pupils involved, along with qualitative data and evidence for each question only. STA staff may wish to accompany the trialling agency on a small number of visits to schools to observe so dates and locations of schools where trialling is taking place are to be provided to STA at least two weeks in advance of the first trial taking place. For any visits STA staff undertake, they should be provided with a clean set of the informal trialling booklets and mark schemes for the tests they are observing. At the start of the informal trialling STA should be sent two clean hard copies of all the Informal Trialling booklets and mark schemes / coding frames. Expected outputs from the trials should be by exception only and should include: - Child-level feedback from discussion in small groups with the administrator on their experience of the items and their level of understanding. - Teacher feedback on the same. - Detailed amendments to items and mark schemes as a result of the trials. Qualitative feedback from the informal trial will be presented at the post-trial meeting. People trialling items must have prior knowledge, preferably through integral involvement in origination, but minimally through having reviewed and discussed the materials with the Item Writers. |
| Post-Trial Handover | Following the informal trial, item writing agencies are required to provide STA with the following documents at least 5 working days in advance of the post-trial meeting: Hard copy: - Two clean hard copies of all the Informal Trialling booklets and mark schemes / coding frames. - Two sets of materials containing the suggested mark-ups or amendments as a result of the informal trialling and any other items that were not trialled Electronic copy: - An electronic report listing the points specified in the previous section and other feedback obtained during informal trialling. - A collated pdf copy of items containing the suggested mark-ups or amendments as a result of the informal trialling. A collated Microsoft Word 2010 (or compatible) or pdf file of mark schemes for these questions, to be provided in the same order as the questions. - A collated pdf copy of any items identified as needing significant amendments at interim review and any new items, which were not included in informal trialling. A collated Microsoft Word 2010 (or compatible) or pdf file of mark schemes for these questions, to be provided in the same order as the questions. - Updated item classification spreadsheet in Microsoft Excel 2010 (or compatible), with summary table(s) showing coverage across content domain strands and all other areas listed in the item writing requirements above, as indicated by the supplied template (Annex B). These should include all items due to be presented for final handover, including those not selected for informal trialling. - (optional if STA identify need for this at interim review) InDesign files (STA uses Adobe Indesign CC, 2015.3 release) of at least 10% of the total marks required at the interim handover stage in order for STA to check that the materials comply with the Design Specification (see Annex F) and software compatibility. For this purpose, the files need to be submitted according to the specification and the template (provided at the start-up meetings) but do not need to be the latest or final versions of the files. The remaining items to be handed over in InDesign or MS Word (or compatible) format. Please note that no other amendments should be introduced to items at this stage; only those discussed at interim review and those arising from informal trialling should be presented. |
| Post-Trial Meeting | The purpose of the post-trial meeting is to agree any amendments that may be needed to items following informal trialling. Only items included in informal trialling and any untrialled items which required significant amendments, or were new, following interim review will be discussed at this meeting. If, following this meeting, insufficient items are deemed suitable for Final Handover to fulfil the requirements of the work package, the supplier may provide substitute items which have been through the full process – including informal trialling – or may provide a reduced amount of items at a reduced cost to be agreed with STA. The meeting will be chaired by STA and take place either by telephone or in STA offices in Coventry or London. |
| Final Handover | Final Handover Meeting must occur during the week beginning 24 July 2017 for both key stages or before. The following materials must be handed over in advance of the Final Handover Meeting: - Hard copies of the following: - 40 copies of all items – the copies should be collated into packs and bound – each pack should have a complete set of all the items, in the same order and labelled clearly. These should be presented in the same order as the curriculum strands are presented in test framework (for KS1 all aural items should be presented at the start of each pack, also order by national curriculum strand). - 24 copies of the mark schemes – the copies should be collated into packs and bound – each pack should be complete, in the same order as the questions and labelled clearly. - The cover of each pack should be uniquely numbered in the format ‘1 of 40’ or ‘1 of 24’ as appropriate. The cover should also include the following information: Key Stage 1 / 2 (please delete as appropriate) Mathematics, Expert Review Autumn 2017, Questions / Mark Schemes (please delete as appropriate) and name of trialling agency. - One copy of the copyright statement (including all formal documentation for copyright transfer) - Electronic copies of the following: - Questions: - A single Adobe Indesign file for each individual test question with associated links and files (STA uses Adobe Indesign CC, 2015.3 release) - Individual PDF files for each question (i.e. one file per question). - A combined PDF of all items. Items in these files should be in the same order as in the hardcopy files. - Mark schemes: - Microsoft Word 2010 (or compatible subject to prior agreement) files for the mark schemes as individual files of each item and a combined file of all items. - A combined PDF of all mark schemes; questions to be presented in an identical order as for the combined question file. - Other: - The sources and copyright details of any data and artwork/images used in the test items included in the source column of the item classification spreadsheet. - All artwork/images used in the test items as unflattened files with all layers intact within the image file where applicable. Please ask for clarification on specific file types which are acceptable - Item classification spreadsheet in Microsoft Excel 2010 (or compatible), with summary table(s) showing coverage across content domain strands and all other areas listed in the item writing requirements above, as indicated by the supplied template (Annex B). Items in the item classification spreadsheet must be in an identical order to the items in the collated pdf file. - Assignments and/or licences of IPR in the commissioned and other third party works to be completed by the Final Handover Date – as stated in the PQQ and the Contract, and all documentation relating to IPR. - In addition to the handover of the above materials, the purpose of the Final Handover meeting, if required, (which will last no more than one full working day) is to discuss the items and the rationale for all amends made. The meeting will be chaired by STA and take place in STA offices in Coventry or London. The decision regarding whether this meeting is required will be taken by STA at the post-trial meeting. If the meeting is not required feedback on final handover materials will be provided in written form either on the same date, or before, acceptance of final handover. |
| Acceptance of Final Handover | Following Final Handover, if STA finds any errors, all materials will be returned to the supplier for a full check and for amendments to be carried out. This will include rectifying any errors in the hardcopy sets of materials, e.g. missing questions, incorrectly ordered questions, or lack of binding for each pack, and/or electronic files, e.g. where questions do not comply with the house style templates. STA will confirm whether any amendments are required no later than two weeks after the Final Handover Date. Error free materials should be returned to STA no later than two weeks after notification of any issues by STA. |

Performance Requirements

Quality criteria: the completed work package must contain a range of item types that: - are challenging and motivating for pupils - expose and complement the richness of the National Curriculum where possible - are manageable for pupils and capable of being completed within any given time constraints eliciting optimum performance - provide systems of recording marking decisions which are easy to use and interpret for teachers - reflect good classroom practice - comply with all requirements of the regulatory framework - meet the criteria on pages 15 to 25 as appropriate to the subjects awarded - comply with higher level reasoning requirements (key stage 2 only); details provided in annex G. Accessibility The items in standard or modified form must be capable of being used by all pupils working within the targeted levels who have followed the key stage 1 or key stage 2 programme of study for the relevant subject, including: - those with special educational needs - those for whom English is an additional language. Items must provide equality of access and opportunity by: - aiming to minimise ethnic, gender and cultural bias - avoiding disadvantaging pupils from particular backgrounds - being free from overt or covert discrimination either through wording or content. In the development of test items the Supplier must take account of all current legislation in relation to equality of opportunity, including the specific duties under the Equality Act 2010 and any successor legislation.

Security

The Supplier and any sub-contractor must meet the following security requirements: - The Supplier and any sub-contractor will comply with the STA's security procedures to maintain the integrity of all materials produced. - The Supplier and any sub-contractor is required to give full access to STA representatives for inspection where requested. - Where any breach of security occurs, the Supplier must follow the STA security incident guidelines. All project team members and any other individual working on this project must be made aware of their obligations under the STA security policy. - All test materials are confidential. Pupil data is confidential. If any pupil data is collected as part of this project, the handling of pupil data on tests and forms must comply with the Data Protection Act. STA does not require that pupil data is collected as part of this project. - All files must be handled in a secure and confidential manner. Transmission of information regarding test materials via unsecured networks or email or by regular postal service is prohibited. - All staff working on the materials must sign a confidentiality agreement. Staff must work on these materials in a secure work area. - Handover forms to be used for all deliveries. Supplier to email to inform and confirm delivery. - See Test Development external Suppliers security policy document, Appendix E for further information with regard to the security of the test materials and compliance to the Security Policy Framework (SPF) completed as part of the Pre-Qualification Questionnaire (PQQ). - Under no circumstances will the supplier and any sub-contractor contact IPR holders of any selected texts. This is strictly prohibited. Security Compliance Supplier and any sub-contractor must be compliant with all SPF requirements highlighted by STA Security. Where compliance has not yet been achieved an action plan and risk register must be agreed to address any issues identified within an acceptable timeframe. In the event that STA, in its sole discretion, considers that the required Security policies or processes have not been implemented by the Supplier and any sub-contractor prior to delivery of the Services, STA reserves the right to cancel any Order and/or terminate the Contract with immediate effect.

# Tenderer's Response

## Key Stage 1 Mathematics

- Please indicate below how many work packages your organisation is submitting a bid for. If bidding for more than one please rank in order of preference.

| - Work Package 1 |  | - Work Package 2 |  |
| --- | --- | --- | --- |

| Single Point of Contact: |  |
| --- | --- |
| E-mail: |  |
| Phone: |  |

Bidders are required to respond to all of the questions in this section.  The weighting for each question is provided next to each question.

Please note that the method of scoring each of the questions will be a 4 point scale, evaluators will use this to assign a score to each evaluation question response:

| Score | Guidance |
| --- | --- |
| 0 | Solution has low probability of successfully delivering requirements. |
| 1 | Solution has some probability of successfully delivering requirements. |
| 2 | Solution has good probability of successfully delivering requirements. |
| 3 | Solution has high probability of successfully delivering requirements. |

Mathematics: Expertise in item development and design Q1) Please provide (in no more than 1,000 words) details of the capability, experience and roles of the personnel* who will be directly involved in item development. Please relate their experience to the work being tendered for, explaining what they will bring to the outcomes. Please include any personnel who are external to the submitting organisation in your response. This should include: - those responsible for writing items and mark schemes; - those responsible for managing/revising items and mark schemes (it is understood these may be the same as those in the category above); - those responsible for classifying items; and - those responsible for undertaking the pupil interviews in trialling. Please describe explicitly the role of each named individual within the project and the proportion of their time dedicated to the project. In each case, please state whether their availability for the project has or has not been secured. *Please include abridged CV's of key personnel in addition to your response as a single embedded pdf file.

Weighting = 35%

| Mathematics: Project Management Q2a) Provide a detailed project plan for this work. The project plan must include: - A proposed timeline with specified dates for all key milestones in the process, including (but not limited to) those listed in the Deliverables/Output section of Specification of Requirements (see Section 5). Where multiple dates are possible for meetings, availability should be indicated; - The identification of all risks relevant to this piece of work and associated contingencies. (STA requires a service provider which will be active in identifying risks and opportunities associated with the procurement process and the documentation it reviews, in the context of the Procurement Regulations and also ensuring that the interests of STA are adequately protected at all times.); - An outline of the approach that will be taken to ensure that all key administrative and technical requirements (excluding item writing/development/design) are met to time and quality, including: - Printing of test materials for trialling and handover, - Meeting the design specification (for test items), and - All other security-critical aspects. Q2b) In no more than 350 words, describe your approach to managing the relationship with STA . |
| --- |
| Weighting = 10% |
| Mathematics: Example Test Materials Q3) Please provide: - Items (and associated mark schemes) totalling 10 marks assessing the following: - Number (approx. 7 marks), - Measures, geometry and Data (approx. 3 marks); - For each example item, please state which content domain reference(s) and cognitive demand profile is being assessed; - A range of item styles should be produced, and should include any artwork as appropriate; - Identification of possible pupil misconceptions that may arise. Your items will be judged on quality, clarity of language, accessibility and the extent to which they are absent of issues of bias and construct irrelevant variance. A range of item types will be considered positively, including items that assess the content domain strands in creative and innovative ways. You should include as part of your 10 marks items that test as wide a range of the content domain as possible – including areas that are infrequently tested – which test the content domain in creative and innovative ways. Please indicate in your submission any particular items which exemplify this. Please submit example test materials in Microsoft Word or equivalent. For each item, please provide a commentary of no more than 500 words that gives a rationale for the choices made. |
| Weighting = 35% |
| Mathematics: Item Management Q4) In no more than 500 words, describe how you will ensure that there will be sufficient, high quality items available to handover at the end of the project. Discuss: - the number of items you plan to write; - where you would target extra item writing; and - what you would do to minimise item attrition without adversely affecting the quality of the items in the Final Handover. |  |
| Weighting = 10% |  |
| Mathematics: Informal trialling Q5) In no more than 1,000 words, describe how you will ensure the validity of the informal trialling through: - the suitability, from a development perspective, of those administering the informal trials; - the collection of evidence ; - the trialling methodology employed to maximise the qualitative evidence for each item; and - the final report format and proposed contents and level of detail. |  |
| Weighting = 10% |  |

- Key stage 1 Mathematics Pricing proposal

The costs provided must include all charges that are applicable to the delivery of the STA Requirements. The Total Price submitted will be the fixed price included within any subsequent contract and there will be no adjustment to the contract pricing if additional charges are subsequently identified.  The Tenderer must complete the cost breakdown in Annex C. Please ensure the totals in the spreadsheet correspond with the figures in the table(s) below.

Work Package 1:

- The Fixed Price to deliver Work Package 1 in full is £                  and is split into two instalments, which correspond to the critical steps, as set out in Section 4.14.

| Milestone Payment | Requirement/Critical Steps | Payment Timescale | Amount £ (Excl. VAT) |
| --- | --- | --- | --- |
| 1 | 1-5 | 17/04/2017 |  |
| 2 | 6- 10 | 17/08/17 |  |
| Total |  |  |  |

Test development is VAT exempt

Work Package 2:

- The Fixed Price to deliver Work Package 2 in full is £                  and is split into two instalments, which correspond to the critical steps, as set out in Section 4.4.

| Milestone Payment | Requirement/Critical Steps | Payment Timescale | Amount £ (Excl. VAT) |
| --- | --- | --- | --- |
| 1 | 1-5 | 17/04/2017 |  |
| 2 | 6-10 | 17/08/2017 |  |
| Total |  |  |  |

Test development is VAT exempt.

- Key stage 1 Mathematics declaration by Tenderer

I have examined the STA requirements and proposed terms and conditions and hereby offer to enter into a contract with STA for the required services at the rates and prices set out in my enclosed Pricing Proposal.

I warrant that I have the required corporate authority to sign this Tender.

I understand that STA is not bound to accept the lowest price or any Tender and that the Contract for Provision of Key Stage 1 Mathematics: Item Writing will be awarded on the basis of the most economically advantageous tender.

This Tender shall remain open for acceptance by STA for a period of 30 days after the due date for return of tenders.

| Signed: |  |
| --- | --- |
| Name: |  |
| Date: |  |
| Role: |  |
| Authorised to sign tenders on behalf of [organisation name]: |  |

## Key Stage 2 Mathematics

- Please indicate below how many work packages your organisation is submitting a bid for. If bidding for more than one please rank in order of preference.

| - Work Package 1 |  | - Work Package 2 |  |
| --- | --- | --- | --- |

| Single Point of Contact: |  |
| --- | --- |
| E-mail: |  |
| Phone: |  |

Bidders are required to respond to all of the questions in this section.  The weighting for each question is provided next to each question.

Please note that the method of scoring each of the questions will be a 4 point scale, evaluators will use this to assign a score to each evaluation question response:

| Score | Guidance |
| --- | --- |
| 0 | Solution has low probability of successfully delivering requirements. |
| 1 | Solution has some probability of successfully delivering requirements. |
| 2 | Solution has good probability of successfully delivering requirements. |
| 3 | Solution has high probability of successfully delivering requirements. |

Mathematics: Expertise in item development and design Q1) Please provide (in no more than 1,000 words) details of the capability, experience and roles of the personnel* who will be directly involved in item development. Please relate their experience to the work being tendered for, explaining what they will bring to the outcomes. Please include any personnel who are external to the submitting organisation in your response. This should include: - those responsible for writing items and mark schemes; - those responsible for managing/revising items and mark schemes (it is understood these may be the same as those in the category above); - those responsible for classifying items; and - those responsible for undertaking the pupil interviews in trialling. Please describe explicitly the role of each named individual within the project and the proportion of their time dedicated to the project. In each case, please state whether their availability for the project has or has not been secured. *Please include abridged CV's of key personnel in addition to your response as a single embedded pdf file.

Weighting = 35%

| Mathematics: Project Management Q2a) Provide a detailed project plan for this work. The project plan must include: - A proposed timeline with specified dates for all key milestones in the process, including (but not limited to) those listed in the Deliverables/Output section of Specification of Requirements (see Section 5). Where multiple dates are possible for meetings, availability should be indicated; - The identification of all risks relevant to this piece of work and associated contingencies. (STA requires a service provider which will be active in identifying risks and opportunities associated with the procurement process and the documentation it reviews, in the context of the Procurement Regulations and also ensuring that the interests of STA are adequately protected at all times.); - An outline of the approach that will be taken to ensure that all key administrative and technical requirements (excluding item writing/development/design) are met to time and quality, including: - Printing of test materials for trialling and handover, - Meeting the design specification (for test items), and - All other security-critical aspects. Q2b) In no more than 350 words, describe your approach to managing the relationship with STA . |
| --- |
| Weighting = 10% |
| Mathematics: Example Test Materials Q3) Please provide: - Items (and associated mark schemes) totalling 10 marks assessing the following: - Number (approx. 7 marks), - Geometry and Data (approx. 3 marks); - For each example item, please state which content domain reference(s) and cognitive demand profile is being assessed; - A range of item styles should be produced, and should include any artwork as appropriate; - Identification of possible pupil misconceptions that may arise. Your items will be judged on quality, clarity of language, accessibility and the extent to which they are absent of issues of bias and construct irrelevant variance. A range of item types will be considered positively, including items that assess the content domain strands in creative and innovative ways. You should include as part of your 10 marks items that test as wide a range of the content domain as possible – including areas that are infrequently tested – which test the content domain in creative and innovative ways. Please indicate in your submission any particular items which exemplify this. Please submit example test materials in Microsoft Word or equivalent. For each item, please provide a commentary of no more than 500 words that gives a rationale for the choices made. |
| Weighting = 35% |
| Mathematics: Item Management Q4) In no more than 500 words, describe how you will ensure that there will be sufficient, high quality items available to handover at the end of the project. Discuss: - the number of items you plan to write; - where you would target extra item writing; and - what you would do to minimise item attrition without adversely affecting the quality of the items in the Final Handover. |  |
| Weighting = 10% |  |
| Mathematics: Informal trialling Q5) In no more than 1,000 words, describe how you will ensure the validity of the informal trialling through: - the suitability, from a development perspective, of those administering the informal trials; - the collection of evidence; - the trialling methodology employed to maximise the qualitative evidence for each item; and - the final report format and proposed contents and level of detail. |  |
| Weighting = 10% |  |

- Key stage 2 Mathematics Pricing proposal

The costs provided must include all charges that are applicable to the delivery of the STA Requirements. The Total Price submitted will be the fixed price included within any subsequent contract and there will be no adjustment to the contract pricing if additional charges are subsequently identified.  The Tenderer must complete the cost breakdown in Annex C. Please ensure the totals in the spreadsheet correspond with the figures in the table(s) below.

Work Package 1:

- The Fixed Price to deliver Work Package 1 in full is £                  and is split into two instalments, which correspond to the critical steps, as set out in Section 4.14.

| Milestone Payment | Requirement/Critical Steps | Payment Timescale | Amount £ (Excl. VAT) |
| --- | --- | --- | --- |
| 1 | 1-5 | 10/04/2017 |  |
| 2 | 6-10 | 10/08/2017 |  |
|  |  | Total £ |  |

Test development is VAT exempt

Work Package 2:

- The Fixed Price to deliver Work Package 2 in full is £                  and is split into two instalments, which correspond to the critical steps, as set out in Section 4.4.

| Milestone Payment | Requirement/Critical Steps | Payment Timescale | Amount £ (Excl. VAT) |
| --- | --- | --- | --- |
| 1 | 1-5 | 10/04/2017 |  |
| 2 | 6-10 | 10/08/2017 |  |
|  |  | Total £ |  |

Test development is VAT exempt.

- Key stage 2 Mathematics declaration by Tenderer

I have examined the STA requirements and proposed terms and conditions and hereby offer to enter into a contract with STA for the required services at the rates and prices set out in my enclosed Pricing Proposal.

I warrant that I have the required corporate authority to sign this Tender.

I understand that STA is not bound to accept the lowest price or any Tender and that the Contract for Provision of Key Stage 2 Mathematics: Item Writing will be awarded on the basis of the most economically advantageous tender.

This Tender shall remain open for acceptance by STA for a period of 30 days after the due date for return of tenders.

| Signed: |  |
| --- | --- |
| Name: |  |
| Date: |  |
| Role: |  |
| Authorised to sign tenders on behalf of [organisation name]: |  |

# Annexes

## Annex A – Test Frameworks

https://www.gov.uk/government/collections/national-curriculum-assessments-test-frameworks

## Annex B – Item Classification Spreadsheet

This is an example of the structure of item classification spreadsheets allowing STA to import materials directly to their item bank. Final versions of the spreadsheet for each subject will be provided to the successful supplier(s) at or before the start-up meeting.

## Annex C – Cost Breakdown

Key Stage 1 Work Package 1 Maths Item Writing Cost Breakdown

| No. | Requirement/Output | Cost (£) |
| --- | --- | --- |
| 1 | Item Writing Costs |  |
| 2 | Informal Trialling – Fixed Costs |  |
| 3 | Informal Trialling - Variable Costs to trial 100% of items written |  |
| 4 | DTP Costs |  |
| 5 | Item Review Costs |  |
| 6 | Item amendment costs |  |
| 7 | Meetings, Travel and Subsistence Costs |  |
| 8 | Print and Handover Costs |  |
| 9 | Illustrations / Artwork |  |
| 10 | Other Costs (please specify) |  |
| 11 | Other Costs (please specify) |  |
| 12 | Other Costs (please specify) |  |
|  | TOTAL COSTS | £ |

Additional Information

Informal Trialling - Variable Costs to trial 25% of items written - £

Informal Trialling - Variable Costs to trial 50% of items written - £

Informal Trialling - Variable Costs to trial 75% of items written - £

Key Stage 1 Work Package 2 Maths Item Writing Cost Breakdown

| No. | Requirement/Output | Cost (£) |
| --- | --- | --- |
| 1 | Item Writing Costs |  |
| 2 | Informal Trialling – Fixed Costs |  |
| 3 | Informal Trialling - Variable Costs to trial 100% of items written |  |
| 4 | DTP Costs |  |
| 5 | Item Review Costs |  |
| 6 | Item amendment costs |  |
| 7 | Meetings, Travel and Subsistence Costs |  |
| 8 | Print and Handover Costs |  |
| 9 | Illustrations / Artwork |  |
| 10 | Other Costs (please specify) |  |
| 11 | Other Costs (please specify) |  |
| 12 | Other Costs (please specify) |  |
|  | TOTAL COSTS | £ |

Additional Information

Informal Trialling - Variable Costs to trial 25% of items written - £

Informal Trialling - Variable Costs to trial 50% of items written - £

Informal Trialling - Variable Costs to trial 75% of items written - £

Key Stage 2 Work Package 1 Maths Item Writing Cost Breakdown

| No. | Requirement/Output | Cost (£) |
| --- | --- | --- |
| 1 | Item Writing Costs |  |
| 2 | Informal Trialling – Fixed Costs |  |
| 3 | Informal Trialling - Variable Costs to trial 20% of items written |  |
| 4 | DTP Costs |  |
| 5 | Item Review Costs |  |
| 6 | Item amendment costs |  |
| 7 | Meetings, Travel and Subsistence Costs |  |
| 8 | Print and Handover Costs |  |
| 9 | Illustrations / Artwork |  |
| 10 | Other Costs (please specify) |  |
| 11 | Other Costs (please specify) |  |
| 12 | Other Costs (please specify) |  |
|  | TOTAL COSTS | £ |

Additional Information

Informal Trialling - Variable Costs to trial 25% of items written - £

Informal Trialling - Variable Costs to trial 50% of items written - £

Informal Trialling - Variable Costs to trial 75% of items written - £

Key Stage 2 Work Package 2 Maths Item Writing Cost Breakdown

| No. | Requirement/Output | Cost (£) |
| --- | --- | --- |
| 1 | Item Writing Costs |  |
| 2 | Informal Trialling – Fixed Costs |  |
| 3 | Informal Trialling - Variable Costs to trial 20% of items written |  |
| 4 | DTP Costs |  |
| 5 | Item Review Costs |  |
| 6 | Item amendment costs |  |
| 7 | Meetings, Travel and Subsistence Costs |  |
| 8 | Print and Handover Costs |  |
| 9 | Illustrations / Artwork |  |
| 10 | Other Costs (please specify) |  |
| 11 | Other Costs (please specify) |  |
| 12 | Other Costs (please specify) |  |
|  | TOTAL COSTS | £ |

Additional Information

Informal Trialling - Variable Costs to trial 25% of items written - £

Informal Trialling - Variable Costs to trial 50% of items written - £

Informal Trialling - Variable Costs to trial 75% of items written - £

## Annex D – Copyright permission letter template

## Annex E – Test Development External Suppliers Security Policy

## Annex F – National curriculum Test Design Specifications

Annex G – Guidelines for KS1 and 2 mathematics item writers

Key Stage 1

House style guidance:

Cognitive domain guidance:

Key Stage 2

House style guidance:

Higher order reasoning guidance:

Cognitive domain guidance: