## Sheet1
Annex A to draft Contract CBRN/00203 Schedule 8
Statement of Work for Atomic Material Subject Matter Experts Technical Support Services to Radiological Detection and Monitoring Equipment
Work Package | Requirement | Contract Deliverable | Date Required | Acceptance Criteria
1. Core Contract Support
1.1. Project Management and Reporting
1.1.1. - Point of Contact | The Contractor shall appoint an In-Service-Support (ISS) contract manager, and deputy, who, with the support of any sub-Contractors, will manage the control, co-ordination, monitoring and reporting of all work packages in this statement of work. The provision of services and supply must be continuous throughout the duration of the contract. Management of suppliers and sub-contractors is the responsibility of the Contractor, and therefore the Point of Contact (POC) will be responsible for ensuring effective communication between the Chemical, Biological, Radiological and Nuclear Delivery Team (CBRN DT) and any sub-contractors. | POC and deputy, named and contact details provided at contract commencement. | At contract commencement. | POC’s phone number and e-mail provided to CBRN DT upon contract award.
| The ISS contract manager, (or their named deputy) shall be the initial POC between CBRN DT and the Contractor for all activities carried out under this Statement of Work (SOW) and shall be contactable by telephone and email 09:00 – 16:00, Monday – Friday (excluding Public holidays). | POC or deputy contactable by telephone and email 09:00 – 16:00, Monday – Friday (excluding Public holidays). | Contract commencement through to end of contract. | Named Contractor representative available to CBRN DT via e-mail or telephone within the times stated.
| The Contractor shall respond to any query within a maximum of 2 working days of the query being communicated to the Contractor, unless otherwise agreed by CBRN DT. | Contractor will provide an initial response to all queries within 2 working days, and a final response within 5 working days. | Contract commencement through to end of contract. | Initial response will, at a minimum, acknowledge receipt of query. Final response will detail plan of action to rectify query and will be accepted by CBRN DT.
1.1.2. - Quarterly Meeting | The Contractor shall host and provide administrative and secretarial support for quarterly progress meetings. During the meetings it is expected discussions will be held covering all work packages stated in the SoW. The agenda for the quarterly meetings should include, but not be limited to, the following items: • Introductions • Current tasking summary • Mean handling time review • Financial summary • Safety • AOB • Review of actions | Quarterly meetings held between the Contractor and assigned CBRN DT representatives. Agenda containing, at a minimum, the items listed in the requirements column. Agenda will be a live document throughout the life of the contract. | At 3 month periods for the duration of the Contract. Call notice and agenda to be issued a minimum of 10 days prior to the meeting. | Quarterly Meetings held at a maximum of 3 months apart between the Contractor and assigned CBRN DT representatives. Date of next meeting to be agreed at end of each meeting. Agenda as detailed in the requirement Column to be provided by e-mail in pdf or Microsoft Word format, and to be approved and accepted by CBRN DT.
1.1.3. - Quarterly meeting Minutes | The Contractor will be expected to produce meeting minutes for each quarterly meeting, detailed in section 1.2, held in support of this contract. The minutes will be expected to include, as a minimum, details of: • Meeting attendees (Inc apologies) • Summary of discussions • Action grid • Record of decisions | Meeting minutes containing, at a minimum, the items listed in the requirements column. | Minutes Template agreed within 1 month of contract commencement. | Minutes Template as detailed in the Requirement Column to be provided by e-mail, in pdf or Microsoft Word format, and to be approved and accepted by CBRN DT.
| The Contractor shall issue draft minutes of the quarterly meetings to CBRN DT, for approval, within 10 working days of the meeting. The Contractor shall incorporate any agreed additions, amendments or comments to the draft minutes prior to publishing an approved version to all attendees of the meeting. The Contractor shall issue the approved minutes within 5 working days of CBRN DT submitting their comments to the Contractor. | Draft quarterly meeting minutes issued to CBRN DT within 10 working days of the meeting. Approved quarterly meeting minutes issued to all attendees of the quarterly meeting within 5 days of receiving comments from CBRN DT. | Contract commencement through to support for final quarterly meeting. | Draft quarterly meeting minutes to be provided by e-mail in pdf or Microsoft Word format, and to be approved and accepted by CBRN DT Project Manager. Approved meeting minutes to be issued to all attendees of the quarterly meeting in pdf of Microsoft Word format once draft has been agreed by CBRN DT.
1.1.4 - Calibration due list | The Contractor shall provide CBRN DT with a monthly calibration due list. The calibration due list should include, but not be limited to, the following items: • Source/instrument description • Serial number • Days remaining until calibration expires • Last known user location | The Contractor shall provide a monthly report containing, at a minimum, the items listed in the requirements column. | Within 1 month of commencement of the contract until the end of the contract. | Calibration due list as detailed in the requirement column to be provided by e-mail, in pdf or Microsoft Word format, to be provide to the CBRN DT on a monthly basis.
1.2. Core Technical Support
1.2.1. - Support Services | The Contractor shall provide atomic material Subject Matter Experts (SMEs) technical support services for CBRN DT sponsored Radiological Detection and Monitoring Equipment (RDME). Technical support shall include, but not be limited to: • Support and attendance at the MOD Radiation Calibration Qualified Persons Committee (MRCQP). • Provide SMEs to attend CBRN DT meetings for review of the RDME programme on a quarterly basis. • Review, assess and maintain calibration protocol documentation. • Attendance to annual JSP425 review meetings and undertake audits of laboratories in accordance with JSP425. | The Contractor shall be able to provide atomic material SMEs to provide technical support services, at a minimum, for the items listed in the requirements column. | Duration of the contract. | The Contractor shall be able to provide atomic material SMEs to provide technical support services on a task by task basis as agreed by the Contractor and CBRN DT. Contractor must be able to demonstrate the SMEs provided are suitably qualified and experienced persons to provide RDME technical support to all the items listed in the requirements column. Attendees at the MRCQP must have the appropriate authority to accept actions.
2. Ad Hoc Technical Support
2.1. - Support Services | The Contractor shall provide Technical Support Services for the equipment as required by the Authority. This arrangement can be used for a wide variety of services which may fall outside of the categories referenced in the Core Tasking. These tasks may include, but are not limited to: • Research and Development of RDME • Test and Evaluation of RDME • SME support and advice to CBRN DT including attendance to meetings Work packages will be tasked to the Contractor using individual Task Approval Forms (TAF) at additional cost. Turn round times are to be agreed on individual tasking. The TAF process will ask for the Contractor to provide an initial quote for the work package, which The Authority can then approve. Work should not begin unless approval has been gained from The Authority. | Technical Support available to be used by The Authority, for the range of activities detailed in the Requirements column, throughout the life of the Contract. | Support required throughout the duration of the contract. | Technical Support will be conducted in accordance with firm man-day rates for the Contract. Sufficient evidence will need to be provided with any TAF quotes to ensure The Authority’s Project Manager can approve the Work Package. Work should not begin unless approval has been received.
3. Equipment Support
3.1. Calibrations
3.1.1 - Standard of Calibrations | The Contractor shall be a defence approved calibration facility in accordance with Joint Service Publication (JSP) 425. | The Contractor shall provide a calibration service that is compliant with the requirement of JSP 425 and is accredited as compliant with the requirements of BS EN ISO/IEC 17025. | Duration of the contract. | The Contractor shall for the duration of the contract be at all times compliant with JSP 425 and be and allow periodic audits in accordance JSP 425.
3.1.2 - Calibration of Radiological Nuclear Sources | The Contractor shall provide Primary Standard Calibration for large area sources on the following; • Photon emission rate on the following nuclides:- 55Fe, 238Pu, 129I, 241Am, 57Co, 137Cs and 60Co The Contractor shall provide Secondary Standard Calibration for the following; • Beta emission rate on the following nuclides: 3H, 63Ni, 14C, 60Co, 137Cs, 36Cl and 90Sr/Y • Alpha emission rate on the following nuclides: 234U,235U, NatU, 238Pu, 239Pu and 241Am | The Contractor shall provide calibration and return of the sources listed in the requirement column within 15 working days of receipt of the sources in accordance with ISO 8769 /ISO 17025. | Duration of the contract. | Calibration and return of the listed sources within 15 working days of receipt in accordance with ISO 8769/ISO 17025. The Contractor shall provide the CBRN DT a Calibration Certificate for each source in accordance with JSP 425.
3.1.3. - Calibration of RDME | The Contractor shall calibrate radiological nuclear instruments in accordance with JSP 425 for the following instruments; • Mk31NRM (NSN: 6665-99-7309303) • DMC2000 (NSN: 6665-14-5671049) • XP120 (NSN: 6635-01-6038777) • UNIDOS (Not codified) | The Contractor shall provide calibration and return of the instruments listed in the requirement column within 10 working days of receipt of the instruments in accordance with JSP 425. | Duration of the contract. | Calibration of the instruments listed in the requirements column within 10 working days of receipt of the instruments in accordance with JSP 425. The Contractor shall provide the CBRN DT a Calibration Certificate for each piece of RDME in accordance with JSP 425.
3.1.4. - Return of Sources | The Contractor shall be responsible for the return transportation of sources to DSTL Alverstoke. | The Contractor shall be responsible for the return transportation of instruments to DSTL Alverstoke. | Duration of the contract. | The Contractor shall be responsible for the return transportation of instruments to DSTL Alverstoke within the timescales detailed in section 3.1.2
3.1.5. - Return of Instruments | The Contractor shall be responsible for the return transportation of instruments to DSTL Alverstoke. | The Contractor shall be responsible for the return transportation of instruments to DSTL Alverstoke. | Duration of the contract. | The Contractor shall be responsible for the return transportation of instruments to DSTL Alverstoke within the timescales detailed in section 3.1.3
3.2. Before First Use Test (BFUT)
3.2.1. - XP120 BFUT | The Contractor will be required to carry out BFUT on the XP120 radiological nuclear instruments in accordance with the JSP 425 calibration protocol. | The Contractor shall provide and carry out a BFUT for XP120 radiological nuclear instruments in accordance with the XP120 calibration protocol. | Duration of the contract. | The Contractor shall complete a BFUT for XP120 radiological nuclear instruments in accordance with the XP120 calibration protocol. The Contractor shall be able to carry out the BFUT throughout the contract as agreed with CBRN DT.