## Detailed
| St Mungo's Broadway Implementation Plan - CHAIN |  |  |  | PRE-MOBILISATION |  |  |  | IMPLEMENTATION PHASE | [11 empty] | 1st Quarter
[5 empty] | 2015-12-01 |  |  |  | 2016-01-01 |  |  |  | 2016-02-01 |  |  |  | 2016-03-01 |  |  |  | 2016-04-01 |  |  |  | 2016-05-01 |  |  |  | 2016-06-01
|  | Task | Responsible Officer | KEY MILESTONE | wk1 | wk2 | wk3 | wk4 | wk1 | wk2 | wk3 | wk4 | wk1 | wk2 | wk3 | wk4 | wk1 | wk2 | wk3 | wk4 | wk1 | wk2 | wk3 | wk4 | wk1 | wk2 | wk3 | wk4 | wk1 | wk2 | wk3 | wk4
Transition / Implementation Management | A1 | Notification of proposed appointment | CHAIN Information Manager | bar: 2016-01-01 wk1
| A2 | Circulate Implementation Plan to relevant internal management and commissioners | CHAIN Information Manager | bar: 2016-01-01 wk1 to 2016-01-01 wk2
| A3 | Set key milestones for project implementation timeline | CHAIN Information Manager & Implementation Manager | KEY MILESTONE | bar: 2016-01-01 wk2
| A4 | Meet with relevant internal departments - IT, HR, Comms, Facilities | CHAIN Information Manager & Implementation Manager | bar: 2016-01-01 wk4; 2016-02-01 wk2; 2016-02-01 wk4; 2016-03-01 wk2; 2016-03-01 wk4
| A5 | Agree and set KPIs & performance targets with GLA | CHAIN Information Manager & Implementation Manager | KEY MILESTONE | bar: 2016-02-01 wk1 to 2016-02-01 wk4
| A6 | Review risk log and confirm contingency plans | CHAIN Information Manager | bar: 2015-12-01 wk4; 2016-01-01 wk4; 2016-02-01 wk4; 2016-03-01 wk4
| A7 | Agree workplan for 2015-16 & Schedule GLA Monitoring meetings | CHAIN Information Manager | bar: 2016-01-01 wk3 to 2016-01-01 wk4
Finance | B1 | Set up new CHAIN only budget | CHAIN Information Manager | KEY MILESTONE | bar: 2016-01-01 wk3 to 2016-01-01 wk4
| B2 | Liaise with Finance to establish procedures/expectations around invoicing and financial reporting | CHAIN Information Manager | bar: 2016-01-01 wk4 to 2016-02-01 wk1
Communications |  | Internal Communications
| C1 | Inform all central services of new contract | CHAIN Information Manager | bar: 2016-01-01 wk3 to 2016-02-01 wk2
| C2 | Ensure coverage of the new contract in Core Brief | CHAIN Information Manager | bar: 2016-02-01 wk3 to 2016-03-01 wk2
| C3 | Ensure coverage of the new contract in The Saint (St Mungo's Broadway quarterly supporter magazine) | CHAIN Information Manager
External Communications
| C4 | Consult GLA about rebranding exercise | CHAIN Information Manager/Coordinator | bar: 2016-03-01 wk3 to 2016-03-01 wk4
| C5 | Meet with St Mungo's Broadway in-house designer and communications manager to establish plan | CHAIN Information Manager/Coordinator / Communications Manager
| C6 | Review proposals internally and with GLA and other stakeholders as appropriate | CHAIN Information Manager/Coordinator/team
| C7 | Launch new branding on all documentation and communications | CHAIN Information Manager/Coordinator/team | KEY MILESTONE
Website Review
| C8 | Liaise with communications manager over website review plans. | CHAIN Information Manager/Coordinator/ Communication and design partners
| C9 | Design and testing phase (New Chain Microsite) | CHAIN Information Manager/Coordinator/ Communication and design partners
| C10 | Launch of CHAIN microsite | CHAIN Information Manager/Coordinator/ Communication and design partners | KEY MILESTONE
Stakeholder Survey
| C11 | Circulate stakeholder survey | CHAIN Support Officers | bar: 2015-12-01 wk1 to 2015-12-01 wk4
| C12 | Review responses from stakeholder survey and integrate any relevant points into 2015-16 workplan | CHAIN Information Coordinator/CHAIN team | bar: 2016-01-01 wk3 to 2016-02-01 wk2
Supporting Other Recommissioned Services | D1 | Contact new service provider agencies to establish requirements around new user training, additional recording, and reporting/KPIs | CHAIN Information Manager/Coordinator | bar: 2016-01-01 wk3 to 2016-01-01 wk4
| D2 | Implement necessary adjustments to recording and reporting | CHAIN Information Manager/ Development Manager | KEY MILESTONE | bar: 2016-02-01 wk1 to 2016-03-01 wk2
| D3 | Train new users | CHAIN Support Officers | bar: 2016-03-01 wk3 to 2016-03-01 wk4
Data Protection | E1 | Finalise revised DPA and data protection materials | CHAIN Information Manager | bar: 2015-12-01 wk3 to 2016-01-01 wk4
| E2 | Ensure communications materials are translated in appropriate languages | CHAIN Information Manager / Communications Manager | bar: 2016-02-01 wk1 to 2016-02-01 wk3
| E3 | Circulate revised DPA to be signed by all CHAIN using organisations | CHAIN Information Coordinator | KEY MILESTONE | bar: 2016-03-01 wk1 to 2016-03-01 wk4
| E4 | Follow up outstanding organisations to ensure all have signed revised agreement | CHAIN Information Coordinator
New Developments |  | Payment By Results
| F1 | Conduct CHAIN/Clearing House data reconciliation exercise | CHAIN Information Coordinator | bar: 2015-12-01 wk1 to 2015-12-01 wk4
| F2 | Meet with GLA to establish requirements | CHAIN Information Manager/Coordinator | bar: 2016-01-01 wk3 to 2016-01-01 wk4
| F3 | Meet with other stakeholders if necessary | CHAIN Information Manager/Coordinator | bar: 2016-01-01 wk4 to 2016-02-01 wk1
| F4 | Agree specification to create proposal | CHAIN Information Manager/Coordinator | bar: 2016-01-01 wk4 to 2016-02-01 wk2
| F5 | Implement system developments | CHAIN Information Manager/Coordinator | KEY MILESTONE | bar: 2016-02-01 wk3 to 2016-03-01 wk4
GIS Mapping
| F6 | Review software options for analysis and presentation of GIS data | CHAIN Information Manager | bar: 2016-01-01 wk1 to 2016-03-01 wk4
| F7 | Test reporting options on initial data | CHAIN Information Manager
| F8 | Develop new reports, as agreed with GLA | CHAIN Information Manager | KEY MILESTONE
Other Developments
| F9 | Meet with GLA (and other stakeholders as appropriate) to establish initial requirements around raw data reporting tool, and enhanced physical and mental health support needs recording | CHAIN Information Manager/Coordinator | bar: 2016-01-01 wk1 to 2016-01-01 wk4
| F10 | Implement developments as agreed | CHAIN Information Manager/Coordinator | KEY MILESTONE | bar: 2016-01-01 wk4 to 2016-03-01 wk4
Equality and Diversity | G1 | Approve communication materials translated into appropriate languages | Head of Equality and Diversity | bar: 2016-02-01 wk4
| G2 | Ensure new staff undertake equality and diversity training | Head of Equality and Diversity | KEY MILESTONE | bar: 2016-03-01 wk3 to 2016-03-01 wk4
Other staffing plans | H1 | Conduct CHAIN team skills audit | CHAIN Information Manager/Coordinator | bar: 2016-02-01 wk2 to 2016-02-01 wk4
| H2 | Review staff contracts to align with new post (adjust contractual hours as necessary) | CHAIN Information Manager / HR Partner | bar: 2016-03-01 wk1 to 2016-03-01 wk4
| H3 | Review and implement training and development of CHAIN team staff | CHAIN Information Manager/Coordinator | KEY MILESTONE | bar: 2016-03-01 wk3 to 2016-03-01 wk4