Council Of The Isles Of Scilly Off Site Toilets & Fire Stations Part 2 - Project Description 4101565 30 June 2023

Version: 1.0 Status: DRAFT

Project Description

| Project Name | Off Site Toilets & Fire Stations |
| --- | --- |
| Description of Phase One work | Works as described PoW_BR 15112022 |
| Scope of Work | Works as described PoW_BR 15112022 |
| Employer | Council Of The Isles Of Scilly |
| Site Address | St Agnes, St Martins, Bryher, St Mary’s & Tresco, Isles of Scilly |
| Employer Contact | Keith Grossett – Council Of The Isles Of Scilly |
| Programme (Construction) | TBC |
| Current Forecast Cost | TBC |
| Form of Procurement | Traditional - 2 Stage |
| Stage 1 Tender Return | 21/07/2023 |
| Contractor Selection due | 28/07/2023 |
| Stage 2 Tender Return | 01/09/2023 |
| Start on Site | 02/10/2023 |
| Anticipated Completion | 31/03/2024 |

Professional Team

The Employer’s Consultant Team comprises:

- Project Manager

- Architect

- Structural Engineer

- Quantity Surveyor

- Principal Designer

## Procurement Route

This is to be a Construct Only contract, with Pre-Construction advice from the selected Contractor. The proposed form of contract will be JCT ICD 2016 with contractor design elements.

The Contract will include some element of Contractor’s Design – see Appendix A – Specification (temporary works associated with the party wall agreements)

## Project Information

Current design, scope and programme details are included in the Tender Documents at Appendix A (Specification – Appendix A). A strategic programme is provided, a Risk Register is also provided. The Contractor is required to focus on post contract programme and overall project risks.

## Programme

Key dates are:

- Contractor Appointment (commencement of Stage 2)	 28/07/2023

- Agree Contract Sum					 08/09/2023

- Construction Start Date				 02/10/2023

- Construction Completion		 		 31/03/2024

## Risk Register

A Risk Register has not been set up for the project.