## Sheet1
CLARIFICATION LOG
Tender: | Park Gerry - Modular Building
Tender Reference:
Published Date: | 2023-04-13
Version number: | 0.6
Number | Clarification | Response | Reply date
1 | Within the tender documents of Vol 1 ITT, the client states they have undertaken a number of surveys. If possible, please provide reports from the surveys undertaken to aide the tender submission. | Following documents have been added for information purposes: South West Water Ltd Drainage & Water Search (Commercial Premium); FLOOD_RISK_ASSESSMENT-7134911; HERITAGE_STATEMENT-7126774; PA22_11292-PRELIMINARY_ECOLOGICAL_APPRAISAL-7126696; TRANSPORT_STATEMENT-7126734; Phase I Preliminary Risk Assessment (PRA) - Park Gerry 21441 | 2023-03-16
2 | Please can you advise where on the park/field the building will be positioned? | This is indicated in the concept designs that are included in the tender pack. Final location will be agreed with the succesful supplier and specified in the fullplanning application | 2023-04-03
3 | Who is responsible for bringing supplies to the building? | During the construction phase, the succesful supplier will be expected to manage all of their own materials to site. This will be via the Trannance Road entrance. | 2023-04-03
4 | Further to Q2 in terms of supplies we are referring to services supplies such as electric water etc? | All service connections are to be included in this tender | 2023-04-06
5 | Will this be awarded through crown commercial services? | No, the contract will be a looking to appoint as a direct result of this tender process. | 2023-04-06
6 | Could you provide a copy of the Contract Particulars, we are assuming that the JCT Conditions have no special amendments | The contract will be a standard JCT D&B, as agreed by both parties on signing. We do not expect there to be any amendments. If there are any specific concerns or recommendations then we will be happy to respond to those. | 2023-04-06
7 | Are further security measures required for the building? For example, would the client require features such as roller shutters over glased areas of the building. | Assume for the building to have no windows, but an allowance for a double door on the community area and this will need a roller shutter. | 2023-04-11
8 | If possible please could you provide an service drawings which you may have for the park. | All drawings that we have available are already uploaded to the contracts finder portal, so please allow a provisional sum for any additional survey work that will need to be conducted. | 2023-04-11
9 | The documents again, we have noticed that the Description of project states the following: Wheeled Sports facility; Full sized football pitch; All weather MUGA pitch; Pavilion modular building; Network of accessible footpaths; Improved Parking etc; Running Routes; Gym Equipment (outdoors); New seating and signage; Wildflower meadows. Would the successful tenderer be required to undertake all above works as a package within the budget(270K) or would this budget be for the supply of the modular building and associated groundworks alone? | That list is just provided to give context. We are only asking for the Modular building and associated works in this tender package though. There will be an expectation that all the separate suppliers would be willing to attend combined delivery meetings and to co-ordinate works packages to assist with a smooth delivery of the overall project. All works will be standalone though, unless agreed post-tender. | 2023-04-11
10 | From the proposed plans, we can meet the clients’ requirements with minor tweaks to the design. Please advise weather the client is striving to fund the project through sports England funding streams as this may alter the layout and provide further design requirements which must be met. | The whole project is funded through Council reserves and the Town Deal Fund. Sport England are not a funder or stakeholder in this project. The template for the building was based upon Sport England’s, but that is as far as it goes. | 2023-04-11
11 | Please could you confirm from the attached drawing if the building is to be located at Location A or B as this will change the deliver and install. | Please price for position B. We will be agreeing the final location with the successful supplier, but B will give us a like for like comparison. | 2023-04-13
12 | Looking at the positioning of the building and the information discouraging access via Park road, access to site may require trackway across the field. Would there be an access road provided or should we make allowance for trackway, furthermore, would any other works be undertaken at the same time which may require us to re-route trackway? | Yes some form of track or haul road will need to be installed. We are running the skate park tender at the same time as this and the first thing we will do when we have the suppliers selected is get everyone together and discuss how best to resolve this so that we aren’t repeating work or making more mess than we have to. There is also the potential to share ground workers, welfare or any other resource that could streamline delivery. If a haul road were to go in, we would envisage it would take the route of where a path is to be installed (as long as it is practical). The bid should include all necessary work to bring supplies to site though. | 2023-04-13
Clarifications will be published against the Contract Notice on Find a Tender and Contracts Finder.
If interested in tendering for this project please ensure you add a "watch this notice" for alerts as from time to time additional information or clarifications may be published related to this tender.
It will be the responsibility of Bidders to ensure they are aware of all published clarifications and ensure that their bid has taken these into account.
In the event of any queries please contact: