

AEMP WELLINGTON BARRACKS VOLUME 2 ANNEX 5 SCOPE

Defence Infrastructure Organisation



DIO PROJECT REF: Z9A2905Y21

DIO TENDER / CONTRACT NO: 709172455

FRAMEWORK NUMBER: CWAS 638-2023-01

VERSION: 3.0

SEPTEMBER 2024

CONTENTS

[2 SCOPE 1](#_Toc63385)

[2.1 Introduction 1](#_Toc63386)

[2.2 Background to the Project 2](#_Toc63387)

[2.3 Project Aim, Objectives, and Key User Requirements 2](#_Toc63388)

[2.4 Project Site/Location 3](#_Toc63389)

[2.5 Building Information Modelling (BIM) 3](#_Toc63390)

[2.6 Works stages and acceptance 6](#_Toc63391)

[2.7 Overview of Works to be Undertaken 9](#_Toc63392)

[2.8 Design and Construction Compliance Certification 16](#_Toc63393)

[2.9 Environmental Actions 21](#_Toc63394)

[2.10 Testing and Inspection 22](#_Toc63395)

[2.11 Contractor Performance 23](#_Toc63396)

[2.12 Town and Country Planning 23](#_Toc63397)

[2.13 Programme 23](#_Toc63398)

[2.14 Technical Standards 24](#_Toc63399)

[2.15 Training 31](#_Toc63400)

[2.16 Constraints 31](#_Toc63401)

[2.17 Quality Management 33](#_Toc63402)

[2.18 Contractor’s Use of MOD Names, Insignia and Badges 33](#_Toc63403)

[2.19 Site Safety and Protection 33](#_Toc63404)

[2.20 Application of Construction (Design and Management) Regulations (CDM) 2015 37](#_Toc63405)

[2.21 Surveys 37](#_Toc63406)

[2.22 Through Life Cost Management 38](#_Toc63407)

[2.23 Contract Records 39](#_Toc63408)

[2.24 Sustainable Development and the Environment 39](#_Toc63409)

[2.25 Issued Property 41](#_Toc63410)

[2.26 Materials Arising from the Contract 41](#_Toc63411)

[2.27 Take Over Process 42](#_Toc63412)

[2.28 Relationship Management 43](#_Toc63413)

[2.29 Project Interfaces 43](#_Toc63414)

[Appendices 48](#_Toc63415)

[Annex F1: Project Specification/ **[REDACTED]** Design Pack and Planning Submission Documents 48](#_Toc63416)

[Annex F2: Window Data Sheets 49](#_Toc63417)

Annex F3: Fire Safety Strategy.................................................................................................................................. 10

Annex F4: BIM Protocol, IDP & Model ...................................................................................................................... 51

Annex F5: Building Regulations Compliance Specification .................................................................................. 52

Annex F6: Sustainability Appraisal Matrix, Net Zero Carbon & DREAM Documentation .................................... 53

Annex F7: Survey and Pre-Construction Information............................................................................................. 54

Annex F8: Infrastructure Guidance Document ........................................................................................................ 55

Annex F09: Site Access and Security ...................................................................................................................... 56

Annex F10: 4Cs Guidance and SOKH form ............................................................................................................. 57

Annex F11: Monthly Contractor Reporting Guidance ............................................................................................. 58

Annex F12: Handover Guidance ............................................................................................................................... 59

Annex F13: Glossary of Terms .................................................................................................................................. 10

Annex F14: Planning Consent & Permitted Development Summary .................................................................... 61

Annex F15: Plain Language Questions .................................................................................................................... 62

Annex F16: **[REDACTED]** site delivery plan .......................................................................................................................... 63

**[REDACTED]**