## Front Cover
Specification of Works:
External Repairs, Landscaping and Conversion of 1 Strickland Place Into Two Residential Dwellings.
At:
1 & 2 Strickland Place, Southwold, Suffolk, IP18 6HN
On behalf of:
Southwold Town Council
Town Hall,
Market Place, Southwold,
IP18 6EF
Ref:
2209019
Version:
B
Date:
April 2023
Prepared by
North & Hawkins Ltd
15 Chestnut Drive
Wymondham
NR18 9SB
Tel: 01603 397055
Web: www.northandhawkins.co.uk

## Preliminaries (hidden)
1 | SECTION 1 – PRELIMINARIES/GENERAL CONDITIONS | Cost (£)
A | JCT 2016 Minor Works Building Contract with Contractor's Design
10 | PROJECT PARTICULARS
A10 | PROJECT PARTICULARS
110 | THE PROJECT
· Name:
· Nature:
· Location:
· Length of contract:
120 | EMPLOYER (CLIENT)
· Name:
· Address:
· Contact:
· Telephone:
· E-mail:
130 | PRINCIPAL CONTRACTOR (CDM)
· Name: TBC.
· Address: TBC.
· Contact: TBC.
· Telephone: TBC.
· E-mail: TBC.
140 | ARCHITECT/ CONTRACT ADMINISTRATOR
· Name:
· Address:
· Contact:
· Telephone:
· E-mail:
150 | PRINCIPAL DESIGNER
· Name:
· Address:
· Contact:
· Telephone:
· E-mail:
200 | CONSULTANTS
· Description:
· Name:
· Address:
· Telephone:
A11 | TENDER AND CONTRACT DOCUMENTS
A11 | TENDER AND CONTRACT DOCUMENTS
110 | TENDER DRAWINGS
· The tender drawings are:
120 | CONTRACT DRAWINGS
· The Contract Drawings: The same as the tender drawings.
160 | PRECONSTRUCTION INFORMATION
· Format: The Preconstruction information is described in these preliminaries in Section A34. It refers to information given elsewhere in the preliminaries and other tender documents.
A12 | THE SITE/ EXISTING BUILDINGS
A12 | THE SITE/ EXISTING BUILDINGS
110 | THE SITE
· Description:
120 | EXISTING BUILDINGS ON/ ADJACENT TO THE SITE
· Description:
140 | EXISTING UTILITIES AND SERVICES
· Drawings: (Information shown is indicative only):
· Other information: None.
180 | HEALTH AND SAFETY FILE
· Availability for inspection: The Health and Safety File for the site/ building may be seen by appointment during normal office hours at: North and Hawkins Building Consultancy.
· Other documents: TBA.
· Arrangements for inspection: By request to CA.
200 | ACCESS TO THE SITE
· Description:
· Limitations:
210 | PARKING
·
220 | USE OF THE SITE
· General: Do not use the site for any purpose other than carrying out the Works.
· Limitations: None.
230 | SURROUNDING LAND/ BUILDING USES
· General: Adjacent or nearby uses or activities are as follows:
240 | HEALTH AND SAFETY HAZARDS
· General: The nature and condition of the site/ building cannot be fully and certainly ascertained before it is opened up. However the following hazards are or may be present: Asbestos
· Information: The accuracy and sufficiency of this information is not guaranteed by the Employer or the Employer’s representative. Ascertain if any additional information is required to ensure the safety of all persons and the Works.
· Site staff: Draw to the attention of all personnel working on the site the nature of any possible contamination and the need to take appropriate precautionary measures.
250 | SITE VISIT
· Assessment: Ascertain the nature of the site, access thereto and all local conditions and restrictions likely to affect the execution of the Works.
· Arrangements for visit: via CA.
A13 | DESCRIPTION OF THE WORK
A13 | DESCRIPTION OF THE WORK
110 | PREPARATORY WORK BY OTHERS
· Works: Carried out under a separate contract and completed before the start of work on site for this Contract.
· Description: None.
120 | THE WORKS
· Description:
130 | WORK BY OTHERS CONCURRENT WITH THE CONTRACT
· Description:
140 | COMPLETION WORK BY OTHERS
· Description: None.
A20 | JCT MINOR WORKS BUILDING CONTRACT WITH CONTRACTOR'S DESIGN (MWD)
A20 | JCT MINOR WORKS BUILDING CONTRACT WITH CONTRACTOR'S DESIGN (MWD)
JCT MINOR WORKS BUILDING CONTRACT WITH CONTRACTOR'S DESIGN
· The Contract: JCT Minor Works Building Contract with Contractor's Design 2016 Edition.
· Requirement: Allow for the obligations, liabilities and services described.
THE RECITALS
First - THE WORKS AND THE CONTRACT ADMINISTRATOR
· The work comprises:
· Architect/ Contract Administrator: See clause A10/140.
Second - CONTRACTOR'S DESIGNED PORTION
· The Works include the design and construction of:
Third - CONTRACT DOCUMENTS
· Contract drawings: As listed in clause A11/120.
Contract documents: The following have been prepared which show and describe the work to be done A specification.
Fourth - PRICED DOCUMENTS
· Documents to be priced or provided by the Contractor: Contract specification.
THE ARTICLES
3 - ARCHITECT/ CONTRACT ADMINISTRATOR
· Architect/ Contract Administrator: See clause A10/140.
4 and 5 - PRINCIPAL DESIGNER/ PRINCIPAL CONTRACTOR
· Principal Designer: See clause A10/150.
· Principal Contractor: See clause A10/130.
CONTRACT PARTICULARS
Fifth Recital and Schedule 2 - BASE DATE
· Base date: N/A.
Fifth Recital and clause 4.2 - CONSTRUCTION INDUSTRY SCHEME (CIS)
· Employer at base date is not a 'contractor' for the purposes of the CIS.
Sixth Recital - CDM REGULATIONS
· The project is not notifiable.
Seventh Recital - FRAMEWORK AGREEMENT
· Framework agreement: Does not apply.
· Details:
- Date: N/A.
- Title: N/A.
- Parties: N/A.
Article 7 - ARBITRATION
· Article 7 and Schedule 1 apply.
Clause 2.3 - COMMENCEMENT AND COMPLETION
· Works Commencement date:
· Date for Completion:
Clause 2.9 - LIQUIDATED DAMAGES
· At the rate of £?? per calendar week or pro-rata thereto.
Clause 2.11 - RECTIFICATION PERIOD
· Period: 12 months from the date of practical completion.
Clause 4.3 - INTERIM PAYMENTS
· Interim Valuation Dates:
- The first Interim Valuation Date is: 4 weeks.
- Thereafter at intervals of: 4 weeks.
· Payments due prior to practical completion:
- Percentage of total value of the work etc.: 95 per cent.
· Payments becoming due on or after practical completion:
- Percentage of the total amount to be paid: 97½ per cent.
Clause 5.3 - CONTRACTOR'S PUBLIC LIABILITY INSURANCE - INJURY TO PERSONS OR PROPERTY
· The required level of cover for any one occurrence or series of occurrences arising out of one event:
- Not less than: £5 million.
Clauses 5.4A, 5.4B and 5.4C - INSURANCE OF THE WORKS, ETC. - ALTERNATIVE PROVISIONS
· Clause 5.4C applies.
· Where clause 5.4.A or 5.4B applies. percentage to cover professional fees: N/A.
· Where clause 5.4.C applies:
- insurance arrangements - details of the required policy or policies: insurance arrangements - details of the required policy or policies: Contractors All Risk Policy of not less than £1,000,000. the contractor must provide evidence of suitable current Contractors All risks, Public Liability and Employers Liability insurance to cover a minimum level of £5 million. The employer will ensure the building.
Clause 7.2 - ADJUDICATION
· The Adjudicator is: TBC.
· Nominating body: Royal Institution of Chartered Surveyors.
Schedule 1 paragraph 2.1 - ARBITRATION
· Appointor of Arbitrator (and of any replacement): President or a Vice president of the: The Royal Institution of Chartered Surveyors.
THE CONDITIONS
SECTION 1: DEFINITIONS AND INTERPRETATION
1.4 - RECKONING PERIODS OF DAYS
· Amendments: None.
1.8 - APPLICABLE LAW
· Amendments: None.
SECTION 2: CARRYING OUT THE WORKS
SECTION 3: CONTROL OF THE WORKS
SECTION 4: PAYMENT
SECTION 5: INJURY, DAMAGE AND INSURANCE
SECTION 6: TERMINATION
SECTION 7: SETTLEMENT OF DISPUTES
EXECUTION
· The Contract: Will be executed as a deed.
CONTRACT GUARANTEE BOND
· Contract Guarantee Bond: None.
A30 | TENDERING/ SUBLETTING/ SUPPLY
A30 | TENDERING/ SUBLETTING/ SUPPLY
MAIN CONTRACT TENDERING
110 | SCOPE
· General: These conditions are supplementary to those stated in the Invitation to Tender and on the form of tender.
145 | TENDERING PROCEDURE
· General: In accordance with the principles of: JCT.
· Arithmetical errors: Pricing document is dominant.
160 | EXCLUSIONS
· Inability to tender: Immediately inform if any parts of the work as defined in the tender documents cannot be tendered.
· Relevant parts of the work: Define those parts, stating reasons for the inability to tender.
170 | ACCEPTANCE OF TENDER
· Acceptance: No guarantee is offered that any tender will be recommended for acceptance or be accepted, or that reasons for non acceptance will be given.
· Costs: No liability is accepted for any cost incurred in the preparation of any tender.
190 | PERIOD OF VALIDITY
· Period: After submission or lodgement, keep tender open for consideration (unless previously withdrawn) for not less than 12 weeks.
· Date for possession/ commencement: See section A20.
PRICING/ SUBMISSION OF DOCUMENTS
210 | PRELIMINARIES IN THE SPECIFICATION
· The Preliminaries/ General conditions sections (A10-A56 inclusive) must not be relied on as complying with SMM7/ NRM2.
250 | PRICED DOCUMENTS
· Alterations: Do not alter or qualify the priced documents without written consent. Tenders containing unauthorised alterations or qualifications may be rejected.
· Measurements: Where not stated, ascertain from the drawings.
· Deemed included: Costs relating to items, which are not priced, will be deemed to have been included elsewhere in the tender.
· Submit: With tender.
310 | TENDER
· General: Tenders must include for all work shown or described in the tender documents as a whole or clearly apparent as being necessary for the complete and proper execution of the Works.
440 | SCHEDULE OF RATES
· Schedule of rates (unpriced): Included with the tender documents. The Contractor may insert additional items. All items must be fully priced.
· Fully priced copy: Submit with the tender.
500 | TENDER STAGE METHOD STATEMENTS
· Method statements: Prepare, describing how and when the following is to be carried out:
TBC.
· Statements: Submit within one week of request.
510 | ALTERNATIVE METHOD TENDERS
· General: In addition to and at the same time as tendering for the Works as defined in the tender documents, alternative methods of construction/ installation may be submitted for consideration. Alternatives, which would involve significant changes to other work, may not be considered.
· Alternative tenders: Such alternatives will be deemed to be alternative tenders and each must include a complete and precise statement of the effects on cost and programme.
· Safety method statement: Carry out a health and safety risk assessment for each alternative and where appropriate provide a safety method statement suitable for incorporation in the Health and Safety Plan.
· Full technical data: Submit for each alternative together with details of any consequential amendments to the design and/ or construction of other parts of the Works.
· Submit: Within one week of request.
515 | ALTERNATIVE TIME TENDERS
· General: In addition to and at the same time as tendering based upon the date or period specified in section A20, an alternative tender based upon a different date for completion or period may be submitted.
· Date for completion: If any such tender is accepted the date for completion inserted in the Contract will be the date stated in the alternative tender or determined from the period stated in the alternative tender.
520 | DESIGN DOCUMENTS
· Scope: Include the following in the Contractor’s Proposals:
Design drawings:
Technical information:
· Submit: With tender.
530 | SUBSTITUTE PRODUCTS
· Details: If products of different manufacture to those specified are proposed, submit details with the tender giving reasons for each proposed substitution. Substitutions, which have not been notified at tender stage, may not be considered.
· Compliance: Substitutions accepted will be subject to the verification requirements of clause A31/200.
550 | HEALTH AND SAFETY INFORMATION
· Content: Describe the organisation and resources to safeguard the health and safety of operatives, including those of subcontractors, and of any person whom the Works may affect.
· Include:
- A copy of the contractor's health and safety policy document, including risk assessment procedures.
- Accident and sickness records for the past five years.
- Records of previous Health and Safety Executive enforcement action.
- Records of training and training policy.
- The number and type of staff responsible for health and safety on this project with details of their qualifications and duties.
· Submit: Within one week of request.
570 | OUTLINE CONSTRUCTION PHASE HEALTH AND SAFETY PLAN
· Content: Submit the following information within one week of request:
- Method statements on how risks from hazards identified in the pre-construction information and other hazards identified by the contractor will be addressed.
- Details of the management structure and responsibilities.
- Arrangements for issuing health and safety directions.
- Procedures for informing other contractors and employees of health and safety hazards.
- Selection procedures for ensuring competency of other contractors, the self-employed and designers.
- Procedures for communications between the project team, other contractors and site operatives.
- Arrangements for cooperation and coordination between contractors.
- Procedures for carrying out risk assessment and for managing and controlling the risk.
- Emergency procedures including those for fire prevention and escape.
- Arrangements for ensuring that all accidents, illness and dangerous occurrences are recorded.
- Arrangements for welfare facilities.
- Procedures for ensuring that all persons on site have received relevant health and safety information and training.
- Arrangements for consulting with and taking the views of people on site.
- Arrangements for preparing site rules and drawing them to the attention of those affected and ensuring their compliance.
- Monitoring procedures to ensure compliance with site rules, selection and management procedures, health and safety standards and statutory requirements.
- Review procedures to obtain feedback.
A31 | PROVISION, CONTENT AND USE OF DOCUMENTS
A31 | PROVISION, CONTENT AND USE OF DOCUMENTS
DEFINITIONS AND INTERPRETATIONS
110 | DEFINITIONS
· Meaning: Terms, derived terms and synonyms used in the preliminaries/ general conditions and specification are as stated therein or in the appropriate British Standard or British Standard glossary.
120 | COMMUNICATION
· Definition: Includes advise, inform, submit, give notice, instruct, agree, confirm, seek or obtain information, consent or instructions, or make arrangements.
· Format: In writing to the person named in clause A10/140 unless specified otherwise.
· Response: Do not proceed until response has been received.
130 | PRODUCTS
· Definition: Materials, both manufactured and naturally occurring, and goods, including components, equipment and accessories, intended for the permanent incorporation in the Works.
· Includes: Goods, plant, materials, site materials and things for incorporation into the Works.
135 | SITE EQUIPMENT
· Definition: All appliances or things of whatsoever nature required in or about the construction for completion of the Works but not materials or other things intended to form or forming part of the Permanent Works.
· Includes: Construction appliances, vehicles, consumables, tools, temporary works, scaffolding, cabins and other site facilities.
140 | DRAWINGS
· Definitions: To BSRIA BG 6 A design framework for building services. Design activities and drawing definitions.
· CAD data: In accordance with BS 1192.
145 | CONTRACTOR'S CHOICE
· Meaning: Selection delegated to the Contractor, but liability to remain with the specifier.
150 | CONTRACTOR'S DESIGN
· Meaning: Design to be carried out or completed by the Contractor and supported by appropriate contractual arrangements, to correspond with specified requirements.
155 | SUBMIT PROPOSALS
· Meaning: Submit information in response to specified requirements.
160 | TERMS USED IN SPECIFICATION
· Remove: Disconnect, dismantle as necessary and take out the designated products or work and associated accessories, fixings, supports, linings and bedding materials. Dispose of unwanted materials. Excludes taking out and disposing of associated pipework, wiring, ductwork or other services.
· Fix: Receive, unload, handle, store, protect, place and fasten in position and disposal of waste and surplus packaging including all labour, materials and site equipment for that purpose.
· Supply and fix: As above, but including supply of products to be fixed. All products to be supplied and fixed unless stated otherwise.
· Keep for reuse: Do not damage designated products or work. Clean off bedding and jointing materials. Stack neatly, adequately protect and store until required by the Employer/ Purchaser or for use in the Works as instructed.
· Make good: Execute local remedial work to designated work. Make secure, sound and neat. Excludes redecoration and/ or replacement.
· Replace: Supply and fix new products matching those removed. Execute work to match original new state of that removed.
· Repair: Execute remedial work to designated products. Make secure, sound and neat. Excludes redecoration and/ or replacement.
· Refix: Fix removed products.
· Ease: Adjust moving parts of designated products or work to achieve free movement and good fit in open and closed positions.
· Match existing: Provide products and work of the same appearance and features as the original, excluding ageing and weathering. Make joints between existing and new work as inconspicuous as possible.
· System: Equipment, accessories, controls, supports and ancillary items, including installation, necessary for that section of the work to function.
170 | MANUFACTURER AND PRODUCT REFERENCE
· Definition: When used in this combination:
- Manufacturer: The firm under whose name the particular product is marketed.
- Product reference: The proprietary brand name and/ or reference by which the particular product is identified.
· Currency: References are to the particular product as specified in the manufacturer’s technical literature current on the date of the invitation to tender.
200 | SUBSTITUTION OF PRODUCTS
· Products: If an alternative product to that specified is proposed, obtain approval before ordering the product.
· Reasons: Submit reasons for the proposed substitution.
· Documentation: Submit relevant information, including:
- manufacturer and product reference;
- cost;
- availability;
- relevant standards;
- performance;
- function;
- compatibility of accessories;
- proposed revisions to drawings and specification;
- compatibility with adjacent work;
- appearance;
- copy of warranty/ guarantee.
· Alterations to adjacent work: If needed, advise scope, nature and cost.
· Manufacturers’ guarantees: If substitution is accepted, submit before ordering products.
210 | CROSS REFERENCES
· Accuracy: Check remainder of the annotation or item description against the terminology used in the section or clause referred to.
· Related terminology: Where a numerical cross-reference is not given the relevant sections and clauses of the specification will apply.
· Relevant clauses: Clauses in the referred to specification section dealing with general matters, ancillary products and execution also apply.
· Discrepancy or ambiguity: Before proceeding, obtain clarification or instructions.
220 | REFERENCED DOCUMENTS
· Conflicts: Specification prevails over referenced documents.
230 | EQUIVALENT PRODUCTS
· Inadvertent omission: Wherever products are specified by proprietary name the phrase 'or equivalent' is to be deemed included.
240 | SUBSTITUTION OF STANDARDS
· Specification to British Standard or European Standard: Substitution may be proposed complying with a grade or category within a national standard of another Member State of the European Community or an international standard recognised in the UK.
· Before ordering: Submit notification of all such substitutions.
· Documentary evidence: Submit for verification when requested as detailed in clause A31/200. Any submitted foreign language documents must be accompanied by certified translations into English.
250 | CURRENCY OF DOCUMENTS AND INFORMATION
· Currency: References to published documents are to the editions, including amendments and revisions, current on the date of the Invitation to Tender.
260 | SIZES
· General dimensions: Products are specified by their co-ordinating sizes.
· Timber: Cross section dimensions shown on drawings are:
- Target sizes as defined in BS EN 336 for structural softwood and hardwood sections.
- Finished sizes for non-structural softwood or hardwood sawn and further processed sections.
DOCUMENTS PROVIDED ON BEHALF OF THE EMPLOYER
410 | ADDITIONAL COPIES OF DRAWINGS/ DOCUMENTS
· Additional copies: Issued free of charge.
440 | DIMENSIONS
· Scaled dimensions: Do not rely on.
450 | MEASURED QUANTITIES
· Ordering products and constructing the Works: The accuracy and sufficiency of the measured quantities is not guaranteed.
· Precedence: The specification and drawings shall override the measured quantities.
460 | THE SPECIFICATION
· Coordination: All sections must be read in conjunction with Main Contract Preliminaries/ General conditions.
DOCUMENTS PROVIDED BY CONTRACTOR/ SUBCONTRACTORS/ SUPPLIERS
600 | CONTRACTOR'S DESIGN INFORMATION
· General: Complete the design and detailing of parts of the Works as specified.
· Provide:
- Production information based on the drawings, specification and other information.
- Liaison to ensure coordination of the work with related building elements and services.
· Master programme: Make reasonable allowance for completing design/ production information, submission (including information relevant to the CDM Regulations), comment, inspection, amendment, resubmission and reinspection.
· Information required: TCB.
- Format: Electronic.
- Number of copies: 1.
· Submit: Within one week of request.
620 | AS BUILT DRAWINGS AND INFORMATION
· Contractor designed work: Provide drawings/ information:
· Submit: At least two weeks before date for completion.
630 | TECHNICAL LITERATURE
· Information: Keep on site for reference by all supervisory personnel:
- Manufacturers' current literature relating to all products to be used in the Works.
- Relevant British, EN or ISO Standards.
640 | MAINTENANCE INSTRUCTIONS AND GUARANTEES
· Components and equipment: Obtain or retain copies, register with manufacturer and hand over on or before completion of the Works.
· Information location: In Building Manual.
· Emergency call out services: Provide telephone numbers for use after completion. Extent of cover: None.
A32 | MANAGEMENT OF THE WORKS
A32 | MANAGEMENT OF THE WORKS
GENERALLY
110 | SUPERVISION
· General: Accept responsibility for coordination, supervision and administration of the Works, including subcontracts.
· Coordination: Arrange and monitor a programme with each subcontractor, supplier, local authority and statutory undertaker, and obtain and supply information as necessary for coordination of the work.
120 | INSURANCE
· Documentary evidence: Before starting work on site submit details, and/ or policies and receipts for the insurances required by the Conditions of Contract.
125 | PROFESSIONAL INDEMNITY INSURANCE
· Provide and maintain insurance in respect of Contractor Designed Works:
- Level of cover: £1,000,000.
- Period of insurance for these purposes: one year.
· Amount of indemnity required: £ 1,000,000.
· Limit of cover for pollution/ contamination claims (If none is stated, the required level of cover shall be the full amount of the indemnity cover stated): £ 1,000,000.
· Expiry of required period of CDP Professional Indemnity insurance: six years
(If no period is selected, the expiry date shall be 6 years from the date of practical completion of the Works).
· Documentary evidence: Submit details before starting work on site and/ or policies and receipts for the insurances required.
- Format: Electronic.
130 | INSURANCE CLAIMS
· Notice: If any event occurs which may give rise to any claim or proceeding in respect of loss or damage to the Works or injury or damage to persons or property arising out of the Works, immediately give notice to the Employer, the person named in clause A10/140 and the Insurers.
· Failure to notify: Indemnify the Employer against any loss, which may be caused by failure to give such notice.
150 | OWNERSHIP
· Alteration/ clearance work: Materials arising become the property of the Contractor except where otherwise stated. Remove from site as work proceeds.
PROGRAMME/ PROGRESS
210 | PROGRAMME
· Master programme: Immediately when requested and before starting work on site submit in an approved form a master programme for the Works, which must include details of:
- Planning and mobilisation by the Contractor
- Subcontractor's work.
- Running in, adjustment, commissioning and testing of all engineering services and installations.
- Work resulting from instructions issued in regard to the expenditure of provisional sums.
- Work by others concurrent with the Contract.
· Submit one copy.
245 | START OF WORK ON SITE
· Notice: Before the proposed date for start of work on site give minimum notice of one week.
250 | MONITORING
· Progress: Record on a copy of the programme kept on site.
· Avoiding delays: If any circumstances arise which may affect the progress of the Works submit proposals or take other action as appropriate to minimize any delay and to recover any lost time.
· Key Performance Indicators:
- Details: None.
- Record progress against each of the KPIs. If performance against KPI falls short of target, submit proposals for remediation.
260 | SITE MEETINGS
· General: Site meetings will be held to review progress and other matters arising from administration of the Contract.
· Frequency: Every two weeks.
· Location: On site.
· Accommodation: Ensure availability at the time of such meetings.
· Attendees: Attend meetings and inform subcontractors and suppliers when their presence is required.
· Chairperson (who will also take and distribute minutes): Contract Administrator.
290 | NOTICE OF COMPLETION
· Requirement: Give notice of the anticipated dates of completion of the whole or parts of the Works.
· Associated works: Ensure necessary access, services and facilities are complete.
· Period of notice (minimum): Two weeks.
310 | EXTENSIONS OF TIME
· Notice: When a notice of the cause of any delay or likely delay in the progress of the works is given under the contract, written notice must also be given of all other causes which apply concurrently.
· Details: As soon as possible submit:
- Relevant particulars of the expected effects, if appropriate, related to the concurrent causes.
- An estimate of the extent, if any, of the expected delay in the completion of the Works beyond the date for completion.
- All other relevant information required.
CONTROL OF COST
420 | REMOVAL/ REPLACEMENT OF EXISTING WORK
· Extent and location: Agree before commencement.
· Execution: Carry out in ways that minimize the extent of work.
430 | PROPOSED INSTRUCTIONS
· Estimates: If a proposed instruction requests an estimate of cost, submit without delay and in any case within seven days.
440 | MEASUREMENT
· Covered work: Give notice before covering work required to be measured.
450 | DAYWORK VOUCHERS
· Before commencing work: Give reasonable notice to person countersigning daywork vouchers.
· Content: Before delivery each voucher must be:
- Referenced to the instruction under which the work is authorised.
- Signed by the Contractor's person in charge as evidence that the operatives' names, the time daily spent by each and the equipment and products employed are correct.
· Submit: By the end of the week in which the work has been executed.
470 | PRODUCTS NOT INCORPORATED INTO THE WORKS
· Ownership: At the time of each valuation, supply details of those products not incorporated into the Works which are subject to any reservation of title inconsistent with passing of property as required by the Conditions of Contract, together with their respective values.
· Evidence: When requested, provide evidence of freedom of reservation of title.
A33 | QUALITY STANDARDS/ CONTROL
A33 | QUALITY STANDARDS/ CONTROL
STANDARDS OF PRODUCTS AND EXECUTIONS
110 | INCOMPLETE DOCUMENTATION
· General: Where and to the extent that products or work are not fully documented, they are to be:
- Of a kind and standard appropriate to the nature and character of that part of the Works where they will be used.
- Suitable for the purposes stated or reasonably to be inferred from the project documents.
Contract documents: Omissions or errors in description and/ or quantity shall not vitiate the Contract nor release the Contractor from any obligations or liabilities under the Contract.
120 | WORKMANSHIP SKILLS
· Operatives: Appropriately skilled and experienced for the type and quality of work.
· Registration: With Construction Skills Certification Scheme.
· Evidence: Operatives must produce evidence of skills/ qualifications when requested.
130 | QUALITY OF PRODUCTS
· Generally: New. (Proposals for recycled products may be considered).
· Supply of each product: From the same source or manufacturer.
· Whole quantity of each product required to complete the Works: Consistent kind, size, quality and overall appearance.
· Tolerances: Where critical, measure a sufficient quantity to determine compliance.
· Deterioration: Prevent. Order in suitable quantities to a programme and use in appropriate sequence.
135 | QUALITY OF EXECUTION
· Generally: Fix, apply, install or lay products securely, accurately, plumb, neatly and in alignment.
· Colour batching: Do not use different colour batches where they can be seen together.
· Dimensions: Check on-site dimensions.
· Finished work: Without defects, e.g. not damaged, disfigured, dirty, faulty, or out of tolerance.
· Location and fixing of products: Adjust joints open to view so they are even and regular.
140 | COMPLIANCE
· Compliance with proprietary specifications: Retain on site evidence that the proprietary product specified has been supplied.
· Compliance with performance specifications: Submit evidence of compliance, including test reports indicating:
- Properties tested.
- Pass/ fail criteria.
- Test methods and procedures.
- Test results.
- Identity of testing agency.
- Test dates and times.
- Identities of witnesses.
- Analysis of results.
150 | INSPECTIONS
· Products and executions: Inspection or any other action must not be taken as approval unless confirmed in writing referring to:
- Date of inspection.
- Part of the work inspected.
- Respects or characteristics which are approved.
- Extent and purpose of the approval.
- Any associated conditions.
160 | RELATED WORK
· Details: Provide all trades with necessary details of related types of work. Before starting each new type or section of work ensure previous related work is:
- Appropriately complete.
- In accordance with the project documents.
- To a suitable standard.
- In a suitable condition to receive the new work.
· Preparatory work: Ensure all necessary preparatory work has been carried out.
170 | MANUFACTURER’S RECOMMENDATIONS/ INSTRUCTIONS
· General: Comply with manufacturer's printed recommendations and instructions current on the date of the Invitation to tender.
· Changes to recommendations or instructions: Submit details.
· Ancillary products and accessories: Use those supplied or recommended by main product manufacturer.
· Agrément certified products: Comply with limitations, recommendations and requirements of relevant valid certificates.
180 | WATER FOR THE WORKS
· Mains supply: Clean and uncontaminated.
· Other: Do not use until:
- Evidence of suitability is provided.
- Tested to BS EN 1008 if instructed.
SAMPLES/ APPROVALS
210 | SAMPLES
· Products or executions: Comply with all other specification requirements and in respect of the stated or implied characteristics either:
- To an express approval.
- To match a sample expressly approved as a standard for the purpose.
220 | APPROVAL OF PRODUCTS
· Submissions, samples, inspections and tests: Undertake or arrange to suit the Works programme.
· Approval: Relates to a sample of the product and not to the product as used in the Works. Do not confirm orders or use the product until approval of the sample has been obtained.
· Complying sample: Retain in good, clean condition on site. Remove when no longer required.
230 | APPROVAL OF EXECUTION
· Submissions, samples, inspections and tests: Undertake or arrange to suit the Works programme.
· Approval: Relates to the stated characteristics of the sample. (If approval of the finished work as a whole is required this is specified separately). Do not conceal, or proceed with affected work until compliance with requirements is confirmed.
· Complying sample: Retain in good, clean condition on site. Remove when no longer required.
ACCURACY/ SETTING OUT GENERALLY
320 | SETTING OUT
· General: Submit details of methods and equipment to be used in setting out the Works.
· Levels and dimensions: Check and record the results on a copy of drawings. Notify discrepancies and obtain instructions before proceeding.
· Inform: When complete and before commencing construction.
330 | APPEARANCE AND FIT
· Tolerances and dimensions: If likely to be critical to execution or difficult to achieve, as early as possible either:
- Submit proposals; or
- Arrange for inspection of appearance of relevant aspects of partially finished work.
· General tolerances (maximum): To BS 5606, tables 1 and 2.
340 | CRITICAL DIMENSIONS
· Critical dimensions: Set out and construct the Works to ensure compliance with the tolerances stated.
· Location: Detailed on drawings Detailed on drawings as applicable.
350 | LEVELS OF STRUCTURAL FLOORS
· Maximum tolerances for designed levels to be:
- Floors to be self-finished, and floors to receive sheet or tile finishes directly bedded in adhesive: +/- 10 mm.
- Floors to receive dry board/ panel construction with little or no tolerance on thickness: +/- 10 mm.
- Floors to receive mastic asphalt flooring/ underlays directly: +/- 10 mm.
- Floors to receive mastic asphalt flooring/ underlays laid on mastic asphalt levelling coat(s): +/- 15 mm.
- Floors to receive fully bonded screeds/ toppings/ beds: +/- 15 mm.
- Floors to receive unbonded or floating screeds/ beds: +/- 20 mm.
360 | RECORD DRAWINGS
· Site setting out drawing: Record details of all grid lines, setting-out stations, benchmarks and profiles. Retain on site throughout the contract and hand over on completion.
SERVICES GENERALLY
410 | SERVICES REGULATIONS
· New or existing services: Comply with the Byelaws or Regulations of the relevant Statutory Authority.
420 | WATER REGULATIONS/ BYELAWS NOTIFICATION
· Requirements: Notify Water Undertaker of any work carried out to or which affects new or existing services and submit any required plans, diagrams and details.
· Consent: Allow adequate time to receive Undertaker's consent before starting work. Inform immediately if consent is withheld or is granted subject to significant conditions.
430 | WATER REGULATIONS/ BYELAWS CONTRACTOR’S CERTIFICATE
· On completion of the work: Submit (copy where also required to the Water Undertaker) a certificate including:
- The address of the premises.
- A brief description of the new installation and/ or work carried out to an existing installation.
- The Contractor's name and address.
- A statement that the installation complies with the relevant Water Regulations or Byelaws.
- The name and signature of the individual responsible for checking compliance.
- The date on which the installation was checked.
435 | ELECTRICAL INSTALLATION CERTIFICATE
· Submit: When relevant electrical work is completed.
· Original certificate: To be lodged in the Building Manual.
440 | GAS, OIL AND SOLID FUEL APPLIANCE INSTALLATION CERTIFICATE
· Before the completion date stated in the Contract: Submit a certificate stating:
- The address of the premises.
- A brief description of the new installation and/ or work carried out to an existing installation.
- Any special recommendations or instructions for the safe use and operation of appliances and flues.
- The Contractor's name and address.
- A statement that the installation complies with the appropriate safety, installation and use regulations.
- The name, qualification and signature of the competent person responsible for checking compliance.
- The date on which the installation was checked.
· Certificate location: To CA.
445 | SERVICE RUNS
· General: Provide adequate space and support for services, including unobstructed routes and fixings.
· Ducts, chases and holes: Form during construction rather than cut.
· Coordination with other works: Submit details of locations, types/ methods of fixing of services to fabric and identification of runs and fittings.
450 | MECHANICAL AND ELECTRICAL SERVICES
· Final tests and commissioning: Carry out so that services are in full working order at completion of the Works.
· Building Regulations notice: Copy to be lodged in the Building Manual.
SUPERVISION/ INSPECTION/ DEFECTIVE WORK
525 | ACCESS
· Extent: Provide at all reasonable times access to the Works and to other places of the Contractor or subcontractors where work is being prepared for the Contract.
· Designate: Contract Administrator.
530 | OVERTIME WORKING
· Notice: Prior to overtime being worked, submit details of times, types and locations of work to be done.
- Minimum period of notice: Two days.
· Concealed work: If executed during overtime for which notice has not been given, it may be required to be opened up for inspection and reinstated at the Contractor's expense.
540 | DEFECTS IN EXISTING WORK
· Undocumented defects: When discovered, immediately give notice. Do not proceed with affected related work until response has been received.
· Documented remedial work: Do not execute work which may:
- Hinder access to defective products or work; or
- Be rendered abortive by remedial work.
560 | TESTS AND INSPECTIONS
· Timing: Agree and record dates and times of tests and inspections to enable all affected parties to be represented.
· Confirmation: One working day prior to each such test or inspection. If sample or test is not ready, agree a new date and time.
· Records: Submit a copy of test certificates and retain copies on site.
580 | CONTINUITY OF THERMAL INSULATION
· Record and report: Confirm that work to new, renovated or upgraded thermal elements has been carried out to conform to specification. Include:
- The address of the premises.
- The Contractor's name and address.
- The name, qualification and signature of the competent person responsible for checking compliance.
- The date on which the installation was checked.
· Submit: Before completion of the Works.
· Copy: To be lodged in the Building Manual.
610 | DEFECTIVE PRODUCTS/ EXECUTIONS
· Proposals: Immediately any work or product is known, or appears, to be not in accordance with the Contract, submit proposals for opening up, inspection, testing, making good, adjustment of the Contract Sum, or removal and re-execution.
· Acceptability: Such proposals may be unacceptable and contrary instructions may be issued.
WORK AT OR AFTER COMPLETION
710 | WORK BEFORE COMPLETION
· General: Make good all damage consequent upon the Works.
Temporary markings, coverings and protective wrappings: Remove unless otherwise instructed.
· Cleaning: Clean the Works thoroughly inside and out, including all accessible ducts and voids. Remove all splashes, deposits, efflorescence, rubbish and surplus materials.
· Cleaning materials and methods: As recommended by manufacturers of products being cleaned, and must not damage or disfigure other materials or construction.
· COSHH dated data sheets: Obtain for all materials used for cleaning and ensure they are used only as recommended by their manufacturers.
· Minor faults: Touch up in newly painted work, carefully matching colour and brushing out edges. Repaint badly marked areas back to suitable breaks or junctions.
· Moving parts of new work: Adjust, ease and lubricate as necessary to ensure easy and efficient operation, including doors, windows, drawers, ironmongery, appliances, valves and controls.
720 | SECURITY AT COMPLETION
· General: Leave the Works secure with, where appropriate, all accesses closed and locked.
· Keys: Account for and adequately label all keys and hand over to Employer with itemized schedule, retaining duplicate schedule signed by Employer as a receipt.
730 | MAKING GOOD DEFECTS
· Remedial work: Arrange access with Contract Administrator.
· Rectification: Give reasonable notice for access to the various parts of the Works.
· Completion: Notify when remedial works have been completed.
A34 | SECURITY/ SAFETY/ PROTECTION
A34 | SECURITY/ SAFETY/ PROTECTION
SECURITY, HEALTH AND SAFETY
140 | CONSTRUCTION PHASE HEALTH AND SAFETY PLAN
· Submission: Present to the Employer/ Client no later than two weeks.
· Confirmation: Do not start construction work until the Employer has confirmed in writing that the Construction Phase Health and Safety Plan includes the procedures and arrangements required by the CDM Regulations.
· Content: Develop the plan from and draw on the Outline Construction Phase Health and Safety Plan, clause A30/570, and the Pre-tender Health and Safety Plan/ Preconstruction information.
150 | SECURITY
· Protection: Safeguard the site, the Works, products, materials, and any existing buildings affected by the Works from damage and theft.
· Access: Take all reasonable precautions to prevent unauthorized access to the site, the Works and adjoining property.
· Special requirements: None.
160 | STABILITY
· Responsibility: Maintain the stability and structural integrity of the Works and adjacent structures during the Contract.
· Design loads: Obtain details, support as necessary and prevent overloading.
210 | EMPLOYER’S REPRESENTATIVES SITE VISITS
· Safety: Submit details in advance, to the Employer or the person identified in clause A10/140, of safety provisions and procedures (including those relating to materials, which may be deleterious), which will require their compliance when visiting the site.
· Protective clothing and/ or equipment: Provide and maintain on site for the Employer and the person stated in clause A10/140 and other visitors to the site.
PROTECT AGAINST THE FOLLOWING
330 | NOISE AND VIBRATION
· Standard: Comply with the recommendations of BS 5228-1, in particular clause 7.3, to minimize noise levels during the execution of the Works.
· Noise levels from the Works: Maximum level: TBC dB(A) when measured from TBC.
· Equipment: Fit compressors, percussion tools and vehicles with effective silencers of a type recommended by manufacturers of the compressors, tools or vehicles.
· Restrictions: Do not use:
- Percussion tools and other noisy appliances without consent during the hours of TBC.
- Radios or other audio equipment or permit employees to use in ways or at times that may cause nuisance.
340 | POLLUTION
· Prevention: Protect the site, the Works and the general environment including the atmosphere, land, streams and waterways against pollution.
· Contamination: If pollution occurs inform immediately, including to the appropriate Authorities and provide relevant information.
350 | PESTICIDES
· Use: Not permitted.
360 | NUISANCE
· Duty: Prevent nuisance from smoke, dust, rubbish, vermin and other causes.
· Surface water: Prevent hazardous build-up on site, in excavations and to surrounding areas and roads.
370 | ASBESTOS CONTAINING MATERIALS
· Duty: Report immediately any suspected materials discovered during execution of the Works.
- Do not disturb.
- Agree methods for safe removal or encapsulation.
371 | DANGEROUS OR HAZARDOUS SUBSTANCES
· Duty: Report immediately suspected materials discovered during execution of the Works.
- Do not disturb.
- Agree methods for safe removal or remediation.
380 | FIRE PREVENTION
· Duty: Prevent personal injury or death, and damage to the Works or other property from fire.
· Standard: Comply with Joint Code of Practice 'Fire Prevention on Construction Sites', published by Construction Industry Publications and The Fire Protection Association (The 'Joint Fire Code').
390 | SMOKING ON SITE
· Smoking on site: Not permitted.
400 | BURNING ON SITE
· Burning on site: Not permitted.
410 | MOISTURE
· Wetness or dampness: Prevent, where this may cause damage to the Works.
· Drying out: Control humidity and the application of heat to prevent:
- Blistering and failure of adhesion.
- Damage due to trapped moisture.
- Excessive movement.
420 | INFECTED TIMBER/ CONTAMINATED MATERIALS
· Removal: Where instructed to remove material affected by fungal/ insect attack from the building, minimize the risk of infecting other parts of the building.
· Testing: carry out and keep records of appropriate tests to demonstrate that hazards presented by concentrations of airborne particles, toxins and other micro organisms are within acceptable levels.
430 | WASTE
· Includes: Rubbish, debris, spoil, surplus material, containers and packaging.
· General: Minimize production. Prevent accumulations. Keep the site and Works clean and tidy.
· Handling: Collect and store in suitable containers. Remove frequently and dispose off site in a safe and competent manner:
- Non-hazardous material: In a manner approved by the Waste Regulation Authority.
- Hazardous material: As directed by the Waste Regulation Authority and in accordance with relevant regulations.
· Recyclable material: Sort and dispose at a Materials Recycling Facility approved by the Waste Regulation Authority.
· Voids and cavities in the construction: Remove rubbish, dirt and residues before closing in.
· Waste transfer documentation: Retain on site.
440 | ELECTROMAGNETIC INTERFERENCE
· Duty: Prevent excessive electromagnetic disturbance to apparatus outside the site.
460 | POWER ACTUATED FIXING SYSTEMS
· Use: Not permitted.
470 | INVASIVE SPECIES
· General: Prevent the spread of species (e.g. plants or animals) that may adversely affect the site or Works economically, environmentally or ecologically.
· Special precautions: None.
· Duty: Report immediately any suspected invasive species discovered during execution of the Works.
- Do not disturb.
- Agree methods for safe eradication or removal.
PROTECT THE FOLLOWING
510 | EXISTING SERVICES
· Confirmation: Notify all service authorities, statutory undertakers and/ or adjacent owners of proposed works not less than one week before commencing site operations.
· Identification: Before starting work, check and mark positions of utilities/ services. Where positions are not shown on drawings obtain relevant details from service authorities, statutory undertakers or other owners.
· Work adjacent to services:
- Comply with service authority's/ statutory undertaker's recommendations.
- Adequately protect, and prevent damage to services: Do not interfere with their operation without consent of service authorities/ statutory undertakers or other owners.
· Identifying services:
- Below ground: Use signboards, giving type and depth;
- Overhead: Use headroom markers.
· Damage to services: If any results from execution of the Works:
- Immediately give notice and notify appropriate service authority/ statutory undertaker.
- Make arrangements for the work to be made good without delay to the satisfaction of service authority/ statutory undertaker or other owner as appropriate.
- Any measures taken to deal with an emergency will not affect the extent of the Contractor's liability.
· Marker tapes or protective covers: Replace, if disturbed during site operations, to service authority's/ statutory undertakers recommendations.
520 | ROADS AND FOOTPATHS
· Duty: Maintain roads and footpaths within and adjacent to the site and keep clear of mud and debris.
· Damage caused by site traffic or otherwise consequent upon the Works: Make good to the satisfaction of the Employer, Local Authority or other owner.
530 | EXISTING TOPSOIL/ SUBSOIL
· Duty: Prevent over compaction of existing topsoil and subsoil in those areas which may be damaged by construction traffic, parking of vehicles, temporary site accommodation or storage of materials and which will require reinstatement prior to completion of the Works.
· Protection: Before starting work submit proposals for protective measures.
540 | RETAINED TREES/ SHRUBS/ GRASSED AREAS
· Protection: Preserve and prevent damage, except those not required.
· Replacement: Mature trees and shrubs if uprooted, destroyed, or damaged beyond reasonable chance of survival in their original shape, as a consequence of the Contractor's negligence, must be replaced with those of a similar type and age at the Contractor's expense.
550 | RETAINED TREES
· Protected area: Unless agreed otherwise do not:
- Dump spoil or rubbish, excavate or disturb topsoil, park vehicles or plant, store materials or place temporary accommodation within an area which is the larger of the branch spread of the tree or an area with a radius of half the tree's height, measured from the trunk.
- Sever roots exceeding 25 mm in diameter. If unintentionally severed give notice and seek advice.
- Change level of ground within an area 3 m beyond branch spread.
560 | EXISTING FEATURES
· Protection: Prevent damage to existing buildings, fences, gates, walls, roads, paved areas and other site features, which are to remain in position during execution of the Works.
· Special requirements: None.
570 | EXISTING WORK
· Protection: Prevent damage to existing work, structures or other property during the course of the work.
· Removal: Minimum amount necessary.
· Replacement work: To match existing.
580 | BUILDING INTERIORS
· Protection: Prevent damage from exposure to the environment, including weather, flora, fauna, and other causes of material degradation during the course of the work.
600 | EXISTING FURNITURE, FITTINGS AND EQUIPMENT
· Protection: Prevent damage or move as necessary to enable the Works to be executed. Reinstate in original positions.
· Extent: Before work in each room starts the Employer will remove the following:
all loose goods, equipment and furniture.
620 | ADJOINING PROPERTY
· Permission: Obtain as necessary from owners if requiring to erect scaffolding on or otherwise use adjoining property.
625 | ADJOINING PROPERTY RESTRICTIONS
· Precautions:
- Prevent trespass of workpeople and take precautions to prevent damage to adjoining property.
- Pay all charges.
- Remove and make good on completion or when directed.
· Damage: Bear cost of repairing damage arising from execution of the Works.
630 | EXISTING STRUCTURES
· Duty: Check proposed methods of work for effects on adjacent structures inside and outside the site boundary.
· Supports: During execution of the Works:
- Provide and maintain all incidental shoring, strutting, needling and other supports as may be necessary to preserve stability of existing structures on the site or adjoining, that may be endangered or affected by the Works.
- Do not remove until new work is strong enough to support existing structure.
- Prevent overstressing of completed work when removing supports.
· Adjacent structures: Monitor and immediately report excessive movement.
· Standard: Comply with BS 5975 and BS EN 12812.
640 | MATERIALS FOR RECYCLING/ REUSE
· Duty: Sort and prevent damage to stated products or materials, clean off bedding and jointing materials and other contaminants.
· Storage: Stack neatly and protect until required by the Employer or for use in the Works as instructed.
A35 | SPECIFIC LIMITATIONS ON METHOD/ SEQUENCE/ TIMING
A35 | SPECIFIC LIMITATIONS ON METHOD/ SEQUENCE/ TIMING
170 | WORKING HOURS
· Specific limitations: 8am - 5pm Monday-Friday.
A36 | FACILITIES/ TEMPORARY WORK/ SERVICES
A36 | FACILITIES/ TEMPORARY WORK/ SERVICES
GENERALLY
110 | SPOIL HEAPS, TEMPORARY WORKS AND SERVICES
· Location: Give notice and details of intended siting.
· Maintenance: Alter, adapt and move as necessary. Remove when no longer required and make good.
ACCOMMODATION
230 | TEMPORARY ACCOMMODATION
· Proposals for temporary accommodation and storage for the Works: Submit two weeks prior to starting on site.
· Details to be included: Type of accommodation and storage, its siting and the programme for site installation and removal.
TEMPORARY WORKS
340 | NAME BOARDS/ ADVERTISEMENTS
· Name boards/ advertisements: Not permitted.
SERVICES AND FACILITIES
410 | LIGHTING
· Finishing work and inspection: Provide temporary lighting, the intensity and direction of which closely resembles that delivered by the permanent installation.
420 | LIGHTING AND POWER
· Supply: Electricity from the Employer's mains may be used for the Works as follows:
- Metering: TBC.
- Point of supply: TBC.
- Available capacity: TBC.
- Frequency: 50 Hz.
- Phase: TBC.
- Current: Alternating.
· Continuity: The Employer will not be responsible for the consequences of failure or restriction in supply.
430 | WATER
· Supply: The Employer's mains may be used for the Works as follows:
- Metering: TBC.
- Source: TBC.
- Location of supply point: TBC.
- Conditions/ Restrictions: TBC.
· Continuity: The Employer will not be responsible for the consequences of failure or restriction in supply.
440 | TELEPHONES
· Direct communication: As soon as practicable after the Date of Possession provide the Contractor's person in charge with a mobile telephone.
520 | USE OF PERMANENT HEATING SYSTEM
· Permanent heating installation: May be used for drying out the Works/ services and controlling temperature and humidity levels.
· Installation: If used:
- Take responsibility for operation, maintenance and remedial work.
- Arrange supervision by and indemnification of the appropriate Subcontractors.
- Pay costs arising.
540 | METER READINGS
· Charges for service supplies: Where to be apportioned ensure that:
- Meter readings are taken by relevant authority at possession and/ or completion as appropriate.
- Copies of readings are supplied to interested parties.
570 | PERSONAL PROTECTIVE EQUIPMENT
· General: Provide for the sole use of those acting on behalf of the Employer, in sizes to be specified:
- Safety helmets to BS EN 397, neither damaged nor time expired. Number required: 2.
- High visibility waistcoats to BS EN ISO 20471 Class 2. Number required: 2.
- Safety boots with steel insole and toecap to BS EN ISO 20345. Pairs required: 2.
- Disposable respirators to BS EN 149.FFP1S.
- Eye protection to BS EN 166.
- Ear protection - muffs to BS EN 352-1, plugs to BS EN 352-2
- Hand protection - to BS EN 388, 407, 420 or 511 as appropriate.
A37 | OPERATION/ MAINTENANCE OF THE FINISHED WORKS
A37 | OPERATION/ MAINTENANCE OF THE FINISHED WORKS
GENERALLY
110 | THE BUILDING MANUAL
· Responsibility: The Contractor
· Content: Obtain and provide comprehensive information for owners and users of the completed Works. Include an overview of the main design principles and describe key components and systems within the finished Works, so affording a complete understanding of the Works, including all buildings and their systems to enable efficient and safe operation and maintenance.
· Specific requirements: N/A.
· Format: paper & electronic.
· Number of copies: 1 paper.
· Delivery to: CA. by (date) practical completion.
115 | THE HEALTH AND SAFETY FILE
· Responsibility: the contractor.
· Content: Obtain and provide the following information: any hazards that have not been eliminated through the design and construction processes, and how they have been addressed (e.g. surveys or other information concerning asbestos or contaminated land);
key structural principles (e.g. bracing, sources of substantial stored energy – including pre- or post-tensioned members) and safe working loads for floors and roofs;
hazardous materials used (e.g. lead paints and special coatings); information regarding the removal or dismantling of installed plant and equipment (e.g. any special arrangements for lifting such equipment);
· the nature, location and markings of significant services, including underground cables; gas supply equipment; fire-fighting services etc.;.
· Format: Paper & electronic
· Delivery to: CA By (date): practical completion.
155 | CONTENT OF THE BUILDING MANUAL
· General: Details of the property, the parties, fire safety strategy, operational requirements and constraints of a general nature.
· Building fabric: Design criteria, maintenance details, product details, and environmental and trafficking conditions.
· Building services: Description and operation of systems, diagrammatic drawings, record drawings, identification of services, product details, equipment settings, maintenance schedules, consumable items, spares and emergency procedures.
· Documentation: Guarantees, warranties, maintenance agreements, test certificates and reports.
160 | PRESENTATION OF BUILDING MANUAL
· Format: A4 size, plastics covered, loose leaf, four ring binders with hard covers, each indexed, divided and appropriately cover titled.
· Selected drawings needed to illustrate or locate items mentioned in the Manual: Where larger than A4, to be folded and accommodated in the binders so that they may be unfolded without being detached from the rings.
· As-built drawings: The main sets may form annexes to the Manual.
A54 | PROVISIONAL WORK/ ITEMS
A54 | PROVISIONAL WORK/ ITEMS
110 | PROVISIONAL SUMS FOR DEFINED WORK
· Item:
· Description of work:
· Provisional Sums:
· Allow for general attendance.
110A | PROVISIONAL SUMS FOR DEFINED WORK
· Item:
· Description of work:
· Provisional Sums:
· Allow for general attendance.
590 | CONTINGENCIES
· Provisional sum: Include: £

## Scope of Work
| SCOPE OF WORK | Cost (£)
SITE SET-UP
1 | Storage, removal and disposal of all debris and waste.
2 | Ensure protection of services and other items that could be damaged during completion of works
Generally
3 | The Contractor shall price each and every clause item individually. All items necessary for the undertaking of the work will be deemed to have been included within the general pricing of the works.
4 | This Specification is to be read in conjunction with Section 1 - Preliminaries and Section 2 - Materials and Workmanship, as well as all drawings and appendices. All clauses therein shall act reciprocally with the works hereafter described.
5 | The Contractor shall carry out all works described, providing all materials, scaffolding, transport, loading / unloading, hoisting and fixing including all labour to complete the works.
6 | The Contractor shall allow for all attendance necessary to execute works, take delivery of materials on site and supervision of nominated sub-contractors.
7 | The Contractor shall remove all rubbish, debris and unwanted materials from site unless otherwise directed by the Contract Administrator (CA), and shall maintain the site in a clean and tidy condition and shall thoroughly clean down all areas upon completion.
8 | All quantities indicated or referred to within the specification, drawings and schedule are for guidance purposes only and it is the Contractor's reasonability to establish / quantify any works hereafter referred or indicated on drawings and make all due allowance in this respect. The Contractor shall be responsible for all dimensions, co-ordination, setting-out, etc in connection with the works.
9 | In addition to the constant management and supervision of the Works provided by the Contractor's person in charge, all significant types of work must be under the close control of competent trade supervisors to ensure maintenance of satisfactory quality and progress.
10 | The contractor is to further consider all health and safety implications to the works as set out in the appended Pre-Construction Information and to provide a Construction Phase Plan and all associated method statements of sufficient detail to the principal designer prior to the commencement of works on site.
11 | The residential properties located around the site will be occupied, including No 2 Strickland Place throughout the works. The contractor is to ensure that all storage and parking is contained on the site and does not impede neighbouring land.
12 | Ensure that all dust created as a consequence of the work is removed from the site as the works progresses and protect residential properties from it.
13 | Notwithstanding any other restrictions regarding noisy works contained within this specification, the Contractor will be expected to take this into account in carrying out the works in such a manner as necessary so as not to jeopardise relationships with adjacent occupiers. The Contractor is to comply generally with the recommendations of BS5228: Part 1, Clause 9.3 for minimising noise levels during execution of the works.
14 | All materials and waste is to be stored within designated areas agreed with CA until such time as it is used or removed from site. Waste is to be removed from site on a regular basis to ensure that all areas are kept clean and tidy throughout the duration of the contract.
15 | At Tender stage, the Contractor is to familiarise himself with the layout of the site and any inherent access restrictions to the property and area generally. The Contractor will be responsible for ensuring that deliveries and collection, including non-waste materials can be accommodated. Where special provision is deemed necessary, the Contractor is to identify and detail these within the Tender return.
16 | Allow for programming the works within the timescales allotted. The proposed start date is to be agreed. A detailed programme of work must be forwarded before start on site.
17 | The contractor is to provide all temporary lighting, barriers warning notices, guardrails, netting and the like necessary for the protection of other people, the public, occupiers, employees and securing the site against trespass and damage.
18 | The contractor is to allow for maintaining the building weatherproof, watertight and secure throughout the contract. The contractor will be held responsible for and must rectify any issues that occurs to the premises and contents as a result of negligence of sub-contractors and / or specialists, to the satisfaction of the CA at the contractor’s own expense.
19 | Contractors compound area is to be created and the exact location will be agreed with the CA and client. The area is to be fenced off using a minimum of 2m high ’HERAS’ panels, secured as necessary around the work area.
20 | All items are to be included but are not exclusive and the contractor is to allow for any other items he feels are necessary according to the drawings and specifications attached.
21 | We envisage the normal working hours to be 8:00am to 5pm Monday to Friday. Careful planning will be required to ensure minimal disruption to the adjoining neighbours.
22 | The contractor is to ensure that a working foreman is appointed for the entire duration of the contract works on site.
THE WORKS
1 Strickland Place
EXTERNAL
GENERAL
23 | The contractor is to remove all asbestos present which is stated in the Asbestos Survey for each building. This is to be completed by a asbestos licenced contractor.
24 | Remove all chattels present through the property entirely.
25 | Test all rainwater goods for leaks and fails in joints. Report faults to CA.
26 | Where windows to the house are single glazed, supply and fit new, timber softwood double glazed sliding sash window units in accordance with BS 644:2009. They are to be sprayed finish to match existing and glazed with 24mm sealed units with a stuck on glazing bars. They are to be half split sash windows with the lower half sash opening. The top sash is to be fixed. U value 1.6. Trickle vents should be installed. To the GF toilet, the glazing is to be obscured.
27 | Provide a cost here _________/lm to rake out the mortar around windows and replace with sealant. Apply this rate to 15lm. Once scaffolding is erected, the CA is to inspect and delegate where the 15lm is used.
28 | Strip out all electrical services back to the head.
29 | Strip out all gas and heating system. This is to include the boiler, associated pipework, pumps, radiators, cylinders etc. This is to be capped off at the meter. The CA and client are jointly arranging the meter to be removed.
30 | Decorate all joinery including windows, fascia's, soffits etc in Dulux Trade Pure brilliant white Gloss Wood paint unless specified differently elsewhere. Prior to this, all surfaces are to be rubbed down. The surfaces are to have a primer coat and then 2no top coats applied. DO NOT paint windows shut.
31 | Redecorate all rainwater goods to match existing.
32 | Redecorate all previously decorated render, including all plinths.
33 | Upon completion of the works, clean all glazing internally and externally.
34 | Please note that before any works commence on repairs to the fascia's, the CA needs to be aware of the erection of scaffolding so an inspection can be made as to the condition of the fascia's and soffits. | Note
35 | Please note the client will be arranging and be paying for a new electricity and water supply to be brought in for the first floor flat. | Note
36 | Please note the client will be arranging and be paying for the existing electrical supply to the ground floor flat to be upgraded to a 100amp. | Note
SERVICES
37 | Carry out a CCTV survey of the drains. Include for No 2 Strickland Place as well in this item. Provide the report to the CA.
38 | The contractor is to design all aspects of the mechanical and electrical components of the project. The designs to be submitted to the CA for review.
39 | The contractor is to take on the energy efficiency responsibility for material change of use requirements relating to SAP design, to demonstrate that the design complies with L1b SAP standards for controlled fittings, services and building materials; and to include the as-built stage, which includes issuing final documentation plus an Energy Performance Certificate (EPC), for No. 1 Strickland Place only.
40 | The contractor is to design the heating system across the whole premises. This is to include wiring, location of radiators, how many radiators etc. However, the contractor is to use electric Myson Finesse radiators. The radiator comes in several sizes, this is up to the contractor as to which size is necessary in each room.
41 | The contractor is to design, install and commission electric hot water provision to service all hot water provision to service all hot water requirements. Allow for Joule or equivalent approved manufacturer, and for all associated wiring, pipework, controls and valves.
42 | According to the drawing 1 Strickland Place - Proposed Electric Plan, the contractor is to design the electric system for the flats. They are to design where to chase and run all cables. The contractor is to use MK Logic Plus 13A 2-Gang DP Switched Plug Socket White 5 Pack across all sockets. However, allow for 25 to be MK Logic Plus 13A 2-Gang DP Switched Socket + 2A 2-Outlet Type A USB Charger White. Allow to supply and install 3no MK Logic Plus 2-Gang Duel Voltage Shaver Socket 115 / 230V White. The location of these is to be agreed with the CA. Allow to supply and install 3no LAP Elva 300MM LED Bathroom Mirror Light Chrome 4.7W 400LM. Location to be agreed with CA. The light switches are to be MK Logic Plus 10AX 1-Gang 2-Way Light Switch White and to be located where stated on drawing 1 Strickland Place - Proposed Electric Plan . Any other switches required (appliance switches, isolator switches etc) are to be from the MK Logic Plus range.
43 | The contractor is to design an Emergency Lighting System for each of the flats using JCC Emergency Downlights 3.5W IP20 6000K 110lm White Non-maintained or equivalent approved.. Please note this is to have a domestic look about it. The contractor is to provide a design, installation and commissioning certificate.
44 | The contractor is to design a Fire detection and alarm system which complies with Building Regulations Category L2 and a BAFE Fire Detection Certificate.
45 | The contractor is to provide an Electrical Installation Condition Report including the complete design, installation and a commissioning of the installation.
46 | The contractor is to provide a UKAS Chlorination Certificate for the building.
Main House
Roof
47 | Clean the chimneys to remove all algae and moss deposits.
48 | Refit 4no bricks to the base of the chimneys using lime mortar.
49 | Clear any vegetation on the roof.
50 | Supply and install new code 4 lead flashing around the base of the base of the far right hand side chimney on the ridge.
51 | Deep clean all leadwork on the roof, including around dormers.
52 | Prime and decorate the render on the sides of the dormer windows to match existing using Dulux Weathershield Masonry Matt Paint Apply 2no coats. The colour is to match existing.
53 | Replace 4no dormer windows with new, timber softwood double glazed units in accordance with BS 644:2009. They are to be sprayed finish to match existing and glazed with 24mm sealed units with a stuck on glazing bar with one opening and one fixed casement. U value 1.6. The ironmongery is to match existing and be black, including pigtail espagnolette security handles, traditional design casement stay and trickle vents.
54 | This involves removing the old units. When doing this, the frame is also to be removed. Include a Provisional Sum of £1,000 for making good and reinstating the render, lead and plaster. | 1000
55 | Allow a provisional sum of £500 for repairs to chimneys once an inspection is made by the CA. | 500
Front Elevation
56 | Provide a price here to cut out 20no weathered bricks and replace with Imperial Soft Red Handmade Facing Bricks to the direction of the CA. A lime mortar is to be used when replacing the bricks.
57 | Remove all ivy growth from the front elevation and any other vegetation growth.
58 | To the right hand side of the fascia, there is a decayed section. Allow to cut a 1000mm section out and replace to match existing.
59 | Rake out current mortar and repoint 10 lm of mortar joints in a lime mortar. Where the 10 lm is used is up to the direction of the CA.
60 | Rake out current mortar and repoint all mortar joints below the height of the GF window cill in a lime mortar across the whole elevation. Where the 10 lm is used is up to the direction of the CA.
61 | Replace 2no plain tiles to the first floor bay windows where these are missing.
62 | Refit 8no plain tiles which have slipped on the first floor bay windows.
63 | To the GF bay windows, fit replacement mock window bars which have come away. Allow for 10no.
64 | Check the leadwork on the two GF bay windows for any leaks.
65 | Provide a Provisional Sum of £200 for lead repairs. | 200
66 | Locally repair areas of wet rot to window frames by cutting out and replace with matching timber. Allow for 3no areas at 250mm long each.
67 | 1no section of a window ledge has come away. This is to the right hand side of the first floor bay window. Allow to cut out remaining wood and replace with existing. Decoration elsewhere.
68 | There is a crack under the second floor window to the left hand side and right hand side of the first floor bay window. This is to be filled with mortar.
Side (East) Elevation
69 | Allow here to rake out and repoint 5 lm with lime mortar.
70 | Repoint the five steps of flashing above the two storey extension where these enter the wall. This should be repointed in a lime mortar.
71 | Repoint the crack to the left of the first floor window. Allow for 1500mm of repointing. This is to be done in lime mortar.
72 | There are 2no broken tiles to the roof over the stairwell. These are to be replaced to match existing.
73 | The canopy over the front door to the First Floor Flat is to be rubbed down, primed and redecorated. To match existing. The leadwork is also to be cleaned.
74 | The light underneath the canopy over the front door is faulty and old. Allow to replace the light with a new JCC RadiaLED Utility Mains IP65 Ø205mm Bulkhead 12W 4000K 700lm LED MW On/Off EM DALI / 1-10V. This is to be on a PIR.
75 | Cut out and replace 10no spalled bricks. The new bricks are to be Imperial Soft Red Handmade Facing Bricks and a lime mortar is to be used.
76 | Upgrade the current glazing in the door to have double glazing which is argon filled. The cavity is to be as wide as the current glazing openings will allow.
77 | Redecorate the front door to match existing.
78 | Refurbish the bell that is currently on the door by rubbing it down, priming it and redecorating to match existing.
79 | The door is to open the opposite way, as stated on drawing '1 Strickland Place - Proposed Floor Plans'.
Rear Elevation
80 | Rake out current mortar and repoint the whole of the elevation. This is to be done in a lime mortar.
81 | The contractor is to design a canopy which is to go over the front door for the GF flat. The canopy needs to have treated wood for the brackets and the roof covering needs to be plain tiles with lead flashings. The canopy needs to extend 150mm either side of the door to create a small overhang.
82 | The contractor is to form a new opening where the current window is serving the current dining room. This is to involve removing and carting away the current window and dismantling the brickwork below to the ground floor level. Close the reveals to suit the new door. Supply and fit a new front door and frame to the GF flat such as Howdens Richmond Frosted Glazed External Door or equivalent approved. This is to fit the current opening and be 44mm thick. The door is to match the current style (two glazed panels), hardwood, decorated as existing, toughened double glazed frosted glass, with a U Value of 2.9W/m2K. the opening is to be the same as drawing 1 Strickland Place - Proposed Floor Plans states. The frame should match the colour of the door on the external and internal sides. To the bottom of the door, a Hardwood Natural Weather bar should be fitted. This is to fit the full width of the door. The relevant ironmongery to be installed isa lock. This is to be Garda Polished Chrome Lever on Backplate Lock Door Handle Pack or equivalent approved. All fixings are to be included in cost.
83 | Remove and cart away the current back door.
84 | Supply and fit a new front door and frame to the GF flat such as Howdens Richmond Frosted Glazed External Door or equivalent approved. This is to fit the current opening and be 44mm thick. The door is to match the current style (two glazed panels), hardwood, decorated as existing, toughened double glazed frosted glass, with a U Value of 2.9W/m2K. the opening is to be the same as drawing 1 Strickland Place - Proposed Floor Plans states. The frame should match the colour of the door on the external and internal sides. To the bottom of the door, a Hardwood Natural Weather bar should be fitted. This is to fit the full width of the door. The relevant ironmongery to be installed isa lock. This is to be Garda Polished Chrome Lever on Backplate Lock Door Handle Pack or equivalent approved. All fixings are to be included in cost.
85 | There is significant moss on the rear wall. Allow to wash clean so no moss is present.
86 | There is wet rot present to the second window. Allow to cut out area of wet rot and replace with matching timber. Decoration included elsewhere.
87 | There are 7no spalled bricks. Allow to cut out and replace with Imperial Soft Red Handmade Facing Brick and lime mortar.
88 | Remove the redundant external wall light and cart away.
89 | Supply and fit a new external wall light. This is to be a Luceco 30W LED Floodlight PIR Black 2400LM IP65. Location is to be agreed with CA.
90 | Modify the downpipe to discharge surface water into the drainage. This is to the far left-hand side of the elevation.
Garage
91 | Remove all ivy growth from the garage walls and dispose of, including internally.
92 | Remove all the chattels present in the garage and cart away.
93 | Remove and then replace all ridge tiles to match existing.
94 | Refit 1no slipped tile on the front slope.
95 | Strip and cart away current rainwater goods, fascia's, bargeboards and verge capping.
96 | Supply and fit new timber bargeboard/verge detail and fascia to where these have been removed and to match existing. They should be painted in Dulux Trade High Gloss in black.
97 | Supply and fit new uPVC rainwater goods. These are to replace the existing and the downpipes should discharge into the current gulley. Allow for 2no downpipes, these are to be 68mm in diameter, uPVC, black and be fitted with appropriate clips. The gutters are to be 112mm wide, black uPVC and fitted with all relevant brackets.
98 | To the bay at the front of the garage, strip off the monopitched tiled roof, setting aside the tiles that are reusable and relay all the tiles. Preserve as many tiles from stripping them off as possible.
99 | To the window frame in the bay, cost to splice the rotten timber, replace with new timber to match existing and redecorate. Allow for a 2no 200mm sections.
100 | Replace 1no pane of glazing to the window in the bay.
101 | Service the up and over door. Any further works are to be treated as a variation.
102 | Block up the current personnel door with Imperial Soft Red Handmade Facing Brick in a Flemish bond pattern to match existing.
103 | Remove the larch cladding to the gable ends and replace with a new Marley Fibre Cement Weatherboard with timber effect grain finish or equivalent approved in black.
104 | Replace the timber architrave around the up and over garage door to match existing. This should be decorated to also match existing.
105 | To all elevations, clean to remove algae and moss deposits.
106 | Allow to decorate the up and over door in a matt black metallic paint.
107 | Clean the glazing to the bay window.
108 | Extend the concrete ramp serving the up and over garage door so that it extends to the roadway.
Back Garden
109 | Remove the current bin store complete and cart away.
110 | Dismantle and cart away the greenhouse.
111 | Remove all vegetation from the garden, including all trees and shrubs, and cart away. No roots should be left. Leave any trees with trunks greater than 75mm diameter.
112 | Remove the fence to the rear of the property going up to the garage and to the right hand side of the garden.
113 | Supply and install new fencing which is to be in accordance with drawing Site Plan - Fence Plan . The fencing is to be a Close Board Fence Panel Dip Treated 6ft x 5ft. The fence posts are to be 2440mm x 109mm x 94mm Supreme Concrete Intermediate Slotted Fence Posts. The gravel boards are to be Concrete Recessed Gravel Boards 50mm x 150mm x 1830mm. The contractor is also to supply and install a gate which is to be situated just in front of the garage, please refer to drawing Site Plan - Fence Plan for the position of this.
114 | Allow to supply and fit 2no Treated Garden Closeboard Heavy Duty Timber Gate 1820mm x 910mm with all relevant ironmongery. These are to be fit where drawing Site Plan - Fence Plan proposes.
115 | The installation of a gravel parking bay next to the existing garage is to be costed. This area should be 4325x5540mm. Allow here to prepare the base, supply and lay the gravel which should be Golden Gravel 20mm and rake to prepare an even finish. Please refer to drawing Site Plan as Proposed for location of the parking bay.
116 | To the proposed rear patio, allow to excavate and break up the concrete present. This could then be crushed and reused for either the base of the parking bays or the new patio.
117 | Supply and install new patio slabs. These are to be Marshalls Utility Pendle Paving Slab Natural 450mm X 450mm X 32mm or equivalent approved. The patio area should be 3500mm (to the nearest whole slab) deep from the house and 6500mm (to the nearest slab) wide from the fence. Also, there is to be a single slab width running from the patio area to the external stores. The slabs are to be laid to the manufacturing guides including a compacted base with a geotextile membrane. Refer to drawing Site Plan as Proposed.
118 | To the rest of the garden, lay new Rolawn Medallion Finest Multi Purpose Grass Turf Roll. This includes providing a suitable topsoil for the turf to be laid onto, levelling out, laying the turf and rolling flat.
Front Garden
119 | Remove all vegetation from the front garden including all shrubbery, plants and trees with trunks less than 75mm in diameter. No roots should be left.
120 | Allow for the paving at the front of the property to be dug up, cleaned and set aside.
121 | Remove and replace the timber slatted fence to the front of the front garden with Pressure Treated Ultima Pale Picket Fence Panel 6ft x 3ft.
122 | Remove and replace the timber slatted fence to the right-hand side of the front garden. Replace the fence with Pressure Treated Ultima Pale Picket Fence Panel 6ft x 3ft.
123 | Supply and install 2no Heavy Duty Pale Gate 900mm x 1m. The location of these are to be taken from drawing Site Plan - Fence Plan.
124 | Supply and install a new Pressure Treated Ultima Pale Picket Fence Panels 900mm tall to separate the entrance for the 1st floor flat and the front garden to the GF flat. This is to run for the full width of the gap. For exact location, please see drawing Site Plan - Fence Plan.
125 | Lay the same patio as specified elsewhere in the same accordance with the manufacturing guide to the area outside the new entrance to the 1st Floor flat. This is to take up the whole area. See drawing Site Plan - Fence Plan.
126 | Around the patio, allow to lay edging. This edging is to be the paving that was taken up, cleaned and set aside. The edging is to go around the full perimeters of the new patio.
127 | To the front of the GF flat, lay new patio as specified else where and in accordance with the manufacturing guides. This patio is to extend from the outer side of the left-hand bay window and run for the width until the outer side of the right-hand bay window. The patio is to come out as far as possible to leave a 1000mm gap to the front of it. See drawing Site Plan as Proposed.
128 | Around the patio at the front of the GF flat, allow to lay edging. This edging is to be the paving that was taken up, cleaned and set aside. The edging is to go around the full perimeter of the new patio. If any extra edging is needed, we will treat this as a variation.
129 | To the left-hand side of the patio (next to the boundary between No 1 and 2), lay Golden Gravel 20mm and rake to prepare an even finish. This is to be laid to finish in line with the patio.
130 | To the front and right-hand side of the new patio, prepare and lay new topsoil, lay new Rolawn Medallion Finest Multi Purpose Grass Turf Roll and roll to leave a flat finish.
Outbuilding
131 | Ease and adjust the door which cannot be opened.
132 | 1no window pane is cracked. Allow to replace this for a like-for-like replacement.
133 | Remove the vegetation from the roof of the outbuilding and any ivy present.
134 | Provide a price here to cut out 8no weathered bricks and replace with Imperial Soft Red Handmade Facing Bricks.
135 | Repoint the section of wall that the window is on. Repointing will go up to the downpipe as past this, the condition is satisfactory. A lime mortar is to be used when repointing this section of wall.
136 | Once all works are done on this building, allow to give all walls a clean using a pressure washer on a soft setting to leave the walls clean.
137 | To the single storey store to No 1 and the single storey kitchen roof to No 2, allow to strip complete, putting to one side the tiles as these will be reused. However, the lead is to be retained and reused.
138 | Allow to lay new breathable roofing membrane and treated roofing battens, in accordance with manufactures recommendations.
139 | Allow to relay the tiles previously removed. Also, to relay the ridge tiles and form the verge detail. As well as this, reinstate the lead appropriately.
140 | Remove flat roof store. This protrudes slightly further than the mono pitched roof store. The size of this is 950mm x 1215mm.
141 | Modify the gutter to stop at the downpipe after removing the flat roof store.
142 | Replace architrave around the store door as this is decayed.
143 | Supply and install a lock on to the store door. This lock is to be a ERA Euro Cylinder Lock Satin Nickel 35/35 or equivalent approved.
144 | In the store room, allow to replace 20no weathered bricks. These are to be cut out and replaced with Imperial Soft Red Handmade Facing Brick.
145 | Fill in crack in the store room with a lime mortar.
INTERNAL
GENERAL
146 | Ease and adjust all painted shut windows across the whole house.
147 | Decorate all surfaces except joinery including walls, soffits and pipework etc where necessary. Colour to be Dulux Trade White Emulsion or other TBA. All surfaces are to be primed and then have 2no coats applied.
148 | Decorate all joinery including windows, doors, architraves, skirtings, coving, window ledges, panelling etc in Dulux Trade Pure brilliant white Gloss Wood paint. Prior to this, all surfaces are to be rubbed down. The surfaces are to have a primer coat and then 2no top coats applied. Where secondary glazing is being installed, the windows are to be decorated prior to this. DO NOT paint windows shut.
149 | Remove and replace all window panes in double glazed units prior to redecoration and towards the start of the project, so this does not affect any timescales. This is due to most double glazed windows being blown.
150 | The contractor is to design the lighting system. Drawing '1 Strickland Place - Proposed Minimum Lux Level' states the lux levels in each room, therefore, the design needs to achieve this. The lights being used are to be Sylvania Obico Swivel & Tilt Fire Rated Led Downlight With CCT Technology White 8.5w 740lm or equivalent approved.
151 | The contractor is to organise and source an EPC assessor to give an estimate to what the EPC will be at the end of the project.
ACOUSTIC DESIGN
152 | Note that the drawing '1 Strickland Place - Acoustic Elements' shows where different elements of the acoustic design are being completed. | Note
153 | Where the AJA Report states there are 2 no layers of Gyproc Soundbloc required, allow for 1 x 12.5mm Gyproc Soundbloc and 1 x 15mm Fireline board across all necessary areas. This is due to the need of maintaining the fire protection.
154 | Allow to upgrade existing ground floor ceilings by underlining with 1 no layer of 12.5mm Gyproc Soundbloc board. This is to be done to the area shaded grey on drawing '1 Strickland Place - Acoustic Elements'.
155 | SEPERATING WALL As set out in Section 3.1 and 5.2 of the AJA Report, it includes cutting the plaster ceiling for the installation of the headplate. Also, the new separating wall will be constructed on the edge of the existing stairs shown. Allow to remove existing balustrades, handrails etc.
156 | CEILINGS TO WC, LOBBY AND DINING AREA Install the ceiling works to part of the ground floor (WC, lobby and dining room) as per the AJA Report, Section 4.1.1 and Figure 6.
157 | ALL OTHER AREAS TO GROUND FLOOR Install new independent ceiling to all other parts of the ground floor as per the AJA Report, Section 4.1.2 and Figure 7.
158 | BASEMENT CEILING Basement area to be acoustically incorporated into the stairs by upgrading ceiling as Figure 4 of the AJA Report states. It is to be abutted to the new separating wall included elsewhere.
159 | Include cost here for possible upgrade of ground floor partitions in accordance with 3.2 and Figure 3 & 4 of the AJA Report. Prior to construction AJA will undertake tests once the ceiling and separating wall are in place, to establish if this is required.
160 | The whole of the first floor is to be over boarded with hardboard to close all gaps.
161 | To the first floor, on top of the hardboard, allow to supply and fit Regupol Sonus Core 5 across the whole floor.
162 | The contractor is also to conform with the design in the AJA Report for services, risers etc.
GROUND FLOOR FLAT
Basement
163 | Strip the basement of all non-structural items. This includes all chattels, shelving etc.
164 | Deep clean the basement to remove all mould present.
165 | Provide 2no air bricks on the external wall. These are to be in a location agreed with the CA. The airbricks are to be Hepworth Square Hole Airbrick 215 x 215mm Red.
166 | Supply and install Gyproc FireLine 12.5mm plasterboard to the underside of the stairs to provide 30 minutes of fire protection.
Ground Floor Flat Lobby / Entrance
167 | Remove the curtain rail above the door and cart away.
168 | Remove all damp paint and plaster to expose masonry. Allow for 2m2.
169 | Replaster this wall in 6mm HardieBacker fibre cement board. This is also to be skimmed.
170 | Remove the coat hook, rail and pegs. Set aside rail.
171 | Allow to replace the doormat. This is to match existing.
172 | Remove and cart away all floor coverings.
173 | Supply and fit LVT. This is to be Classic Oak Herringbone Luxury Rigid Core Click Vinyl Flooring or equivalent approved.
174 | Refit door handle so it does not move.
Lobby Toilet
175 | Remove chattels present and cart away.
176 | Remove wall mounted unit and cart away. Make good.
177 | Deep clean floor tiles and regrout.
178 | Remove and cart away the toilet seat. Replace toilet seat with a TP New Rhea Soft Close Toilet Seat or equivalent approved.
179 | Rake out and regrout the splashback tiles behind the sink. The grout should be white.
180 | Supply and install a mirror above the wash handbasin. This is to be a Light Tech Mirrors Hudson Rectangular Illuminated LED Mirror With 1100lm LED Light 500 X 700mm or equivalent approved.
181 | Remove coat pegs and the towel rail. Cart away.
182 | Install new towel rail. This is to be a Bristan RD RAIL C Round Towel Rail Brass Chrome Plated or equivalent approved.
183 | Include a provisional sum of £200 to supply and fit a wall mounted storage unit. CA to agree which unit. | 200
184 | Remove current light fitting. Replacement light is to be included in the contractors design portion.
185 | Remove and cart away the current sink.
186 | Supply and fit a new sink. This is to be an Ideal Standard i.life B 50cm/55cm/60cm Washbasin or equivalent approved.
187 | Replace the taps with Bristan Opus Basin Mixer with Clicker Waste - Chrome or equivalent approved.
188 | Remove the current light switch. The installation of a new light switch is covered in the contractors design portion.
Ground Floor Flat Hallway
189 | Supply and fit LVT. This is to be Classic Oak Herringbone Luxury Rigid Core Click Vinyl Flooring or equivalent approved.
190 | Remove current light fitting. Replacement light is to be included in the contractors design portion.
191 | Remove the curtain rail present and cart away.
Kitchen/diner
192 | Strip kitchen out, including all units, wall mounted units, light fittings, cupboards, curtains, curtain rails and tiles.
193 | Allow a provisional sum of £8,000 to supply the kitchen. This is for the fitted base units and wall units, worktops, sinks, taps and appliances. The contractor is to get Howdens to come and design a kitchen suitable and for the approval by the CA. | 8000
194 | The contractor is to provide a cost here to install a kitchen for the appropriate size.
195 | Supply and install new 4Trade White Tile 150 x 150mm tiles which are to be a splashback. These should run for the length of the units and to a height of 400mm.
196 | Remove the current floor covering.
197 | Supply and fit LVT. This is to be Quick Step Balance LVT Victorian Oak Natural Flooring or equivalent approved.
198 | Remove all damp paint and plaster to expose masonry on the elevation where the new opening is being made. Supply and fit a Newton Membrane to this elevation. This is to then have plasterboard applied to the top of it and skimmed.
199 | Remove arch over opening from the diner to the kitchen. This is to be squared off.
Ground Floor Lounge
200 | Remove and cart away all blinds, curtains and curtain rails.
201 | Strip out all cupboards and shelves. Cart away.
202 | Strip out flooring and cart away.
203 | Remove the current light fitting and cart away.
204 | Supply and install new carpet. This is to be Twickenham Twist Carpet or equivalent approved. Colour to be linen.
205 | The downpipe in the bay window flat roof is to be checked internally due to damp on the inside face of the soffit of the bay window. Therefore, remove the soffit to this bay window.
206 | Replaster this soffit with 37.5mm insulating plasterboard. This is to be Gyproc Thermaline PIR insulated plasterboard or equivalent approved.
Ground floor bedroom
207 | Hack off friable plaster. Allow for 1m2 .
208 | Strip out floor coverings, curtains, blinds, curtain rail, light fittings, hessian mat and fire door.
209 | Supply and install new carpet, even where the hessian carpet previously was. This is to be Twickenham Twist Carpet or equivalent approved. Colour to be linen.
210 | Remove the soffit to the bay window to show extent of the damp.
211 | Replaster this soffit with 37.5mm insulating plasterboard. This is to be Gyproc Thermaline PIR insulated plasterboard or equivalent approved.
212 | Supply and fit a new door and frame to where the fire door was removed such as Howdens Richmond Frosted Glazed External Door or equivalent approved. This is to fit the current opening and be 44mm thick. The door is to have two glazed panels, hardwood, decorated as existing, toughened double glazed clear glass, with a U Value of 2.9W/m2K. The opening is to be the same as drawing 1 Strickland Place - Proposed Floor Plans states. The frame should match the colour of the door on the external and internal sides. To the bottom of the door, a Hardwood Natural Weather bar should be fitted. This is to fit the full width of the door. The relevant ironmongery to be installed is a lock. This is to be Garda Polished Chrome Lever on Backplate Lock Door Handle Pack or equivalent approved. All fixings are to be included in cost.
Bathroom
213 | Strip en suite out complete, except cupboard holding the boiler and the sink.
214 | Include a provisional sum of £4,000 to supply a new bathroom. | 4000
215 | Provide a cost to fit the new bathroom.
216 | Supply and fit LVT. This is to be Quick Step Balance LVT Victorian Oak Natural Flooring or equivalent approved. This is to run into the boiler cupboard.
217 | Supply and install new extractor fan. This is to be situated above the shower and to be an in line vent and to be a Silent Fan VASF100HTO (Fixed Speed, Intermittent, Humidity Timer) open grille or equivalent approved. This forms part of the electrical contractors design.
218 | Allow to deep clean the sink and replace the taps with Bristan Opus Basin Mixer with Clicker Waste - Chrome or equivalent approved.
219 | Decorate all walls, skirtings, window ledge and doors as well as the boiler cupboard door.
FIRST FLOOR FLAT
Generally
220 | Upgrade all current fire doors so they are in accordance with BS 8214. This will include all new ironmongery including hinges, door handles and the closers.
221 | Ease and adjust all fire doors so that they will close fully shut.
First Floor Flat Entrance / Stairwell
222 | The contractor is to build the lobby in the position of drawing '1 Strickland Place - Proposed Floor Plans' and as stated by the acoustics design and drawing. This separating wall is to be 60 minute fire rated between flats.
223 | Upgrade the current glazing in the door to have double glazing which is argon filled. The cavity is to be as wide as the current glazing openings will allow.
224 | Redecorate the front door to match existing.
225 | Refurbish the bell that is currently on the door by rubbing it down, priming it and redecorating to match existing.
226 | The door is to open the opposite way, as stated on drawing '1 Strickland Place - Proposed Floor Plans'.
227 | Remove blinds and the curtain rail.
228 | Remove and cart away all shelving.
229 | Remove carpet and cart away.
230 | Supply and fit LVT. This is to be Quick Step Balance LVT Victorian Oak Natural Flooring or equivalent approved. This is to also go from the front door, up the stairs all the way to the first opening on the first floor landing.
Landing / Stairwell to Flat 1B
231 | Remove all floor coverings and cart away.
232 | Relay carpet past the first opening at the top of the stairs. This is to be Twickenham Twist Carpet or equivalent approved. Colour to be linen.
233 | Supply and fit LVT to the cupboard under the stairs. This is to be Quick Step Balance LVT Victorian Oak Natural Flooring or equivalent approved.
234 | Remove curtains and curtain rails.
235 | Remove light fittings. Replacement is included in the contractors design portion.
Toilet Off Landing
236 | Remove and cart away all current flooring.
237 | Supply and fit new LVT to the toilet. This is to be Classic Oak Herringbone Luxury Rigid Core Click Vinyl Flooring or equivalent approved.
238 | Remove the sink and wall mounted unit and curtain rail.
239 | Allow to supply and fit secondary glazing.
240 | Supply and fit a new sink. This is to be an Ideal Standard i.life B 50cm/55cm/60cm Washbasin or equivalent approved.
241 | Include a provisional sum of £200 to supply and fit a wall mounted storage unit. CA to agree which unit. | 200
242 | Allow to deep clean the toilet.
243 | Allow to supply and fit new duo flush toilet handle. This is to be Chatsworth Luxury White Ceramic Cistern Lever Handle or equivalent approved.
244 | Remove and cart away the toilet seat. Replace toilet seat with a TP New Rhea Soft Close Toilet Seat or equivalent approved.
245 | Remove light fittings. Replacement is included in the contractors design portion.
New kitchen
246 | Allow a provisional sum of £8,000 for the supply of a kitchen. | 8000
247 | The contractor is to provide a cost here to install the kitchen.
248 | Strip out bathroom complete.
249 | Strip off all wallpaper.
250 | Supply and install new 4Trade White Tile 150 x 150mm tiles which are to be a splashback. These should run for the length of the units and to a height of 400mm.
251 | Supply and fit new LVT to the kitchen. This is to be Classic Oak Herringbone Luxury Rigid Core Click Vinyl Flooring or equivalent approved.
252 | Remove light fittings. Replacement is included in the contractors design portion.
Dining room
253 | Strip the floor covering and cart away.
254 | Supply and fit new LVT. This is to be Classic Oak Herringbone Luxury Rigid Core Click Vinyl Flooring or equivalent approved.
255 | Remove light fittings. Replacement is included in the contractors design portion.
256 | Remove all wallpaper, curtain rail and curtain.
257 | Make good any penetrations from screwed shut windows.
Second hallway
258 | Remove all floor coverings and cart away.
259 | Remove light fittings. Replacement is included in the contractors design portion.
260 | Supply and install new carpet, even where the hessian carpet previously was. This is to be Twickenham Twist Carpet or equivalent approved. Colour to be linen.
261 | Install a handle on each door to the cupboard.
262 | Decorate shelves the same as the rest of the walls.
New living room
263 | Strip all floor coverings and cart away.
264 | Supply and install new carpet, even where the hessian carpet previously was. This is to be Twickenham Twist Carpet or equivalent approved. Colour to be linen.
265 | Make good penetrations from screwed shut windows.
266 | Remove curtains and curtain rails. Make good.
267 | Remove light fittings. Replacement is included in the contractors design portion.
Bathroom
268 | Strip and cart away towel rail/radiator, wall mounted unit, shower unit, toilet seat, shelf, pegs and floor blind.
269 | Install soft close toilet seat. This is to fit the current toilet and is to be white.
270 | Deep clean all retained sanitaryware.
271 | Install a new towel rail unit. This is to be a Myson Electric Avonmore towel rail unit or equivalent approved. The location is to be as existing.
272 | Install a new shower unit. This is to be a Trafalgar Traditional Rigid Riser with 190mm Shower Head, Hand shower and Diverter or equivalent approved. The shower unit is to be situated where the current one is and in the retained bath.
273 | Install a new shower screen. This is to be a Cruze 900 x 1400 Chrome 6mm Bi-Fold Hinged Bath Screen or equivalent approved.
274 | Supply and install new 4Trade White Tile 150 x 150mm tiles which are to be a splashback. These should run for the length of the bath and run to the ceiling. Also, behind the sink to a height of 300mm.
275 | Allow to supply and fit new duo flush toilet handle. This is to be Chatsworth Luxury White Ceramic Cistern Lever Handle or equivalent approved.
276 | Supply and install new extractor fan. This is to be situated above the shower and to be an in line vent and to be a Silent Fan VASF100HTO (Fixed Speed, Intermittent, Humidity Timer) open grille or equivalent approved. This is to form part of the electrical contractors design element.
277 | Supply and fit new LVT. This is to be Classic Oak Herringbone Luxury Rigid Core Click Vinyl Flooring or equivalent approved.
278 | Include a provisional sum of £200 to supply and fit a wall mounted storage unit. CA to agree which unit. | 200
279 | Remove light fittings. Replacement is included in the contractors design portion.
280 | Allow to over plasterboard the ceiling and plaster in a gypsum plaster.
Stairs to second floor
281 | Decorate balustrades and handrails.
282 | Remove all carpet.
283 | Supply and install new carpet. This is to be Twickenham Twist Carpet or equivalent approved. Colour to be Linen.
284 | Redecorate all walls and soffit.
285 | Remove light fittings. Replacement is included in the contractors design portion.
SECOND FLOOR
General
286 | Supply and fit new Celotex 52.5mm insulated plasterboard or equivalent approved to the internal faces of all external walls. The insulation is to be PIR insulation.
287 | Supply and fit new Celotex 12.5mm insulated plasterboard or equivalent approved to the internal faces of the soffit in the dormer window. The insulation is to be PIR insulation.
288 | Hack off the plaster to the cheeks of the dormer windows and the angled soffit. There is to be Celotex 75mm rigid insulation or equivalent approved laid. As the depth behind these sections are unknow, price for 75mm rigid insulation.
289 | Plasterboard and skim over the hacked off areas.
Second floor landing
290 | Remove all floor coverings and cart away.
291 | Supply and install new carpet. This is to be Twickenham Twist Carpet or equivalent approved. Colour to be Linen.
292 | Remove all wallpaper and cart away.
293 | Decorate all walls, soffit and skirtings.
294 | Remove light fittings. Replacement is included in the contractors design portion.
Bedroom 1
295 | Hack off any friable plaster. Allow for 3m2.
296 | Remove all damp wallpaper and plaster to expose masonry on the chimney breast.
297 | Where the brickwork is exposed, replaster board it in 6mm Hardiebacker backing board or equivalent approved around all three sides of the chimney breast. This is also to be skimmed.
298 | Supply and install a Rytons Building Products Ltd '9 x 6' Louvre Ventilator with Flyscreen - White to the chimney breast, allowing it to dry out. This is to be located in a suitable location agreed with the CA.
299 | Strip all wallpaper and cart away. This is to show the extent of damp.
300 | Strip all floor coverings and cart away.
301 | Remove blinds, curtains and shelving.
302 | Supply and install new carpet, even where the hessian carpet previously was. This is to be Twickenham Twist Carpet or equivalent approved. Colour Linen.
303 | Install rigid insulation to the external wall and soffit of the first floor bay window through the hatch in the wall. This is to be 100mm thick.
304 | Remove light fittings. Replacement is included in the contractors design portion.
305 | Redecorate all walls, soffits, cupboard doors and inside cupboard.
Bedroom 2
306 | Remove all floor coverings and cart away.
307 | Supply and install new carpet, even where the hessian carpet previously was. This is to be Twickenham Twist Carpet or equivalent approved. Colour to be Linen.
308 | Strip all wallpaper and cart away.
309 | Strip electric heater and cart away.
310 | Remove light fittings. Replacement is included in the contractors design portion.
311 | Hack off any friable plaster. Allow for 3m2.
312 | Replaster all areas where friable plaster has been hacked off.
313 | Lay rigid insulation to the external wall and soffit of the first floor bay window through the hatch in the wall. This is to be 100mm thick.
Second floor bathroom
314 | Strip all floor coverings.
315 | Replace window with a double glazed unit. This is to fit in the same opening. The window is to be a timber double glazed unit and painted white. It must have a minimum U-Value of 1.6 W/m2K.
316 | Allow a provisional sum of £4,000 for the supply of a new bathroom. | 4000
317 | The contractor is to provide a cost here to fit the new bathroom.
318 | Supply and install new extractor fan. This is to be situated above the shower and to be an in line vent and to be a Silent Fan VASF100HTO (Fixed Speed, Intermittent, Humidity Timer) open grille or equivalent approved.
319 | Supply and fit new LVT. This is to be Classic Oak Herringbone Luxury Rigid Core Click Vinyl Flooring or equivalent approved.
320 | Around the side and front of the bath, supply and fit Altro Whiterock Gloss White Shower Wall Panels. These are to go from the height of the bath to the soffit.
321 | Remove light fittings. Replacement is included in the contractors design portion.
322 | Remove all damp wallpaper and plaster to expose masonry on the chimney breast.
323 | Where the brickwork is exposed, replaster board it in 6mm Hardiebacker backing board or equivalent approved around all three sides of the chimney breast. This is also to be skimmed.
324 | Supply and install a Rytons Building Products Ltd '9 x 6' Louvre Ventilator with Flyscreen - White to the chimney breast, allowing it to dry out. This is to be located in a suitable location agreed with the CA.
325 | Lay rigid insulation to the external wall and soffit of the first floor bay window through the hatch in the wall. This is to be 100mm thick.
Second floor cupboard/tank room
326 | Remove and cart away water tank.
327 | Remove all friable plaster. Allow for 2m2.
328 | Replaster all areas where friable plaster has been hacked off.
329 | Supply and fit new LVT. This is to be Classic Oak Herringbone Luxury Rigid Core Click Vinyl Flooring or equivalent approved.
Bedroom 3
330 | Strip shelving, wallpaper, floor coverings, electric heater.
331 | Remove light fittings. Replacement is included in the contractors design portion.
332 | Supply and install new carpet. This is to be Twickenham Twist Carpet or equivalent approved. Colour to be linen.
333 | Lay rigid insulation to the external wall and soffit of the first floor bay window through the hatch in the wall. This is to be 100mm thick.
Roof space
334 | Remove chattels from the roof space.
335 | Remove all current insulation.
336 | Supply and install new insulation quilts which is to be laid in the whole of the roof space. This is to achieve a depth of 350mm across the whole roof. Lay the first layer in between the joists and then the second layer perpendicular to this and so forth.
337 | Over the loft hatch, encapsulate some quilt insulation which is then to be stuck onto the loft hatch opening.
338 | Repoint all chimney breasts in the loft area.
2 Strickland Place
EXTERNAL
Main House
339 | Replace 4no dormer windows with new, timber softwood double glazed units in accordance with BS 644:2009. They are to be sprayed finish to match existing and glazed with 24mm sealed units with a stuck on glazing bar with one opening and one fixed casement. U value 1.6. The ironmongery is to match existing and be black, including pigtail espagnolette security handles, traditional design casement stay and trickle vents.
340 | This involves removing the old units. When doing this, the frame is also to be removed. Include a Provisional Sum of £1,000 for making good and reinstating the render, lead and plaster. | 1000
341 | The door to the entrance hall has a single point lock and does not shut. Allow to ease and adjust the door to shut property.
342 | Allow to improve the security of the door to the entrance hall by installing a second barrel lock. The lock is to have six pin.
343 | Allow to ease and adjust window above the door to the entrance hall so that it is fully operational.
344 | There are multiple failed units in the window above the door to the entrance hall. Allow to re-gas and reseal 4no units.
345 | On the front elevation, allow to rake out and repoint the whole area below the height of the stone cill. This is to be repointed in a lime mortar.
346 | Provide a price per odd brick to cut out and replace with an Imperial Soft Red Handmade Facing Brick and repointed in a lime mortar. This rate will then be applied at the direction of the CA. Allow for 20no.
347 | The replacement of the roofing membrane, battens and relaying/bedding of the tiles are included elsewhere in Item 147 - 149.
348 | Allow to remove the ivy from the two elevations of the kitchen extension.
349 | Allow to rake out current mortar and repoint whole of the two faces of the kitchen extension. This is to be done in a lime mortar.
350 | Allow to rake out the current mortar and repoint the rear elevation between the kitchen and the pantry, up to windowsill level. This is to be repointed in a lime mortar.
Grounds and Boundaries
351 | Allow to demolish the garage whole. At the time of the work starting, the garage will be empty. Any lose items remaining will be treated as a variation. The masonry from the garage is to be reused and broken up to be used in the base of the gravel driveway, if cost effective to do so.
352 | Demolish the fencing at the rear of the property and the fence which separates No 1 and 2.
353 | The area where the garage previously was, is now to be a gravel parking bay. This area should be 6000x5000mm. Allow to prepare the base, including a geotextile membrane, supply and lay the gravel which should be Golden Gravel 20mm and rake to prepare an even finish. Lastly, around the sides of the gravel parking pay, allow to supply and lay Supreme Path Concrete Edging Round Top 36in x 6in x 2in or equivalent approved by the CA.
354 | Allow to supply and install new fencing which is to be in accordance with drawing Site Plan - Fence Plan (separating No 1 and 2 for the full length of the garden, to the rear and side of the parking bay, and to the rear of the garden). The fencing is to be a Close Board Fence Panel Dip Treated 6ft x 5ft. The fence posts are to be 2440mm x 109mm x 94mm Supreme Concrete Intermediate Slotted Fence Posts. The gravel boards are to be Concrete Recessed Gravel Boards 50mm x 150mm x 1830mm. These are to sit underneath each fence panel. The contractor is also to supply and install a gate which is to be to the rear left of the parking bay. This should be a Treated Garden Closeboard Heavy Duty Timber Gate 1820mm x 910mm.
355 | Supply and install a new Overlap Pressure Treated Apex Shed with No Windows 6 ft x 4 ft shed. This is to be placed to the direction of the CA. Indicatively, it will be placed as per drawing Site Plan as Proposed (to the left of the parking bay). Include here to place the shed on a concrete base. Between the sheds joists and the concrete slab, there should be DPC applied only along the joists.
356 | Allow to rake out all areas of mortar and repoint the whole of the front wall, including both properties sides. This is to be repointed in a lime mortar.
357 | Allow to excavate and breakdown the current pathway to the side of the house. Use the broken down concrete to lay a base for new paving. The paving is to be Bradstone Peak Riven Paving Slabs 450x450x35mm or equivalent and the colour is TBC. The path is to be two slabs wide and run from the front gate to the gate leading to the back garden. The base is to be made up of a hardcore base with a mortar bed.
358 | The newly laid path is to have edging to it. This is to run both sides of the path and for the full length. The edging should be a double sided paving edging and 150mm high.
359 | To the front of the new path, there is a decayed gate. Allow to remove this and cart away.
360 | Supply and fit a new gate to fit the existing opening. The gate should be a pale gate and include all relevant ironmongery including a self closer.
INTERNAL
361 | Hack off the plaster to the cheeks of the dormer windows and the angled soffit. There is to be Celotex 75mm rigid insulation or equivalent approved laid. As the depth behind these sections are unknow, price for 75mm rigid insulation.
362 | Supply and fit new Celotex 12.5mm insulated plasterboard or equivalent approved to the internal faces of the soffit in the dormer window. The insulation is to be PIR insulation.
363 | Plasterboard and skim over the hacked off areas.
364 | Allow to ease and adjust both the attic landing window and the 1st floor landing window to leave it fully operational.
365 | Measure, supply and install a new sliding secondary glazing unit to both the attic landing and the 1st floor landing window.
366 | Allow to ease and adjust the 3no first floor windows to leave it fully operational.
367 | Measure, supply and install new sliding secondary glazing to the 3no first floor windows.
368 | Allow to supply and lay new quilt to the whole of the attic area to achieve a depth of 350mm throughout the whole attic area. Lay the first layer between the joists and then the second perpendicular to this and so forth.
369 | The door to the entrance hall has a single point lock and does not shut. Allow to ease and adjust the door to shut property. Also, allow to improve the security of the door by installing a second barrel lock. The lock is to have six pin.
370 | Measure, supply and install new secondary glazing to the 3no windows to the lounge bay window. 2no of the secondary glazing will be fixed shut and the main section should open with the windows.
371 | Allow to ease and adjust the middle window to the ground floor on the rear elevation so it is fully operational.
Services
372 | Allow to complete a drainage survey as stated above.
Contingency Sum
373 | Allow £10,000.00 as a contingency which is to be expended at direction of CA. | 10000

## Form of Tender
Form of Tender
*I/We: ..................................................
carrying on business at:
…………………………………………………………………………………….
having examined the specification and manufacturers recommendations and literature, hereby tender and undertake to execute and complete the whole of the said Works in conformity with the aforementioned documentation for the sum of:
£………………………………………………………… ……(in figures)
……………………………………………………………………(in words)
exclusive of VAT (or such other sum as may be ascertained in accordance with the Conditions of Contract).
Should My/Our tender be accepted, and if requested by the Employer, I/We agree to enter into the Articles of Agreement. Unless and until such an agreement is executed this Form of Tender and the acceptance hereof shall constitute a binding contract between us.
I/We agree that the insertion by me/us of any conditions qualifying this tender or any unauthorised alteration to any of the tender documents may cause the tender to be rejected and confirm that I/We have not inserted any conditions qualifying this tender or made any unauthorised alteration to any of the tender documents.
I/We certify that the details of this tender have not been communicated to any other person or adjusted in accordance with any agreement or arrangement with any other person, firm or company.
I/We also certify that I/We am/are not a party to a scheme or arrangement under which any other tenderer was reimbursed any part of his/her tender cost.
I/We confirm that the above sum includes all Provisional Sums and all Contingencies and agree that this tender shall remain open for acceptance by you and shall not be withdrawn for a period of 30 days from the closing date for return of tenders.
I/We understand that you are not bound to accept the lowest or any tender you may receive, and you will not pay any expenses incurred by us in connection with the preparation and submission of this tender.
I/We hereby warrant and undertake to you in the terms set out in the Instructions to Tenders.
I/We certify that this is a bona fide Tender.
I/We undertake to complete and deliver the whole of the Works comprised in the Contract within 16 weeks from the Date of Possession.
Contractor's Representative's Signature:
(Print Name in Full): ............................................
Position in Company/Firm (must be a director or secretary or another person authorised by the company to sign *):
...............................................................................
Name of Company/Firm:
..............................................................................................................
Address:
.....................................................................................................................................
…………………………………………………………………..............................…………
…………………………………………………………………..............................…………
Tel. No(s): ......................................................
Email Contact: .................................................
Date .................................