**ITP Technical: Panel Instruction**

|  |  |  |
| --- | --- | --- |
| **Multidisciplinary** | ITP No: MC/NEYH/ATLAS/17 | |
| HCA_Logo | Consultant Instruction No: | |
| File Reference: | Date:  16/03/2016 |
| Program: | |
| Location: | |
| Project / Site Title:  Housing Zone  Estate Regeneration Best Practice | |
| To:  Mott MacDonald Ltd  Demeter House, Station Road, Cambridge, CB1 2RS | Office:  Bedford | |
| Details of work required:  To identify best practice and effective case studies in regenerating large  estates with mixed tenure and mixed housing stock that are applicable to  regeneration schemes, and which can be used by the ATLAS to aid councils adapt  and refine their approach to estate regeneration.  TASK ONE: Definition of project & desktop research  1. Agreement of nature / scale of regeneration schemes to be examined &  definition of successful outcomes for estate regeneration  2. Agreement of list of potential schemes to be examined  3. Desktop review by consultants to review how these schemes were devised and  implemented including community engagement, governance arrangements, deciding  on appropriate planning/design strategies to deliver expected outcomes, funding  arrangements, implementation process, and monitoring arrangements & extraction  of key learning points from these schemes.  TASK TWO: Dissemination of best practice to ATLAS  1. Dissemination of key learning points to ATLAS via appropriate tools that can  be retained & reused by ATLAS e.g. an executive summary linked to learning &  dissemination materials such as a powerpoint presentation. (Need to discuss  whether presentation or workshop with team is appropriate). Dissemination to  include:  - Identifying critical success factors in creating new quality designed  places for people to live, work and recreate  - How can design quality be defined & secured in this context to create a  place-making premium. This may include recommendations for policy making.  - What route map / process was used to secure quality outcomes (in terms  of funding, management and planning)?  - Where specific design challenges such as retention of existing  buildings of a multi-story nature exist, how can they be addressed and  integrated into the wider regeneration scheme most effectively.  - Effective community engagement strategies and techniques that have  worked in relation to estate regeneration schemes  - Effective project governance structures for developing and securing  delivery of quality estate regeneration schemes including roles and  responsibilities of involved parties  - Timelines for delivery of successful estate regeneration schemes. | | |
| Is this confirmation of verbal request? No | Original Target Date: 31/03/2016  Latest Target Date: 31/03/2016 | |
| Notes: | Original Target Cost: 17216  Latest Target Cost: 17216 | |
| Purchase Order Number: IT70759 | |
| Originator Ref/Contact: Zahur Gitay | Prepared By: Zahur Gitay | |
| Previous References: | | |
| CDM Linked Instruction? N | | |