SCHEDULE 8

GOVERNANCE

8.1	Governance

8.2	Change Control Procedure

8.3	Dispute Resolution Procedure

8.4	Reports and Records Provisions

8.5	Exit Management

8.6	Service Continuity Plan and Corporate Resolution Planning

8.7	Conduct of Claims

8.8	Management Information

# SCHEDULE 8.1 - GOVERNANCE

## Annual Review

### An annual review meeting shall be held throughout the Term on a date to be agreed between the Parties.

### The meetings shall be attended by the Head of Employment, Skills and Enterprise of the Supplier and the Commercial Contract Lead of the Authority and any other persons considered by the Authority necessary for the review.

### A chairperson shall be appointed by the Authority for each annual review meeting.  The chairperson shall be responsible for:

#### scheduling the meeting;

#### setting the agenda for the meeting and circulating to all attendees in advance of such meeting;

#### chairing the meeting;

#### monitoring the progress of any follow up tasks and activities agreed to be carried out following the meeting;

#### ensuring that minutes for the meeting are recorded and disseminated electronically to the appropriate persons and to all meeting participants within seven (7) Working Days after the meeting; and

#### facilitating the process or procedure by which any decision agreed at the meeting is given effect in the appropriate manner.

## Contract Management Mechanisms

### Both Parties shall pro-actively manage risks attributed to them under the terms of this Agreement.

### The Supplier shall develop, operate, maintain and amend, as agreed with the Authority, processes for

#### the identification and management of risks;

#### the identification and management of issues;

#### monitoring and controlling project plans.

# SCHEDULE 8.2 - CHANGE CONTROL PROCEDURE

## Definitions

In this Schedule, the following definitions shall apply:

| “Change Authorisation Letter” | a letter sent in accordance with the Change Control Procedure which: #### when signed by both Parties, and #### is received by the First Party from the Second Party, #### constitutes a variation to the Agreement; |
| --- | --- |
| “First Party” | has the meaning given in paragraph 2.2; |
| “Second Party” | has the meaning given in paragraph 2.2. |

## Change Control Procedure

### The following Change Control Procedure applies in relation to any Contract Changes.

### A Party (the “First Party”) may propose Contract Changes by issuing Change Authorisation Letters to the other Party (the “Second Party”) detailing the changes that the First Party proposes are made to the Agreement.

### For any Change Authorisation Letter to be valid under this Schedule, it must be sent either to the Authority Representative or the Supplier Representative, as applicable.  The provisions of Clause J10 (Notices) shall apply to a Change Authorisation Letter as if it were a notice.

### The First Party must sign a Change Authorisation Letter before the First Party sends it to the Second Party.

### If the Second Party agrees to the Change Authorisation Letter it must sign the Change Authorisation Letter and send it to the First Party within ten (10) Working Days of receipt, unless the Authority determines that a different period should apply.

### The First Party may withdraw a Change Authorisation Letter it has sent at any point before it has received the signed Change Authorisation Letter from the Second Party.

### If the Second Party amends the Change Authorisation Letter before signing the Change Authorisation Letter and sending it to the First Party, then the Change Authorisation Letter shall be treated as being withdrawn by the First Party.

### No proposed Contract Change is effective until the Change Authorisation Letter has been signed by both Parties, and received by the First Party from the Second Party.  The Parties shall not implement a proposed Contract Change until the Change Authorisation Letter has been signed by both Parties, and received by the First Party from the Second Party.

### If the Change Authorisation Letter cannot be agreed between both Parties, then either Party may refer the matter for resolution in accordance with Clause J11 (Disputes).

### By signing the Change Authorisation Letter the Supplier also confirms the consent of the Guarantor to the Contract Changes.

## Operational Change Procedure

### Any Operational Changes identified by the Supplier to improve operational efficiency of the Services may be implemented by the Supplier without following the Change Control Procedure for proposed Contract Changes provided they do not:

#### have an impact on the business of the Authority;

#### require a change to this Agreement;

#### have a direct impact on use of the Services; or

#### involve the Authority in paying any additional Fees or other costs.

### The Authority may request an Operational Change by submitting a written request for Operational Change (“RFOC”) to the Supplier Representative.

### The RFOC shall include the following details:

#### the proposed Operational Change; and

#### the time-scale for completion of the Operational Change.

### The Supplier shall inform the Authority of any impact on the Services that may arise from the proposed Operational Change.

### The Supplier shall complete the Operational Change by the timescale specified for completion of the Operational Change in the RFOC, and shall promptly notify the Authority when the Operational Change is completed.

# SCHEDULE 8.3 - DISPUTE RESOLUTION PROCEDURE

## Definitions

In this Schedule, the following definitions shall apply:

| “CEDR” | the Centre for Effective Dispute Resolution of International Dispute Resolution Centre, 70 Fleet Street, London, EC4Y 1EU; |
| --- | --- |
| “Counter Notice” | has the meaning given in Paragraph 7.2; |
| “Expert” | in relation to a Dispute, a person appointed in accordance with Paragraph 6.2 to act as an expert in relation to that Dispute; |
| “Expert Determination” | determination by an Expert in accordance with Paragraph 6; |
| “Mediation Notice” | has the meaning given in Paragraph 4.2; |
| “Mediator” | the independent third party appointed in accordance with Paragraph 5.2 to mediate a Dispute; |
| “Multi-Party Dispute” | a Dispute which involves the Parties and one or more Related Third Parties; |
| “Multi-Party Dispute Representatives” | has the meaning given in Paragraph 9.6; |
| “Multi-Party Dispute Resolution Board” | has the meaning given in Paragraph 9.6; |
| “Related Third Party” | a party to: - another contract with the Authority or the Supplier which is relevant to this Agreement; or - a Sub-contract; and |
| “Supplier Request” | a notice served by the Supplier requesting that the Dispute be treated as a Multi-Party Dispute, setting out its grounds for that request and specifying each Related Third Party that it believes should be involved in the Multi-Dispute Resolution Procedure in respect of that Dispute. |

## Dispute Notices

### If a Dispute arises then:

#### the Authority Representative and the Supplier Representative shall attempt in good faith to resolve the Dispute; and

#### if such attempts are not successful within a reasonable period, not being longer than twenty (20) Working Days, either Party may issue to the other a Dispute Notice.

### A Dispute Notice:

#### shall set out:

##### the material particulars of the Dispute;

##### the reasons why the Party serving the Dispute Notice believes that the Dispute has arisen; and

##### if the Party serving the Dispute Notice believes that the Dispute should be dealt with under the Expedited Dispute Timetable, the reason why; and

#### may specify in accordance with the requirements of Paragraphs 9.2 and 9.3 that the Party issuing the Dispute Notice has determined (in the case of the Authority) or considers (in the case of the Supplier) that the Dispute is a Multi-Party Dispute, in which case Paragraph 2.3 shall apply.

### If a Dispute Notice specifies that the Dispute has been determined or is considered to be a Multi-Party Dispute pursuant to Paragraph 2.2(b), then:

#### if it is served by the Authority it shall be treated as a Multi-Party Procedure Initiation Notice; and

#### if it is served by the Supplier it shall be treated as a Supplier Request,

and in each case the provisions of Paragraph 9 shall apply.

### Subject to Paragraphs 2.5 and 3.2 and so long as the Authority has not served a Multi-Party Procedure Initiation Notice in respect of the relevant Dispute, following the issue of a Dispute Notice the Parties shall seek to resolve the Dispute:

#### first by commercial negotiation (as prescribed in Paragraph 4);

#### then, if either Party serves a Mediation Notice, by mediation (as prescribed in Paragraph 5); and

#### lastly by recourse to arbitration (as prescribed in Paragraph 7) or litigation (in accordance with Clause J12 (Governing Law and Jurisdiction)).

### Specific issues shall be referred to Expert Determination (as prescribed in Paragraph 6) where specified under the provisions of this Agreement and may also be referred to Expert Determination where otherwise appropriate as specified in Paragraph 6.1.

### Unless agreed otherwise in writing, the Parties shall continue to comply with their respective obligations under this Agreement regardless of the nature of the Dispute and notwithstanding any issue of a Dispute Notice or a Multi-Party Procedure Initiation Notice or proceedings under Paragraph 8 (Urgent Relief).

## Expedited Dispute Timetable

### In exceptional circumstances where the use of the times in this Schedule would be unreasonable, including (by way of example) where one Party would be materially disadvantaged by a delay in resolving the Dispute, the Parties may agree to use the Expedited Dispute Timetable.  If the Parties are unable to reach agreement on whether to use the Expedited Dispute Timetable within five (5) Working Days of the issue of a Dispute Notice, the use of the Expedited Dispute Timetable shall be at the sole discretion of the Authority.

### If the Expedited Dispute Timetable is to be used pursuant to the provisions of Paragraph 3.1 or is otherwise specified under the provisions of this Agreement, then the following periods of time shall apply in lieu of the time periods specified in the applicable Paragraphs:

#### in Paragraph 4.2(c), ten (10) Working Days;

#### in Paragraph 5.2, ten (10) Working Days;

#### in Paragraph 6.2, five (5) Working Days; and

#### in Paragraph 7.2, ten (10) Working Days.

### If at any point it becomes clear that an applicable deadline cannot be met or has passed, the Parties may (but shall be under no obligation to) agree in writing to extend the deadline.  If the Parties fail to agree within two (2) Working Days after the deadline has passed, the Authority may set a revised deadline provided that it is no less than five (5) Working Days before the end of the period of time specified in the applicable paragraphs (or two (2) Working Days in the case of Paragraph 6.2).  Any agreed extension shall have the effect of delaying the start of the subsequent stages by the period agreed in the extension.  If the Authority fails to set such a revised deadline, then the use of the Expedited Dispute Timetable shall cease and the normal time periods shall apply from that point onwards.

## Commercial negotiation

### Following the service of a Dispute Notice, then, so long as the Authority has not served a Multi-Party Procedure Initiation Notice in respect of the relevant Dispute, the Authority and the Supplier shall make reasonable endeavours to resolve the Dispute as soon as possible by commercial negotiation between the Authority’s [insert role] and the Supplier’s [insert role].

### If:

#### either Party is of the reasonable opinion that the resolution of a Dispute by commercial negotiation, or the continuance of commercial negotiation, will not result in an appropriate solution;

#### the Parties have already held discussions of a nature and intent (or otherwise were conducted in the spirit) that would equate to the conduct of commercial negotiation in accordance with this Paragraph 4; or

#### the Parties have not settled the Dispute in accordance with Paragraph 4.1 within thirty (30) Working Days of service of the Dispute Notice,

either Party may serve a written notice to proceed to mediation in accordance with Paragraph 5 (a “Mediation Notice”).

## Mediation

### If a Mediation Notice is served, the Parties shall attempt to resolve the dispute in accordance with the version of CEDR's Model Mediation Procedure which is current at the time the Mediation Notice is served (or such other version as the Parties may agree).

### If the Parties are unable to agree on the joint appointment of an independent person to mediate the Dispute within twenty (20) Working Days from (and including) the service of a Mediation Notice, then either Party may apply to CEDR to nominate such a person.

### If the Parties are unable to reach a settlement in the negotiations at the mediation, and only if both Parties so request and the Mediator agrees, the Mediator shall produce for the Parties a non-binding recommendation on terms of settlement.  This shall not attempt to anticipate what a court might order but shall set out what the Mediator suggests are appropriate settlement terms in all of the circumstances.

### Any settlement reached in the mediation shall not be legally binding until it has been reduced to writing and signed by, or on behalf of, the Parties (in accordance with the Change Control Procedure where appropriate).  The Mediator shall assist the Parties in recording the outcome of the mediation.

## Expert determination

### If a Dispute relates to any aspect of the technology underlying the provision of the Services or otherwise relates to a technical matter of an IT, accounting or financing nature and the Dispute has not been resolved by commercial negotiation in accordance with Paragraph 4 or, if applicable, mediation in accordance with Paragraph 5, then either Party may by written notice to the other request (agreement to which request shall not be unreasonably withheld or delayed) that the Dispute be referred to an expert for determination.

### The expert shall be appointed by agreement in writing between the Parties, but in the event of a failure to agree within ten (10) Working Days of the relevant request made pursuant to Paragraph 6.1, or if the person appointed is unable or unwilling to act, the expert shall be appointed:

#### if the Dispute relates to any aspect of the technology underlying the provision of the Services or a matter of an IT technical nature, on the instructions of the President of the British Computer Society (or any other association that has replaced the British Computer Society);

#### if the Dispute relates to a matter of a financial technical nature, on the instructions of the President of the Institute of Chartered Accountants of England and Wales; or

#### if the Dispute relates to a matter of a technical nature not falling within Paragraphs 6.2(a) or (b), on the instructions of the president (or equivalent) of:

##### an appropriate body agreed between the Parties; or

##### if the Parties do not reach agreement on the relevant body within fifteen (15) Working Days of the relevant request made pursuant to Paragraph 6.1, such body as may be specified by the President of the Law Society on application by either Party.

### The Expert shall act on the following basis:

#### he/she shall act as an expert and not as an arbitrator and shall act fairly and impartially;

#### the Expert's determination shall (in the absence of a material failure to follow the agreed procedures) be final and binding on the Parties;

#### the Expert shall decide the procedure to be followed in the determination and shall be requested to make his/her determination within thirty (30) Working Days of his appointment or as soon as reasonably practicable thereafter and the Parties shall assist and provide the documentation that the Expert requires for the purpose of the determination;

#### any amount payable by one Party to another as a result of the Expert's determination shall be due and payable within twenty (20) Working Days of the Expert's determination being notified to the Parties;

#### the process shall be conducted in private and shall be confidential; and

#### the Expert shall determine how and by whom the costs of the determination, including his/her fees and expenses, are to be paid.

## Arbitration

### Subject to compliance with its obligations under Paragraph 4.1 and to the provisions of Paragraph 6, the Authority may at any time before court proceedings are commenced refer the Dispute to arbitration in accordance with the provisions of Paragraph 7.5.

### Before the Supplier commences court proceedings or arbitration, it shall serve written notice on the Authority of its intentions and the Authority shall have fifteen (15) Working Days following receipt of such notice to serve a reply (a “Counter Notice”) on the Supplier requiring the Dispute to be referred to and resolved by arbitration in accordance with Paragraph 7.5 or be subject to the exclusive jurisdiction of the courts of England and Wales.  The Supplier shall not commence any court proceedings or arbitration until the expiry of such fifteen (15) Working Day period.

### If the Authority serves a Counter Notice, then:

#### if the Counter Notice requires the Dispute to be referred to arbitration, the provisions of Paragraph 7.5 shall apply; or

#### if the Counter Notice requires the Dispute to be subject to the exclusive jurisdiction of the courts of England and Wales, the Dispute shall be so referred to those courts and the Supplier shall not commence arbitration proceedings.

### If the Authority does not serve a Counter Notice within the fifteen (15) Working Day period referred to in Paragraph 7.2, the Supplier may either commence arbitration proceedings in accordance with Paragraph 7.5 or commence court proceedings in the Courts of England and Wales which shall (in those circumstances) have exclusive jurisdiction.

### The Parties hereby confirm that if any arbitration proceedings are commenced pursuant to Paragraphs 7.1 to 7.4:

#### the Dispute shall be referred to and finally resolved by arbitration under the Rules of the London Court of International Arbitration (“LCIA”) (subject to Paragraphs 7.5(e), (f) and (g));

#### the arbitration shall be administered by the LCIA;

#### the LCIA procedural rules in force at the date that the Dispute was referred to arbitration shall be applied and are deemed to be incorporated by reference into this Agreement and the decision of the arbitrator shall be binding on the Parties in the absence of any material failure to comply with such rules;

#### if the Parties fail to agree the appointment of the arbitrator within ten (10) Working Days from the date on which arbitration proceedings are commenced or if the person appointed is unable or unwilling to act, the arbitrator shall be appointed by the LCIA;

#### the chair of the arbitral tribunal shall be British;

#### the arbitration proceedings shall take place in London and in the English language; and

#### the seat of the arbitration shall be London.

## Urgent relief

Either Party may at any time take proceedings or seek remedies before any court or tribunal of competent jurisdiction:

#### for interim or interlocutory remedies in relation to this Agreement or infringement by the other Party of that Party’s Intellectual Property Rights; and/or

#### where compliance with Paragraph 2.1 and/or referring the Dispute to mediation may leave insufficient time for that Party to commence proceedings before the expiry of the limitation period.

## Multi-Party Disputes

### All Multi-Party Disputes shall be resolved in accordance with the procedure set out in this Paragraph 9 (the “Multi-Party Dispute Resolution Procedure”).

### If at any time following the issue of a Dispute Notice, the Authority reasonably considers that the matters giving rise to the Dispute involve one or more Related Third Parties, then the Authority shall be entitled to determine that the Dispute is a Multi-Party Dispute and to serve a notice on the Supplier which sets out the Authority’s determination that the Dispute is a Multi-Party Dispute and specifies the Related Third Parties which are to be involved in the Multi-Party Dispute Resolution Procedure, such notice a “Multi-Party Procedure Initiation Notice”.

### If following the issue of a Dispute Notice but before the Dispute has been referred to Expert Determination or to arbitration in accordance with Paragraph 7, the Supplier has reasonable grounds to believe that the matters giving rise to the Dispute have been contributed to by one or more Related Third Parties, the Supplier may serve a Supplier Request on the Authority.

### The Authority shall (acting reasonably) consider each Supplier Request and shall determine within five (5) Working Days whether the Dispute is:

#### a Multi-Party Dispute, in which case the Authority shall serve a Multi-Party Procedure Initiation Notice on the Supplier; or

#### not a Multi-Party Dispute, in which case the Authority shall serve written notice of such determination upon the Supplier and the Dispute shall be treated in accordance with Paragraphs 3 to 8.

### If the Authority has determined, following a Supplier Request, that a Dispute is not a Multi-Party Dispute, the Supplier may not serve another Supplier Request with reference to the same Dispute.

### Following service of a Multi-Party Procedure Initiation Notice a Multi-Party Dispute shall be dealt with by a board (in relation to such Multi-Party Dispute, the “Multi-Party Dispute Resolution Board”) comprising representatives from the following parties to the Multi-Party Dispute, each of whom shall be of a suitable level of seniority to finalise any agreement with the other parties to settle the Multi-Party Dispute:

#### the Authority;

#### the Supplier;

#### each Related Third Party involved in the Multi-Party Dispute; and

#### any other representatives of any of the Parties and/or any Related Third Parties whom the Authority considers necessary,

(together “Multi-Party Dispute Representatives”).

### The Parties agree that the Multi-Party Dispute Resolution Board shall seek to resolve the relevant Multi-Party Dispute in accordance with the following principles and procedures:

#### the Parties shall procure that their Multi-Party Dispute Representatives attend, and shall use their best endeavours to procure that the Multi-Party Dispute Representatives of each Related Third Party attend, all meetings of the Multi-Party Dispute Resolution Board in respect of the Multi-Party Dispute;

#### the Multi-Party Dispute Resolution Board shall first meet within ten (10) Working Days of service of the relevant Multi-Party Procedure Initiation Notice at such time and place as the Parties may agree or, if the Parties do not reach agreement on the time and place within five (5) Working Days of service of the relevant Multi-Party Procedure Initiation Notice, at the time and place specified by the Authority, provided such place is at a neutral location within England and that the meeting is to take place between 9.00am and 5.00pm on a Working Day; and

#### in seeking to resolve or settle any Multi-Party Dispute, the members of the Multi-Party Dispute Resolution Board shall have regard to the principle that a Multi-Party Dispute should be determined based on the contractual rights and obligations between the Parties and the Related Third Parties and that any apportionment of costs should reflect the separate components of the Multi-Party Dispute.

### If a Multi-Party Dispute is not resolved between the Parties and all Related Third Parties within twenty-five (25) Working Days of the issue of the Multi-Party Procedure Initiation Notice (or such longer period as the Parties may agree in writing), then:

#### either Party may serve a Mediation Notice in respect of the Multi-Party Dispute in which case Paragraph 5 shall apply;

#### either Party may request that the Multi-Party Dispute is referred to an expert in which case Paragraph 6 shall apply; and/or

#### subject to Paragraph 9.9, Paragraph 7 shall apply to the Multi-Party Dispute,

and in each case references to the “Supplier” or the “Parties” in such provisions shall include a reference to all Related Third Parties.

### If a Multi-Party Dispute is referred to arbitration in accordance with Paragraph 7 or a Dispute becomes a Multi-Party Dispute during the course of arbitration proceedings and either Party is unable to compel a Related Third Party to submit to such arbitration proceedings, the Authority or the Supplier may discontinue such arbitration proceedings and instead initiate court proceedings.  The costs of any such discontinued arbitration proceedings shall be borne by the Party which is in a direct contractual relationship with the Related Third Party or, where the Related Third Party is a Sub-Contractor, by the Supplier.

# SCHEDULE 8.4 - REPORTS AND RECORDS PROVISIONS

## Transparency Reports

### Within three (3) months of the Effective Date the Supplier shall provide to the Authority for its approval (such approval not to be unreasonably withheld or delayed) draft reports in accordance with Annex 1 (once approved, the “Transparency Reports”).

### If the Authority rejects any draft Transparency Report, the Supplier shall submit a revised version of the relevant report for further approval by the Authority within five (5) days of receipt of any notice of rejection, taking account of any recommendations for revision and improvement to the report provided by the Authority.  If the Parties fail to agree on a draft Transparency Report the Authority shall determine what should be included.

### The Supplier shall provide accurate and up-to-date versions of each Transparency Report to the Authority at the frequency referred to in Annex 1.

### Any disagreement in connection with the preparation and/or approval of Transparency Reports, other than under paragraph 1.2 above in relation to the contents of a Transparency Report, shall be treated as a Dispute.

### The requirements for Transparency Reports are in addition to any other reporting requirements in this Agreement.

## Other reports

The Authority may require any or all of the following reports:

#### delay reports;

#### reports relating to tests carried out under Schedule 2.4 (Security Requirements) and Schedule 8.6 (Service Continuity Plan and Corporate Resolution Planning);

#### reports which the Supplier is required to supply as part of the Management Information;

#### annual reports on the Insurances;

#### security reports; and

#### Force Majeure Event reports.

## Records

### The Supplier shall retain and maintain all the records (including superseded records) referred to in Paragraph 1 and Annex 1 (together “Records”):

#### in accordance with the requirements of The National Archives and Good Industry Practice;

#### in chronological order;

#### in a form that is capable of audit; and

#### at its own expense.

### The Supplier shall make the Records available for inspection to the Authority on request, subject to the Authority giving reasonable notice.

### Where Records are retained in electronic form, the original metadata shall be preserved together with all subsequent metadata in a format reasonably accessible to the Authority.

### The Supplier shall, during the Term and a period of at least seven (7) years following the expiry or termination of this Agreement, maintain or cause to be maintained complete and accurate documents and records in relation to the provision of the Services including but not limited to all Records.

### Records that contain financial information shall be retained and maintained in safe storage by the Supplier for a period of at least seven (7) years after the expiry or termination of this Agreement.

### Without prejudice to the foregoing, the Supplier, at the Authority’s request, shall provide the Authority:

#### as soon as they are available, and in any event within sixty (60) Working Days after the end of the first six (6) months of each financial year of the Supplier during the Term, a copy, certified as a true copy by an authorised representative of the Supplier, of its un-audited interim accounts and, if applicable, of consolidated un-audited interim accounts of the Supplier and its Affiliates which would (if the Supplier were listed on the London Stock Exchange (whether or not it is)) be required to be sent to shareholders as at the end of and for each such six (6) month period; and

#### as soon as they shall have been sent to its shareholders in order to be laid before an annual general meeting of the Supplier, but not later than one-hundred and thirty (130) Working Days after the end of each accounting reference period of the Supplier part or all of which falls during the Term, the Supplier's audited accounts and if applicable, of the consolidated audited accounts of the Supplier and its Affiliates in respect of that period together with copies of all related directors' and auditors' reports and all other notices/circulars to shareholders.

# ANNEX 1: TRANSPARENCY REPORTS

| # TITLE | # CONTENT | # FORMAT | # FREQUENCY |
| --- | --- | --- | --- |
| (Performance) |  |  |  |
| (Fees) |  |  |  |
| (Sub-contractors) |  |  |  |
| (Technical) |  |  |  |
| (Performance management) |  |  |  |

# ANNEX 2: Records to be kept by the Supplier

The records to be kept by the Supplier are:

- This Agreement, its Schedules and all amendments to such documents.

- All other documents which this Agreement expressly requires to be prepared.

- Records relating to the appointment and succession of the Supplier Representative and each member of the Key Personnel.

- Notices, reports and other documentation submitted by any Expert.

- All operation and maintenance manuals prepared by the Supplier for the purpose of maintaining the provision of the Services and the underlying IT Environment and Supplier Equipment.

- Documents prepared by the Supplier or received by the Supplier from a third party relating to a Force Majeure Event.

- All formal notices, reports or submissions made by the Supplier to the Authority Representative in connection with the provision of the Services.

- All certificates, licences, registrations or warranties in each case obtained by the Supplier in relation to the provision of the Services.

- Documents prepared by the Supplier in support of claims for the Fees.

- Documents submitted by the Supplier pursuant to the Change Control Procedure.

- Documents submitted by the Supplier pursuant to invocation by it or the Authority of the Dispute Resolution Procedure.

- Documents evidencing any change in ownership or any interest in any or all of the shares in the Supplier and/or the Guarantor, where such change may cause a Change of Control; and including documents detailing the identity of the persons changing such ownership or interest.

- Invoices and records related to VAT sought to be recovered by the Supplier.

- Financial records, including audited and un-audited accounts of the Guarantor and the Supplier.

- Records required to be retained by the Supplier by Law, including in relation to health and safety matters and health and safety files and all consents.

- All documents relating to the insurances to be maintained under this Agreement and any claims made in respect of them.

- All documents produced by the Supplier pursuant to Schedule 2.4 (Security Requirements).

- All other records, notices or certificates required to be produced and/or maintained by the Supplier pursuant to this Agreement.

# ANNEX 4: SUPPLY CHAIN TRANSPARENCY INFORMATION TEMPLATE

|  | Financial Year 20[ ] |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Under this Agreement |  | Supplier as a whole |  |  |  |
|  | £ | % | £ | % |  |  |
| Estimated total contract revenue (£) to be received in this Financial Year | £[ ] | 100% | £[ ] | 100% |  |  |
| Total value of Sub-contracted revenues (£) in this Financial Year | £[ ] | [ ] | £[ ] | [ ] |  |  |
| Total value of Sub-contracted revenues to SMEs (£) in this Financial Year | £[ ] | [ ] | £[ ] | [ ] |  |  |
| Total value of Sub-contracted revenues to VCSEs (£) in this Financial Year | £[ ] | [ ] | £[ ] | [ ] |  |  |

# SCHEDULE 8.5 - EXIT MANAGEMENT

## Definitions

In this Schedule, the following definitions shall apply:

| “Application Programming Interface” or “API” | Means a piece of software that facilitates access to the Supplier’s application(s) to provide access to business functionality and/or Authority Data to support any relevant Termination Services which conforms to the Government Digital Service API technical and data standards set online at: https://www.gov.uk/guidance/gds-api-technical-and-data-standards |
| --- | --- |
| “Emergency Exit” | any termination of this Agreement which is a: - termination of the whole or part of this Agreement in accordance with Clause I1 (Termination Rights), except where the period of notice given under that Clause is greater than or equal to six (6) months; - termination of the provision of the Services for any reason prior to the expiry of any period of notice of termination served pursuant to Clause I1 (Termination Rights); or - wrongful termination or repudiation of this Agreement by either Party; |
| “Exclusive Assets” | those Assets used by the Supplier or a Key Sub-contractor which are used exclusively in the provision of the Services; |
| “Exit Information” | has the meaning given in Paragraph 3.1; |
| “Exit Manager” | the person appointed by each Party pursuant to Paragraph 2.3 for managing the Parties' respective obligations under this Schedule; |
| “Net Book Value” | the net book value of the relevant Asset(s) calculated in accordance with the depreciation policy of the Supplier set out in the letter in the agreed form from the Supplier to the Authority of the same date as this Agreement; |
| “Non-Exclusive Assets” | those Assets (if any) which are used by the Supplier or a Key Sub-contractor in connection with the Services but which are also used by the Supplier or Key Sub-contractor for other purposes of material value; |
| “Ordinary Exit” | any termination of the whole or part of this Agreement which occurs: pursuant to Clause I1 (Termination Rights) where the period of notice given by the Party serving notice to terminate pursuant to such Clause is greater than or equal to six (6) months; or as a result of the expiry of the Term; |
| “Registers” | the register and configuration database referred to in Paragraphs 2.1(a) and 2.1(b); |
| “Transferable Assets” | those of the Exclusive Assets which are capable of legal transfer to the Authority; |
| “Transferable Contracts” | the Sub-contracts, licences for Supplier's Software, licences for Third Party Software or other agreements which are necessary to enable the Authority or any Replacement Supplier to perform the Services or the Replacement Services, including in relation to licences all relevant Documentation; and |
| “Transferring Contracts” | has the meaning given in Paragraph 6.2(c). |

## Obligations during the Term to facilitate Exit

### During the Term, the Supplier shall:

#### create and maintain a register of all:

##### Assets, detailing their:

        - make, model and asset number;

        - ownership and status as either Exclusive Assets or Non-Exclusive Assets;

        - Net Book Value;

        - condition and physical location; and

        - use (including technical specifications); and

##### Sub-contracts and other relevant agreements (including relevant software licences, maintenance and support agreements and equipment rental and lease agreements) required for the performance of the Services;

#### create and maintain a configuration database detailing the technical infrastructure and operating procedures through which the Supplier provides the Services, which shall contain sufficient detail to permit the Authority and/or Replacement Supplier to understand how the Supplier provides the Services and to enable the smooth transition of the Services with the minimum of disruption;

#### agree the format of the Registers with the Authority as part of the process of agreeing the Exit Plan; and

#### at all times keep the Registers up to date, in particular in the event that Assets, Sub-contracts or other relevant agreements are added to or removed from the Services.

### The Supplier shall procure that all Exclusive Assets listed in the Registers are clearly marked to identify that they are exclusively used for the provision of the Services under this Agreement.

### Each Party shall appoint a person for the purposes of managing the Parties' respective obligations under this Schedule and provide written notification of such appointment to the other Party within three (3) months of the Effective Date.  The Supplier's Exit Manager shall be responsible for ensuring that the Supplier and its employees, agents and Sub-contractors comply with this Schedule.  The Supplier shall ensure that its Exit Manager has the requisite authority to arrange and procure any resources of the Supplier as are reasonably necessary to enable the Supplier to comply with the requirements set out in this Schedule.  The Parties' Exit Managers will liaise with one another in relation to all issues relevant to the termination of this Agreement and all matters connected with this Schedule and each Party's compliance with it.

## Obligations to assist on re-tendering of Services

### On reasonable notice at any point during the Term, the Supplier shall provide to the Authority and/or its potential Replacement Suppliers (subject to the potential Replacement Suppliers entering into reasonable written confidentiality undertakings), the following material and information in order to facilitate the preparation by the Authority of any invitation to tender and/or to facilitate any potential Replacement Suppliers undertaking due diligence:

#### details of the Service(s);

#### a copy of the Registers, updated by the Supplier up to the date of delivery of such Registers;

#### an inventory of Authority Data in the Supplier's possession or control;

#### details of any key terms of any third party contracts and licences, particularly as regards charges, termination, assignment and novation;

#### a list of on-going and/or threatened disputes in relation to the provision of the Services;

#### to the extent permitted by applicable Law, all information relating to Transferring Supplier Employees required to be provided by the Supplier under this Agreement; and

#### such other material and information as the Authority shall reasonably require,

(together, the “Exit Information”).

### The Supplier acknowledges that the Authority may disclose the Supplier's Confidential Information to an actual or prospective Replacement Supplier or any third party whom the Authority is considering engaging to the extent that such disclosure is necessary in connection with such engagement (except that the Authority may not under this Paragraph 3.2 disclose any Supplier’s Confidential Information which is information relating to the Supplier’s or its Sub-contractors’ prices or costs).

### The Supplier shall:

#### notify the Authority within five (5) Working Days of any material change to the Exit Information which may adversely impact upon the potential transfer and/or continuance of any Services and shall consult with the Authority regarding such proposed material changes; and

#### provide complete updates of the Exit Information on an as-requested basis as soon as reasonably practicable and in any event within ten (10) Working Days of a request in writing from the Authority.

### The Supplier may charge the Authority for its reasonable additional costs to the extent the Authority requests more than four (4) updates in any six (6) month period.

### The Exit Information shall be accurate and complete in all material respects and the level of detail to be provided by the Supplier shall be such as would be reasonably necessary to enable a third party to:

#### prepare an informed offer for those Services; and

#### not be disadvantaged in any subsequent procurement process compared to the Supplier (if the Supplier is invited to participate).

## Exit Plan

### The Supplier shall, within three (3) months after the Effective Date, deliver to the Authority an Exit Plan which:

#### sets out the Supplier's proposed methodology for achieving an orderly transition of the relevant Services from the Supplier to the Authority and/or its Replacement Supplier on Partial Termination, expiry or termination of this Agreement;

#### complies with the requirements set out in Paragraph 4.2; and

#### is otherwise reasonably satisfactory to the Authority.

### The Parties shall use reasonable endeavours to agree the contents of the Exit Plan.  If the Parties are unable to agree the contents of the Exit Plan within twenty (20) Working Days of its submission, then such Dispute shall be resolved in accordance with the Dispute Resolution Procedure.

### The Exit Plan shall set out, as a minimum:

#### how the Exit Information is obtained;

#### separate mechanisms for dealing with Ordinary Exit and Emergency Exit, the provisions relating to Emergency Exit being prepared on the assumption that the Supplier may be unable to provide the full level of assistance which is required by the provisions relating to Ordinary Exit, and in the case of Emergency Exit, provision for the supply by the Supplier of all such reasonable assistance as the Authority shall require to enable the Authority or its Sub-contractors to provide the Services;

#### a mechanism for dealing with Partial Termination on the assumption that the Supplier will continue to provide the remaining Services under this Agreement;

#### the management structure to be employed during both transfer and cessation of the Services in an Ordinary Exit and an Emergency Exit;

#### the management structure to be employed during the Termination Assistance Period;

#### a detailed description of both the transfer and cessation processes, including a timetable, applicable in the case of an Ordinary Exit and an Emergency Exit;

#### how the Services will transfer to the Replacement Supplier and/or the Authority, including details of the processes, documentation, data transfer, systems migration, security and the segregation of the Authority's technology components from any technology components operated by the Supplier or its Sub-contractors (where applicable);

#### the scope of the Termination Services that may be required for the benefit of the Authority (including such of the services set out in Annex 1 as are applicable);

#### a timetable and critical issues for providing the Termination Services;

#### any charges that would be payable for the provision of the Termination Services (calculated in accordance with the methodology that would apply if such Services were being treated as a Contract Change), together with a capped estimate of such charges;

#### how the Termination Services would be provided (if required) during the Termination Assistance Period;

#### procedures to deal with requests made by the Authority and/or a Replacement Supplier for Staffing Information pursuant to Schedule 9.1 (Staff Transfer); and

#### how each of the issues set out in this Schedule will be addressed to facilitate the transition of the Services from the Supplier to the Replacement Supplier and/or the Authority with the aim of ensuring that there is no disruption to or degradation of the Services during the Termination Assistance Period.

### The Parties acknowledge that the migration of the Services from the Supplier to the Authority and/or its Replacement Supplier may be phased, such that certain of the Services are handed over before others.

### The Supplier shall review and (if appropriate) update the Exit Plan on a basis consistent with the principles set out in this Schedule in the first month of each Contract Year (commencing with the second Contract Year) and if requested by the Authority following the occurrence of a Financial Distress Event, within fourteen (14) days of such request, to reflect any changes in the Services that have occurred since the Exit Plan was last agreed.  Following such update the Supplier shall submit the revised Exit Plan to the Authority for review.  Within twenty (20) Working Days following submission of the revised Exit Plan, the Parties shall meet and use reasonable endeavours to agree the contents of the revised Exit Plan.  If the Parties are unable to agree the contents of the revised Exit Plan within that twenty (20) Working Day period, such dispute shall be resolved in accordance with the Dispute Resolution Procedure.

Finalisation of the Exit Plan

### Within twenty (20) Working Days after service of a Termination Notice by either Party or six (6) months prior to the expiry of this Agreement, the Supplier will submit for the Authority's approval the Exit Plan in a final form that could be implemented immediately.  The final form of the Exit Plan shall be prepared on a basis consistent with the principles set out in this Schedule and shall reflect any changes in the Services that have occurred since the Exit Plan was last agreed.

### The Parties will meet and use their respective reasonable endeavours to agree the contents of the final form of the Exit Plan.  If the Parties are unable to agree the contents of the Exit Plan within twenty (20) Working Days following its delivery to the Authority, then such Dispute shall be resolved in accordance with the Dispute Resolution Procedure.  Until the agreement of the final form of the Exit Plan, the Supplier shall provide the Termination Services in accordance with the principles set out in this Schedule and the last approved version of the Exit Plan (insofar as relevant).

## Termination Services

Notification of requirements for Termination Services

### The Authority shall be entitled to require the provision of Termination Services at any time during the Term by giving written notice to the Supplier (a “Termination Assistance Notice”) at least four (4) months prior to the date of Partial Termination, termination or expiry of this Agreement or as soon as reasonably practicable (but in any event, not later than 1 month) following the service by either Party of a Termination Notice.  The Termination Assistance Notice shall specify:

#### the date from which Termination Services are required;

#### the nature of the Termination Services required; and

#### the period during which it is anticipated that Termination Services will be required, which shall continue no longer than twenty-four (24) months after the date that the Supplier ceases to provide the terminated Services.

### The Authority shall have:

#### an option to extend the period of assistance beyond the period specified in the Termination Assistance Notice provided that such extension shall not extend for more than six (6) months after the date the Supplier ceases to provide the terminated Services or, if applicable, beyond the end of the Termination Assistance Period and provided that it shall notify the Supplier to such effect no later than twenty (20) Working Days prior to the date on which the provision of Termination Services is otherwise due to expire; and

#### the right to terminate its requirement for Termination Services by serving not less than twenty (20) Working Days' written notice upon the Supplier to such effect.

Termination Assistance Period

### Throughout the Termination Assistance Period, or such shorter period as the Authority may require, the Supplier shall:

#### continue to provide the Services (as applicable) and, if required by the Authority pursuant to Paragraph 5.1, provide the Termination Services;

#### in addition to providing the Services and the Termination Services, provide to the Authority any reasonable assistance requested by the Authority to allow the Services to continue without interruption following the Partial Termination, termination or expiry of this Agreement and to facilitate the orderly transfer of responsibility for and conduct of the Services to the Authority and/or its Replacement Supplier;

#### use all reasonable endeavours to reallocate resources to provide such assistance as is referred to in Paragraph 5.3(b) without additional costs to the Authority;

#### provide the Services and the Termination Services at no detriment to the Customer Service Standards, Tender Minimum Performance Levels and RNOs, save to the extent that the Parties agree otherwise in accordance with Paragraph 5.5; and

#### at the Authority's request and on reasonable notice, deliver up-to-date Registers to the Authority.

### Without prejudice to the Supplier’s obligations under Paragraph 5.3(c), if it is not possible for the Supplier to reallocate resources to provide such assistance as is referred to in Paragraph 5.3(b) without additional costs to the Authority, any additional costs incurred by the Supplier in providing such reasonable assistance which is not already in the scope of the Termination Services or the Exit Plan shall be subject to the Change Control Procedure.

### If the Supplier demonstrates to the Authority's reasonable satisfaction that transition of the Services and provision of the Termination Services during the Termination Assistance Period will have a material, unavoidable adverse effect on the Supplier's ability to meet one or more particular Customer Service Standards, Tender Minimum Performance Levels or RNOs, the Parties shall vary the relevant Customer Service Standards, Tender Minimum Performance Levels or RNOs to take account of such adverse effect.

Termination obligations

### The Supplier shall comply with all of its obligations contained in the Exit Plan in respect of any Partial Termination or termination.

### At the end of the Termination Assistance Period (or earlier if this does not adversely affect the Supplier's performance of the Services and the Termination Services and its compliance with the other provisions of this Schedule) in respect of the Services that have been terminated, the Supplier shall:

#### cease to use the Authority Data;

#### provide the Authority and/or the Replacement Supplier with a complete and uncorrupted version of the Authority Data in electronic form (or such other format as reasonably required by the Authority);

#### erase from any computers, storage devices and storage media that are to be retained by the Supplier after the end of the Termination Assistance Period all Authority Data and promptly certify to the Authority that it has completed such deletion;

#### return to the Authority such of the following as is in the Supplier's possession or control:

##### all copies of the Authority Software and any other software licensed by the Authority to the Supplier under this Agreement;

##### all materials created by the Supplier under this Agreement in which the IPRs are owned by the Authority;

##### any parts of the IT Environment and any other equipment which belongs to the Authority; and

##### any items that have been on-charged to the Authority, such as consumables;

#### vacate any Authority Premises unless access is required to continue to deliver the Services;

#### provide access during normal working hours to the Authority and/or the Replacement Supplier for up to twelve (12) months after the Partial Termination, expiry or termination of this Agreement to:

##### such information relating to the Services as remains in the possession or control of the Supplier; and

##### such members of the Supplier Personnel as have been involved in the design, development and provision of the Services and who are still employed by the Supplier, provided that the Authority and/or the Replacement Supplier shall pay the reasonable costs of the Supplier actually incurred in responding to requests for access under this Paragraph 5.7(f)(ii).

### Upon Partial Termination, termination or expiry (as the case may be) or at the end of the Termination Assistance Period (or earlier if this does not adversely affect the Supplier's performance of the Services and the Termination Services and its compliance with the other provisions of this Schedule), each Party shall return to the other Party (or if requested, destroy or delete) all Confidential Information of the other Party in respect of the terminated Services and shall certify that it does not retain the other Party's Confidential Information save to the extent (and for the limited period) that such information needs to be retained by the Party in question for the purposes of providing or receiving any Services or Termination Services or for statutory compliance purposes.

### Except where this Agreement provides otherwise, all licences, leases and authorisations granted by the Authority to the Supplier in relation to the terminated Services shall be terminated with effect from the end of the Termination Assistance Period.

## Assets, Sub-contracts and software

### Following notice of termination or Partial Termination of this Agreement and during the Termination Assistance Period, the Supplier shall not, in respect of the terminated Services, without the Authority's prior written consent:

#### terminate, enter into or vary any Sub-contract except to the extent that such change does not or will not affect the provision of Services or the Fees;

#### (subject to normal maintenance requirements) make material modifications to, or dispose of, any existing Assets or acquire any new Assets; or

#### terminate, enter into or vary any licence for software in connection with the Services.

### Within twenty (20) Working Days of receipt of the up-to-date Registers provided by the Supplier pursuant to Paragraph 5.3(e), the Authority shall provide written notice to the Supplier setting out:

#### which, if any, of the Transferable Assets the Authority requires to be transferred to the Authority and/or the Replacement Supplier in respect of the terminated Services (“Transferring Assets”);

##### which, if any, of:

##### the Exclusive Assets that are not Transferable Assets; and

##### the Non-Exclusive Assets,

the Authority and/or the Replacement Supplier requires the continued use of; and

#### which, if any, of Transferable Contracts the Authority requires to be assigned or novated to the Authority and/or the Replacement Supplier (the “Transferring Contracts”),

in order for the Authority and/or its Replacement Supplier to provide the Services from the expiry of the Termination Assistance Period.  Where requested by the Authority and/or its Replacement Supplier, the Supplier shall provide all reasonable assistance to the Authority and/or its Replacement Supplier to enable it to determine which Transferable Assets and Transferable Contracts the Authority and/or its Replacement Supplier requires to provide the Services or Replacement Services.

### With effect from the expiry of the Termination Assistance Period, the Supplier shall sell the Transferring Assets to the Authority and/or its nominated Replacement Supplier for a consideration equal to their Net Book Value, except where:

#### a Termination Payment is payable by the Authority to the Supplier, in which case, payment for such Assets shall be included within the Termination Payment; or

#### the cost of the Transferring Asset has been partially or fully paid for through the Fees at the time of expiry or termination of this Agreement, in which case the Authority shall pay the Supplier the Net Book Value of the Transferring Asset less the amount already paid through the Fees.

### Risk in the Transferring Assets shall pass to the Authority or the Replacement Supplier (as appropriate) at the end of the Termination Assistance Period and title to the Transferring Assets shall pass to the Authority or the Replacement Supplier (as appropriate) on payment for the same.

### Where the Supplier is notified in accordance with Paragraph 6.2(b) that the Authority and/or the Replacement Supplier requires continued use of any Exclusive Assets that are not Transferable Assets or any Non-Exclusive Assets, the Supplier shall as soon as reasonably practicable:

#### procure a non-exclusive, perpetual, royalty-free licence (or licence on such other terms that have been agreed by the Authority) for the Authority and/or the Replacement Supplier to use such assets (with a right of sub-licence or assignment on the same terms); or failing which

#### procure a suitable alternative to such assets and the Authority or the Replacement Supplier shall bear the reasonable proven costs of procuring the same.

### The Supplier shall as soon as reasonably practicable assign or procure the novation to the Authority and/or the Replacement Supplier of the Transferring Contracts.  The Supplier shall execute such documents and provide such other assistance as the Authority reasonably requires to effect this novation or assignment.

### The Authority shall:

#### accept assignments from the Supplier or join with the Supplier in procuring a novation of each Transferring Contract; and

#### once a Transferring Contract is novated or assigned to the Authority and/or the Replacement Supplier, carry out, perform and discharge all the obligations and liabilities created by or arising under that Transferring Contract and exercise its rights arising under that Transferring Contract, or as applicable, procure that the Replacement Supplier does the same.

### The Supplier shall hold any Transferring Contracts on trust for the Authority until such time as the transfer of the relevant Transferring Contract to the Authority and/or the Replacement Supplier has been effected.

### The Supplier shall indemnify the Authority (and/or the Replacement Supplier, as applicable) against each loss, liability and cost arising out of any claims made by a counterparty to a Transferring Contract which is assigned or novated to the Authority (and/or Replacement Supplier) pursuant to Paragraph 6.6 both:

#### in relation to any matters arising prior to the date of assignment or novation of such Sub-contract; and

#### in relation to any matters arising after the date of assignment or novation of such Sub-contract where the loss, liability or cost arises as a result of the Supplier’s failure to comply with Clauses F1 (Intellectual Property Rights) and/or Clause F2 (Transfer and Licences Granted by the Supplier).

## Supplier Personnel

### The Authority and Supplier agree and acknowledge that in the event of the Supplier ceasing to provide the Services or part of them for any reason, Schedule 9.1 (Staff Transfer) shall apply.

### The Supplier shall not take any step (expressly or implicitly or directly or indirectly by itself or through any other person) to dissuade or discourage any employees engaged in the provision of the Services from transferring their employment to the Authority and/or the Replacement Supplier.

### During the Termination Assistance Period, the Supplier shall give the Authority and/or the Replacement Supplier reasonable access to the Supplier's personnel to present the case for transferring their employment to the Authority and/or the Replacement Supplier.

### The Supplier shall immediately notify the Authority or, at the direction of the Authority, the Replacement Supplier of any period of notice given by the Supplier or received from any person referred to in the Staffing Information, regardless of when such notice takes effect.

### The Supplier shall not for a period of twelve (12) months from the date of transfer re-employ or re-engage or entice any employees, suppliers or Sub-contractors whose employment or engagement is transferred to the Authority and/or the Replacement Supplier, except that this paragraph shall not apply where the employee, supplier or Sub-contractor applies in response to a public advertisement of a vacancy.

## Fees

### During the Termination Assistance Period (or for such shorter period as the Authority may require the Supplier to provide the Termination Services), the Authority shall pay the Fees to the Supplier in respect of the Termination Services in accordance with the rates set out in the Exit Plan (but shall not be required to pay costs in excess of the estimate set out in the Exit Plan).  If the scope or timing of the Termination Services is changed and this results in a change to the costs of such Termination Services, the estimate may be varied in accordance with the Change Control Procedure.

### Where the Authority requests an extension to the Termination Services beyond the Termination Assistance Period in accordance with Paragraph 5.2:

#### where more than six (6) months’ notice is provided, the same rate as set out in the Exit Plan (or the Fees when not stated in the Exit Plan) shall be payable; and

#### where less than six (6) months’ notice is provided, no more than 1.2 times the rate as set out in the Exit Plan (or the Fees when not stated in the Exit Plan) shall be payable.

### For the purpose of calculating the costs of providing the Termination Services for inclusion in the Exit Plan or, if no Exit Plan has been agreed, the costs of providing Termination Services shall be determined in accordance with the Change Control Procedure.

### Except as otherwise expressly specified in this Agreement, the Supplier shall not make any charges for the services provided by the Supplier pursuant to, and the Authority shall not be obliged to pay for costs incurred by the Supplier in relation to its compliance with, this Schedule including the preparation and implementation of the Exit Plan and any activities mutually agreed between the Parties to carry on after the expiry of the Termination Assistance Period.

## Apportionments

### All outgoings and expenses (including any remuneration due) and all rents, royalties and other periodical payments receivable in respect of the Transferring Assets and Transferring Contracts shall be apportioned between the Authority and the Supplier and/or the Replacement Supplier and the Supplier (as applicable) as follows:

#### the amounts shall be annualised and divided by three-hundred and sixty-five (365) to reach a daily rate;

#### the Authority shall be responsible for (or shall procure that the Replacement Supplier shall be responsible for) or entitled to (as the case may be) that part of the value of the invoice pro rata to the number of complete days following the transfer, multiplied by the daily rate; and

#### the Supplier shall be responsible for or entitled to (as the case may be) the rest of the invoice.

### Each Party shall pay (and/or the Authority shall procure that the Replacement Supplier shall pay) any monies due under Paragraph 9.1 as soon as reasonably practicable.

# ANNEX 1: Scope of the Termination Services

## The Termination Services to be provided by the Supplier shall include such of the following services as the Authority may specify:

#### ceasing all non-critical Software changes (except where agreed in writing with the Authority);

#### notifying the Sub-contractors of procedures to be followed during the Termination Assistance Period and providing management to ensure these procedures are followed;

#### providing assistance and expertise as necessary to examine all operational and business processes (including all supporting documentation) in place and re-writing and implementing processes and procedures such that they are appropriate for use by the Authority and/or the Replacement Supplier after the end of the Termination Assistance Period;

#### delivering to the Authority the existing systems support profiles, monitoring or system logs, problem tracking/resolution documentation and status reports all relating to the twelve (12) month period immediately prior to the commencement of the Termination Services;

#### providing details of work volumes and staffing requirements over the twelve (12) month period immediately prior to the commencement of the Termination Services;

#### with respect to work in progress as at the end of the Termination Assistance Period, documenting the current status and stabilising for continuity during transition;

#### providing the Authority with any problem logs which have not previously been provided to the Authority;

#### providing assistance and expertise as necessary to examine all governance and reports in place for the provision of the Services and re-writing and implementing these during and for a period of twelve (12) months after the Termination Assistance Period;

#### providing assistance and expertise as necessary to examine all relevant roles and responsibilities in place for the provision of the Services and re-writing and implementing these such that they are appropriate for the continuation of the Services after the Termination Assistance Period;

#### reviewing all Software libraries used in connection with the Services and providing details of these to the Authority and/or the Replacement Supplier;

#### providing assistance and expertise as necessary to support the Authority and/or the Replacement Supplier develop the migration plan for business operations and Authority Data to the Replacement Supplier, which may include migration approach, testing of plans, contingency options, and handling of historic or archived Authority Data;

#### provide all necessary support, equipment, tools, and Software such as data migration services and/or Automated Programming Interfaces, in order to enable and support the execution of the migration plan by the Authority and/or Replacement Supplier;

#### making available to the Authority and/or the Replacement Supplier expertise to analyse training requirements and provide all necessary training for the use of tools by such staff as are nominated by the Authority (acting reasonably) at the time of termination or expiry;

#### assisting in establishing naming conventions for any new production site;

#### analysing and providing information about capacity and performance requirements, processor requirements and bandwidth requirements, and known planned requirements for capacity growth across these areas;

#### generating a computer listing of the Source Code of [insert details of relevant Software] in a form and on media reasonably requested by the Authority;

#### agreeing with the Authority a handover plan for all of the Supplier’s responsibilities as set out in Schedule 2.4 (Security Requirements);

#### delivering copies of the production databases (with content listings) to the Authority's and/or the Replacement Supplier's operations staff (on appropriate media) as reasonably requested by the Authority;

#### assisting with the loading, testing and implementation of the production databases;

#### assisting in the execution of a parallel operation until the effective date of expiry or termination of this Agreement;

#### in respect of the maintenance and support of the Supplier System, providing historical performance data for the duration of the Agreement;

#### assisting in the execution of a parallel operation of the maintenance and support of the Supplier System until the end of the Termination Assistance Period or as otherwise specified by the Authority (provided that these Services shall end on a date no later than the end of the Termination Assistance Period);

#### providing an information pack listing and describing the Services for use by the Authority in the procurement of the Replacement Services;

#### answering all reasonable questions from the Authority and/or the Replacement Supplier regarding the Services;

#### agreeing with the Authority and/or the Replacement Supplier a plan for the migration of the Authority Data to the Authority and/or the Replacement Supplier;

#### providing access to the Authority and/or the Replacement Supplier during the Termination Assistance Period and for a period not exceeding 6 months afterwards for the purpose of the smooth transfer of the Services to the Authority and/or the Replacement Supplier:

##### to information and documentation relating to the Transferring Services that is in the possession or control of the Supplier or its Sub-contractors (and the Supplier agrees and shall procure that its Sub-contractors do not destroy or dispose of that information within this period) including the right to take reasonable copies of that material; and

##### following reasonable notice and during the Supplier's normal business hours, to members of the Supplier Personnel who have been involved in the provision or management of the Services and who are still employed or engaged by the Supplier or its Sub-contractors; and

#### knowledge transfer services, including:

##### transferring all training material and providing appropriate training to those Authority and/or Replacement Supplier staff responsible for internal training in connection with the provision of the Services;

##### providing for transfer to the Authority and/or the Replacement Supplier of all knowledge reasonably required for the provision of the Services which may, as appropriate, include information, records and documents; and

##### providing the Supplier and/or the Replacement Supplier with access to such members of the Supplier's or its Sub-contractors' personnel as have been involved in the design, development, provision or management of the Services and who are still employed or engaged by the Supplier or its Sub-contractors.

### The Supplier shall:

    - provide a documented plan relating to the training matters referred to in Paragraph 1.1(k) for agreement by the Authority at the time of termination or expiry of this Agreement;

co-operate fully in the execution of the handover plan agreed pursuant to Paragraph 1.1(o), providing skills and expertise of a suitable standard; and

fully co-operate in the execution of the Authority Database migration plan agreed pursuant to Paragraph 1.1(w), providing skills and expertise of a reasonably acceptable standard.

### To facilitate the transfer of knowledge from the Supplier to the Authority and/or its Replacement Supplier, the Supplier shall provide a detailed explanation of the procedures and operations used to provide the Services, the change management process and other procedures to the operations personnel of the Authority and/or the Replacement Supplier.

### The information which the Supplier shall provide to the Authority and/or the Replacement Supplier pursuant to Paragraph 1.1(y) shall include:

#### copies of up-to-date procedures and operations manuals;

#### product information;

#### agreements with third party suppliers of goods and services which are to be transferred to the Authority and/or the Replacement Supplier;

#### key support contact details for third party supplier personnel under contracts which are to be assigned or novated to the Authority pursuant to this Schedule;

#### information regarding any unresolved faults in progress at the commencement of the Termination Assistance Period as well as those expected to be in progress at the end of the Termination Assistance Period;

#### details of physical and logical security processes and tools which will be available to the Authority; and

#### any relevant interface information.

### During the Termination Assistance Period the Supplier shall grant any agent or personnel (including employees, consultants and Suppliers) of the Replacement Supplier and/or the Authority access, during business hours and upon reasonable prior written notice, to any Sites for the purpose of effecting a prompt knowledge transfer provided that:

#### any such agent or personnel (including employees, consultants and suppliers) having access to any Sites pursuant to this Paragraph 1.5 shall:

##### sign a confidentiality undertaking in favour of the Supplier (in such form as the Supplier shall reasonably require); and

##### during each period of access comply with the security, systems and facilities operating procedures of the Supplier relevant to such Site and that the Authority deems reasonable; and

#### the Authority and/or the Replacement Supplier shall pay the reasonable, proven and proper costs of the Supplier incurred in facilitating such access.

# SCHEDULE 8.6 - SERVICE CONTINUITY PLAN AND CORPORATE RESOLUTION PLANNING

## Part 1:  Service Continuity Plan

## Definitions

### In this Schedule, the following definitions shall apply:

| “Business Continuity Plan” | has the meaning given in Paragraph 2.2(a)(ii); |
| --- | --- |
| “Business Continuity Services” | has the meaning given in Paragraph 4.2(b); |
| “Department” | a body listed in one of the following sub-categories of the Central Government classification of the Public Sector Classification Guide, as published and amended from time to time by the Office for National Statistics: #### Government Department; or #### Non-Ministerial Department. |
| “Disaster” | the occurrence of one or more events which, either separately or cumulatively, mean that the Services, or a material part of the Services will be unavailable for a period of fourteen (14) days or which is reasonably anticipated will mean that the Services or a material part of the Services will be unavailable for that period; |
| “Disaster Recovery Plan” | has the meaning given in Paragraph 2.2(a)(iii); |
| “Disaster Recovery Services” | the services embodied in the processes and procedures for restoring the Services following the occurrence of a Disaster; |
| “Disaster Recovery System” | the system identified by the Supplier in the Supplier Solution which shall be used for the purpose of delivering the Disaster Recovery Services; |
| “Insolvency Continuity Plan” | has the meaning given in Paragraph 2.2(a)(iv). |
| “Related Service Provider” | any person who provides services to the Authority in relation to this Agreement from time to time; |
| “Review Report” | has the meaning given in Paragraphs 7.2(a) to 7.2(c); |
| “Service Continuity Plan” | means the plan prepared pursuant to Paragraph 2 of this Schedule which incorporates the Business Continuity Plan, Disaster Recovery Plan and the Insolvency Continuity Plan; |

## Service Continuity Plan

### Within forty (40) Working Days from the Effective Date the Supplier shall prepare and deliver to the Authority for the Authority’s written approval a plan, which shall detail the processes and arrangements that the Supplier shall follow to:

#### ensure continuity of the business processes and operations supported by the Services following any failure or disruption of any element of the Services (including where caused by an Insolvency Event of the Supplier, any Key Sub-contractor and/or any Supplier Group member); and

#### the recovery of the Services in the event of a Disaster.

### The Service Continuity Plan shall:

#### be divided into four parts:

##### Part A which shall set out general principles applicable to the Service Continuity Plan;

##### Part B which shall relate to business continuity (the “Business Continuity Plan”);

##### Part C which shall relate to disaster recovery (the “Disaster Recovery Plan”);

##### Part D which shall relate to an Insolvency Event of the Supplier, any Key Sub-contractors and/or any Supplier Group member (the “Insolvency Continuity Plan”); and

#### unless otherwise required by the Authority in writing, be based upon and be consistent with the provisions of Paragraphs 3, 4, 5 and 6.

### Following receipt of the draft Service Continuity Plan from the Supplier, the Authority shall:

#### review and comment on the draft Service Continuity Plan as soon as reasonably practicable; and

#### notify the Supplier in writing that it approves or rejects the draft Service Continuity Plan no later than twenty (20) Working Days after the date on which the draft Service Continuity Plan is first delivered to the Authority.

### If the Authority rejects the draft Service Continuity Plan:

#### the Authority shall inform the Supplier in writing of its reasons for its rejection; and

#### the Supplier shall then revise the draft Service Continuity Plan (taking reasonable account of the Authority's comments) and shall re-submit a revised draft Service Continuity Plan to the Authority for the Authority's approval within twenty (20) Working Days of the date of the Authority's notice of rejection.  The provisions of Paragraph 2.3 and this Paragraph 2.4 shall apply again to any resubmitted draft Service Continuity Plan, provided that either Party may refer any disputed matters for resolution by the Dispute Resolution Procedure at any time.

## Service Continuity Plan: Part A – General principles and requirements

### Part A of the Service Continuity Plan shall:

#### set out how the business continuity, disaster recovery and insolvency continuity elements of the plan link to each other;

#### provide details of how the invocation of any element of the Service Continuity Plan may impact upon the operation of the Services and any services provided to the Authority by a Related Service Provider;

#### contain an obligation upon the Supplier to liaise with the Authority and (at the Authority's request) any Related Service Provider with respect to issues concerning business continuity, disaster recovery and insolvency continuity where applicable;

#### detail how the Service Continuity Plan links and interoperates with any overarching and/or connected disaster recovery, business continuity and/or insolvency continuity plan of the Authority and any of its other Related Service Providers in each case as notified to the Supplier by the Authority from time to time;

#### contain a communication strategy including details of an incident and problem management service and advice and help desk facility which can be accessed via multi-channels (including but without limitation a web-site (with FAQs), e-mail, phone and fax) for both portable and desk top configurations, where required by the Authority;

#### contain a risk analysis, including:

##### failure or disruption scenarios and assessments and estimates of frequency of occurrence;

##### identification of any single points of failure within the Services and processes for managing the risks arising therefrom;

##### identification of risks arising from the interaction of the Services with the services provided by a Related Service Provider;

##### identification of risks arising from an Insolvency Event of the Supplier, any Key Sub-contractors and/or Supplier Group member; and

##### a business impact analysis (detailing the impact on business processes and operations) of different anticipated failures or disruptions;

#### provide for documentation of processes, including business processes, and procedures;

#### set out key contact details (including roles and responsibilities) for the Supplier (and any Sub-contractors) and for the Authority;

#### identify the procedures for reverting to “normal service”;

#### set out method(s) of recovering or updating data collected (or which ought to have been collected) during a failure or disruption to ensure that there is no more than the accepted amount of data loss and to preserve data integrity;

#### identify the responsibilities (if any) that the Authority has agreed it will assume in the event of the invocation of the Service Continuity Plan; and

#### provide for the provision of technical advice and assistance to key contacts at the Authority as notified by the Authority from time to time to inform decisions in support of the Authority’s business continuity plans.

### The Service Continuity Plan shall be designed so as to ensure that:

#### the Services are provided in accordance with this Agreement at all times during and after the invocation of the Service Continuity Plan;

#### the adverse impact of any Disaster; service failure; an Insolvency Event of the Supplier, any Key Sub-contractor and/or any Supplier Group member; or disruption on the operations of the Authority, is minimal as far as reasonably possible;

#### it complies with the relevant provisions of ISO/IEC 27002 and all other industry standards from time to time in force; and

#### there is a process for the management of disaster recovery testing detailed in the Service Continuity Plan.

### The Service Continuity Plan shall be upgradeable and sufficiently flexible to support any changes to the Services, to the business processes facilitated by and the business operations supported by the Services, and/or changes to the Supplier Group structure.

### The Supplier shall not be entitled to any relief from its obligations relating to the Customer Service Standards, Tender Minimum Performance Levels and RNOs or to any increase in the Fees to the extent that a Disaster occurs as a consequence of any breach by the Supplier of this Agreement.

## Service Continuity Plan: Part B - Business Continuity

## Principles and contents

### The Business Continuity Plan shall set out the arrangements that are to be invoked to ensure that the business processes and operations facilitated by the Services remain supported and to ensure continuity of the business operations supported by the Services including, unless the Authority expressly states otherwise in writing:

#### the alternative processes (including business processes), options and responsibilities that may be adopted in the event of a failure in or disruption to the Services; and

#### the steps to be taken by the Supplier upon resumption of the Services in order to address any prevailing effect of the failure or disruption including a root cause analysis of the failure or disruption.

### The Business Continuity Plan shall:

#### address the various possible levels of failures of or disruptions to the Services;

#### set out the services to be provided and the steps to be taken to remedy the different levels of failures of and disruption to the Services (such services and steps, the “Business Continuity Services”);

#### specify any applicable Customer Service Standards, Tender Minimum Performance Levels and RNOs with respect to the provision of the Business Continuity Services and details of any agreed relaxation to the Customer Service Standards, Tender Minimum Performance Levels and RNOs in respect of other Services during any period of invocation of the Business Continuity Plan; and

#### clearly set out the conditions and/or circumstances under which the Business Continuity Plan is invoked.

## Service Continuity Plan: Part C – Disaster Recovery

## Principles and contents

### The Disaster Recovery Plan shall be designed so as to ensure that upon the occurrence of a Disaster the Supplier ensures continuity of the business operations of the Authority supported by the Services following any Disaster or during any period of service failure or disruption with, as far as reasonably possible, minimal adverse impact.

### The Disaster Recovery Plan shall be invoked only upon the occurrence of a Disaster.

### The Disaster Recovery Plan shall include the following:

#### the technical design and build specification of the Disaster Recovery System;

#### details of the procedures and processes to be put in place by the Supplier in relation to the Disaster Recovery System and the provision of the Disaster Recovery Services and any testing of the same including but not limited to the following:

##### data centre and disaster recovery site audits;

##### backup methodology and details of the Supplier's approach to data back-up and data verification;

##### identification of all potential disaster scenarios;

##### risk analysis;

##### documentation of processes and procedures;

##### hardware configuration details;

##### network planning including details of all relevant data networks and communication links;

##### invocation rules;

##### Service recovery procedures; and

##### steps to be taken upon resumption of the Services to address any prevailing effect of the failure or disruption of the Services;

#### any applicable Customer Service Standards, Tender Minimum Performance Levels and RNOs with respect to the provision of the Disaster Recovery Services and details of any agreed relaxation to the Customer Service Standards, Tender Minimum Performance Levels and RNOs in respect of other Services during any period of invocation of the Disaster Recovery Plan;

#### details of how the Supplier shall ensure compliance with security standards ensuring that compliance is maintained for any period during which the Disaster Recovery Plan is invoked;

#### access controls to any disaster recovery sites used by the Supplier in relation to its obligations pursuant to this Schedule; and

#### testing and management arrangements.

## Service Continuity Plan: Part D – Insolvency Continuity Plan

## Principles and contents

### The Insolvency Continuity Plan shall be designed by the Supplier to permit continuity of the business operations of the Authority supported by the Services through continued provision of the Services following an Insolvency Event of the Supplier, any Key Sub-contractor and/or any Supplier Group member with, as far as reasonably possible, minimal adverse impact.

### The Insolvency Continuity Plan shall include the following:

#### communication strategies which are designed to minimise the potential disruption to the provision of the Services, including key contact details in respect of the supply chain and key contact details for operational and contract Supplier Personnel, Key Sub-contractor personnel and Supplier Group member personnel;

#### identification, explanation, assessment and an impact analysis of risks in respect of dependencies between the Supplier, Key Sub-contractors and Supplier Group members where failure of those dependencies could reasonably have an adverse impact on the Services;

#### plans to manage and mitigate identified risks;

#### details of the roles and responsibilities of the Supplier, Key Sub-contractors and/or Supplier Group members to minimise and mitigate the effects of an Insolvency Event of such persons on the Services;

#### details of the recovery team to be put in place by the Supplier (which may include representatives of the Supplier, Key Sub-contractors and Supplier Group members); and

#### sufficient detail to enable an appointed insolvency practitioner to invoke the plan in the event of an Insolvency Event of the Supplier.

## Review and amendment of the Service Continuity Plan

### The Supplier shall review and update the Service Continuity Plan (and the risk analysis on which it is based):

#### on a regular basis and as a minimum once every six (6) months;

#### within three calendar months of the Service Continuity Plan (or any part) having been invoked pursuant to Paragraph 9;

#### within fourteen (14) days of a Financial Distress Event;

#### within thirty (30) days of a Corporate Change Event; and

#### where the Authority requests any additional reviews (over and above those provided for in Paragraphs 7.1(a) to 7.1(d)) by notifying the Supplier to such effect in writing, whereupon the Supplier shall conduct such reviews in accordance with the Authority's written requirements.  Prior to starting its review, the Supplier shall provide an accurate written estimate of the total costs payable by the Authority for the Authority’s approval.  The costs of both Parties of any such additional reviews shall be met by the Authority except that the Supplier shall not be entitled to charge the Authority for any costs that it may incur above any estimate without the Authority’s prior written approval.

### Each review of the Service Continuity Plan pursuant to Paragraph 7.1 shall be a review of the procedures and methodologies set out in the Service Continuity Plan and shall assess their suitability having regard to any change to the Services or any underlying business processes and operations facilitated by or supported by the Services which have taken place since the later of the original approval of the Service Continuity Plan or the last review of the Service Continuity Plan and shall also have regard to any occurrence of any event since that date (or the likelihood of any such event taking place in the foreseeable future) which may increase the likelihood of the need to invoke the Service Continuity Plan.  The review shall be completed by the Supplier within the period required by the Service Continuity Plan or, if no such period is required, within such period as the Authority shall reasonably require.  The Supplier shall, within twenty (20) Working Days of the conclusion of each such review of the Service Continuity Plan, provide to the Authority a report (a “Review Report”) setting out:

#### the findings of the review;

#### any changes in the risk profile associated with the Services; and

#### the Supplier's proposals (the “Supplier's Proposals”) for addressing any changes in the risk profile and its proposals for amendments to the Service Continuity Plan following the review detailing the impact (if any and to the extent that the Supplier can reasonably be expected to be aware of the same) that the implementation of such proposals may have on any services or systems provided by a third party.

### Following receipt of the Review Report and the Supplier’s Proposals, the Authority shall:

#### review and comment on the Review Report and the Supplier’s Proposals as soon as reasonably practicable; and

#### notify the Supplier in writing that it approves or rejects the Review Report and the Supplier’s Proposals no later than twenty (20) Working Days after the date on which they are first delivered to the Authority.

### If the Authority rejects the Review Report and/or the Supplier’s Proposals:

#### the Authority shall inform the Supplier in writing of its reasons for its rejection; and

#### the Supplier shall then revise the Review Report and/or the Supplier’s Proposals as the case may be (taking reasonable account of the Authority's comments and carrying out any necessary actions in connection with the revision) and shall re-submit a revised Review Report and/or revised Supplier’s Proposals to the Authority for the Authority's approval within twenty (20) Working Days of the date of the Authority's notice of rejection.  The provisions of Paragraph 7.3 and this Paragraph 7.4 shall apply again to any resubmitted Review Report and Supplier’s Proposals, provided that either Party may refer any disputed matters for resolution by the Dispute Resolution Procedure at any time.

### The Supplier shall as soon as is reasonably practicable after receiving the Authority's approval of the Supplier's Proposals (having regard to the significance of any risks highlighted in the Review Report) effect any change in its practices or procedures necessary so as to give effect to the Supplier's Proposals.  Any such change shall be at the Supplier’s expense unless it can be reasonably shown that the changes are required because of a material change to the risk profile of the Services.

## Testing of the Service Continuity Plan

### The Supplier shall test the Service Continuity Plan on a regular basis (and in any event not less than once in every Contract Year).  Subject to Paragraph 8.2, the Authority may require the Supplier to conduct additional tests of some or all aspects of the Service Continuity Plan at any time where the Authority considers it necessary, including where there has been any change to the Services or any underlying business processes, or on the occurrence of any event which may increase the likelihood of the need to implement the Service Continuity Plan.

### If the Authority requires an additional test of the Service Continuity Plan, it shall give the Supplier written notice and the Supplier shall conduct the test in accordance with the Authority's requirements and the relevant provisions of the Service Continuity Plan.  The Supplier's costs of the additional test shall be borne by the Authority unless the Service Continuity Plan fails the additional test in which case the Supplier's costs of that failed test shall be borne by the Supplier.

### The Supplier shall undertake and manage testing of the Service Continuity Plan in full consultation with the Authority and shall liaise with the Authority in respect of the planning, performance, and review, of each test, and shall comply with the reasonable requirements of the Authority in this regard.  Each test shall be carried out under the supervision of the Authority or its nominee.

### The Supplier shall ensure that any use by it or any Sub-contractor of “live” data in such testing is first approved with the Authority. Copies of live test data used in any such testing shall be (if so required by the Authority) destroyed or returned to the Authority on completion of the test.

### The Supplier shall, within twenty (20) Working Days of the conclusion of each test, provide to the Authority a report setting out:

#### the outcome of the test;

#### any failures in the Service Continuity Plan (including the Service Continuity Plan's procedures) revealed by the test; and

#### the Supplier's proposals for remedying any such failures.

### Following each test, the Supplier shall take all measures requested by the Authority, (including requests for the re-testing of the Service Continuity Plan) to remedy any failures in the Service Continuity Plan and such remedial activity and re-testing shall be completed by the Supplier, at no additional cost to the Authority, by the date reasonably required by the Authority and set out in such notice.

### For the avoidance of doubt, the carrying out of a test of the Service Continuity Plan (including a test of the Service Continuity Plan’s procedures) shall not relieve the Supplier of any of its obligations under this Agreement.

### The Supplier shall also perform a test of the Service Continuity Plan in the event of any major reconfiguration of the Services or as otherwise reasonably requested by the Authority.

## Invocation of the Service Continuity Plan

### In the event of a loss of any critical part of the Service or a Disaster, the Supplier shall immediately invoke the business continuity and disaster recovery provisions in the Service Continuity Plan, including any linked elements in other parts of the Service Continuity Plan, and shall inform the Authority promptly of such invocation.  In all other instances the Supplier shall invoke the business continuity and disaster recovery plan elements only with the prior consent of the Authority.

### The Insolvency Continuity Plan element of the Service Continuity Plans, including any linked elements in other parts of the Service Continuity Plan, shall be invoked by the Supplier:

#### where an Insolvency Event of a Key Sub-contractor and/or Supplier Group member (other than the Supplier) could reasonably be expected to adversely affect delivery of the Services; and/or

#### where there is an Insolvency Event of the Supplier and the insolvency arrangements enable the Supplier to invoke the plan;

PART 2: CORPORATE RESOLUTION PLANNING

## Service status and Supplier Status

### This Agreement is a Critical Service Contract.

### The Supplier shall notify the Authority in writing within five (5) Working Days of the Effective Date and throughout the Term within one-hundred and twenty (120) days after each Accounting Reference Date as to whether or not it is a Public Sector Dependent Supplier.

## Provision of Corporate Resolution Planning information

### Paragraphs 11 to 13 of this Part 2 shall apply if this Agreement has been specified as a Critical Service Contract under Paragraph 10.1 of this Part 2 or the Supplier is or becomes a Public Sector Dependent Supplier.

### Subject to Paragraphs 11.6, 11.10 and 11.11 of this Part 2:

#### the Supplier shall provide the Relevant Authority with the CRP Information within sixty (60) days of the Effective Date; and

#### except where it has already been provided in accordance with Paragraph 11.2(a) of this Part 2, where the Supplier is a Public Sector Dependent Supplier, it shall provide the Relevant Authority with the CRP Information within sixty (60) days of the date of the Relevant Authority’s request.

### The Supplier shall ensure that the CRP Information:

#### is full, comprehensive, accurate and up to date;

#### is split into two parts:

##### Group Structure Information and Resolution Commentary;

##### UK Public Service / CNI Contract Information

#### and is structured and presented in accordance with the requirements and explanatory notes set out at Annex I of the latest published version of the Resolution Planning Guidance published by the Cabinet Office Government Commercial Function and available at https://www.gov.uk/government/publications/the-outsourcing-playbook and contains the level of detail required (adapted as necessary to the Supplier’s circumstances);

#### incorporates any additional commentary, supporting documents and evidence which would reasonably be required by the Relevant Authority to understand and consider the information for approval;

#### provides a clear description and explanation of the Supplier Group members that have agreements for goods, services or works provision in respect of UK Public Sector Business and/or Critical National Infrastructure and the nature of those agreements; and

#### complies with the requirements set out at Appendix I (Group Structure Information and Resolution Commentary) and Appendix II (UK Public Sector / CNI Contract Information) respectively.

### Following receipt by the Relevant Authority of the CRP Information pursuant to Paragraphs 11.2, 11.8 and 11.9 of this Part 2, the Supplier and the Relevant Authority shall discuss in good faith the contents of the CRP Information and:

#### where the Authority is the Relevant Authority, the Authority shall; and

#### where the Cabinet Office Markets and Suppliers Team is the Relevant Authority, the Authority shall use reasonable endeavours to procure that the Cabinet Office Markets and Suppliers Team shall,

#### no later than sixty (60) days after the date on which the CRP Information was delivered by the Supplier either provide an Assurance to the Supplier that it approves the CRP Information or that it rejects it.

### If the Relevant Authority rejects the CRP Information:

#### the Authority shall (and shall procure that the Cabinet Office Markets and Suppliers Team shall) inform the Supplier in writing of its reasons for its rejection; and

#### the Supplier shall revise the CRP Information, taking reasonable account of the Relevant Authority’s comments, and shall re-submit the CRP Information to the Relevant Authority for approval within thirty (30) days of the date of the Relevant Authority’s rejection.  The provisions of paragraph 11.3 to 11.5 of this Part 2 shall apply again to any resubmitted CRP Information provided that either Party may refer any disputed matters for resolution by the Dispute Resolution Procedure at any time.

### Where the Supplier has already provided CRP Information to a Department(or, in the case of a Strategic Supplier, to the Cabinet Office Markets and Suppliers Team) and has received an Assurance of its CRP Information from that Department (or, in the case of a Strategic Supplier, from the Cabinet Office Markets and Suppliers Team), then provided that the Assurance remains Valid, the Supplier shall not be required to provide the CRP Information or updated CRP Information under Paragraphs 11.2 and 11.8(a) to 11.8(c) of this Part 2 if it provides a copy of the Valid Assurance to the Authority on or before the date on which the CRP Information would otherwise have been required.

### An Assurance shall be deemed Valid for the purposes of Paragraph 11.6 of this Part 2 if:

#### in respect of the Supplier’s obligations under Paragraph 11.2:

##### the CRP Information on which the Assurance was based was provided to the Department providing the Assurance (or, in the case of Strategic Suppliers, to the Cabinet Office Markets and Suppliers Team) within the twelve (12) months prior to the deadline by which the CRP Information would otherwise have been required under Paragraph 11.2; and

##### no Corporate Change Events or Financial Distress Events (or events which would be deemed to be Corporate Change Events or Financial Distress Events if this Agreement had then been in force) have occurred since the date on which the CRP Information was provided; and

#### in respect of the Supplier’s obligations under Paragraphs 11.8(a) to 11.8(c), the CRP Information on which the Assurance was based was provided to the Department providing the Assurance (or, in the case of Strategic Suppliers, to the Cabinet Office Markets and Suppliers Team) after the date of the event triggering the obligation to provide the CRP Information under Paragraphs 11.8(a) to 11.8(c).

### Subject to Paragraph 11.6, if this Agreement is a Critical Service Contract, the Supplier shall provide an updated version of the CRP Information (or, in the case of Paragraph 11.8(c) of this Part 2 its initial CRP Information) to the Relevant Authority:

#### within fourteen (14) days of the occurrence of a Financial Distress Event (along with any additional highly confidential information no longer exempted from disclosure under Paragraph 11.11 of this Part 2);

#### within thirty (30) days of a Corporate Change Event unless not required pursuant to Paragraph 11.10;

#### within thirty (30) days of the date that:

##### the credit rating(s) of each of the Supplier and its Parent Undertakings fail to meet any of the criteria specified in Paragraph 11.10; or

##### none of the credit rating agencies specified at Paragraph 11.10 hold a public credit rating for the Supplier or any of its Parent Undertakings; and

#### in any event, within six (6) months after each Accounting Reference Date or within fifteen (15) months of the date of the previous Assurance received from the Relevant Authority (whichever is the earlier), unless:

##### updated CRP Information has been provided under any of Paragraphs 11.8(a) 11.8(b) or 11.8(c) since the most recent Accounting Reference Date (being no more than twelve (12) months previously) within the timescales that would ordinarily be required for the provision of that information under this Paragraph 11.8(d); or

##### unless not required pursuant to Paragraph 11.10

### Where the Supplier is a Public Sector Dependent Supplier and this Agreement is not a Critical Service Contract, then on the occurrence of any of the events specified in Paragraphs 11.8(a) to (d) of this Part 2, the Supplier shall provide at the request of the Relevant Authority and within the applicable timescales for each event as set out in Paragraph 11.8 (or such longer timescales as may be notified to the Supplier by the Authority), the CRP Information to the Relevant Authority.

### Where the Supplier or a Parent Undertaking of the Supplier has a credit rating of either:

##### Aa3 or better from Moody’s;

##### AA- or better from Standard and Poors;

##### AA- or better from Fitch;

the Supplier will not be required to provide the CRP Information unless or until either (i) a Financial Distress Event occurs or (ii) the Supplier and its Parent Undertakings cease to fulfil the criteria set out in this Paragraph 11.10, in which cases the Supplier shall provide the updated version of the CRP Information in accordance with paragraph 11.8.

### Subject to Paragraph 13, where the Supplier demonstrates to the reasonable satisfaction of the Relevant Authority that a particular item of CRP Information is highly confidential, the Supplier may, having orally disclosed and discussed that information with the Relevant Authority, redact or omit that information from the CRP Information provided that if a Financial Distress Event occurs, this exemption shall no longer apply and the Supplier shall promptly provide the relevant information to the Relevant Authority to the extent required under Paragraph 11.8.

## Termination rights

### The Authority shall be entitled to terminate this Agreement under Clause I1.1(b) (Termination by the Authority) if the Supplier is required to provide CRP Information under Paragraph 11 of this Part 2 and either:

#### the Supplier fails to provide the CRP Information within four (4) months of the Effective Date if this is a Critical Service Contract or otherwise within four (4) months of the Relevant Authority’s request; or

#### the Supplier fails to obtain an Assurance from the Relevant Authority within four (4) months of the date that it was first required to provide the CRP Information under this Agreement.

## Confidentiality and usage of CRP information

### The Authority agrees to keep the CRP Information confidential and use it only to understand the implications of an Insolvency Event of the Supplier and/or Supplier Group members on its UK Public Sector Business and/or services in respect of CNI and to enable contingency planning to maintain service continuity for end users and protect CNI in such eventuality.

### Where the Relevant Authority is the Cabinet Office Markets and Suppliers Team, at the Supplier’s request, the Authority shall use reasonable endeavours to procure that the Cabinet Office enters into a confidentiality and usage agreement with the Supplier containing terms no less stringent than those placed on the Authority under paragraph 13.1 of this Part 2 and Clause F6.

### The Supplier shall use reasonable endeavours to obtain consent from any third party which has restricted the disclosure of the CRP Information to enable disclosure of that information to the Relevant Authority pursuant to Paragraph 11 of this Part 2 subject, where necessary, to the Relevant Authority entering into an appropriate confidentiality agreement in the form required by the third party.

### Where the Supplier is unable to procure consent pursuant to Paragraph 13.3 of this Part 2, the Supplier shall use all reasonable endeavours to disclose the CRP Information to the fullest extent possible by limiting the amount of information it withholds including by:

            - redacting only those parts of the information which are subject to such obligations of confidentiality;

            - providing the information in a form that does not breach its obligations of confidentiality including (where possible) by:

              - summarising the information;

              - grouping the information;

              - anonymising the information; and

              - presenting the information in general terms.

### The Supplier shall provide the Relevant Authority with contact details of any third party which has not provided consent to disclose CRP Information where that third party is also a public sector body and where the Supplier is legally permitted to do so.

APPENDIX I

Group structure information and resolution commentary

- The Supplier shall:

  - provide sufficient information to allow the Relevant Authority to understand the implications on the Supplier Group’s UK Public Sector Business and CNI contracts listed pursuant to Appendix II if the Supplier or another member of the Supplier Group is subject to an Insolvency Event.

  - ensure that the information is presented so as to provide a simple, effective and easily understood overview of the Supplier Group; and

  - provide full details of the importance of each member of the Supplier Group to the Supplier Group’s UK Public Sector Business and CNI contracts listed pursuant to Appendix II and the dependencies between each.

APPENDIX II

UK Public Sector / CNI contract information

- The Supplier shall:

  - provide details of all agreements held by members of the Supplier Group where those agreements are for goods, services or works provision and:

    - are with any UK public sector bodies including: central Government departments and their arms-length bodies and agencies, non-departmental public bodies, NHS bodies, local authorities, health bodies, police fire and rescue, education bodies and the devolved administrations;

    - are with any private sector entities where the end recipient of the service, goods or works provision is any of the bodies set out in paragraph 1.1.1 of this Appendix II and where the member of the Supplier Group is acting as a Key Sub-contractor under the agreement with the end recipient; or

    - involve or could reasonably be considered to involve CNI;

  - provide the Relevant Authority with a copy of the latest version of each underlying contract worth more than five million pounds (£5m) per contract year and their related key sub-contracts, which shall be included as embedded documents within the CRP Information or via a directly accessible link;

# SCHEDULE 8.7 - CONDUCT OF CLAIMS

# 1	Indemnities

### This Schedule shall apply to the conduct, by a Party from whom an indemnity is sought under this Agreement (the “Indemnifier”), of claims made by a third person against a party having (or claiming to have) the benefit of the indemnity (the “Beneficiary”).

### If the Beneficiary receives any notice of any claim for which it appears that the Beneficiary is, or may become, entitled to indemnification under this Agreement (a “Claim”), the Beneficiary shall give notice in writing to the Indemnifier as soon as reasonably practicable and in any event within ten (10) Working Days of receipt of the same.

### Subject to Paragraph 2, on the giving of a notice by the Beneficiary, where it appears that the Beneficiary is or may be entitled to indemnification from the Indemnifier in respect of all (but not part only) of the liability arising out of the Claim, the Indemnifier shall (subject to providing the Beneficiary with a secured indemnity to its reasonable satisfaction against all costs and expenses that it may incur by reason of such action) be entitled to dispute the Claim in the name of the Beneficiary at the Indemnifier’s own expense and take conduct of any defence, dispute, compromise or appeal of the Claim and of any incidental negotiations relating to the Claim.  If the Indemnifier does elect to conduct the Claim, the Beneficiary shall give the Indemnifier all reasonable cooperation, access and assistance for the purposes of such Claim and, subject to Paragraph 2.2, the Beneficiary shall not make any admission which could be prejudicial to the defence or settlement of the Claim without the prior written consent of the Indemnifier.

### With respect to any Claim conducted by the Indemnifier pursuant to Paragraph 1.3:

#### the Indemnifier shall keep the Beneficiary fully informed and consult with it about material elements of the conduct of the Claim;

#### the Indemnifier shall not bring the name of the Beneficiary into disrepute;

#### the Indemnifier shall not pay or settle such Claim without the prior written consent of the Beneficiary, such consent not to be unreasonably withheld or delayed; and

#### the Indemnifier shall conduct the Claim with all due diligence.

### The Beneficiary shall be entitled to have conduct of the Claim and shall be free to pay or settle any Claim on such terms as it thinks fit and without prejudice to its rights and remedies under this Agreement if:

#### the Indemnifier is not entitled to take conduct of the Claim in accordance with Paragraph 1.3;

#### the Indemnifier fails to notify the Beneficiary in writing of its intention to take conduct of the relevant Claim within ten (10) Working Days of the notice from the Beneficiary or if the Indemnifier notifies the Beneficiary in writing that it does not intend to take conduct of the Claim; or

#### the Indemnifier fails to comply in any material respect with the provisions of Paragraph 1.4.

## Sensitive Claims

### With respect to any Claim which the Beneficiary, acting reasonably, considers is likely to have an adverse impact on the general public's perception of the Beneficiary (a “Sensitive Claim”), the Indemnifier shall be entitled to take conduct of any defence, dispute, compromise or appeal of the Sensitive Claim only with the Beneficiary's prior written consent.  If the Beneficiary withholds such consent and elects to conduct the defence, dispute, compromise or appeal of the Sensitive Claim itself, it shall conduct the Sensitive Claim with all due diligence and if it fails to do so, the Indemnifier shall only be liable to indemnify the Beneficiary in respect of that amount which would have been recoverable by the Beneficiary had it conducted the Sensitive Claim with all due diligence.

### The Beneficiary shall be free at any time to give written notice to the Indemnifier that it is retaining or taking over (as the case may be) the conduct of any Claim, to which Paragraph 1.3 applies if, in the reasonable opinion of the Beneficiary, the Claim is, or has become, a Sensitive Claim.

## Recovery of sums

### If the Indemnifier pays to the Beneficiary an amount in respect of an indemnity and the Beneficiary subsequently recovers (whether by payment, discount, credit, saving, relief or other benefit or otherwise) a sum which is directly referable to the fact, matter, event or circumstances giving rise to the Claim, the Beneficiary shall forthwith repay to the Indemnifier whichever is the lesser of:

#### an amount equal to the sum recovered (or the value of the discount, credit, saving, relief, other benefit or amount otherwise obtained) less any out-of-pocket costs and expenses properly incurred by the Beneficiary in recovering or obtaining the same; and

#### the amount paid to the Beneficiary by the Indemnifier in respect of the Claim under the relevant indemnity.

## Mitigation

### Each of the Authority and the Supplier shall at all times take all reasonable steps to minimise and mitigate any loss for which the relevant Party is entitled to bring a claim against the other Party pursuant to the indemnities in this Schedule.

##### SCHEDULE 8.8 – MANAGEMENT INFORMATION

- General

  - The Supplier grants the Authority a non-exclusive, transferable, perpetual, irrevocable, royalty-free licence to:

use and share with:

      - any Crown Body;

      - any other Contracting Authority; and

      - any other third party as may be agreed by the Authority and the Supplier from time to time (such Supplier's agreement not to be unreasonably withheld); and/or

    - publish (subject to any information that is exempt from disclosure in accordance with the provisions of FOIA being redacted),

- any Management Information supplied to the Authority for the Authority's normal operational activities including but not limited to administering this Agreement, monitoring public expenditure, identifying savings or potential savings and planning future procurement Activity.

Management Information and format

The Supplier agrees to provide timely Management Information and/or MI Reports to the Authority which incorporates the data listed below, in the correct format, and which the Supplier represents and warrants are full, accurate and complete as at the date of provision to the Authority.

| - Management Information required | - Frequency or date required by |
| --- | --- |
| - All MI relating to Customer Service Standards. | - Each at the frequency required and immediately on request |
| - Any material changes to the Supplier’s and/or Guarantor’s organisation that impacts on its ongoing financial viability including details of the revenue replacement strategy and impact awareness on the organisation’s profitability and stability where significant contracts are due to end. | - Immediately |
| - Any proposed Change of Control, changes to the organisational control or group structure of the Supplier and/or the Guarantor, proposed mergers or acquisitions or proposed changes to the Supplier’s financial viability. | - Immediately |
| - Any financial information relating to the Supplier which could include but is not limited to a copy of its annual accounts, annual returns, management accounts, evidence to the Authority’s satisfaction of its assets, liabilities and funding position, and copies of its board papers and board minutes. | - Immediately on request |
| - Where a Guarantee has been provided in accordance with Clause B1.2, a copy of its annual accounts, annual returns, management accounts, evidence to the satisfaction of its assets, liabilities and funding position, and copies of its board papers and board minutes for the Guarantor, including a translation and conversion (profit and loss, balance sheet and key balance sheet notes) into pounds sterling, stating the conversion rate used. | - Immediately on request |
| - Any MI relating to Sub-contracts and Sub-contractors required by Clause E2. | - Immediately on request |
| - Details of the wages, salaries, bonuses and profit sharing arrangements as applicable in respect of all Supplier Personnel. | - Immediately on request |
| - Any further information as the Authority may reasonably request. | - Immediately on request |
| - The number of supplier and end-to-end supply chain staff working on this Agreement (including data on absences) and in what roles, (including identification of whether each staff member is in a management or direct delivery role),including a full-time equivalent (FTE) breakdown. The FTE breakdown should include individual names, individual FTE as well as the total FTE, | - 1st working day of each month |
| - Caseload sizes per adviser (including the maximum caseload sizes of the Supplier Personnel in the end-to-end supply chain). | - Monthly MI Report |
| - The number of people participating within the main element of the Delivery Model. | - Monthly MI Report |
| - All MI relating to the Supplier’s and each Sub-contractors performance and management, including cohort performance against the performance levels and Customer Service Standards, in addition to a composite summary of this performance MI. | - Monthly MI Report |
| - Participant fail to attend rates by Participant group/segment for interviews, group sessions and other interventions. | Monthly MI Report |
| - Participant attendance at face-to-face and group sessions and potentially other agreed channels of engagement within the last two months. | - Monthly MI Report |
| - The percentage of each type of engagement with Participants taking place either in person, via a digital method, via a telephone call, or other medium. | - Monthly MI Report |
| - The names of each Sub-contractor used by the Supplier, the Supplier’s main contact (name, phone number and email address) for each Sub-contractor with an alternative contact for contingency, the Services delivered by each Sub-contractor, the geographic area covered by each Sub-contractor, the amount paid to each Sub-contractor each Month, the Supplier’s risk assessment of the stability of each Sub-contractor, and the Supplier’s contingency plan(s) should a Sub-contractor become insolvent. | - Monthly MI Report |
| - A summary of the Supplier’s compliance with its obligation to pay any undisputed sums which are due from it to a Sub-contractor within thirty (30) days from the receipt of a valid invoice. | - Quarterly MI Report |
| - Analysis of Participant complaints, analysis of trends and themes, and management action plans to reduce future occurrences. | - Quarterly MI Report |
| - Data on the Supplier’s high level order book, and turnover analysis, including but not limited to: the commissioner of each of the Supplier’s contracts, the percentage of the Supplier’s turnover represented by each contract, and contract key dates (e.g. income start and end). | - Quarterly MI Report |
| - Marginal costs information, which is all costs, including financial and time costs, which the Supplier would have incurred to achieve one extra Outcome from each Cohort from which it has earned an Outcome in the immediately preceding twelve (12) months. | - No less frequently than once in each Contract Year in an MI Report |
| - Analysis of data and trends in relation to all Participant job entries by industry. This should include, but is not limited to, insight on markets trends and job vacancy shifts by industry, as well as identification of, and insight on, new vacancy opportunities. | - No less frequently than the more frequent of: - every 6 months - a minimum of 5 working days before each Supplier Relationship Management meeting with the Authority |
| - Details of the Supplier’s policy, process and methodology for its risk assessments of the stability of each Sub-contractor. | within 10 Working Days of the Effective Date, when updated, reviewed or amended by the Supplier, and annually. |
| - A Termination Estimate pursuant to paragraph 11.2 of Schedule 7.2. | - No less frequently than every six months. |
| - The Supplier's Personnel List containing all Supplier Personnel who are at the date of the list wholly or mainly engaged in or assigned to the provision of the Services. | - No less frequently than every six months commencing in the 13th month of the Referral Period. |

The Authority may from time to time make changes to the data it requires the Supplier to provide in a MI Report including to the data required or format of the report and notify such changes to the Supplier.  The Authority shall give notice in writing of any such change to the MI Report and shall specify the date from which such changes to the content or format of the MI Reports shall be effective which date shall be at least thirty (30) calendar days following the date of the notice.

If the Authority changes the data required or format of the MI Report at any time, then the Supplier agrees to provide all future MI Reports in accordance with such notification.

The Authority may provide the Supplier with supplemental guidance for completing the MI Report or submitting MI Reports from time to time which may for example indicate which fields are mandatory and which are optional.  The Supplier agrees to complete the MI Report in accordance with any such guidance.

The Authority shall have the right from time to time (on reasonable written notice) to amend the nature of the Management Information which the Supplier is required to supply to the Authority.

Frequency and coverage

All MI Reports must be returned to the Authority on or prior to the Reporting Date every month during the Term and thereafter, until all transactions relating to Agreements to which the Supplier is a party have permanently ceased.

The MI Report should be used (among other things) to report activity and transactions occurring during the month(s) to which the MI Report relates.

Unless otherwise notified to the Supplier by the Authority, the Supplier must return the MI Report for each month(s) even where there are no transactions to report in the relevant month (a "Nil Return").

The Supplier must inform the Authority of any errors or corrections to the Management Information:

    - in the next MI Report due immediately following discovery of the error by the Supplier; or

as a result of the Authority querying any data contained in an MI Report.

Submission of the MI Report

- The completed MI Report shall be completed electronically and returned to the Authority by uploading and/or sending the MI Report in accordance with the instructions notified by the Authority to the Supplier from time to time.  The Supplier agrees to comply with any such instructions provided they do not materially increase the burden on the Supplier.

Defective Management Information

The Supplier acknowledges that it is essential that the Authority receives timely and accurate Management Information pursuant to this Agreement because Management Information is used by the Authority to inform strategic decision making.

Following an MI Failure the Authority may issue reminders to the Supplier or require the Supplier to rectify defects in the MI Report provided to the Authority.  The Supplier shall rectify any deficient or incomplete MI Report as soon as possible and not more than five (5) Working Days following receipt of any such reminder.

Meetings

- The Supplier agrees to attend meetings between the Authority and the Supplier in person  to discuss the circumstances of any MI Failure(s) at the request of the Authority (without prejudice to any other rights the Authority may have).  If the Authority requests such a meeting the Supplier shall propose measures to ensure that the MI Failures are rectified and do not occur in the future.  The Authority and the Supplier shall document these measures and continue to monitor the Supplier's performance.

MI Admin Fees

If, in any rolling three (3) month period, two (2) or more MI Failures occur, the Supplier acknowledges and agrees that the Authority shall have the right to invoice the Supplier for MI Admin Fees and (subject to paragraph 7.2) in respect of any MI Failures as they arise in subsequent months.

If, following activation of the Authority's right to charge Admin Fee(s) in respect of MI Failures pursuant to paragraph 7.1, the Supplier submits the monthly MI Report for two (2) consecutive months and no MI Failure occurs then the right to charge the Admin Fee(s) shall lapse.  For the avoidance of doubt the Authority shall not be prevented from exercising such right again during the Term if the conditions in paragraph 7.1 are met.

The Supplier acknowledges and agrees that the MI Admin Fees are a fair reflection of the additional costs incurred by the Authority as a result of the Supplier failing to supply Management Information as required by this Agreement.

The Authority shall notify the Supplier if any MI Admin Fees arise pursuant to paragraph 7.1 above and shall be entitled to invoice the Supplier for such MI Admin Fees, which shall be payable by the Supplier within thirty (30) days of the date of the relevant invoice.  Any exercise by the Authority of its rights under this paragraph 7.4 shall be without prejudice to any other rights that may arise pursuant to the terms of this Agreement.