## Sheet1
MILESTONE PAYMENTS
A | B | C | D | E
Milestone Number | Milestone Claim Date | Description | Criteria | Firm Price £
1 | 2019-07-01 | cSRD Delivery | A | FOIA 2000, Section 43, Commercial Interests
2 | 2019-07-01 | Integrated Test Evaluation and Acceptance Plan submitted to WDT | A
3 | 2019-09-01 | ATE (Indra) Programme launch | B
4 | 2019-09-01 | Quality Assurance Plan submitted to the WDT | A
5 | 2019-12-01 | ATE System Requirement Review Held | C
6 | 2020-02-01 | ATE PDR | C
7 | 2020-03-01 | Rotors Running Re-Arming Army (RRRA) Courseware Delivered | A
8 | 2020-03-01 | Delta Presentation for existing Personnel Complete | B
9 | 2020-05-01 | MTE (PTSL) Programme Launch | B
10 | 2020-05-01 | FDT Courseware Delivered | A
11 | 2020-06-01 | ATE CDR | C
12 | 2020-11-01 | FDT Completed | A
13 | 2020-12-01 | MTE CDR | C
14 | 2020-12-01 | DSE Update Complete | B
15 | 2021-06-01 | RRRA Media Delivered | B
16 | 2021-08-01 | Maintainer Courseware Steady State Complete | A
17 | 2021-11-01 | MTE Factory Acceptance Test Readiness Review | C
18 | 2022-01-01 | MTE Site Acceptance Test Readiness Review | C
19 | 2022-04-01 | MTE Compliance workshops held | C
20 | 2022-06-01 | ATE Factory Acceptance Test Readiness Review | C
21 | 2022-09-01 | ATE Site Acceptance Test Readiness Review | C
22 | 2023-02-01 | Aircrew Courseware Steady State Complete | A
23 | 2023-04-01 | ATE Compliance Workshops Held | C
24 | 2023-04-01 | FASGW Training Contract Complete (cSRD Compliant) | D
TOTAL
CRITERIA:
A - Submitted by the Contractor and acknowledged by the Authority to be in a state of sufficient completion and in sufficient detail to reflect adequate progress for the purpose of signature of the Milestone claim concerned whilst recognising that further discussion may be required to achieve final acceptance in accordance with the Contract.
B - Written statement from the Contractor, endorsed by the Authority, confirming that the event has been successfully completed.
C - Agreed Minutes and Action Plan issued.
D - Written statement from the Authority confirming that delivery of all articles are complete and cSRD compliant.