## Sheet1
# | CLARIFICATION | RESPONSE
1 | Heavy duty loadliner - use ? | To be able to take large water tanks and sharp tools, so not brittle plastic
2 | Double cabs do not come with spare wheels ? | Please provide a spare wheeel for all vehicles
3 | Tow ball & twin Electrics is the 2nd feed to be 13 or 7 pin | All Vehicles:- Second feed to be the new 13pin with a connector/converter to use the older7 pin.
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30

## Sheet2
17
7. The retained substation sits in the proposed hard landscape area. Looking at its current position and level we are concerned that it may sit low within the area and water may therefore fall towards and into the substation. Please confirm this is acceptable or the drainage design for interface around the retained substation? LDA to comment
8. Is the removed knee rail to be re-used anywhere? Not unless it can be used in the current design?
9. We will need to change the routing of the irrigation system around the footpath/tree to be removed. (Dwg LC401-LPR-NPK-L-DGA-0007-004). The proposed path location also runs very close to the main line at it’s southern/eastern end and some ducting and re-connection may be required where it ducts under the existing footpath LDA to comment
10. There are several manhole covers onsite that are not identified on the drawings. Please confirm all these need to be raised or are they now redundant and can be removed? Should these not have been picked up on the survey? If so I will ask them to reconfirm
11. Should there be insufficient site won material to create the landform we assume additional imported material would not be required to make up the shortfall and the mound would simply be reduced in size? The mounding shown in the approved planning drawing is the minimum height required so if additional soil is required then it will need to be imported. Details of soil specification should have been provided.
12. Are we able to use the carpark as our compound? The car park adjacent the site will be available for site set up, however damage to existing landscaping will need to be avoided/rectified.
13. Please confirm section drawing 0150 is correct and as design intent. According to dwg 0104 the path is meant to run at a constant and even grade from top of slope (6.55) to bottom (6.43). If this is the case then the existing hard paved levels at either end of the path are generally lower than the landscape areas in between (7.02-7.10) meaning the path will need to be cut down into the existing landscape by around 600mm with banking on either side. This banking is implied on dwg 0104 but not to the full length of the path and only to the northern side. Please clarify. LDA to comment
14. Is any drainage required around the new entrance? Are drains required in the paving to prevent water running onto adjacent highways footpath or are the new hard surfaces to be set to fall towards the soft areas potentially requiring land drains? LDA to comment
15. The existing tree to be moved is unwell and actually likely to be dead. This also applies to many of the other trees in the avenue along Temple Mills Lane. Please confirm if allowance should be made for replacing all the trees? No allowances for replacement. LDA to comment on tree to be removed.
16. The brick unit/substation/housing seems to be secured with a timber door. Are there actually any utilities in this building which need to be removed? If so, please provide the utility/service drawings for the works areas so we can make appropriate contact with the affected utility providers. TBC
17. Please confirm if soil validation reports will need to be provided for this project and if so the details for this procedure. Evidence of type/source/quality of any soil to imported to site will need to be provided
18. Please confirm if maintenance is required and for what time period? Note that no defects liability can be provided for the soft works if we are not maintaining them. Please provide a price for 12 months and a price for 18 months.
19. Question 17 of the SECTION 2: TECHNICAL AND PROFESSIONAL ABILITY ITT asks for ‘As evidence please state how will you ensure the campsite remains fully operational during the works’. Having visited site we are unclear as to where the campsite is and how this would impact our works. Please confirm and clarify where the campsite is so we can appropriately address this concern. Please ignore this comment, it is not relevant to the works.