Latest/Revised Deliverables and Payment Schedule Table

|  | Project Deliverables | Detail of Deliverables | Responsible Party | Payment Schedule, Date of completion, end (e.g. by week 2): |
| --- | --- | --- | --- | --- |
| 1 | Kick off Meeting | Meeting to discuss the proposed scope and approach to the project (as defined in the bid/project specification) and gather stakeholder input. Agreement of timetable for further deliverables (listed below) | Contractor, Defra Project Manager, SWS Taskforce and Project Advisory Group | Week 1 (week immediately after contract is awarded) |
| 2 | Refined Project Plan | A refined project plan sent to Defra, SWS Taskforce and Project Advisory Group. The project plan will provide an updated methodology and timetable (beyond the original proposal) following the kick-off meeting. | Contractor, Defra Project Manager, SWS Taskforce and Project Advisory Group. | End of week 3 |
| 3 | Project Plan update Meeting | Discussion of the project plan to agree its outlook and reach consensus on next steps | Contractor, Defra Project Manager, SWS Taskforce and Project Advisory Group | End of week 4 |
| 4 | Project Management Meeting | Project Management Review meeting between the Contractor presents and Defra and / SWS Taskforce on project progress. | Contractor, Defra Project Manager, SWS Taskforce | End of week 8 |
| The details and dates of the following deliverables will be agreed between Defra, the SWS Taskforce and the successful contractor. |  |  |  |  |
| 5 | Progress review Presentation (Data findings) | Meeting between Defra, SWS Taskforce, Project Advisory Group and the Contractor to discuss progress and next steps (suggested completion date for data gathering). | Contractor, Defra, SWS Taskforce and Project Advisory Group to review and input | End of week 16 End of week 14 (50% payment) |
| 6 | Progress review Presentation (Economic modelling) | Meeting between Defra, SWS Taskforce, Project Advisory Group and the Contractor to discuss progress and next steps (suggested completion date for economic modelling). | Contractor, Defra, SWS Taskforce and Project Advisory Group to review and input | End of week 20 Start of week 18 (30% of payment) |
| 7 | Progress review Presentation (Implementation Models) | Contractor presents proposals on potential models of implementation and potential positive/negative consequences. | Contractor, Defra, SWS Taskforce and Project Advisory Group to review and input | Start of week 24 Beginning of week 21 (10% of payment) |
| 8 | Final Report Presentation | Final report to be submitted to Defra. As an independent report authored by the Contractor, no influence on content at this stage by Defra or SWS Taskforce. | Contractor, Defra and SWS Taskforce to review the report regarding service levels and quality. | End of month week 28 Beginning of week 23 (10% balance payment) |