‘Think im gamma need a beer’

William Watson & Mat Richardson Nuclear Resilience Team

February 2020

Contents

Executive Summary	2

Introduction	3

Background	4

RIMNET monitor networks	4

Monitor network support and maintenance	6

Transition to RREMS	6

Options	7

Option 1 - Commission a bridging solution to RREMS	7

Option 2 – Decommission Fixed Monitor network	8

Option 2C - with existing SARAs and additional spectroscopic monitors	10

Option 3 – Recompete existing support contracts with change of scope	11

Implementation	12

Existing Monitoring Network	12

Appendices	14

References	15

# Executive Summary

# Introduction

The fixed network of gamma dose rate monitors makes up just under 40% of the UK’s RIMNET monitoring capability. Currently, the private network that the monitors sit upon terminates in CGI data centres. This solution is not enduring as the RIMNET system will be decommissioned and replaced by a cloud-based application called RREMS (due for completion in December 2021). To ensure RREMS can communicate and receive data from the fixed monitors, a new computing interface needs to be developed to facilitate the two-way information exchange between the monitors and the application.

In addition to the need for this new interface, the existing monitor support and maintenance contract with Ultra Electronics is due to expire in July 2022. This paper outlines several options to maintain the existing national monitor network capability in view of the dates for RREMS deployment and monitor contract renewal.

# Background

As part of BEIS’ Lead Government Department (LGD) responsibilities, they are responsible for the management of the Radioactive Incident Monitoring Network (RIMNET). RIMNET is the UK Government’s national radiation monitoring and nuclear emergency response system and monitoring network. RIMNET was set up in 1988 following the Chernobyl accident to provide the UK with the capability to monitor the effects from overseas nuclear incidents.

## RIMNET monitor networks

The original RIMNET network was comprised of 96 gamma radiation detectors distributed geographically evenly across the UK. The original monitors were designed and built by Ultra Energy Ltd and are referred to as ‘fixed monitors’ (Geiger-Muller tubes). A BT Cardway network is used to transmit dose rate data over a private MPLS network, routing to both RIMNET Data Centres (Exeter and Waterton).

Figure 1 – Insert caption here

The RIMNET network has more recently been supplemented with an additional 140 gamma dose rate monitors. These are referred to as ‘RIMNET 3 Mobile (R3M) monitors’ (Geiger-Muller tubes) and are sited around the UK coastlines, but also surrounding civil nuclear sites (all operational and some decommissioning sites).

The R3M Gamma Monitor is a self-contained unit designed and manufactured by Ultra Energy Ltd. Each R3M contains a GSM phone and GPS receiver, and has been designed to transmit dose rate and position information in RIMNET Supplementary Data format.  By default, this data is sent via e-mail to the RIMNET Central Database. The R3M comms network makes use of a number of ‘free at the point of use’ services to reduce cost, including:

- Global Positioning Satellite (GPS),

- General Packet Radio Service (GPRS)

- The Internet

A low-cost Simple Mail Transfer Protocol (SMTP) service has been purchased from Amazon (Elastic Compute 2) to facilitate the sending of e-mails over the internet.

Figure 2 provides a simple diagram of the key comms components of the R3M network.

Figure 2 – Insert caption

In response to recommendation FR-7 of the Weightman review, the RIMNET operations team procured several mobile spectroscopic monitors with a view to deploying these within the RIMNET network to complement the existing gamma dose monitors. In September 2016, the Met Office deployed 10 of these monitors at a Met Office site in Camborne, Cornwall. The Met Office have delayed deploying these monitors across the UK and integrating them with the RIMNET system until they receive policy guidance from BEIS. This issue was considered as part of the PHE Monitoring Review conducted between March 2018 and April 2019. However, the review did not provide BEIS with specific guidance on where the monitors should be deployed within the network and how they should be configured. Given this, BEIS are currently reviewing this with the stakeholder community and in conjunction with the options from this paper that are pursued.

## Monitor network support and maintenance

The support and maintenance contract is currently run by Ultra Electronics Ltd. The contract is managed on behalf of BEIS by the Met Office. Ultra were awarded this contract in 2014 following a competition. In 2018, a two-year extension option was exercised in the contract as it was hoped BEIS would receive clarity on future specification for the network in the UK monitoring review published by PHE in 2019. However, as mentioned in the previous section, this review did not provide BEIS with sufficient strategic direction to help define the composition of a future national monitoring network. BEIS subsequently developed a strategic outline case for further investment in the RIMNET monitor network and the procurement of an airborne monitoring capability [ref]. The strategic case was published in April 2020 and supported the BEIS Nuclear Resilience team’s bid into the Government’s Comprehensive Spending Review (CSR) in August 2020. In light of the CSR timelines, the Met Office obtained approval from [Met Office Commercial??] to extend the existing contract until 31st July 2022. Approval was obtained on the proviso that BEIS would utilise this time to update the specification for the existing contract and compete this contract

## Transition to RREMS

The RIMNET System is due to be replaced by the Radiological Response and Emergency Management System (RREMS) towards the end of the 2021-22 FY. Upon completion, data from the R3M network (in the form of emails) will be re-diverted to RREMS via internet. However, the telecommunications network for the fixed monitor network cannot be reconfigured to send data to RREMS and a bespoke technical solution must be implemented to support this requirement. This solution will need to be in place at the start of the parallel running phase for RREMS and RIMNET to allow full testing of the RREMS application.

# Options for monitor support and maintenance

## Option 1 - Commission a bridging solution to RREMS

One option to resolve this issue is to develop a ‘bridge’ from the fixed monitor’s BT Cardway polling system to the new RREMS application. The bridge will be in the form of a fully managed webservice.

BEIS already have received quotations for this service from both CGI Ltd and Ultra Energy Ltd. The requirement was shared with both organisation in 2019 and ??

The webservice will need to be available to RREMS at the point at which parallel running with RIMNET commences. In the CGI proposal [ref] they suggested it would take 4 months to implement, meaning the contract for these services would need to be awarded by June 2021.

|  | CGI Ltd | Ultra Energy Ltd |  |
| --- | --- | --- | --- |
| Development | 69,568 | £98,532 (exc. VAT) |  |
| Annual support charges | £205,488 | £34,650 (exc. VAT) |  |
| Lead time | 4-months | 4 months |  |

#### Assumptions

- The service will need to be competed due to…..

- Parallel running of RREMS and RIMNET could begin as early as October 2021 therefore the contract will need to be run in early 2021 to take account of the solution delivery times.

- The webservice will only support the existing fixed monitor network.

#### Exclusions

- Previous quotes have excluded the infrastructure costs of the BT Cardway system and monitors. The BT Cardway comms are within the scope of Ultra’s contract with the Met Office. This will be an additional one-off cost (circa £10k).

#### Risks

- Significant annual running costs – this requirement can only be removed once the fixed monitors have been decommissioned.

- Need to add section highlighting that Ultra own the IPR for fixed monitors and R3Ms which may impact future providers taking on the service. Solution would be to obtain a licence from Ultra to allow these monitors to be used by other providers.

## Option 2 – Decommission Fixed Monitor network

If the fixed network was replaced with an alternative solution which network wirelessly networked, this would negate the need for a bridging solution.

### Option 2A – Decommission network and do not replace

All 92 monitors in the fixed network would be decommissioned and the RIMNET monitoring network would only consist of R3M monitors.

#### Assumptions

- Terms of contract can be amended prior to 31 July 2022 end date to exclude support and maintenance of fixed monitor network

- Decommissioning can be completed prior RREMS completion date

#### Exclusions

- Decommissioning costs

#### Risks

- Significantly reduced monitoring coverage across the UK. With RIMNET data published quarterly online, BEIS may come under significant pressure from the public and NGOs especially when considering the recent implementation of the new radiation emergency preparedness regulations (REPPIR19).

### Option 2B – Replace with R3M (Gamma)

Procurement and roll-out of 92 new R3M monitors to the current fixed monitor locations and decommissioning of the fixed monitor unit and private data communication network.

93 R3Ms: 93 x £5k = £465k

Cost of calibration per monitor (based on 2019 costs) = £1716.65, therefore: 93 x -£1716.65 = £159,648.45

SIM card costs: 93 x £150/annum = £13.95k/annum

#### Assumptions

- The roll-out of new R3M monitors (92) will take approximately 18-24 months.

- Ultra Energy Ltd will be needed to support the roll-out - Met Office engineer resource cannot be expanded to meet new demand.

- Would be a competition

#### Exclusions

- Decommissioning costs for fixed monitors

- SLA costs

#### Risks

- Temporary reduction in network coverage – It is unlikely that all fixed monitors could be replaced before RIMNET is decommissioned and existing ‘link’ from RREMS to fixed monitors is severed.

- Comms reliability – If fixed monitors are replaced, the entire UK network will reliant on wireless communications. An interruption to wireless services may result in an outage to all UK gamma monitors (Ref Will’s report here).

R3M support and maintenance cost breakdown update for Q3 of 2019-20 (112 monitors):

| Item | Q3 Update | Comments |
| --- | --- | --- |
| Site License / Agreements | £0 |  |
| Rent / Electricity supply | £29,000 |  |
| Comms | £36,618 | SIM cards – £31,018; SMTP - £5,600 |
| Maintenance & Calibration | £86,000 | £50k – calibration of ~30 monitors; £36k – engineers time & materials for maintenance & swap-outs |
| Total | £151,618 |  |

Table 7 – R3M support and maintenance cost breakdown for 2019-20 (112 monitors)

The annual support and maintenance fee for the fixed network in 2018-19 was £855k. This included:

- Annual probe calibrations and monitor repairs

- Pro-active BT Cardway Network Monitoring

- Help Desk (normal working hours)

- Fault Reporting - 24-hours / 7-days a week

- Response for most sites (UK Mainland) 24-hours / 7-days a week), dependant on site access, ferry's and flights (where applicable)

- Monthly Services Reviews and Reporting

The annual fee is split approximately three ways (£285k) between: BT Cardway network monitoring, repairs/maintenance/calibration, and engineers.

If we take the annual repair/maintenance/calibration fee and subtract this by the annual calibration fee for 93 new R3M units to obtain an estimate for a revised annual repair/maintenance fee: £285k – £159.65k = £125.35k

Therefore: total Y1 costs for R3M replacement = £465k + £159.65k + £13.95k + £125.35k = £763.95k

Assumptions:

- Site licences/agreements: Given that most fixed monitors are stationed at Met Office sites, this is not currently charged to BEIS as part of the existing agreement with the Met Office.

- Rent/electricity supply: No charge to BEIS for the same reason given above.

- Existing Service Level Agreement for monitor repairs maintained for these sites

Exclusions:

- Future cost for two-year contract to maintain interface between RREMS and fixed monitor network (approximately £30k/annum)

- Decommissioning costs for fixed monitors

This option provides a cost saving of ~£91k in Y1. However, this will increase once the calibration schedule is revised and once RREMS becomes operational (as the application-monitor network interface is operated and maintained by a chosen supplier).

### Option 2C - with existing SARAs and additional spectroscopic monitors

Procurement and roll-out of 92 new spectrometric monitors to the current fixed monitor locations enabling the decommissioning of the fixed monitor technology and associated comms

If the fixed network of monitors was replaced with a spectrometric technology solution that was wirelessly networked, this would negate the need for bridging solution for RREMS.

Notes from the Monitor paper….

Monitors = (60-11) x £12k = £720k

SARA NMC server maintenance: £38.9k/annum

Based on Kromek’s support and maintenance cost (£1k/annum for diagnostics, labour, and repair estimate with one annual calibration and firmware upgrade): 60 x £1k = £60k

Therefore: £720k + £38.9k + £60k = £818.9k

Assumptions:

- SIM card costs are identical to those currently issued for R3Ms (therefore no additional cost as like-for-like replacement).

- Increased cost for Field Engineers time and materials for maintenance and swap-outs covered in current annual budget for monitor support and maintenance (if cost savings realised through replacement of fixed monitors with R3M monitors)

Exclusions:

- SIM cards with private network access

- Monitor installation costs

## Option 3 – Recompete existing support contracts with change of scope

- Procurement…timescales

- IPR challenges

Assumptions

- ??

Exclusions

- ??

Risks

- ??

## Implementation

#### Procurement

BEIS will be responsible for procuring new services to support the proposed options. This must be done in accordance with……

If an award for Option 1 is made to CGI Ltd, the delivery of this webservice can be managed under the current RIMNET contract change process.

#### Contract Management

Depending upon the option (1-3) chosen, BEIS should consider:

- BEIS managed implementation - The Nuclear Resilience team (ideally the RREMS Service Manager or Service Delivery Manager, or a long-term extension of the Commercial Lead role) manages the new contract directly with the supplier.

- Met Office managed implementation on behalf of BEIS – BEIS could delegate the implementation and running of this service to the Met Office in the event that Option 1 is selected. The Met Office would hand over this responsibility when parallel running commences (or when RIMNET is decommissioned. The current MoU could be adjusted to include the broader responsibilities – the MoU currently covers the period through to August 2024.

In either case, BEIS should maintain the contract for supply.

### Existing Monitoring Network

Should the chosen option require the extension of the monitoring contracts (beyond 31st July 2022) this will require agreement from the Met Office who hold the contract with Ultra Energy Ltd. The current agreement can be terminated at 6-months’ notice; however, this will come with a pro-rata penalty of between £0 – £21,939.

The Met Office have confirmed that in their opinion, the rationale for single tender actions still exists for this service; on the basis that:

- Ultra Energy Ltd are the sole suppliers of the current / existing RIMNET monitors, and have the proprietary rights in the product(s). This means they are the only viable supplier of network support and maintenance services.

- Ultra Energy Ltd are unique in that they are one of a few commercial organisations in the UK to own and operate a radiation calibration cell.

As the situation remains largely the same for 2021-22, the option to Direct Award to ULTRA meets Regulation 32 of EC Directives 2015-

Use of Negotiation Procedures without Call for Competition on the basis of the works, supplies or services can be supplied only by a particular economic operator for any of the following reasons:—

- the aim of the procurement is the creation or acquisition of a unique work of art or artistic performance,

- competition is absent for technical reasons,

- the protection of exclusive rights, including intellectual property rights,

The Met Office have outlined a series of prerequisites for entering into a further contract extension with Ultra Energy Ltd:

- The scope of the requirement does not change.

- BEIS can give a clear, realistic date for the procurement of the new monitoring network requirement (as defined in the Options paper [Ref])

#### Project Delivery

Different resourcing will be required depending upon the option chose –

Option 1 –

- BEIS Procurement and Commercial support to prepare tender details and to manage competitive process.

- BEIS Project Management resource for implementation or (subject to agreement) this responsibility could be delegated to the Met Office. The current MoU could be adjusted to include the broader responsibilities. This responsibility would be handed back to BEIS when RIMNET is decommissioned.

Option 2 –

- BEIS Procurement and Commercial support to prepare tender details and to manage competitive process.

- ??

Option 3 –

- BEIS Procurement and Commercial support to prepare tender details and to manage competitive process.

- ?? Recommendations

# Appendices

# References

© Crown copyright 2017

This publication is licensed under the terms of the Open Government Licence v3.0 except where otherwise stated. To view this licence, visit nationalarchives.gov.uk/doc/open-government-licence/version/3 or write to the Information Policy Team, The National Archives, Kew, London TW9 4DU, or email: psi@nationalarchives.gsi.gov.uk.Where we have identified any third party copyright information you will need to obtain permission from the copyright holders concerned.

This publication available from www.gov.uk/beis

Contact us if you have any enquiries about this publication, including requests for alternative formats, at:

Department for Business, Energy and Industrial Strategy
1 Victoria Street
London SW1H 0ET
Tel: 020 7215 5000

[] ‘Specification for the ZP1221/01 Geiger Muller tube’, 22 March 2012, https://www.gov.uk/government/publications/specification-for-the-zp1221-01-geiger-muller-tube--2

Now 93.

Envinet SARA

There are currently 37 ‘hot spares’ which were procured through the original R3M procurement. The availability of these spares could reduce this cost but this will be dependent on: the minimum number of monitors required for routine swap-outs; the number of ‘hot spares’ required; the requirements set out in a prospective Service Level Agreement (SLA).

Calibration cost will be significantly less year-on-year once calibration schedule for new units moves to four-year cycles. If we assume 50 calibrations/annum, calibration costs would come down to ~£85.8k.

Includes the 11 SARA already procured by the Met Office and assumes the unit cost of the SARA is equivalent to the unit cost of the monitors chosen for the R3M upgrade

A longer-term objective will see the replication of NMC server functionality within RREMS. This cost is not included in the total as it is included in the allocation for the current support and maintenance contract.

BEIS currently budgets ~£1.1m for the fixed and R3M monitor contracts