	[image: image1.jpg]AR
% O B¢l

Department for
Communities and
| ocal Government




	
	



AMENDMENT TO CONTRACT

The details contained in this document form a binding amendment to the Contract referenced below between the Contractor and the Secretary of State for Communities and Local Government (“DCLG”).
Contract title
:
Contract for Communities Rights Programme Grant Administration Services (Lot 2)
Contract reference
:
CPD/004/109/036B
Purchase order no.
:
4500333106
Contractor
:
Groundwork UK
Amendment no.
:
04
Effective date of
: 
1st April 2018
amendment

Details of amendment
:
As follows:


Amendments to Contract Award Letter:


Contract Term:



Delete: ‘Subject to any termination provisions within the Contract, the initial term of the Contract shall commence on 
2 February 2015 (the “Effective Date”) and shall expire on 
31 March 2018.’


Insert:  ‘Subject to any termination provisions within the Contract, the initial term of the Contract shall commence on 2 February 2015 (the “Effective Date”) and shall expire on 30th June 2018.’



Prices and Invoicing, following Paragraph 5:



Insert ‘5a. The firm price for the fourth term (year 4, 1st April 2018 to 30th June 2018) of the Contract is £11,700 (exclusive of Value Added Tax (VAT)).’
Contract Representatives, Paragraph 9:


Delete: 
‘Commercial Representative: -, 


Crown Commercial Service, 1st Floor, Fry Building. 2 Marsham Street, London. SW1P 4DF. 



Tel: -


Email: -


Contract Manager: -, The Department for Communities and Local Government, 1st Floor Fry building, 2 Marsham Street, London. SW1P 4DF. 



Tel: -


Email: -


Insert: 
‘Commercial Representative:, 1st Floor, Fry Building, 2 Marsham Street London SW1P 4DF
Tel: -
Email: -
‘Contract Manager: -, Department for Communities and Local Government, Fry Building, 2 Marsham Street, London, SW1P 4DF
Tel: -
Email: -


Amendments to Annex A – Specification:
Insert:

‘The extended contract period 1st April 2018 to 30th June 2018 is required to enable grants to be paid out until mid February 2018 to align with close down of the Lot 6 technical support packages, and to allow sufficient time for the subsequent close down period of grants and preparation of the final report.
At least 3 months is needed to fully close down a year’s worth of grants. When the application deadline of 31 January has been reached the Lot 6 Contractor will hold their final grant panel(s) and will send to the Contractor final grant approvals in early to mid February 2018.

The Contractor will then send out final grant offer letters and will begin to process payments for final approvals in mid to late February 2018. The final approved groups will then have 4-6 weeks to spend their grant up to 31 March 2018, they will then need to send in their final report and return any underspend.
The closedown activities during the extended period shall consist of ensuring that all applicants spend grant money appropriately in accordance with the terms of the grant offer and as a minimum complete and submit to the Contractor an end of grant report, and where required a staged payment report and/or a Statement of Grant Usage.  

The Contractor shall confirm to the Authority that all grant funding has been spent according to the terms of the grant offers or clawed back, including identifying any underspend, within 3 months of the end of the Programme.
	Key closedown milestones:


	Timescale

	Final date for applications


	31st Jan 2018

	Grant funded activity deadline (for recipients)


	31st Mar 2018

	Progress update to the Authority, including projection of total unspent funds to be repaid


	May 2018

	Final reconciliation and repayment of unspent funds


	June 2018




Amendments to Annex C – Price Schedule

The details set out in Appendix 1 of this Contract Amendment are to be inserted into Annex C accordingly.
Contract value prior to
:
£452,722.86 (ex VAT) 

this amendment



Maximum value of this
:
£11,700.00 (ex VAT)
amendment 
Revised maximum value
:
£464,422.86 (ex VAT)
of the Contract 
Terms and conditions
:
All other terms and conditions shall remain unchanged for this Contract.
	FOR AND ON BEHALF OF THE SECRETARY OF STATE FOR COMMUNITIES AND LOCAL GOVERNMENT
	FOR AND ON BEHALF OF THE CONTRACTOR

	Name:
	Name:

	Title
	Title:

	Signed:
	Signed:

	Date:
	Date:


APPENDIX 1
<REDACTED>

Page 4 of 5
CPD/004/109/036B
DCLG Amendment No.04

[image: image1.jpg]