This contract is made on      	   	day of                        2019

between:

1	THE SECRETARY OF STATE FOR EDUCATION of Sanctuary Buildings, 20 Great Smith Street, London, SW1P 3BT (“DFE” or “the Department”); and

2	The Education and Training Foundation (ETF), registered in 157 -197 Buckingham Palace Road, London, SW1W 9SP and Company registration number 08540597,  (the “Contractor” or “Delivery Partner”)

each a “Party” and together the “Parties”.

It is agreed that:

- this contract, together with the attached schedules and annexes, collectively form the “Contract”; and

- if there is a conflict between the provisions of the clauses of the Contract and the provisions of the schedules, the following order of precedence shall apply:

- (a)	schedule 2 (Terms and Conditions);

- (b)	schedule 1 (Specification);

- (c)	schedules 3 to 11; and

- (d)	schedule 12 (Contractor’s Solution).

- The Contract has been executed on the date stated at the beginning of this page.

Table of Contents

Contract Schedules

Schedule 1 	Specification

Schedule 2	Terms and Conditions

Schedule 3  	Financials

Schedule 4	Key Performance Indicators (KPIs)

Schedule 5	Implementation and Project Plan

Schedule 6   	Change Control Procedure

Schedule 7 	Key Personnel and Key Sub-Contractors

Schedule 8		[Not used]

Schedule 9		Departmental Security Standards

Schedule 10		Data Processing, Personal Data and Data Subjects

Schedule 11 	Commercially Sensitive Information

Schedule 12 	Contractor’s Solution

This Contract shall be governed by and interpreted in accordance with English Law and the parties submit to the jurisdiction of the English courts.

As witness the hands of the parties

Authorised to sign for and on		Authorised to sign for and on

behalf of the Secretary of		behalf of the Education and

State for Education		Training Foundation (ETF)

Signature		Signature

Name in CAPITALS		Name in CAPITALS

CLARE MACDONALD

Position in organisation		Position in organisation

Deputy Director,

Careers Advice and Basic Skills

Address in full		Address in full

Department for Education

Sanctuary Buildings

20 Great Smith Street

London

SW1P 3BT

Date		Date

Schedule 1

The Specification

Policy background

- The Smith Review demonstrates that England has a basic numeracy deficit. This presents a risk to the government’s strategic priority of improving economic productivity, as set out in the Industrial Strategy (2017).

- Over 30% of young people do not achieve a GCSE grade C/4 in English and maths by the age of 16. Within this group, three quarters still have not attained this level of English and Maths by the time they are 19. This means that we lag behind our international competitors. We are the only OECD country where literacy and numeracy amongst 16-24 year olds is no better than 55-65 year olds. This problem is most acute amongst disadvantaged young people. The lowest attainment aligns to some of the most disadvantaged areas in the country – and success is significantly linked to socio-economic background.

- Education providers use the 16-19 study programme, apprenticeship and the Adult Education (AEB) budgets to pay for basic maths courses for students who need to improve their skills. However, the quality of teaching requires further support and there has been minimal, medium-term investment in researching, developing, testing and disseminating mathematics teaching methods that work for a cohort with low prior-attainment.

- At Autumn Budget 2017, £40.3m was committed from financial year 2018/2019 to establish Centres for Excellence across the country to build teaching capacity and spread best practice on what works to improve basic maths.

- The Centres for Excellence programme will build on the success of the Maths Hubs model in schools, adapting it to improve the quality of teaching and learning, and build teaching capacity for the post 16 sector.

- The purpose of the Centres for Excellence programme is to enhance basic maths teaching (up to GCSE and equivalent) so that students 16+ with low prior attainment can improve their skills and secure valuable qualifications.

- The ambition of the programme is to increase the number of young people leaving compulsory education with the necessary basic maths skills to engage with employment.  As a result, we intend to increase the proportion of those at 19 achieving a Level 2 maths qualification, who hadn’t done so by 16. In 2017, this proportion was 20.9%.

Delivery Approach

- The DFE’s delivery approach is designed to separate the activities of the Delivery Partner, the Evaluation Partner and the Centres for Excellence.

Figure 1 – visualisation of the Centres for Excellence programme

The Role of the Delivery Partner

- The DFE Contractor, as the Department’s Delivery Partner, will research, develop, implement, support evaluate and disseminate high quality basic maths teaching approaches that focus on students aged 16+ with low prior attainment.

- Whilst DFE will select and grant fund the Centres for Excellence, they will be operationally managed by the Delivery Partner. The Delivery Partner will be responsible for training, mentoring and supporting the Centres for Excellence to trial the approaches within their institution and maths network.

- The Delivery Partner will monitor and review the Centres for Excellence to establish and maintain exemplary standards of provision to meet both local and national maths priorities.

- The Delivery Partner will support the Centres for Excellence to network and disseminate the new or improved ways of teaching maths to those aged 16 and over.

- The Delivery Partner will also commission an Evaluation Partner to conduct an ongoing, independent and objective evaluation to determine whether the new and improved teaching approaches being trialled are having an impact on the quality of teaching and improving outcomes for students.

The Role of the Evaluation Partner

- The Delivery Partner will contract with an independent Evaluation Partner. The specification of work, costs and selection of the Evaluation Partner will be agreed with the Department. This should be a separate organisation to that of the Delivery Partner and the Delivery Partner and Evaluation Partner shall make clear as to whether any conflicts of interest may exist between the organisations.

- The Evaluation Partner will not be responsible for evaluating the Delivery Partner or the Centres for Excellence. Rather, they will have responsibility for evaluating the impact of the trials of the new teaching approaches on the quality of teaching and attainment.

- The Evaluation Partner will support the Delivery Partner to design robust research methods for the trials of the teaching approaches and will provide an independent, ongoing analysis of whether the teaching approaches being trialled are having an impact.

- The Evaluation Partner will collect, identify and analyse on an ongoing basis quantitative (such as attainment and attendance data) and qualitative data (such as teacher surveys) as proxy measures to determine whether the new approaches are enhancing the quality of post-16 basic maths teaching.

- To determine the impact of the new approaches of post-16 basic maths teaching; the evaluation partner will undertake robust impact evaluation of trials which may, if appropriate, make use of randomised control trials or quasi-experimental methods.

- Where interventions are being trialled, the evaluation partner will be expected to include a control group (i.e. a group of learners undertaking the same provision, but using a standard method of delivery rather than the newly designed one) to compare against the learners receiving the new approaches.

- The Evaluation Partner will only be concerned with whether the teaching approaches are impacting on the quality of teaching. They will not be responsible for directly evaluating the programme, the Delivery Partner or the DFE more broadly.

The Role of the Centres for Excellence

- The DFE has selected 21 Centres for Excellence through a competitive grant application process. The Centres for Excellence will be directly grant funded and grant managed against their conditions of grant funding by the DFE. Full information relating to the guidance and selection process undertaken can be found here: https://www.gov.uk/government/publications/basic-maths-centres-for-excellence-application

- Whilst the Delivery Partner did not have any role in the initial selection process of the Centres, they may be required, if necessary, to manage the selection of additional or replacement Centres in the future.

- The Delivery Partner’s costings are based upon supporting and managing the 21 Centres for Excellence in place.

- The selected Centres, their networks and the Delivery Partner will work together closely. The role of the Centres for Excellence will be to support the Delivery Partner to research, develop and trial the maths teaching approaches. The Centres will be supported by the Delivery Partner through research, good practice case studies, high quality resources, training, mentoring and ongoing evaluation.

- The Centres will develop existing or create new Maths Networks as a platform for sharing and fully embedding best practice to improve maths across their network. Networks may be geographic or non-geographic in nature. The Delivery Partner will support the Centres for Excellence in building and managing this network. DFE expects this network to cover a minimum of 10 institutions, covering a range of different provider types. Over the Initial Term of the Contract, DFE expect the programme to indirectly reach and enhance maths provision for more than 50,000 learners.

- To ensure the programme covers the breadth of the country, at least one Centre for Excellence has been selected per English region, with no more than three Centres for Excellence per any region. Below is the eligibility criteria that the DFE used to select the Centres for Excellence.

| Eligibility Criteria Required to Progress to Application Stage |  |
| --- | --- |
| Criterion | Measured by |
| The total number of students with prior attainment below grade 9-4 for maths in the lead institution to be a minimum of 250. | Measured by the number of students at the end of 16-18 study included in the maths progress measure |
| Institution’s capacity to deliver the programme | Measured by an Ofsted grade of Good or Outstanding |
| Prudent management of public funds | Measured by ESFA financial health data as either Satisfactory or above. |

- Institutions below these criteria were able to apply to be a Centre for Excellence by partnering up with a lead institution that does meet all of the eligibility criteria through a consortium.

- If the lead institution fell below these criteria at any point during the selection process, they became ineligible.

- If there is a drop in criteria during the programme, this will trigger a review of the Centre to determine their suitability to continue to deliver the programme. The Delivery Partner will manage this review process.

- Below is the full application criteria that were used to determine successful applicants:

| Full Application Criteria |  |  |
| --- | --- | --- |
| Criterion | Summary of evidence or examples required | Weight |
| Maths credibility and capacity | - Maths attainment and progress measure performance - Examples of previous maths improvement initiatives - Previous maths workforce development practices - Approaches to innovation in maths teaching | 25% |
| Leadership credibility, capacity and commitment | - Expertise of the nominated senior leader and track record of enhancing learning and teaching and financial accountability - Capacity of the provider to deliver the programme against other existing and proposed initiatives - Evidence of effective maths leadership skills | 25% |
| Partnership and networking credibility | - Evidence of collaborative leadership across multiple providers - Evidence of existing networks and strategic partners - An outline of how the Centre proposes to run its Maths Network, including scope for activities, type of support and scale of reach (number of students and anticipated impact) | 25% |
| Quality of the proposed approach, alignment to the teaching approaches and support for SEND and disadvantaged students | - Evidence of understanding of the teaching themes and proposed pedagogical approaches - An outline of how the Centre might implement a trial of the teaching approach - Evidence of understanding the needs of SEND and disadvantaged students and successful and inclusive teaching practices | 25% |

Development of the Teaching Approaches

- This programme aims to support the post-16 sector to develop, test, deliver and share pedagogical approaches to improve maths teaching for students aged 16+ with low prior attainment. Existing research shows a range of themes (see below) that DFE anticipate will form a core part of the Centres for Excellence work. The Delivery Partner, on the basis of its research and ongoing engagement with the Centres, will identify if any other themes are relevant. They will then use the themes to develop new or adapted approaches with the Centres to improve how students with low prior attainment are taught. The Centres will then trial these approaches before further rollout across their wider maths networks. The themes that DFE require the Delivery Partner to explore are:

- An adapted mastery approach for lower attaining students post-16 – Mastery is an approach used in Maths Hubs to ensure pupils achieve a comprehensive understanding of mathematical concepts and learn how to apply the maths to a variety of contexts using a Shanghai/Singapore approach to teaching maths. DFE anticipate the Centres for Excellence programme will trial an adapted mastery approach that is suitable for the cohort of post-16 low attaining students and relevant to the post-16 timetable and teaching environment.

- Motivating and engaging learners - Evidence suggests that students find re-sitting maths and English qualifications to be a demotivating experience. It is a significant challenge to engage students with low prior attainment to attend classes and to motivate students with catch-up provision. This approach will research, develop and trial engaging approaches to teaching maths to demotivated learners and practical methods to supporting students to overcome any barriers to their engagement.

- Contextualisation of content towards vocational learning - Building on existing research supported by Education Endowment Foundation (EEF), Mathematics Education Innovation (MEI) and CFE Research and other evidence, DFE know that students  may improve their engagement and attainment when maths aligns to their vocational aspirations. In anticipation of the 15 technical routes for T-Levels, DFE will trial embedding route-specific numeracy content in to students’ study programmes. DFE will also consider how this approach applies to ‘Transition Year’ students.

- Use of technology - This theme will research, develop and trial the use of technology, exploring whether there are more efficient or innovative ways to manage and support teaching and learning. This theme will explore the use of prior attainment data, diagnostics tools and online/virtual learning.

Vision of success at the end of the Centres for Excellence Delivery Partner contract

- Through the procurement of the Delivery Partner, DFE expect to:

  - Research best practice in the teaching and delivery of post-16 basic maths

  - Trial different teaching approaches in the Centres

  - Train and support leaders and teachers to deliver the trials of the new, high quality teaching methods

  - Develop and fully embed across Centres, Maths Networks and the country, high quality resources and curriculum

  - Create, develop and support post-16 Maths Networks

  - Evaluate, share and fully embed best practice through Maths Networks and across the post-16 sector.

- The ambition for the Centres for Excellence programme is to substantially enhance the quality of post-16 maths education and, as a result, improve the number of young people securing the vital numeracy skills they need for employment and adult life in modern Britain.

- As a result of the Centres for Excellence programme, DFE intend to increase the proportion of those at 19 achieving a Level 2 maths qualification, who hadn’t done so by 16. In 2017, this proportion was 20.9%.  DFE will also intend to increase the levels of progress that the Centres are able to secure for their students, as measured by the 16-19 basic maths progress measure. DFE will agree with the Delivery Partner in financial year 1 (by March 2019) additional KPIs relating to programme outcomes for future financial years of the programme.

SECTION A – Vision of the Centres for Excellence Programme

A1 	Overall vision

- The Contractor as the Department’s Delivery Partner for the Centres for Excellence Programme will support the Government’s ambition to enhance the teaching and delivery of post-16 basic maths and DFE’s vision to substantially increase the proportion of those at 19 achieving a Level 2 maths qualification, who hadn’t done so by 16.

- In delivering the Specification in Schedule 1 the Delivery Partner will  incorporate the following aspects: 

Capacity

- Ability to provide a comprehensive service nationally while meeting differing regional and local needs.

- Ability to react to developing policy and produce practical evidence-based advice on teaching maths to students 16+ with low prior attainment.

- Ability to liaise with a wide range of mathematical and educational organisations (e.g. learned societies, awarding organisations, sector bodies and education and training stakeholders).

Quality

- Demonstrate a thorough understanding of effective mathematics teaching pedagogy in further education and post-16 settings based on national and international evidence and considerable experience.

- Exhibit a strong approach to conducting research and developing new understanding on what works to improve maths teaching and delivery.

- Demonstrate a high degree of expertise and experience of developing successful professional development programmes for mathematics teachers in a relevant context.

- Demonstrate abilities in providing ongoing mentoring and support for teachers and leaders and equipping them with the tools and resources needed to be successful in their roles.

- Demonstrate robust understanding of approaches to evaluation of all aspects of the programme incorporating effective techniques for measuring success.

- Use of the very best national and international practice.

Demand

- Ability to support expert groups, schools/colleges, adult providers and others to raise awareness amongst schools/colleges/providers and students of the importance of mathematics for the individual and for society more widely.

- Work with relevant stakeholders groups to raise awareness and share good practice.

- Increase teachers’ understanding of the role and importance of teaching models and methods to pupil success.

SECTION B – Managing the Centres for Excellence

B1	Co-ordinating and monitoring the Centres for Excellence

- The Delivery Partner will coordinate and monitor the work of the Centres for Excellence to establish and maintain exemplary standards of provision to meet both local and national priorities.

Delivery Plan

- The Delivery Partner will develop a clear delivery plan for each year of the Centres for Excellence programme, which should be agreed on an annual basis with DFE. This will include:

  - Overall objectives for the Centres for Excellence programme

  - Key outputs and KPIs

  - Clear timelines and milestones

  - Financial plan

  - Risks, issues and mitigation plans

  - Evaluation plan for the Evaluation Partner

- The Delivery Plan for financial years 18/19 and 19/20 is included in Schedule 5 of the contract. The Parties will update Schedule 5 to reflect any changes they agree post contract award, for example, to deliverables, timelines and activity.

Developing Centre Action Plans

- Each Centre for Excellence will be required to develop and submit their own individual action plan for each financial year of the programme.

- The Delivery Partner will support, advise and challenge the Centres for Excellence leadership teams to prioritise, plan, deliver and evaluate their work, to ensure that they meet the DFE’s mathematics education priorities. This includes meeting with each of the Centres for Excellence on a monthly basis and providing them with access to a key contact, whose role will include:

    - Providing challenge and support to each Centre for Excellence on the development of an annual action plan.

    - Negotiating and managing which teaching approaches each Centre will be focussed towards trialling, ensuring a reasonable spread of approaches across all Centres.

    - Supporting Centres in their resource planning and holding them to account to ensure resources are spent responsibly and transparently.

    - Supporting and facilitating networking for their area – ensuring that every Centre has an established maths network, which covers a minimum of 10 other institutions and focuses on improving maths outcomes in the network.

    - Providing monthly reporting information to the DFE on all Centre of Excellence’s performance through an agreed reporting template.

    - Developing, promoting and delivering training and CPD opportunities for the Centre and wider maths network.

    - Encouraging collaboration and resource sharing between the Centres.

Monitoring Centres

- The Delivery Partner will assess the progress and effectiveness of each Centre for Excellence against their action plans, identifying successes and issues. The Delivery Partner will report to and work with the DFE to address issues each month through an agreed reporting template. Where performance is off track, the Delivery Partner will resolve issues and support improved performance. Urgent or serious matters will be escalated to DFE as soon as they become apparent.

- The grant funding to Centres will become repayable (through a future reduction in ESFA funding) if:

- the grant funding is not spent by 31 July of each year of grant funding (or by an alternative date agreed in advance with the ESFA)

- the grant funding is not spent on eligible activities outlined in the application (or variants thereof agreed with the ESFA, using the process described)

- reports on expenditures and outcomes are not submitted

- significant underperformance determined through a formal review

- If the DFE deem that a Centre is not sufficiently meeting its requirements or the lead institution falls below the eligibility criteria at any stage, then the Delivery Partner will coordinate a formal review of the Centre. If this review deems the Centre unsuitable to continue, then the DFE may withhold future grant funding for the Centre. If necessary, the Delivery Partner and the DFE will identify a replacement Centre from the reserve list of applicants or through a further selection process.

Managing the additional grant process for Centres

- The Delivery Partner will, on an annual basis, manage the process by which the Centres can bid for additional resources. For the first financial year (2018-19), 70% of the available grant will be secured as core grant, with the Delivery Partner managing the bidding process for the remaining 30% as additional grant. DFE envisage that the proportions of available grant in future years will  remain at 70% of the available grant secured as core grant, , with the Delivery Partner managing the bidding process for the remaining 30% as additional grant. The Delivery Partner will need to comply with Cabinet Office Grant Standards. The action plans and additional grant recommendations will be approved through the DFE.

- However, we intend to wait until the Delivery Partner is procured and until we have selected the Centres before confirming this percentage. The extent to which we limit the percentage of core grant available will be a risk based judgement against the overall quality, scale of ambition and volume of the applications that we receive. The percentage of additional grant available will be reviewed by DFE and the Delivery Partner on an annual basis.

- The Delivery Partner will scrutinise the Centres’ additional bids and the Delivery Partner will maximise value for money of DFE’s additional grant funding whilst also assuring against any risks. The Delivery Partner will be required to secure approval from the DFE within this process. Factors which the Delivery Partner could consider as part of this process could include:

- The scale of ambition of the Centre for Excellence’s action plan.

- Variances of costs between teaching approaches.

- Adjusting the funding depending on the size of the maths re-sit cohort within the Centre, including adult and apprentice students.

- Adjusting the funding depending on the number of institutions or size of cohort within the maths network.

- London weighting.

- Adjusting the funding depending on geographical variances, such as travel costs.

- The Centres will not be restricted to a predetermined list of activities. Centres may, in principle, include proposals for a wide variety of activities and projects that can help improve the quality of provision at the Centre and within their maths networks, and that address key improvement needs. Some examples of activities include:

- A diagnosis of the Centre’s and/or its Maths Network’s maths quality challenges, and development of a programme of work to address these.

- Professional development activities for teachers, managers, the senior leadership team for the Centre and/or its Maths Network.

- Time release for teachers and staff at the Centre and/or its Maths Network to allow them to participate in the programme of work (in such cases, funding may cover temporary replacement of that staff member).

- Hiring of additional staff members for the Centre and/or its Maths Network whose time will be fully dedicated to the Centres for Excellence programme.

- The collation or development and trialling of new maths teaching resources (such as new textbooks or workbooks).

- The creation, coordination and management of a maths network.

- Evaluation of the Centre’s programme of work.

- However, a number of activities cannot be funded through the Centres for Excellence programme, such as:

- Capital expenditures: spending on the purchase of assets (for example buildings, furniture, fittings) valued at £2,500 or more. The purchasing of information technology and software should demonstrate good value for money and be agreed by DFE and the Delivery Partner in advance.

- Restructuring recommended by an area review process.

- Staff restructuring.

- Independent business reviews.

- Any activities that are not related to the provider’s basic maths skills provision.

- Any activities that the Centre would otherwise be able to access free of charge.

- Formal grant conditions will be managed and monitored by ESFA’s Conditions of Funding Agreement for each institution.

- Core funding will be issued along with general funding allocations by ESFA in September of each year, with subsequent, additional funding (possibly up to 30%) paid in arrears along with future allocations.

- Conditions of Funding will accompany the Centre’s grant, ensuring planned actions are monitored and controlled in line with expectations. Where successful delivery is not demonstrated as part of DFE’s ongoing evaluations, this will trigger a formal review process, which could result in a cut to the Centre’s future funding for participation in the Centres for Excellence Programme and/or removal from the Centres for Excellence Programme.

- DFE will also have mechanisms in place to allow it to recoup funding if a Centre fails to deliver the level of service which was agreed in their action plans. This includes the right for ESFA to review future allocations with a view to reducing in the event of non-delivery or non-compliance with funding conditions.

- Grant offers and conditions of funding will clearly outline how expenditure will be monitored and the required caveats of this expenditure to ensure propriety and regularity are maintained. 

Supporting the Centres to Collaborate

- The Delivery Partner will assist the Centres for Excellence to build high-level professional knowledge, enabling them to learn from each other about effective approaches to basic mathematics improvement.

This will include:

- Coordination of a termly Centres for Excellence Forum meeting for all Centres to network, share good practice and drive forward priorities to improve maths outcomes. This will also be used as a forum for the Delivery Partner and DFE to consult Centres on the future direction of the programme and to seek feedback on any issues.

- Coordination and join-up between Centres working on similar, interrelated activities through termly meetings. This should include specific, networking events relating to the teaching approaches. These will be used to encourage collaboration between Centres to develop best practice and resources relating to each teaching approach.

- Issue monthly bulletins and create online platforms for sharing information between the Centres and wider maths networks

Leadership Training for Centres

- The Delivery Partner will train and develop all Centre’s leadership teams in their role as mathematics system leaders, building strong capability for local leadership of mathematics, ensuring that sufficient talent and expertise is in place within the Centres to lead and deliver improvements to teaching practice that will positively impact on standards. The delivery Partner will plan and deliver high quality and accessible system leadership training to all Centres.

- The Delivery Partner will ensure this training is of high quality and can substantially support and develop Centre leadership teams in their roles. DFE has identified in its KPIs that it expects this training and development package to achieve a 90% rating from evaluation surveys.

SECTION C – Delivering the teaching approaches

- The Delivery Partner will be required to support the government’s ambitions for mathematics education and basic skills delivery through close liaison with DFE’s relevant policy teams.

- The teaching approaches have been identified as good practice from existing research and evidence on what works to enhance the delivery of Post-16 basic skills. They will form the basis of the initial scoping research and trials, however, emerging good practice or innovative approaches could also be considered for further research and development throughout the Centres for Excellence Programme. The Delivery Partner will have a good understanding of the following publications (and any other studies deemed relevant) and how they will build on the findings from previous and ongoing studies, including:

  - CFE Research - Effective practice in the delivery and teaching of post 16 English and mathematics.

  - Behavioural Insights Team (BIT) - Improving engagement and attainment in maths and English courses: insights from behavioural research.

  - Education Endowment Foundation (EEF) – Mathematics Mastery Study.

  - Education Endowment Foundation (EEF) – Embedding contextualisation in English and maths GCSE teaching.

  - University of Nottingham and EEF – Maths for Life.

- The Delivery Partner will research, develop, implement, evaluate and disseminate high quality teaching approaches that focus on students aged 16+ with low prior attainment. Across all teaching approaches, the Delivery Partner shall work closely with the Centres to test, develop and research ideas.

- Over the course of the Initial Term of the Contract, the Delivery Partner will be responsible for:

  - Scoping and developing the teaching approach;

  - Collating, adapting existing resources and teaching materials, and developing new ones;

  - Working with identified Centres to design and plan the trials of the teaching approach;

  - Training teachers in the proposed approach;

  - Implementing the trials and refining the approach based on the trials;

  - Facilitating the evaluation of the trials; and

  - Supporting the Centres to spread best practice across their Network and beyond.

C1	Designing and developing our teaching approaches and supporting resources: An adapted mastery approach for lower attaining students over the age of 16

- For this teaching approach, the Delivery Partner will lead the Centres for Excellence to test how a “mastery” approach (as used in Shanghai and Singapore and modelled by the National Centre for the Teaching of Mathematics in Primary and Secondary Schools) can be adapted successfully for the Post-16 basic maths cohort.

- The Delivery Partner will review existing literature, case studies, best practice and resources to identify how to adapt “mastery” for post-16 students with low prior maths attainment.  This will inform the Delivery Partner’s development and/or adaptation of resources and their plan to implement the mastery trials within selected Centres for Excellence.

Scoping research

- The Delivery Partner will produce a high quality, engaging, publishable report which provides the Centres for Excellence and wider sector with a clear and informative toolkit which enables them to understand and implement a “mastery” teaching approach. This report must be easy for teachers and leaders to understand and use, and will:

  - Include a short literature review of existing, relevant research which summarises and facilitates understanding of mastery approaches. If the Delivery Partner identifies that a literature review already exists, the Delivery Partner should instead focus on making this available in a way the Sector can easily understand, rather than conducting a new literature review.

  - Showcase existing good practice or case studies relating to mastery in schools and the post-16 sector and demonstrate how it could enhance teaching within Centres for Excellence and beyond.

  - Identify, collate and assess appropriateness of existing resources and teaching tools relating to mastery and provide clear guidelines to Centres on how resources will be tested and rolled out further. Analyse the case for developing new, bespoke resources for the post-16 sector and demonstrate a clear timeline on how the Delivery Partner will develop them with input from the Centres and their Maths Networks.

  - Interview relevant key stakeholders with expertise in mastery approaches and consult teachers and leaders across the Centres for Excellence to inform the design of the teaching approach.

  - Provide clear, practical information and instructions about how this teaching approach will be tested further within the Centres for Excellence and wider Maths Networks.

- This will be developed and approved as ready for publication by DfE by 14 August 2019.

Development of Mastery resources

- The Delivery Partner will lead the development of resources – working with the relevant Centres and other partners – to ensure that materials and tools for teaching and accessing mastery are of high quality and able to be made freely available to all providers.

- The Delivery Partner will need to collate and adapt existing resources or develop bespoke, new resources, working closely with the relevant Centres and sector.  Examples of these resources could include, but are not limited to, teacher training modules, teacher guides, pupil textbooks, exercise books, practice books, online lessons, and other mastery-related resources.  The Delivery Partner willenable ongoing access to and dissemination of these resources.

- A resource “pack” to enable centres to teach using a mastery approach should be developed and submitted to the DFE in time to inform the trials. During financial year 2 this will then be delivered by the Delivery Partner (through leadership training, teacher training and ongoing support) to Centres, used for the trials, and further refined (in financial years 2 and 3) in advance of potential further roll-out.

- By financial year 3 (by 31 March 2021), the Delivery Partner will survey students and teachers to identify whether the resources and materials being used are effective and meeting their needs to improve mathematics competence.

Develop Trials

- The Delivery Partner, with input from the Centres and the Evaluation Partner, will design robust, high quality and valid trials of mastery approaches within the Centres and their Maths Networks.

- The plan for these trials will be submitted to DFE by end of financial year 1 (31 March 2019).  This will be further refined and implemented in financial years 2 (by 31 March 2020) and 3 (by 31 March 2021) of the programme.

- The Delivery Partner will need to ensure the evaluation will measure success of the methods being trialled against other variables such as:

  - Staff:Student ratios

  - Disadvantage

  - Prior attainment

- The Evaluation Partner will, on an annual basis, report to DFE on the impact of these trials against robust, pre-determined and agreed data metrics.

Share and embed best practice for mastery through engagement with Centres and their Maths Networks

- In addition to the above work, the Delivery Partner will bring together a group of representatives from the Centres trialling approaches to mastery, on a termly basis, to provide oversight to the teaching approach, to share resources, develop good practice and to network.

- If the Initial Term of the Contract were to be extended from financial year 3 (by 31 March 2021) onwards, the Delivery Partner would support the Centres trialling this approach to showcase and disseminate their findings through their Maths Networks. The Delivery Partner would support the Centre to train and develop teachers and leaders across their Maths Network to fully embed the new teaching practices and resources across other institutions.

C2   Designing and developing our teaching approaches and supporting resources: Motivating and engaging learners

- Building on existing research, DFE know that re-taking maths and English qualifications is a challenging experience for some learners. Students may deploy a range of avoidance behaviours and engaging and motivating students is essential to their learning and attainment.

- The Delivery Partner shall research, develop and test approaches to motivate and engage learners. 

Scoping research

- The Delivery Partner will produce a high quality, engaging, publishable written report which provides the Centres for Excellence and wider sector with a clear and informative toolkit which enables them to understand and implement a teaching approaches designed to enhance motivation and engagement in post-16 maths. This report must be easy for teachers and leaders to understand and use, and should:

  - Include a short literature review of existing, relevant research which summarises and facilitates understanding of approaches to maths engagement and motivation. If the Delivery Partner identifies that a literature review already exists, the Delivery Partner should instead focus on making this available in a way the Sector can easily understand, rather than conducting a new literature review. This should identify opportunities for going further to engage post-16 learners, clearly building on extensive existing literature from the CFE Research, Behavioural Insights Team and other studies.

  - Showcase existing good practice or case studies relating to motivation and engagement in schools and the post-16 sector and demonstrate how it could enhance teaching within Centres for Excellence and beyond.

  - Identify, collate and assess appropriateness of existing resources and teaching tools relating to engagement and motivation and provide clear guidelines to Centres on how resources will be tested and rolled out further. Analyse the case for developing new, bespoke resources for the post-16 sector and demonstrate a clear timeline on how the Delivery Partner will develop them with input from the Centres and their Maths Networks.

  - Interview relevant key stakeholders with expertise in engagement and motivation approaches and consult teachers and leaders across the Centres for Excellence to inform the design of the teaching approach.

  - Provide clear, practical information and instructions about how this teaching approach will be tested further within the Centres for Excellence and wider Maths Networks.

- This will be developed and approved, ready for publication by DFE by 14 August 2019. Research on this teaching approach should cover:

  - Effective approaches to timetabling and curriculum design

  - What works to incentivise attainment – what can we learn from behavioural insights?

  - How effective teacher/learner relationships impact engagement

  - The role of the parent(s)/carer(s) in motivating students

  - The impact of pastoral support from the institution

  - Attitudes towards numeracy/mathematics and overcoming the fear of failure

  - The impact of student disadvantage on student aspiration

Development of engagement and motivation resources

- The Delivery Partner will lead the development of resources – working with the relevant Centres and other partners – to ensure that materials and tools for improving learner engagement and motivation are of high quality and able to be made freely available to all providers.

- The Delivery Partner will need to collate and adapt existing resources or develop bespoke, new resources, working closely with the relevant Centres and sector.  Examples of these resources could include, but are not limited to, teacher training modules, teacher guides, mentoring or pastoral support guides or student communication platforms. The Delivery Partner will enable ongoing access to and dissemination of these resources.

- A resource “pack” to enable Centres to teach using an engagement and motivation approach should be developed and submitted to the DFE in time to inform the trials. During financial year 2 this will then be delivered by the Delivery Partner (through leadership training, teacher training and ongoing support) to Centres, used for the trials, and further refined (in financial years 2 and 3) in advance of potential further roll-out.  By financial year 3 (by 31 March 2021), the Delivery Partner will survey students and teachers to identify whether the resources and materials being used are effective and meeting their needs to improve mathematics competence.

Develop Trials

- The Delivery Partner, with input from the Centres and the Evaluation Partner, will design robust, high quality and valid trials of motivation and engagement approaches within the Centres and their Maths Networks.

- The plan for these trials will be submitted to DFE by end of financial year 1 (31 March 2019).  This will be further refined and implemented in financial years 2 (by 31 March 2020) and 3 (by 31 March 2021) of the programme.

- The Delivery Partner will need to ensure the evaluation will measure success of the methods being trialled against other variables such as:

  - Staff:Student ratios

  - Disadvantage

  - Prior attainment

- The Evaluation Partner will, on an annual basis, report to the Delivery Partner and the DFE on the impact of these trials against robust, pre-determined and agreed data metrics.

Share and embed best practice for engagement and motivation through engagement with Centres and their Maths Networks

- In addition to the above work, the Delivery Partner will bring together a group of representatives from the Centres trialling approaches to engagement and motivation, on a termly basis, to provide oversight to the teaching approach, to share resources, develop good practice and to network.

- If the contract were to be extended from financial year 3 (by 31 March 2021) onwards, the Delivery Partner would support the Centres trialling this approach to showcase and disseminate their findings through their Maths Networks. The Delivery Partner would support the Centre to train and develop teachers and leaders across their Maths Network to fully embed the new teaching practices and resources across other institutions.

C3   Designing and developing our teaching approaches and supporting resources:  Contextualisation of content towards vocational learning

- Research indicates that when Post-16 catch up maths content is contextualised and made relevant towards students’ vocational aspirations, they are potentially more likely to engage. For example, students studying a hair dressing qualification may find it easier to understand, or more engaging to learn about ratios when they are contextualised as problems relating to the mixing of hair dyes, rather than as abstract maths problems.

- Many students study maths qualifications alongside technical/vocational courses. Maths will also form an important part of the 15 new T level routes. As part of this teaching approach, the Delivery Partner will explore how to deliver contextualised and embedded maths within and alongside technical/vocational training, in line with the government’s ambition for a world-class technical education system.

- This work will build on existing work that Mathematics Education Innovation (MEI) is doing with the Education Endowment Foundation (EEF) on embedding contextualisation in English and mathematics in GCSE teaching and other relevant studies deemed appropriate.

- The Delivery Partner will  research, develop and test approaches to contextualising maths. 

Scoping Research

- The Delivery Partner will produce a high quality, engaging, publishable report which provides the Centres for Excellence and wider sector with a clear and informative toolkit which enables them to understand and implement a teaching approach relating to contextualisation. This report must be easy for teachers and leaders to understand and use, and should:

  - Include a short literature review of existing, relevant research which summarises and facilitates understanding of contextualisation approaches. If the Delivery Partner identifies that a literature review already exists, the Delivery Partner should instead focus on making this available in a way the Sector can easily understand, rather than conducting a new literature review.

  - Showcase existing good practice or case studies relating to contextualisation in schools and the post-16 sector and demonstrate how it could enhance teaching within Centres for Excellence and beyond.

  - Identify, collate and assess appropriateness of existing resources and teaching tools relating to contextualisation and provide clear guidelines to Centres on how resources will be tested and rolled out further. Analyse the case for developing new, bespoke resources for the post-16 sector and demonstrate a clear timeline on how the Delivery Partner will develop them with input from the Centres and their Maths Networks.

  - Interview relevant key stakeholders with expertise in contextualisation approaches and consult teachers and leaders across the Centres for Excellence to inform the design of the teaching approach.

  - Provide clear, practical information and instructions about how this teaching approach will be tested further within the Centres for Excellence and wider Maths Networks.

- Research on this teaching approach should cover:

- Approaches to institutional governance and organisation – e.g. a centralised maths department compared to embedding maths within vocational departments.

- An analysis of how to effectively contextualise the GCSE, Functional Skills, T Level and other vocational technical qualifications’ subject content

- A review of existing materials and good practice already taking place within the post-16 sector

- Comparisons with other, international post-16 technical education systems to review lessons learnt

- This will be developed and approved as ready for publication by DfE by 14 August 2019.

Development of contextualisation resources

- The Delivery Partner will lead the development of resources – working with the relevant Centres and other partners – to ensure that materials and tools for teaching and accessing contextualisation are of high quality and able to be made freely available to all providers.

- The Delivery Partner will need to collate and adapt existing resources or develop bespoke, new resources, working closely with the relevant Centres and sector.  Examples of these resources could include, but are not limited to, teacher training modules, teacher guides, pupil textbooks / exercises, practice books, online lessons, and other contextualisation-related resources.  The Delivery Partner should identify how it intends to enable ongoing access to and dissemination of these resources.

- A resource “pack” to enable centres to teach using a contextualisation approach will be developed and submitted to the DFE in time to inform the trials. During financial year 2 this will then be delivered by the Delivery Partner (through leadership training, teacher training and ongoing support) to Centres, used for the trials, and further refined (in financial years 2 and 3) in advance of potential further roll-out.  By financial year 3 (by 31 March 2021), the Delivery Partner will survey students and teachers to identify whether the resources and materials being used are effective and meeting their needs to improve mathematics competence.

Develop Trials

- The Delivery Partner, with input from the Centres and the Evaluation Partner, will design robust, high quality and valid trials of contextualisation approaches within the Centres and their Maths Networks.

- The plan for these trials will be submitted to DFE by end of financial year 1 (31 March 2019).  This will be further refined and implemented in financial years 2 (by 31 March 2020) and 3 (by 31 March 2021) of the programme.

- The Delivery Partner will need to ensure that the evaluation will measure success of the methods being trialled against other variables such as:

  - Staff:Student ratios

  - Disadvantage

  - Prior attainment

- The Evaluation Partner will, on an annual basis, report to the Delivery Partner and the DFE on the impact of these trials against robust, pre-determined and agreed data metrics.

Share and embed best practice for contextualisation through engagement with Centres and their Maths Networks

- In addition to the above work, the Delivery Partner will bring together a group of representatives from the Centres trialling approaches to contextualisation, on a termly basis, to provide oversight to the teaching approach, to share resources, develop good practice and to network.

- If the contract were to be extended from financial year 3 (by 31 March 2021) onwards, the Delivery Partner would support the Centres trialling this approach to showcase and disseminate their findings through their Maths Networks. The Delivery Partner would support the Centre to train and develop teachers and leaders across their Maths Network to fully embed the new teaching practices and resources across other institutions.

C4   Designing and developing our teaching approaches and supporting resources:  Use of technology and data

- The Delivery Partner will research, develop and trial the use of technology, exploring whether there are more efficient, innovative or advanced ways to manage and support teaching and learning.

- The Delivery Partner will research, develop and test approaches to the use of technology to enhance maths teaching and delivery. 

Scoping research

- The Delivery Partner will produce a high quality, engaging, publishable written report which provides the Centres for Excellence and wider sector with a clear and informative toolkit which enables them to understand and implement a teaching approach relating to technology and data. This report must be easy for teachers and leaders to understand and use, and should:

  - Include a short literature review of existing, relevant research which summarises and facilitates understanding of data and technology approaches. If the Delivery Partner identifies that a literature review already exists, the Delivery Partner should instead focus on making this available in a way the Sector can easily understand, rather than conducting a new literature review.

  - Showcase existing good practice or case studies relating to data and technology in schools and the post-16 sector and demonstrate how it could enhance teaching within Centres for Excellence and beyond.

  - Identify, collate and assess appropriateness of existing resources and teaching tools relating to data and technology and provide clear guidelines to Centres on how resources will be tested and rolled out further. Analyse the case for developing new, bespoke resources for the post-16 sector and demonstrate a clear timeline on how the Delivery Partner will develop them with input from the Centres and their Maths Networks.

  - Interview relevant key stakeholders with expertise in data and technology approaches and consult teachers and leaders across the Centres for Excellence to inform the design of the teaching approach.

  - Provide clear, practical information and instructions about how this teaching approach will be tested further within the Centres for Excellence and wider Maths Networks.

- Research on this teaching approach will cover:

  - The availability and use of prior attainment data and contextual data (such as SEND learner requirements and learner behaviour/characteristics) and how information can be used to enhance teaching and delivery. This will analyse the difficulties institutions have in accessing this data from central bodies, whilst also identifying issues surrounding data protection.

  - The effective use of initial assessment and diagnostics tools (such as BKSB, Forskills, Diagnostic Questions and others) and how post-16 institutions can test and develop best practice in their usage.

  - The use of technology and e-learning platforms and how they can be used most effectively to track, deliver and enhance learning and attainment.

This should be developed and approved, ready for publication by DFE by 14 August 2019.

Development of technology and data resources

- The Delivery Partner will lead the development of resources – working with the relevant Centres and other partners – to ensure that materials and tools for using data and technology are of high quality and able to be made freely available to all providers.

- The Delivery Partner will need to collate and adapt existing resources or develop bespoke, new resources, working closely with the relevant Centres and sector.  Examples of these resources could include, but are not limited to e-learning platforms, learner tracking and monitoring systems, online communication platforms, initial assessments and diagnostics tools, online quizzes, smart boards, and other data and technology related resources.  The Delivery Partner will enable ongoing access to and dissemination of these resources.

- A resource “pack” to enable centres to teach using a technology and data approach will be developed and submitted to the DFE in time to inform the trials. During financial year 2 this will then be delivered by the Delivery Partner (through leadership training, teacher training and ongoing support) to Centres, used for the trials, and further refined (in financial years 2 and 3) in advance of potential further roll-out.  By financial year 3 (by 31 March 2021), the Delivery Partner will survey students and teachers to identify whether the resources and materials being used are effective and meeting their needs to improve mathematics competence.

Develop Trials

- The Delivery Partner, with input from the Centres and the Evaluation Partner, will design robust, high quality and valid trials of data and technology approaches within the Centres and their Maths Networks.

- The plan for these trials will be submitted to DFE by end of financial year 1 (31 March 2019).  This will be further refined and implemented in financial years 2 (by 31 March 2020) and 3 (by 31 March 2021) of the programme.

- The Evaluation Partner will need to demonstrate how they will measure success of the methods being trialled against other variables such as:

  - Staff:Student ratios

  - Disadvantage

  - Prior attainment

- The Evaluation Partner will, on an annual basis, report to DFE on the impact of these trials against robust, pre-determined and agreed data metrics.

Share and embed best practice for data and technology through engagement with Centres and their Maths Networks

- In addition to the above work, the Delivery Partner will bring together a group of representatives from the Centres trialling approaches to data and technology, on a termly basis, to provide oversight to the teaching approach, to share resources, develop good practice and to network.

- From financial years 3 (by 31 March 2021) onwards, the Delivery Partner should support the Centres trialling this approach to showcase and disseminate their findings through their Maths Networks. The Delivery Partner will support the Centre to train and develop teachers and leaders across their Maths Network to fully embed the new teaching practices and resources across other institutions.

Section D - Communications and engagement

D1	Communications plan

- The success of the overall programme, and the scale up of the teaching approaches, is largely about fostering a cultural shift in Post-16 basic mathematics teaching. More generally, the Centres for Excellence will need to raise awareness of training opportunities and promote networking and sharing of best practice. The Delivery partner will encourage key stakeholders to engage with their work.

- The Delivery Partner will:

  - Develop and deliver strong, clear messages for teachers about the value of our teaching approaches targeting key audiences and leading to enhanced teaching approaches.

  - Drive up awareness within the post-16 sector of the Centres for Excellence and the opportunities that they can offer to improve outcomes for the entire post-16 basic maths cohort (16-19 students, adults and apprentices).

Important information on the government’s approach to communications:

- In line with the government’s commitment to efficiency controls, there are restrictions on all paid-for communications and marketing activities funded by the Department either delivered directly or indirectly via partner organisations in receipt of funding. The controls apply to most communications activity including printing and publications, events, PR and digital communications activity.

- Exemptions may be granted for essential activities where cost effectiveness and return on investment can be evidenced and where all other no cost or low cost options have been exhausted. The Delivery Partner will consider proposed marketing and communications activity in this context.

- DFE does not expect marketing and communications to be a significant element of the work of the Delivery Partner and would only expect to see necessary activity in this area. The cost of this cannot exceed £100,000 for the Initial Term of the contract. The Delivery Partner will provide a full business case and communications plan for approval by DFE prior to the release of this element of funding.

- DFE will be looking primarily for no cost and low cost approaches, with an emphasis on utilising all existing owned and earned communications channels.  Any paid-for activity will be subject to approval via the marketing and advertising efficiency controls exemptions process.

SECTION E - Project Management

E1 	Management of the project

- DFE and the Delivery Partner shall each appoint a Contract Manager to act on their behalf on the matters set out in, or in connection with, this Contract.

- Contract management and governance arrangements will operate based upon the proposals set out in Schedule 12, and as agreed post contract award.

E2 	Risks and Issues

- The Delivery Partner shall maintain a risk register detailing as a minimum contingencies and countermeasures to mitigate the risks and shall report to the DFE’s Contract Manager..

- Schedule 2

- Terms and Conditions

- CONTENTS

CLAUSE

1	DEFINITIONS AND INTERPRETATION

2	TERM

3	THE SERVICES

4	CONSORTIA

5	TRANSFER AND SUB-CONTRACTING

6	PERSONNEL

7	TUPE

8	CHARGES

9	TAX AND VAT

10	PREVENTION OF CORRUPTION

11	DISCRIMINATION

12	INTELLECTUAL PROPERTY

13	DATA SYSTEMS, HANDLING AND SECURITY

14	PUBLICITY AND PROMOTION

15	CONFIDENTIALITY

16	FREEDOM OF INFORMATION

17	OFFICIAL SECRETS ACT AND FINANCE ACT

18	LIABILITY

19	WARRANTIES AND REPRESENTATIONS

20	FORCE MAJEURE

21	MONITORING AND REMEDIATION

22	STEP-IN RIGHTS

23	TERMINATION

24	RETENDERING AND HANDOVER

25	EXIT MANAGEMENT

26	AUDIT

27	ENTIRE AGREEMENT

28	PARTNERSHIP

29	WAIVER

30	CHANGE CONTROL

31	COUNTERPARTS

32	CONTRACTS (RIGHTS OF THIRD PARTIES) ACT 1999

33	CONFLICTS OF INTEREST

34	FURTHER ASSURANCE

35	NOTICES

36	DISPUTE RESOLUTION

37	GOVERNING LAW AND JURISDICTION

1.	DEFINITIONS AND INTERPRETATION

- 1.1	In the Contract, the following expressions have the following meanings, unless inconsistent with the context:

- “Agreed Programme Branding” means “Centres for Excellence Programme”, or such other branding for the Services as may be agreed between the DFE and the Contractor.

- “Area” means the geographical area within England in respect of which the Contractor is appointed to provide the Services.

- “Associated Company” means any company which is, in relation to another company, its holding company or its subsidiary or a subsidiary of its holding company. “Holding company” and “subsidiary” will have the meanings attributed to them in section 1159 of the Companies Act 2006.

- “Business Days” means Mondays to Fridays (inclusive) in each week, excluding bank and other public holidays in England.

- “CCN” means a Change Control Note in the form set out in schedule 6.

- “Charges” means the fees subject to clause 8 payable to the Contractor for the provision of the Services in accordance with clause 3.

- “Centres for Excellence”means the institutions appointed to take part in the programme, leading networks.

- “Centres” means the Centres for Excellence.

- “Clawback” means the amount at risk in the event that the Contractor fails to meet the Key Performance Indicators (KPIs) specified in schedule 4.

- “Commercially Sensitive Information” means the information set out in schedule 11 comprising the information of a commercially sensitive nature relating to:

- (a)	the Price;

- (b)	details of the Contractor’s Intellectual Property Rights; and

- (c)	the Contractor’s business and investment plans

- which the Contractor has indicated to DFE that, if disclosed by DFE, would cause the Contractor significant commercial disadvantage or material financial loss.

- “Confidential Information” means any information which has been designated as confidential by either Party in writing or that ought to be considered as confidential (however it is conveyed or on whatever media it is stored) including information the disclosure of which would, or would be likely to, prejudice the commercial interests of any person or trade secrets or Intellectual Property Rights of either Party and all Personal Data and sensitive Personal Data within the meaning of the GDPR. Confidential Information shall not include information which:

- (a)	was public knowledge at the time of disclosure;

- (b)	was in the possession of the receiving Party, without restriction as to its disclosure, before receiving it from the disclosing Party;

- (c)	is received from a third party (who lawfully acquired it) without restriction as to its disclosure; or

- (d)	is independently developed without access to the Confidential Information.

- “Consortium” means an association of 2 or more persons acting together to deliver the Services but excludes Sub-Contractors.

- “Consortium Agreement” means, if the Contractor is a Consortium, an agreement:

- (a)	signed by all the Consortium Members as at the Effective Date; and

- (b)	adhered to by Consortium Members who join the Consortium after the Effective Date by signing a Deed of Adherence

- which sets out, amongst other things, how the Consortium Members will work together to deliver the Services.

- “Consortium Member” means a member of a Consortium (if any).

- “Contractor” means ETF

- “Contractor Equipment” means the Contractor’s ICT equipment.

“Contractor Intellectual Property” means any knowledge, item, product, designs or artefact which pre-dates the existence of this Contract but which supports the delivery of the Centres for Excellence programme. This might include software / digital platforms, extant research, or non-published resource in the ownership of ETF or partners.

- “Contractor’s Solution” means the Contractor’s proposal submitted in response to the DFE’s invitation to tender and attached at schedule 12.

- “Controller”, “Processor”, “Data Subject”, “Personal Data”, “Personal Data Breach”, “Data

- Protection Officer” take the meaning given in the GDPR.

- “Copyright” means as it is defined in s.1 of Part 1 Chapter 1 of the Copyright, Designs and Patents Act 1988.

- “Crown” means the government of the United Kingdom (including the Northern Ireland Executive Committee and Northern Ireland Departments, the Scottish Executive and the National Assembly for Wales), including, but not limited to, government ministers, government departments, government offices and government agencies and “Crown Body” is an emanation of the foregoing.

- “Data Loss Event” means any event that results, or may result, in unauthorised access to Personal Data held by the Contractor under the Contract, and/or actual or potential loss and/or destruction of Personal Data in breach of the Contract, including any Personal Data Breach.

- “Data Protection Impact Assessment” means an assessment by the Controller of the impact of the

- envisaged processing on the protection of Personal Data.

- “Data Protection Legislation” means (i) the GDPR, the LED and any applicable national implementing Laws as amended from time to time (ii) the DPA 2018 subject to Royal Assent to the extent that it relates to processing of personal data and privacy; (iii) all applicable Law about the processing of personal data and privacy.

- “Data Subject Access Request” means a request made by, or on behalf of, a Data Subject in accordance with rights granted pursuant to the Data Protection Legislation to access their Personal Data.

- “Database Rights” means as rights in databases are defined in s.3A of Part 1 Chapter 1 of the Copyright, Designs and Patents Act 1988.

- “Deed of Adherence” means a deed under which a new Consortium Member shall covenant with the other Consortium Members to adhere to the terms of the Consortium Agreement in a form approved by DFE in writing.

- “Default” means breach of the obligations of the relevant Party (including abandonment of the Contract in breach of its terms, repudiatory breach or breach of a fundamental term) or any other default, act, omission, negligence or statement of the relevant Party or the Personnel in connection with the subject matter of the Contract and in respect of which such Party is liable to the other.

- “Delivery Partner” means Education and Training Foundation (ETF)

- “Department” means the Department for Education.

- “DFE” means the Department for Education.

- “DFE Contract Manager” means Ashley Hussey or such other official as DFE shall nominate from time to time, and of whose identity DFE shall inform the Contractor in writing.

- “DFE Premises” means any premises owned by, leased or hired to or otherwise controlled by DFE or which DFE nominates as such by notice in writing to the Contractor, but does not include schools or further education colleges or any other premises which are owned, leased or hired by DFE or any of its executive agencies solely or primarily for the purpose of providing educational services.

- “DFE Security Standards” means the security standards as set out in schedule 9.

- “DFE Trade Marks” means proprietary trade mark rights of DFE including those notified to the Contractor by DFE from time to time.

“Disclosure and Barring Service” and “DBS” mean the non-departmental public body of that name, or such other successor body or organisation as may be appropriate.

- “Dispute” means any dispute between the Parties in connection with the Contract.

- “DOTAS” means the Disclosure of Tax Avoidance Schemes rules which require a promotor of tax schemes to tell HMRC of any specified notifiable arrangements or proposals and to provide prescribed information on those arrangements or proposals within set time limits as contained in Part 7 of the Finance Act 2004 and in secondary legislation made under vires contained in Part 7 of the Finance Act 2004 and as extended to national insurance contributions by the National Insurance (Application of Part 7 of the Finance Act 2004) regulations 2012, SI 2012/1868 made under section 132A of the Social Security Administration Act 1992.

- “DPA” means the Data Protection Act 2018 and any subordinate legislation made under that Act from time to time together with any guidance and/or codes of practice published by the Information Commissioner or relevant government department in relation to such legislation.

- “Effective Date” means 6 February 2019.

- “EIR” means the Environmental Information Regulations 2004 and any guidance and/or codes of practice issued by the Information Commissioner or relevant government department in relation to them.

- “Employment Liabilities” means all actions, proceedings, costs (including reasonable legal costs), losses, damages, fines, penalties, compensation, awards, demands, orders, expenses and liabilities connected with or arising from all and any laws including, without limitation, directives, statutes, secondary legislation, orders, codes of practice, contractual obligations and other common law rights whether of the European Union, the United Kingdom or any other relevant authority relating to or connected with:

- (a)	the employment and dismissal of employees (including their health and safety at work); and

- (b)	the engagement, use and termination of individuals other than employees who provide services (including their health and safety at work),

- and all wages, holiday pay and employment benefit costs due in respect of (a) or (b) above, including claims for protective awards.

- “FOIA” means the Freedom of Information Act 2000 together with any guidance and/or codes of practice issued by the Information Commissioner or relevant government department in relation to it.

- “Force Majeure” means any event or occurrence which is outside the reasonable control of the Party concerned and which is not attributable to any act or failure to take reasonable preventative action by that Party, including fire; flood; violent storm; pestilence; explosion; malicious damage; armed conflict; acts of terrorism; nuclear, biological or chemical warfare; or any other disaster, natural or man-made, but excluding:

- (a)	any industrial action occurring within the Contractor’s or any of its Sub-Contractors’ organisation, or otherwise involving the Personnel; or

- (b)	the failure by any Sub-Contractor of the Contractor to perform its obligations under any sub-contract.

- “GDPR” means the General Data Protection Regulation (Regulation (EU) 2016/679).

- “General Anti-Abuse Rule” means:

- (a)	the legislation in Part 5 of the Finance Act 2013; and

- (b)	any future legislation introduced into parliament to counteract tax advantages arising from abusive arrangements to avoid NICs.

- “Good Industry Practice” means the standards, practices, methods and procedures conforming to the Law and the degree of skill and care, diligence, prudence and foresight which would reasonably and ordinarily be expected from a skilled and experienced person or body engaged in a similar type of undertaking under the same or similar circumstances.

- “Halifax Abuse Principle” means the principle explained in the CJEU Case C-255/02 Halifax and others.

- “HMRC” means Her Majesty’s Revenue and Customs.

- “ICT” means information and communications technology.

- “Implementation and Project Plan” means the plan and time schedule for the completion of the obligations of the Contractor under the Contract as set out in schedule 5 as may be replaced by any subsequent more detailed Implementation and Project Plan as the Parties may agree in writing from time to time.

- “Initial Term” means the period from the Effective Date to [31 March 2021].

- “Intellectual Property Rights” means patents, inventions, trade-marks, service marks, logos, design rights (whether registrable or otherwise), applications for any of the foregoing, copyright, database rights, domain names, trade and/or business names, rights in confidential information and know how, moral rights and other similar rights or obligations whether registrable or not in any country (including but not limited to the United Kingdom) and the right to sue for passing off.

- “IP Materials” means any materials used or developed for the purposes of the Contract including any programme materials, guidance, papers and research data, results, specifications, instructions, toolkits, plans, data, drawings, databases, patents, patterns, models and designs.

- “Key Performance Indicators (KPIs)” means the key performance indicators in relation to the Services as set out in schedule 4 and with which the Contractor shall comply.

- “Key Personnel” means any of the Personnel identified as such in schedule 7 or otherwise identified as such by DFE pursuant to clause 6.

- “Key Sub-Contractor” means any Sub-Contractor identified as such in schedule 7 or otherwise identified as such by DFE.

- “Law” means any law, subordinate legislation within the meaning of Section 21(1) of the Interpretation Act 1978, bye-law, enforceable right within the meaning of Section 2 of the European Communities Act 1972, regulation, order, regulatory policy, mandatory guidance or code of practice, judgment of a relevant court of law, or directives or requirements with which the Contractor is bound to comply.

- “LED” means the Law Enforcement Directive (Directive (EU) 2016/680).

- “Material Breach” means:

- a breach (including an anticipatory breach) that is serious in the widest sense of having a serious effect on the benefit which the DFE would otherwise derive from:

        - a substantial portion of the Contract; or

        - any of the obligations set out in clauses 9, 10, 12, 15, 17 and 33 and in schedules 4, 8 and 9; and/or

(b)	a Material KPI Failure.

- “Material KPI Failure” has such meaning given in Schedule 4, paragraph 12.

- “NICs” means National Insurance Contributions.

- “Occasion of Tax Non-Compliance” means:

- (a)	any tax return of the Contractor submitted to a Relevant Tax Authority on or after 1 October 2012 which is found on or after 1 April 2013 to be incorrect as a result of:

- (i)	a Relevant Tax Authority successfully challenging the Contractor under the General Anti-Abuse Rule or the Halifax Abuse Principle or under any tax rules or legislation that have an effect equivalent or similar to the General Anti-Abuse Rule or the Halifax Abuse Principle;

- (ii)	the failure of an avoidance scheme which the Contractor was involved in, and which was, or should have been, notified to the Relevant Tax Authority under the DOTAS or any equivalent or similar regime; and/or

- (b)	any tax return of the Contractor submitted to a Relevant Tax Authority on or after 1 October 2012 which gives rise on or after 1 April 2013 to a criminal conviction in any jurisdiction for tax related offences which is not spent at the Commencement Date or to a civil penalty for fraud or evasion.

- “Performance Reporting Year” means each year of the Term. The first Performance Reporting Year will begin on the Effective Date and conclude on 31 March 2019. Each subsequent Performance Reporting Year shall begin on 1 April and and concluding on the day immediately preceding the next following anniversary thereof.

- “Personnel” means all persons employed by the Contractor to perform its obligations under the Contract together with the Contractor’s servants, agents, suppliers and Sub-Contractors used in the performance of its obligations under the Contract.

- “Prohibited Act” means:

- (a)	to directly or indirectly offer, promise or give any person working for or engaged by the DFE a financial or other advantage to:

- (i)	induce that person to perform improperly a relevant function or activity; or

- (ii)	reward that person for improper performance of a relevant function or activity;

- (b)	to directly or indirectly request, agree to receive or accept any financial or other advantage as an inducement or a reward for improper performance of a relevant function or activity in connection with the Contract;

- (c)	an offence:

- (i)	under the Bribery Act 2010 (or any legislation repealed or revoked by such Act);

- (ii)	under legislation or common law concerning fraudulent acts; or

- (iii)	the defrauding, attempting to defraud or conspiring to defraud the DFE;

- (d)	any activity, practice or conduct which would constitute one of the offences listed under (c) above if such activity, practice or conduct had been carried out in the UK.

- “Protective Measures” means appropriate technical and organisational measures which may include: pseudonymising and encrypting Personal Data, ensuring confidentiality, integrity, availability and resilience of systems and services, ensuring that availability of and access to Personal Data can be restored in a timely manner after an incident, and regularly assessing and evaluating the effectiveness of the such measures adopted by it.

- “Quality Standards” means the quality standards published by BSI British Standards, the National Standards Body of the United Kingdom, the International Organisation for Standardization or other reputable or equivalent body, (and their successor bodies) that a skilled and experienced operator in the same type of industry or business sector as the Contractor would reasonably and ordinarily be expected to comply with, and as may be further detailed in the Specification.

“Regulated Activity”:

- (a)	in relation to children, takes the definitions contained in Part 1 of Schedule 4 to the Safeguarding Vulnerable Groups Act 2006 (as amended) and in Part 1 of Schedule 2 to The Safeguarding Vulnerable Groups (Northern Ireland) Order 2007 (as amended); and

- (b)	in relation to vulnerable adults, takes the definitions contained in Part 2 of Schedule 4 to the Safeguarding Vulnerable Groups Act 2006 (as amended) and in Part 2 of Schedule 2 to The Safeguarding Vulnerable Groups (Northern Ireland) Order 2007 (as amended).

- “Regulations” means the Public Contract Regulations 2015.

“Regulatory Body” means a government department and regulatory, statutory and other entities, committees, ombudsmen and bodies which, whether under statute, rules, regulations, codes of practice or otherwise, are entitled to regulate, investigate, or influence the matters dealt with in the Contract or any other affairs of the DFE.

“Relevant Requirements” means all applicable Law relating to bribery, corruption and fraud, including the Bribery Act 2010 and any guidance issued by the Secretary of State for Justice pursuant to section 9 of the Bribery Act 2010.

“Relevant Tax Authority” means HMRC or, if applicable, a tax authority in the jurisdiction in which the Contractor is established.

“Replacement Contractor” means any third party supplier appointed by the DFE to supply any services which are substantially similar to any of the Services in substitution for the Contractor following the expiry, termination or partial termination of the Contract.

“Request for Information” means a request for information under the FOIA or the EIR.

“Restricted Country” means:

a)	any country outside the European Economic Area; and

b)	any country not deemed adequate by the European Commission pursuant to Article 25(6) of Directive 95/46/EC

- “Returning Employees” means those persons agreed by the Parties to be employed by the Contractor (and/or any Sub-Contractor) wholly or mainly in the supply of the Services immediately before the end of the Term.

- “Services” means the services described in the Specification.

- “Services Commencement Date” means 6 February 2019.

- “Service Users” means those receiving the Services.

- “Specification” means the description of the Services to be supplied under the Contract set out in schedule 1.

- “Staff” means all persons employed by the Contractor to perform its obligations under the Contract together with the Contractor’s servants, agents, suppliers and Sub-Contractors used in the performance of its obligations under the Contract.

- “Sub-Contract” means a contract between 2 or more suppliers, at any stage of remoteness from DFE in a sub-contracting chain, made wholly or substantially for the purpose of performing (or contributing to the performance of) the whole or any part of the Contract and “Sub-Contractor” shall be construed accordingly.

- “Sub-Processor” means any third Party appointed to process Personal Data on behalf of the

- Contractor related to the Contract.

- “Term” means the period from the Effective Date until the date the Contract ends for whatever reason.

- “TFEU” means the Treaty on the Functioning of the European Union.

- “Treaties” means the TFEU and the Treaty on European Union.

- “TUPE” means the Transfer of Undertakings (Protection of Employment) Regulations 2006.

- “Variation” means any variation to the Contract requiring a Change Control Note to be completed in accordance with schedule 6.

  - The following notes of construction and interpretation apply to the Contract:

    - references to a statute or statutory provision shall, unless the context otherwise requires, include a reference to that statute or statutory provision as from time to time amended, modified, extended, re-enacted or consolidated and all statutory instruments or orders made pursuant to it whether replaced before or after the date of the Contract which are in force prior to the date of the Contract;

    - the expression “person” means any individual, firm, body corporate, unincorporated association, partnership, government, state or agency of a state or joint venture;

    - the words “include”, “includes”, “including” and “included” will be construed without limitation unless inconsistent with the context;

    - the masculine includes the feminine and the neuter, and the singular includes the plural and vice versa as the context shall admit or require;

    - any reference in the Contract to a clause or schedule is a reference to a clause or schedule of the Contract and references in any schedule to paragraphs relate to the paragraphs in that schedule;

    - the clause headings are included for convenience only and shall not affect the interpretation of the Contract; and

    - the schedules and appendices form part of the Contract and shall have effect as if set out in full in the body of the Contract and any reference to the Contract includes the schedules.

2.	TERM

2.1	The Contract commences on the Effective Date and, subject to any provision of this Contract for earlier termination, or extension set out in this clause 2, will terminate at the end of the Initial Term.

2.2	DFE may extend the Initial Term for a period or periods totalling not more than 2 years by giving not less than 6 months’ written notice to the Contractor prior to the expiry of the Initial Term.

3.	THE SERVICES

3.1	The Contractor shall provide the Services in the Area(s) in accordance with the Specification and undertake and be responsible for all obligations of the Contractor in respect of the Services.

3.2	The DFE may appoint other contractors for the Services in the Area.

3.3	The Contractor shall, in performing its obligations under the Contract:

3.3.1	conform to the requirements of the Specification and the Contractor’s Solution or as otherwise agreed in writing between the Parties;

3.3.2	carry out and complete the Services in a proper professional manner (taking account of the standards of a reasonably proficient practitioner) and in conformity with all reasonable directions and requirements of the DFE specified by the DFE from time to time;

3.3.3	comply with Good Industry Practice;

3.3.4	ensure that the Services are provided by competent and appropriately trained personnel;

3.3.5	comply with the Quality Standards and where applicable, shall maintain accreditation with the relevant Quality Standards authorisation body;

3.3.6	comply with the Key Performance Indicators (KPIs) set out in schedule 4;

3.3.7	comply with the Implementation and Project Plan;

3.3.8	in so far as is reasonably practicable, comply with any policies and procedures adopted by the DFE from time to time within 14 days of the same being brought to the attention of the Contractor by the DFE;

    - comply with applicable Law, any applicable codes of practice or governmental regulation, and monitor compliance with relevant legislation;

    - comply with all health and safety legislation, adopt and maintain safe operating systems of work and appropriate safety policies in order to protect the health and safety of Personnel, employees of the DFE, the Service Users and all other persons including members of the public; and

    - comply with all safety, security, acceptable use and other policies of the DFE from time to time notified to it and procure that the Personnel also comply.

3.4	The DFE may provide data and materials to the Contractor and access to systems for the purposes of providing the Services that the Contractor may use but only to the extent necessary to enable the Contractor to provide the Services.

  - All equipment and other property brought onto DFE Premises shall be at the Contractor’s own risk and the DFE shall have no liability for any loss of or damage to any such equipment and property unless the Contractor is able to demonstrate that such loss or damage was caused by the negligence of the DFE.

  - Any DFE Premises made available from time to time to the Contractor by the DFE in connection with the Contract shall be made available to the Contractor on a non-exclusive licence basis free of charge and shall be used by the Contractor solely for the purpose of performing its obligations under the Contract. The Contractor shall have the use of such DFE Premises as a licensee and shall vacate the same on completion, termination or abandonment of the Contract or the task in respect of which such DFE Premises was made available.

  - The Contract does not create a tenancy of any nature whatsoever in favour of the Contractor or any of the Personnel and no such tenancy has or shall come into being and, notwithstanding any rights granted pursuant to the Contract, the DFE retains the right at any time to use any DFE Premises in any manner.

4.	CONSORTIA

4.1	If the Contractor is a Consortium it shall comply with the terms of this clause 4.

4.2	The Contractor may appoint additional or replacement Consortium Members to assist it in carrying out its obligations under the Contract subject to compliance with clause 4.3.

4.3	No new person or entity may become a Consortium Member until:

4.3.1	the DFE has given its prior written consent to the new Consortium Member;

4.3.2	the new Consortium Member has signed a Deed of Adherence; and

4.3.3	a copy of the Deed of Adherence has been given to the DFE.

4.4	The Contractor shall promptly inform the DFE if and how any Consortium Member breaches the terms of the Consortium Agreement.

5.	TRANSFER AND SUB-CONTRACTING

5.1	Save as set out in this clause 5 and save as specified in the Contractor’s Solution (schedule 12) the Contractor may not sub-contract, assign, transfer, charge the benefit and/or delegate the burden of the whole or any part of the Contract (a “Transfer”) without the prior written consent of the DFE.

5.2	If the DFE consents to a Transfer the Contractor will evidence the Transfer in writing and provide a copy of the Transfer document on request.

5.3	The Contractor may award Sub-Contracts with a value per annum not exceeding £10,000 without the DFE’s consent.

5.4	Where the DFE has consented to a Sub-Contract, copies of each Sub-Contract shall, at the request of the DFE, be sent by the Contractor to the DFE as soon as reasonably practicable.

5.5	The Contractor will, within 3 months of the effective date of each Sub-Contract, deliver to the DFE a plan which sets out the Contractor’s proposals for achieving an orderly transition of Services from the Sub-Contractor to the Contractor and/or a Replacement Sub-Contractor in the event that the Sub-Contractor ceases to be able to perform its obligations under the Sub-Contract, or to do so in a satisfactory manner (a “Transfer of Sub-Contractor Undertakings Plan”).

5.6	Within 30 days of the submission of the Transfer of Sub-Contractor Undertakings Plan, both Parties will use reasonable endeavours to agree the Transfer of Sub-Contractor Undertakings Plan. If the Parties are unable to agree the Transfer of Sub-Contractor Undertakings Plan the dispute shall be referred to the dispute resolution procedure in clause 36.

5.7	The Contractor will review and (if appropriate) update each Transfer of Sub-Contractor Undertakings Plan in the first month of each year of the term of the relevant Sub-Contract to reflect changes to the services provided by the relevant Sub-Contractor. Following such update the Contractor will submit the revised Transfer of Sub-Contractor Undertakings Plan to the DFE for review. Within 30 days following submission of the revised Transfer of Sub-Contractor Undertakings Plan, the Parties shall meet and use reasonable endeavours to agree the revised Transfer of Sub-Contractor Undertakings Plan and the changes that have occurred in the services since the Transfer of Sub-Contractor Undertakings Plan was last agreed. If the Parties are unable to agree the revised Transfer of Sub-Contractor Undertakings Plan within 30 days, such dispute shall be referred to the dispute resolution procedure in clause 36.

5.8	The Contractor shall not terminate or materially amend the terms of any Sub-Contract without the DFE’s prior written consent, which shall not be unreasonably withheld.

5.9	The DFE may require the Contractor to terminate a Sub-Contract if the acts or omissions of the Sub-Contractor have given rise to the DFE’s right of termination pursuant to clause 23 unless the Sub-Contractor can remedy the breach to the DFE’s satisfaction within 21 days of receipt by the Contractor of written notice from the DFE requiring the Sub-Contract to be terminated.

5.10	The Contractor shall remain responsible for all acts and omissions of its Sub-Contractors as if they were its own.

5.11	If the DFE believes there are:

5.11.1	compulsory grounds for excluding a Sub-Contractor pursuant to regulation 57 of the Regulations, the Contractor shall replace or not appoint the Sub-Contractor; or

5.11.2	non-compulsory grounds for excluding a Sub-Contractor pursuant to regulation 57 of the Regulations, the DFE may require the Contractor to replace or not appoint the Sub-Contractor and the Contractor shall comply with such requirement.

6.	PERSONNEL AND SAFEGUARDING

6.1	The DFE may refuse admission to DFE Premises and/or direct the Contractor to end the involvement in the Services of any Personnel whom the DFE believes are a security risk.

6.2	If the DFE require the removal of any Personnel pursuant to clause 6.1, any Employment Liabilities and any other costs connected with that removal shall be at the Contractor’s cost.

6.3	The Contractor shall use its reasonable endeavours to ensure continuity of Personnel and to ensure that the turnover rate of Personnel is at least as good as the prevailing industry norm for similar services, locations and environments.

6.4	Not used.

6.5	The Contractor acknowledges that Key Personnel and Key Sub-Contractors are essential to the proper provision of the Services. The Parties have agreed to the appointment of Key Personnel and Key Sub-Contractors listed in schedule 7 as at the Effective Date.

6.6	Key Personnel shall not be released from supplying the Services without the DFE’s consent except by reason of long-term sickness, maternity leave, paternity leave or termination of employment or other similar reason.

6.7	Any replacements of Key Personnel shall be subject to DFE consent and shall be of at least equal status, experience and skills to Key Personnel being replaced and be suitable for the responsibilities of that person in relation to the Services.

6.8	The DFE shall not unreasonably withhold consent under clauses 6.6 or 6.7. Such agreement shall be conditional on appropriate arrangements being made by the Contractor to minimise any adverse effect on Services which could be caused by a change in Key Personnel or Key Sub-Contractors.

6.9	DFE may require the Contractor to remove any Key Personnel who the DFE considers in any respect unsatisfactory.

6.10	The DFE shall not be liable for the cost of replacing any Key Personnel and the Contractor shall indemnify the DFE against all Employment Liabilities that may arise in this respect.

6.11	Except in respect of any transfer of staff under TUPE, for the Term and for 12 months after the Term neither Party shall (except with the prior written consent of the other) solicit the services of any staff of the other Party who have been engaged in providing the Services or the management of the Contract or any significant part thereof either as principal, agent, employee, independent contractor or in any other form of employment or engagement other than by means of an open national advertising campaign and not specifically targeted at staff of the other Party.

6.12	The Contractor must ensure that it at all times has in place an effective and appropriate policy in order to safeguard and promote the welfare of children and vulnerable adults with whom Personnel may come into contact or to whom Personnel may have access in the course of performance of the Contract.

6.13	The Contractor shall have in place appropriate policies and procedures to establish safer recruitment practices, which minimise the risk of harm to children and vulnerable adults, and which ensure the suitability of Personnel who will administer and deliver the programme.

6.14	The Contractor shall carry out checks with the Disclosure and Barring Service on all Personnel involved in a Regulated Activity. Contractors must have a Disclosure and Barring Service check done every three years for any relevant Personnel. The Disclosure and Barring Service check must be completed before any of the Contractor’s Personnel work with children or vulnerable adults in Regulated Activity. The Contractor shall immediately notify the DFE of any information that it reasonably requests to enable it to be satisfied that the Contractor’s obligations of have been met.

6.15	The Contractor shall not (and shall ensure that any Sub-Contractor shall not) engage or continue to employ in the provision of the Services any person who is barred from, or whose previous conduct or records indicate that he or she would not be suitable to carry out a Regulated Activity or who may otherwise present a risk to children or vulnerable adults.

7.	TUPE

7.1	The Parties recognise that the Transfer of Undertakings (Protection of Employment) Regulations 2006 (TUPE) may apply in respect of the award of the Contract, and that for the purposes of TUPE, the undertaking concerned (or any relevant part of the undertaking) shall transfer to the Contractor on the commencement of the Contract.

7.2 	No later than 6 months prior to the end of the Term the Contractor shall fully and accurately disclose to the DFE, within 30 days of the request, all information that the DFE may reasonably request in relation to the Staff including the following:

7.2.1	the total number of Staff whose employment/engagement shall terminate at the end of the Term;

7.2.2	the age, gender, salary or other remuneration, future pay settlements and redundancy and pensions entitlement of the Staff referred to in clause 7.2.1;

7.2.3	the terms and conditions of employment/engagement of the Staff referred to in clause 7.2.1, their job titles and qualifications;

7.2.4	details of any current disciplinary or grievance proceedings ongoing or circumstances likely to give rise to such proceedings and details of any claims current or threatened; and

7.2.5	details of all collective agreements with a brief summary of the current state of negotiations with any such bodies and with details of any current industrial disputes and claims for recognition by any trade union

(together the “TUPE Information”).

7.3	At intervals determined by the DFE (which shall not be more frequent than once every 30 days) the Contractor shall give the DFE updated TUPE Information.

7.4	Each time the Contractor supplies TUPE Information to the DFE it shall warrant its completeness and accuracy and the DFE may assign the benefit of this warranty to any Replacement Contractor.

7.5	The DFE may use TUPE Information for the purposes of any retendering process. The Contractor will co-operate with the re-tendering of the Contract by allowing the Transferee to communicate with and meet the affected employees and/or their representatives.

7.6	The Contractor agrees to indemnify the Department fully and to hold it harmless at all times from and against all actions, proceedings, claims, expenses, awards, costs and all other liabilities whatsoever in any way connected with or arising from or relating to the provision of TUPE Information under Clause 7.2.

7.7	The Contractor agrees to indemnify the Department from and against all actions, proceedings, claims, expenses, awards, costs and all other liabilities (including legal fees) in connection with or as a result of any claim or demand by any employee or other employee or person claiming to be an employee on any date upon which the Contract is terminated and/or transferred to any third party (“Relevant Transfer Date”) arising out of their employment or its termination whether such claim or claims arise before or after the Relevant Transfer Date.

7.8	In the event that the information provided by the Contractor in accordance with Clause 7.2 above becomes inaccurate, whether due to changes to the employment and personnel details of the affected employees made subsequent to the original provision of such information or by reason of the Contractor becoming aware that the information originally given was inaccurate, the Contractor shall promptly notify the Department of the inaccuracies and provide the amended information.

7.9	The Contractor undertakes to the DFE that, during the 12 months prior to the end of the Term the Contractor shall not (and shall procure that any Sub-Contractor shall not) without written approval of DFE (such approval not to be unreasonably withheld or delayed):

7.9.1	amend or vary (or purport to amend or vary) the terms and conditions of employment or engagement (including, for the avoidance of doubt, pay) of any Personnel (other than where such amendment or variation has previously been agreed between the Contractor and the Personnel in the normal course of business and where any such amendment or variation is not in any way related to the transfer of the Services);

7.9.2	terminate or give notice to terminate the employment or engagement of any Personnel (other than in circumstances in which the termination is for reasons of misconduct or lack of capability);

7.9.3	transfer away, remove, reduce or vary the involvement of any other Personnel from or in the provision of the Services (other than where such transfer or removal: (i) was planned as part of the individual’s career development; (ii) takes place in the normal course of business; and (iii) will not have any adverse effect on the delivery of the Services, (provided that any such transfer, removal, reduction or variation is not in any way related to the transfer of the Services); or

7.9.4	recruit or bring in any new or additional individuals to provide the Services who were not already involved in providing the Services prior to the relevant period.

8.       CHARGES

8.1	Except where otherwise expressly stated in the Contract the only payments to be paid by the DFE for the performance by the Contractor of its obligations under the Contract shall be the Charges which shall be inclusive of all costs and expenses incurred by the Contractor in the performance of its obligations.

8.2	In consideration for the provision of the Services the DFE shall pay the Charges in accordance with schedule 3 subject to the receipt of correct invoices pursuant to clause 8.7 being issued by the Contractor.

- 8.3	Except where otherwise expressly stated in schedule 3 the Contractor shall not be entitled to increase the Charges or any rates identified in schedule 3 throughout the Term.

8.4	The Charges are exclusive of Value Added Tax (“VAT”) and all other taxes, duties and levies, but shall be inclusive of all charges, costs and expenses of whatever nature the Contractor incurs in providing the Services, and performing all other obligations of the Contractor, under the Contract (unless expressly stated otherwise in the Contract). The Contractor should notify the DFE of any direct VAT charges for the delivery of the Contract. The Contractor shall identify VAT and other applicable taxes, duties and levies separately on invoices, including identifying the elements of the Charges that are subject to VAT at the standard rate or at any other rates and that are zero rated or exempt from VAT.

- 8.5	Payment of the Charges by the DFE shall be without prejudice to any rights the DFE may have by reason of any Services, or any part thereof, failing to comply with any provision of the Contract and any breach by the Contractor of the Contract shall not be deemed to be accepted or waived by the DFE by reason of such payment.

- 8.6	The DFE may deduct from or offset against any monies due or becoming due to the Contractor under the Contract (including the Charges) any monies due from the Contractor under the Contract or otherwise under any other agreement or account whatsoever.

- 8.7	Invoices shall be submitted by email to the relevant DFE Contract Manager and, once approved (such approval not to be unreasonably withheld or delayed), sent within 30 days of the end of the relevant invoicing date, to SSCL Accounts Payable Team, PO Box 407, Phoenix House, Celtic Springs Business Park, Newport, NP10 8FZ. An invoice is a “Valid Invoice” if it is legible and includes:

- 8.7.1	the date of the invoice;

- 8.7.2	Contractor’s full name and address;

- 8.7.3	Contract reference number;

- 8.7.4	the correct purchase order number, to be provided by the DFE Contract Manager to the Contractor within 5 Business Days of the Effective Date;

- 8.7.5	the charging period;

- 8.7.6	a detailed breakdown of the appropriate Charges including deliverables or milestones achieved (if applicable);

- 8.7.7	days and times worked (if applicable);

- 8.7.8	Clawback (if applicable); and

- 8.7.9	VAT if applicable.

8.8	The DFE shall not pay an invoice which is not a Valid Invoice.

8.9	The DFE intends to pay Valid Invoices within 10 days of receipt. Valid Invoices not paid within 30 days are subject to interest at the rate specified in the Late Payment of Commercial Debts (Interest) Act 1998 or any successor legislation as may come into force.

8.10	The DFE shall not be responsible for any delay in payment caused by receipt of invoices which are not Valid Invoices and shall, within 10 Business Days of receipt, return to the Contractor for correction invoices that are not Valid Invoices together with an explanation of the need for correction.

8.11	At the end of the Term the Contractor shall promptly draw-up a final invoice which shall cover all Services provided up to the end of the Term which have not already been invoiced to the DFE. The final invoice shall be submitted not later than 30 days after the end of the Term.

8.12	The DFE shall not be obliged to pay the final invoice until the Contractor has carried out all of the Service.

8.13	The Contractor shall ensure that a term is included in all Sub-Contracts which requires payment to be made of all sums due to Sub-Contractors within 30 days from the receipt of a valid invoice.

8.14	If the DFE disputes any amount specified in a Valid Invoice it shall within 5 Business Days notify the Contractor of the reasons for disputing the invoice. The DFE may withhold the disputed payment pending resolution of the dispute.

8.15	The Parties shall use all reasonable endeavours to resolve any dispute over invoices within 10 Business Days of the dispute being raised, after which period either Party may refer the matter for resolution in accordance with clause 36.

9.	TAX and VAT

9.1	Where the Contractor is liable to be taxed in the UK in respect of consideration received under the Contract it shall at all times comply with the Income Tax (Earnings and Pensions) Act 2003 and all other statutes and regulations relating to income tax in respect of that consideration.

9.2	If the Services are liable for VAT the Contractor shall comply with HMRC rules and regulations. The Contractor will be liable for paying to HMRC any identified VAT including those which may fall due.

9.3	If the Contractor is liable to NICs in respect of consideration received under the Contract it shall comply with the Social Security Contributions and Benefits Act 1992 and all other statutes and regulations relating to NICs in respect of that consideration.

9.4	The DFE may ask the Contractor to provide information which demonstrates how the Contractor complies with clauses 9.1 to 9.3 or why those clauses do not apply to it.

9.5	A request under clause 9.4 may specify the information which the Contractor must provide and the period within which that information must be provided.

9.6	The DFE may terminate this Contract if:

9.6.1	in the case of a request mentioned in clause 9.4 the Contractor:

(i)	fails to provide information in response to the request within a reasonable time; or

(ii)	provides information which does not demonstrate either how the Contractor complies with clauses 9.1 to 9.3 or why those clauses do not apply to it;

9.6.2	it receives information which demonstrates that, if clauses 9.1 to 9.3 apply, the Contractor is not complying with those clauses.

9.7	The DFE may supply any information which it receives under clause 9.4 to HMRC.

9.8	The Contractor bears sole responsibility for the payment of tax and national insurance contributions due from it in relation to any payments or arrangements made under the Contract or in relation to any payments made by the Contractor to its officers or employees in connection with the Contract.

9.9	The Contractor will account to the appropriate authorities for any applicable income tax, national insurance, VAT and all other taxes, liabilities, charges and duties relating to any payments made to the Contractor under the Contract or in relation to any payments made by the Contractor to its officers or employees in connection with the Contract. The Contractor shall indemnify DFE against any liability, assessment or claim made by the HMRC or any other relevant authority arising out of the performance by the Contractor of its obligations under the Contract (other than in respect of employer's secondary national insurance contributions) and any costs, expenses, penalty fine or interest incurred or payable by DFE in connection with any such assessment or claim.

9.10	The Contractor authorises the DFE to provide HMRC and all other departments or agencies of the Government with any information which they may request as to fees and/or expenses paid or due to be paid under the Contract whether or not DFE is obliged as a matter of law to comply with such request.

9.11	If, during the Term, an Occasion of Tax Non-Compliance occurs, the Contractor shall:

9.11.1	notify the DFE in writing of such fact within 5 Business Days of its occurrence; and

9.11.2	promptly give the DFE:

(i)	details of the steps it is taking to address the Occasion of Tax Non-Compliance and to prevent the same from recurring, together with any mitigating factors it considers relevant; and

(ii) 	such other information in relation to the Occasion of Tax Non-Compliance as the DFE may reasonably require.

10.	PREVENTION OF CORRUPTION

10.1	The Contractor represents and warrants that neither it, nor to the best of its knowledge any Personnel, have at any time prior to the Effective Date:

10.1.1	committed a Prohibited Act or been formally notified that it is subject to an investigation or prosecution which relates to an alleged Prohibited Act; or

10.1.2	been listed by any government department or agency as being debarred, suspended, proposed for suspension or debarment, or otherwise ineligible for participation in government procurement programmes or contracts on the grounds of a Prohibited Act.

10.2	The Contractor shall not:

10.2.1	commit a Prohibited Act; or

10.2.2	do or suffer anything to be done which would cause the DFE or any of its employees, consultants, contractors, Sub-Contractors or agents to contravene any of the Relevant Requirements or otherwise incur any liability in relation to the Relevant Requirements.

10.3	The Contractor shall:

10.3.1	procure that its Sub-Contractors shall, establish, maintain and enforce, policies and procedures which are adequate to ensure compliance with the Relevant Requirements and prevent the occurrence of a Prohibited Act; and

10.3.2	keep appropriate records of its compliance with its obligations under clause 10.3.1 and make such records available to the DFE on request.

10.4	The Contractor shall immediately notify the DFE in writing if it becomes aware of any breach of clauses 10.1 and/or 10.2, or has reason to believe that it has or any of the Personnel have:

10.4.1	been subject to an investigation or prosecution which relates to an alleged Prohibited Act;

10.4.2	been listed by any government department or agency as being debarred, suspended, proposed for suspension or debarment, or otherwise ineligible for participation in government procurement programmes or contracts on the grounds of a Prohibited Act; or

10.4.3	received a request or demand for any undue financial or other advantage of any kind in connection with the performance of the Contract or otherwise suspects that any person directly or indirectly connected with the Contract has committed or attempted to commit a Prohibited Act.

10.5	If the Contractor notifies the DFE pursuant to clause 10.4, the Contractor shall respond promptly to the DFE’s enquiries, co-operate with any investigation, and allow the DFE to audit any books, records and any other relevant documentation.

10.6	If the Contractor is in Default under clauses 10.1 and/or 10.2, the DFE may by notice:

10.6.1	require the Contractor to remove from performance of the Contract any Staff whose acts or omissions have caused the Default; or

10.6.2	immediately terminate the Contract.

10.7	Any notice served by the DFE under clause 10.6 shall specify the nature of the Prohibited Act, the identity of the party who the DFE believes has committed the Prohibited Act and the action that the DFE has taken (including, where relevant, the date on which the Contract shall terminate).

11.	DISCRIMINATION

11.1	The Contractor shall perform its obligations under the Contract in accordance with all applicable equality law.

11.2	The Contractor shall comply with requirements and instructions which the DFE reasonably imposes in connection with any equality obligations imposed on the DFE at any time under equality law.

11.3	The Contractor indemnifies the DFE in full from and against all Employment Liabilities that may arise as a result of any claims brought against the DFE by any of its employees, agents, consultants and contractors (“DFE Personnel”) and/or any of the Personnel where such claim arises from any act or omission of the Personnel in respect of anti-discrimination legislation. The Contractor will also provide all reasonable cooperation, assistance and information as the DFE may request in connection with any investigation by the DFE into any complaint or other grievance received by it from any of the DFE Personnel or Personnel in respect of anti-discrimination legislation which may have arisen from, or been contributed to by, any act or omission of the Contractor or any Personnel.

12.	INTELLECTUAL PROPERTY

12.1	All Intellectual Property Rights in materials:

12.1.1	furnished to or made available to the Contractor by or on behalf of the DFE (the “DFE IP Materials”) shall remain the property of the DFE (save for Copyright and Database Rights which shall remain the property of the Crown); and

12.1.2	prepared by or for the Contractor on behalf of the DFE in connection with the Contract (the “Service Specific IP Materials”) shall vest in the DFE (save for Copyright and Database Rights which shall vest in the Crown);

(together the “IP Materials”).

12.2	The Contractor, nor any sub-Contractor, shall not, and shall ensure that Personnel shall not, use or disclose IP Materials without the DFE’s approval save to the extent necessary for the performance by the Contractor of its obligations under the Contract.

12.3	The Contractor hereby assigns to the DFE or undertakes to procure the assignment to the DFE of all Intellectual Property Rights which may subsist in the Service Specific IP Materials (save for Copyright and Database Rights which it hereby assigns to the Crown or undertakes to procure the assignment of to the Crown). These assignments shall be given with full title guarantee, shall take effect on the Effective Date or as a present assignment of future rights that will take effect immediately on the coming into existence of the Intellectual Property Rights in the Service Specific IP Materials and shall include, without limitation, an assignment to the DFE (or the Crown as appropriate) of all rights arising in the United Kingdom and the world together with the right to sue for damages and other remedies for infringement occurring prior to the date of assignment. The Contractor shall execute all documents and do all other acts requested by the DFE and necessary to execute and perfect these assignments and to otherwise evidence the DFE’s or the Crown’s ownership of such rights.

12.4	The Contractor shall waive or procure a waiver on an irrevocable and unconditional basis of any moral rights subsisting in copyright produced by or in connection with the Contract or the performance of the Contract.

12.5	The Contractor shall ensure that the third party owner of any Intellectual Property Rights that are or which may be used to perform the Services grants to the DFE a non-exclusive licence or, if itself a licensee of those rights, shall grant to the DFE an authorised sub-licence, to use, reproduce, modify, develop and maintain the Intellectual Property Rights in the same. Such licence or sub-licence shall be non-exclusive, perpetual, royalty-free, worldwide and irrevocable and shall include the right for the DFE to sub-licence, transfer, novate or assign to a Replacement Contractor. The Contractor shall notify the DFE of any third party Intellectual Property Rights to be used in connection with the Contract prior to their use in connection with the Contract or the creation or development of the Service Specific IP Materials.

12.6	The Contractor shall not infringe any Intellectual Property Rights of any third party in performing its obligations under the Contract and the Contractor shall indemnify and keep indemnified the DFE and any Replacement Contractor from and against all actions, suits, claims, demands, losses, charges, damages, costs and expenses and other liabilities which the DFE may suffer or incur as a result of or in connection with any breach of this clause 12, except to the extent that any such claim arises from:

12.6.1	items or materials supplied by the DFE; or

12.6.2	the use of data supplied by the DFE which is not required to be verified by the Contractor under any provision of the Contract.

12.7	The DFE shall notify the Contractor in writing of any claim or demand brought against the DFE for infringement or alleged infringement of any Intellectual Property Right in materials supplied and/or licensed by the Contractor.

12.8	The Contractor shall at its own expense conduct all negotiations and any litigation arising in connection with any claim for infringement of Intellectual Property Rights in materials supplied and/or licensed by the Contractor to the DFE, provided always that the Contractor shall:

12.8.1	consult the DFE on all substantive issues which arise during the conduct of such litigation and negotiations;

12.8.2	take due and proper account of the interests and concerns of the DFE; and

12.8.3	not settle or compromise any claim without the DFE’s prior written consent (not to be unreasonably withheld or delayed).

12.9	Notwithstanding clause 12.8. the DFE may take any action it deems appropriate with respect to any such claim and shall have exclusive control of such claim. If the DFE takes action the Contractor shall at the request of the DFE afford all reasonable assistance to the DFE for the purpose of contesting such claim.

12.10	The DFE shall at the request of the Contractor afford to the Contractor all reasonable assistance for the purpose of contesting any claim or demand made or action brought against the DFE or the Contractor by a third party for infringement or alleged infringement of any third party Intellectual Property Rights in connection with the performance of the Contractor’s obligations under the Contract subject to the Contractor indemnifying the DFE on demand and in full for all reasonable costs and expenses (including, but not limited to, legal costs and disbursements) incurred in doing so.

12.11	If a claim, demand or action for infringement or alleged infringement of any Intellectual Property Right is made in connection with the Contract or in the reasonable opinion of the Contractor is likely to be made, the Contractor shall notify the DFE and, at its own expense and subject to the consent of the DFE (not to be unreasonably withheld or delayed), use reasonable endeavours to:

12.11.1	modify any or all of the Service Specific IP Materials and, where relevant, the Services without reducing the performance or functionality of the same, or substitute alternative materials or services of equivalent performance and functionality, so as to avoid the infringement or the alleged infringement, provided that the provisions of this clause 12 shall apply mutatis mutandis to such modified materials or services or to the substitute materials or services; or

12.11.2	procure a licence to use and supply the Service Specific IP Materials, other relevant Intellectual Property Rights and Services, which are the subject of the alleged infringement, on terms which are acceptable to the DFE.

12.12	If the Contractor is unable to comply with clauses 12.11.1 and 12.11.2 within 20 Business Days of receipt of the Contractor’s notification the DFE may terminate the Contract with immediate effect by notice in writing.

12.13	The Contractor grants to the DFE and, if requested by DFE, to a Replacement Contractor, a royalty-free, perpetual, irrevocable and non-exclusive licence (with a right to sub-licence) to use any Intellectual Property Rights the Contractor owned or developed prior to the Effective Date or otherwise not in connection with the Contract (“Contractor IP”) and which the DFE (or a Replacement Contractor) reasonably requires in order to exercise its rights and take the benefit of the Contract including the Services provided and the use and further development of the IP Materials. The Contractor shall not, however, be required to grant such a licence with respect to Contractor IP developed by the Contractor prior to the Effective Date independently of this or any other Government contract and without the assistance of Departmental or Government funding, although it may still choose to do so in return for an agreed fee.

12.14	The DFE shall comply with the reasonable instructions of the Contractor in respect of the way in which it uses the Contractor IP.

12.15	If the Contractor is not able to grant to the DFE a licence to use any Contractor IP for any reason, including due to any Intellectual Property Rights that a third party may have in such Contractor IP, the Contractor shall use its reasonable endeavours to:

12.15.1	procure that the third party owner of any Intellectual Property Rights that are or that may be used to perform the Contract grants to the DFE a licence on the terms set out in clause 12.13; or

12.15.2	if the Contractor is itself a licensee of those rights and is able to do so under the terms of its licence, grant to the DFE a sub-licence on the terms set out in clause 12.13.

12.16	The Contractor shall not knowingly do or permit to be done, or omit to do in connection with its use of Intellectual Property Rights which are or are to be the DFE IP Materials any act or thing which:

12.16.1	would or might jeopardise or invalidate any trade mark application or registration comprised within the same or give rise to an application to remove or amend any such application or registration from the register maintained by the relevant trade mark registry; or

12.16.2	would or might prejudice the right or title of the DFE to any of the DFE IP Materials.

12.17	The Contractor shall provide the Services under the Agreed Programme Branding. In doing so, the Contractor shall comply with the DFE’s branding guidelines and shall not use any other branding, including its own, other than as set out in the DFE’s branding guidelines or as otherwise agreed with the DFE.

12.18	When using DFE Trade Marks the Contractor shall observe all reasonable directions given by the DFE from time to time as to colour and size and the manner and disposition thereof on any materials it provides to persons in connection with the Services. The Contractor may not:

12.18.1	adopt or use any trade mark, symbol or device which incorporates or is confusingly similar to, or is a simulation or colourable imitation of, any DFE Trade Mark, or unfairly competes with any DFE Trade Mark; or

12.18.2	apply anywhere in the world to register any trade marks identical to or so nearly resembling any DFE Trade Mark as to be likely to deceive or cause confusion.

12.19	In the event that any Service Specific IP Materials prepared by or for the Contractor on behalf of the DFE and in connection with this or any predecessor contract are hosted on a publicly accessible website or other information technology platform which itself is Contractor IP and will continue to be owned and/or operated by the Contractor following the conclusion of the Term, the Contractor shall, at the end of the Term, afford to the DFE (or, if requested by the DFE, a Replacement Contractor) reasonable assistance to transfer these Service Specific IP Materials to an alternative website or other platform nominated by DFE, subject to reimbursement by the DFE of the Contractor’s reasonable costs incurred in providing such assistance, such costs to be agreed between the Parties in advance.

12.20	The Contractor shall take reasonable steps to ensure that any Service Specific IP Materials prepared by or for the Contractor on behalf of the DFE and in connection with the Contract are developed in such a way as would, if required, facilitate those Service Specific IP Materials’ eventual transfer to and subsequent use and further development by DFE or a Replacement Contractor.

13.	DATA SYSTEMS, HANDLING AND SECURITY

13.1	The Parties shall comply with the provisions of schedule 9.

13.2	The Parties acknowledge that for the purposes of the Data Protection Legislation, DFE is the Controller and the Contractor is the Processor. The only processing that the Contractor is authorised to do is listed in schedule 10 by DFE and may not be determined by the Contractor.

13.3	The Contractor shall notify DFE immediately if it considers that any of DFE's instructions infringe the Data Protection Legislation.

13.4	The Contractor shall provide all reasonable assistance to DFE in the preparation of any Data Protection Impact Assessment prior to commencing any processing. Such assistance may, at the discretion of DFE, include:

13.4.1	a systematic description of the envisaged processing operations and the purpose of the processing;

13.4.2	an assessment of the necessity and proportionality of the processing operations in relation to the Services;

13.4.3	an assessment of the risks to the rights and freedoms of Data Subjects; and

13.4.4	the measures envisaged to address the risks, including safeguards, security measures and mechanisms to ensure the protection of Personal Data.

13.5	The Contractor shall, in relation to any Personal Data processed in connection with its obligations under the Contract:

13.5.1	process that Personal Data only in accordance with schedule 10, unless the Contractor is required to do otherwise by Law. If it is so required the Contractor shall promptly notify DFE before processing the Personal Data unless prohibited by Law;

13.5.2	ensure that it has in place Protective Measures, which have been reviewed and approved by DFE as appropriate to protect against a Data Loss Event having taken account of the:

(i)	nature of the data to be protected;

(ii)	harm that might result from a Data Loss Event;

(iii)	state of technological development; and

(iv)	cost of implementing any measures;

13.5.3	ensure that:

(i)	Personnel do not process Personal Data except in accordance with the Contract (and in particular schedule 10);

(ii)	it takes all reasonable steps to ensure the reliability and integrity of any Personnel who have access to the Personal Data and ensure that they:

(a)	are aware of and comply with the Contractor’s duties under this clause;

(b)	are subject to appropriate confidentiality undertakings with the Contractor or any Sub-Processor;

(c)	are informed of the confidential nature of the Personal Data and do not publish, disclose or divulge any of the Personal Data to any third party unless directed in writing to do so by DFE or as otherwise permitted by the Contract; and

(d)	have undergone adequate training in the use, care, protection and handling of Personal Data; and

13.5.4	not transfer Personal Data outside of the European Union unless the prior written consent of DFE has been obtained and the following conditions are fulfilled:

(i)	DFE or the Contractor has provided appropriate safeguards in relation to the transfer (whether in accordance with GDPR Article 46 or LED Article 37) as determined by DFE;

(ii)	the Data Subject has enforceable rights and effective legal remedies;

(iii)	the Contractor complies with its obligations under the Data Protection Legislation by providing an adequate level of protection to any Personal Data that is transferred (or, if it is not so bound, uses its best endeavours to assist DFE in meeting its obligations); and

(iv)	the Contractor complies with any reasonable instructions notified to it in advance by DFE with respect to the processing of the Personal Data;

13.5.5	at the written direction of DFE, delete or return Personal Data (and any copies of it) to DFE on termination of the Contract unless the Contractor is required by Law to retain the Personal Data.

13.6	Subject to clause 13.7, the Contractor shall notify DFE immediately if it:

13.6.1	receives a Data Subject Access Request (or purported Data Subject Access Request);

13.6.2	receives a request to rectify, block or erase any Personal Data;

13.6.3	receives any other request, complaint or communication relating to either Party's obligations under the Data Protection Legislation;

13.6.4	receives any communication from the Information Commissioner or any other regulatory authority in connection with Personal Data processed under the Contract;

13.6.5	receives a request from any third party for disclosure of Personal Data where compliance with such request is required or purported to be required by Law; or

13.6.6	becomes aware of a Data Loss Event.

13.7	The Contractor’s obligation to notify under clause 13.6 shall include the provision of further information to DFE in phases, as details become available.

13.8	Taking into account the nature of the processing, the Contractor shall provide DFE with full assistance in relation to either Party’s obligations under Data Protection Legislation and any complaint, communication or request made under clause 13.6 (and insofar as possible within the timescales reasonably required by DFE) including by promptly providing:

13.8.1	DFE with full details and copies of the complaint, communication or request;

13.8.2	such assistance as is reasonably requested by DFE to enable DFE to comply with a Data Subject Access Request within the relevant timescales set out in the Data Protection Legislation;

13.8.3	DFE, at its request, with any Personal Data it holds in relation to a Data Subject;

13.8.4	assistance as requested by DFE following any Data Loss Event;

13.8.5	assistance as requested by DFE with respect to any request from the Information Commissioner’s Office, or any consultation by DFE with the Information Commissioner’s Office.

13.9	The Contractor shall maintain complete and accurate records and information to demonstrate its compliance with this clause. This requirement does not apply where the Contractor employs fewer than 250 staff, unless:

13.9.1	DFE determines that the processing is not occasional;

13.9.2	DFE determines the processing includes special categories of data as referred to in Article 9(1) of the GDPR or Personal Data relating to criminal convictions and offences referred to in Article 10 of the GDPR; and

13.9.3	DFE determines that the processing is likely to result in a risk to the rights and freedoms of Data Subjects.

13.10	The Contractor shall allow for audits of its Data Processing activity by DFE or DFE’s designated auditor.

13.11	The Contractor shall designate a data protection officer if required by the Data Protection Legislation.

13.12	Before allowing any Sub-Processor to process any Personal Data related to the Contract, the Contractor must:

13.12.1	notify DFE in writing of the intended Sub-Processor and processing;

13.12.2	obtain the written consent of DFE;

13.12.3	enter into a written agreement with the Sub-Processor which gives effect to the terms set out in this clause 13 such that they apply to the Sub-Processor; and

13.12.4	provide DFE with such information regarding the Sub-Processor as DFE may reasonably require.

13.13	The Contractor shall remain fully liable for all acts or omissions of any Sub-Processor.

13.14	DFE may, at any time on not less than 30 Business Days’ notice, revise this clause by replacing it with any applicable controller to processor standard clauses or similar terms forming part of an applicable certification scheme (which shall apply when incorporated by attachment to the Contract).

13.15	The Parties agree to take account of any guidance issued by the Information Commissioner’s Office. DFE may on not less than 30 Business Days’ notice to the Contractor amend the Contract to ensure that it complies with any guidance issued by the Information Commissioner’s Office.

14.	PUBLICITY AND PROMOTION

14.1	Subject to clause 15.2, without prejudice to the DFE’s obligations under the FOIA, the EIR, the Regulations, or any policy requirements as to transparency, neither Party shall make any press announcement or publicise the Contract or any part thereof in any way, except with the written consent of the other Party.

14.2	The Contractor shall use reasonable endeavours to ensure its Personnel comply with clause 14.1.

14.3	Without prejudice to the generality of clauses 12.18 and 14.1, the Contractor shall not itself, and shall procure that Consortium Members shall not, use the DFE’s name, brand or DFE Trade Marks or the Personal Data of the DFE to sell, promote, market or publicise the Contractor’s other programmes, courses, services or other activities.

14.4	Subject to clauses 12 and 15 DFE may disclose, copy and otherwise distribute to the public, including but not limited to, by way of the Open Government Licence, any information arising out of the Services or comprised in any work relating to the Services.

- 15.	CONFIDENTIALITY

15.1	Except to the extent set out in this clause 15 or if disclosure or publication is expressly permitted elsewhere in the Contract each Party shall treat all Confidential Information belonging to the other Party as confidential and shall not disclose any Confidential Information belonging to the other Party to any other person without the other Party’s consent, except to such persons and to such extent as may be necessary for the performance of the Party’s obligations under the Contract.

15.2	The Contractor hereby gives its consent for the DFE to publish the whole Contract including from time to time agreed changes to the Contract.

15.3	The Contractor may only disclose the DFE’s Confidential Information to Personnel who are directly involved in the provision of the Services and who need to know the information, and shall ensure that Personnel are aware of and shall comply with these obligations as to confidentiality.

15.4	The Contractor shall not, and shall procure that Personnel do not, use any of the DFE’s Confidential Information received otherwise than for the purposes of the Contract.

15.5	Clause 15.1 shall not apply to the extent that:

15.5.1	such disclosure is a requirement of Law placed upon the Party making the disclosure, including any requirements for disclosure under the FOIA or the EIR;

15.5.2	such information was in the possession of the Party making the disclosure without obligation of confidentiality prior to its disclosure by the information owner;

15.5.3	such information was obtained from a third party without obligation of confidentiality;

15.5.4	such information was already in the public domain at the time of disclosure otherwise than by a breach of the Contract; or

15.5.5	it is independently developed without access to the other Party’s Confidential Information.

15.6	Nothing in clause 15 shall prevent the DFE disclosing any Confidential Information obtained from the Contractor:

15.6.1	for the purpose of the examination and certification of the DFE’s accounts;

15.6.2	for the purpose of any examination pursuant to section 6(1) of the National Audit Act 1983 of the economy, efficiency and effectiveness with which the DFE has used its resources;

15.6.3	to any other crown body and the Contractor hereby acknowledges that all government departments receiving such Confidential Information may further disclose the Confidential Information to other government departments on the basis that the information is confidential and is not to be disclosed to a third party which is not part of any government department; or

15.6.4	to any consultant, contractor or other person engaged by the DFE;

provided that in disclosing information under clauses 15.6.3 and 15.6.4 the DFE discloses only the information which is necessary for the purpose concerned and requests that the information is treated in confidence and that a confidentiality undertaking is given where appropriate.

15.7	Nothing in clauses 15.1 to 15.6 shall prevent either Party from using any techniques, ideas or know-how gained during the performance of its obligations under the Contract in the course of its normal business, to the extent that this does not result in a disclosure of the other Party’s Confidential Information or an infringement of the other Party’s Intellectual Property Rights.

15.8	The DFE shall endeavour to ensure that any government department, employee, third party or sub-contractor to whom the DFE's Confidential Information is disclosed pursuant to clause 15.6 is made aware of the DFE's obligations of confidentiality.

15.9	If the Contractor does not comply with clauses 15.1 to 15.5 the DFE may terminate the Contract immediately on notice to the Contractor.

16.	FREEDOM OF INFORMATION

16.1	The Contractor acknowledges that the DFE is subject to the requirements of the FOIA and the EIR.

16.2	The Contractor shall transfer to the DFE all Requests for Information that it receives as soon as practicable and in any event within 2 Business Days of receipt:

16.2.1	give the DFE a copy of all Information in its possession or control in the form that the DFE requires within 5 Business Days (or such other period as the DFE may specify) of the DFE’s request;

16.2.2	provide all necessary assistance as reasonably requested by the DFE to enable the DFE to comply with its obligations under the FOIA and EIR; and

16.2.3	not respond to directly to a Request for Information unless authorised to do so in writing by the DFE.

16.3	The DFE shall determine in its absolute discretion and notwithstanding any other provision in the Contract or any other agreement whether the Commercially Sensitive Information and any other information is exempt from disclosure in accordance with the provisions of the FOIA and/or the EIR.

17.	OFFICIAL SECRETS ACTS AND FINANCE ACT

17.1	The Contractor shall comply with the provisions of:

17.1.1	the Official Secrets Acts 1911 to 1989; and

17.1.2	section 182 of the Finance Act 1989.

18.	LIABILITY

18.1	Neither Party excludes or limits its liability (if any) to the other:

18.1.1	for breach of any obligations arising under section 12 Sale of Goods Act 1979 or section 2 Supply of Goods and Services Act 1982;

18.1.2	for personal injury or death resulting from its negligence;

18.1.3	under section 2(3) Consumer Protection Act 1987;

18.1.4	any breach of clause 15 or schedule 9;

18.1.5	for its own fraud; or

18.1.6	for any other matter which it would be unlawful for it to exclude or to attempt to exclude its liability.

18.2	Subject to clauses 18.1 and 18.3, the Contractor shall indemnify the DFE and keep the DFE indemnified fully against all claims, proceedings, demands, charges, actions, damages, costs, breach of statutory duty, expenses and any other liabilities which may arise out of the supply, or the late or purported supply, of the Services or the performance or non-performance by the Contractor or any Personnel on the Premises, including in respect of death or personal injury, loss of or damage to property, financial loss arising from any advice given or omitted to be given by the Contractor, or any other loss which is caused directly by any act or omission of the Contractor.

18.3	The Contractor does not exclude or limit its liability (if any) pursuant to any indemnities given by it in clauses 12 (Intellectual Property) and 9 (Tax and VAT).

18.4	Subject to clauses 18.1, 18.3 and 18.6, neither Party shall have any liability to the other under or in connection with the Contract, whether in contract, tort (including negligence) or otherwise:

18.4.1	for any losses of an indirect or consequential nature;

18.4.2	for any claims for loss of profits, revenue, business or opportunity (whether direct, indirect or consequential); or

18.4.3	to the extent that it is prevented from meeting any obligation under the Contract as a result of any breach or other default by the other Party.

18.5	Subject to clauses 18.1 and 18.3, the maximum liability of either Party to the other under the Contract, whether in contract, tort (including negligence) or otherwise:

18.5.1	in respect of damage to property is limited to £5,000,000.00 in respect of any one incident or series of connected incidents; and

18.5.2	in respect of any claim not covered by clause 18.5.1, is limited in each calendar year in aggregate to 150% of the sum of the Charges payable in that year.

18.6	The DFE may recover from the Contractor the following losses incurred by the DFE to the extent they arise as a result of a Default by the Contractor:

18.6.1	any reasonable additional operational and/or administrative costs and expenses incurred by the DFE, including costs relating to time spent by or on behalf of the DFE in dealing with the consequences of the default;

18.6.2	any wasted expenditure or charges;

18.6.3	the additional costs of procuring a Replacement Contractor for the remainder of the Contract and or replacement deliverables which shall include any incremental costs associated with the Replacement Contractor and/or replacement deliverables above those which would have been payable under the Contract;

18.6.4	any compensation or interest paid to a third party by the DFE; and

18.6.5	any fine or penalty incurred by the DFE and any costs incurred by the DFE in defending any proceedings which result in such a fine or penalty.

18.7	Except as otherwise expressly provided by the Contract, all remedies available to either Party for breach of the Contract are cumulative and may be exercised concurrently or separately, and the exercise of any one remedy shall not be deemed an election of such remedy to the exclusion of other remedies.

18.8	All property of the Contractor whilst on the DFE’s premises shall be there at the risk of the Contractor and the DFE shall accept no liability for any loss or damage howsoever occurring to it.

18.9	The Contractor shall effect and maintain in force with a reputable insurance company employer’s liability and public liability insurances for the sum and range of cover as the DFE deems to be appropriate but not less than £5,000,000 for any one claim, for professional indemnity insurances for the sum and range of cover as the DFE deems to be appropriate but not less than £1,000,000 for any one claim and insurance to cover the liability of the Contractor under the Contract. Such insurances shall be maintained:

18.9.1	in the case of professional indemnity insurances, for the Term and for a minimum of 6 years following the end of the Term; and

18.9.2	in the case of all other insurances, for the Term.

18.10	The Contractor shall supply to the DFE on demand copies of the insurance policies maintained under clause 18.9.

18.11	The provisions of any insurance or the amount of cover shall not relieve the Contractor of any liabilities under the Contract.

18.12	It shall be the responsibility of the Contractor to determine the amount of insurance cover that will be adequate to enable the Contractor to satisfy any liability it has under, or in connection with, the Contract.

19.	WARRANTIES AND REPRESENTATIONS

19.1	The Contractor warrants and represents that:

19.1.1	it has full capacity and authority and all necessary consents (including where its procedures so require, the consent of its parent company) to enter into and perform its obligations under the Contract and that the Contract is executed by a duly authorised representative of the Contractor;

19.1.2	in entering the Contract it has not committed any fraud;

19.1.3	as at the Effective Date, all information contained in the Contractor’s Solution remains true, accurate and not misleading, save as may have been specifically disclosed in writing to the DFE prior to execution of the Contract;

19.1.4	no claim is being asserted and no litigation, arbitration or administrative proceeding is presently in progress or, to the best of its knowledge and belief, pending or threatened against it or any of its assets which will or might, and it is not subject to any contractual obligation, compliance with which is likely to, have a material adverse effect on its ability to perform its obligations under the Contract;

19.1.5	it owns, has obtained or is able to obtain valid licences for all Intellectual Property Rights that are necessary for the performance of its obligations under the Contract;

19.1.6	the Service Specific IP Materials will be its original work and will not have been copied wholly or substantially from another party’s work or materials provided that this clause 19.1.6 shall not apply to any IP Materials used by the Contractor under permission or licence from any other person or entity (including, without limitation, any Sub-Contractor); and

19.1.7	the use by the DFE of any Intellectual Property Rights assigned or licensed to it by the Contractor under the Contract will not infringe or conflict with the rights of any third party;

19.1.8	in the 3 years (or actual period of existence if the Contractor has been in existence for less time) prior to the Effective Date:

(i)	it has conducted all financial accounting and reporting activities in compliance in all material respects with the generally accepted accounting principles that apply to it in any country where it files accounts;

(ii)	it has been in full compliance with all applicable securities and tax laws and regulations in the jurisdiction in which it is established; and

(iii)	it has not done or omitted to do anything which could have a material adverse effect on its assets, financial condition or position as an ongoing business concern or its ability to fulfil its obligations under the Contract;

19.1.9	it has and will continue to hold all necessary regulatory approvals from the Regulatory Bodies necessary to perform its obligations under the Contract; and

19.1.10	it has notified the DFE in writing of any Occasions of Tax Non-Compliance or any litigation in which it is involved that is in connection with any Occasion of Tax Non-Compliance.

20.	FORCE MAJEURE

20.1	If either Party is prevented or delayed in the performance of any of its obligations under the Contract by Force Majeure, that Party shall immediately serve notice in writing on the other Party specifying the nature and extent of the circumstances giving rise to Force Majeure, and shall subject to service of such notice and to clause 20.3 have no liability in respect of the performance of such of its obligations as are prevented by the Force Majeure events during the continuation of such events, and for such time after they cease as is necessary for that Party, using all reasonable endeavours, to recommence its affected operations in order for it to perform its obligations.

20.2	If either Party is prevented from performance of its obligations for a continuous period in excess of 3 months, the other Party may terminate the Contract forthwith on service of written notice upon the Party so prevented, in which case neither Party shall have any liability to the other except that rights and liabilities which accrued prior to such termination shall continue to subsist.

20.3	The Party claiming to be prevented or delayed in the performance of any of its obligations under the Contract by reason of Force Majeure shall use reasonable endeavours to end Force Majeure or to find solutions by which the Contract may be performed despite the Force Majeure.

21.	MONITORING AND REMEDIATION

21.1	The DFE or its authorised representatives may visit on reasonable notice to the Contractor any premises of the Contractor, any Consortium Member or any other premises at which the Services (or any part of them) are being or are to be performed to ascertain that the Contractor is conforming in all respects with its obligations arising under the Contract and otherwise to monitor and quality assure the provision of the Services.

21.2	During such visits, the DFE may inspect and take copies of such of the records of the Contractor and any Consortium Member as relate to the performance of their obligations under the Contract.

21.3	If the DFE reasonably considers that any provision of the Contract is at risk of not being complied with it may, notwithstanding and without prejudice to any other right or remedy that it may have under the Contract or otherwise:

21.3.1	require the Contractor to produce a plan of remedial action in order to remedy or remove such risk, which shall be subject to the approval of the DFE (not to be unreasonably withheld) and which, once approved, the Contractor shall implement; and

21.3.2	monitor, supervise, direct and/or guide the Contractor’s provision of the Services until the DFE reasonably considers that any such risk has been remedied or removed. The Contractor shall cooperate at all times with the DFE in this regard.

21.4	If the Contractor fails to comply with any provision of the Contract or fails to supply any of the Services in accordance with the provisions of the Contract and such failure is capable of remedy, then the DFE may instruct the Contractor to remedy the failure and the Contractor shall at its own cost and expense remedy such failure (and any damage resulting from such failure) within 21 days or such other period of time as the DFE may direct.

21.5	The DFE may review from time to time the progress of the Contractor against the Implementation and Project Plan. The Contractor shall cooperate with the DFE in this regard and provide any information and evidence reasonably required by the DFE.

21.6	The DFE may instruct the Contractor to take appropriate remedial action where the DFE reasonably considers that the Implementation and Project Plan is not being complied with or is at risk of not being complied with and the Contractor shall take such remedial action.

22.	STEP-IN RIGHTS

22.1 	Without prejudice to DFE’s rights of termination under clause 23 the DFE may exercise one or more of the rights set out in this clause 22 (“Step-In Rights”) if:

22.1.1	there is a Default by the Contractor which materially prevents or materially delays performance of the Services or any part of the Services;

22.1.2	an event of Force Majeure occurs which materially prevents or materially delays the performance of the Services or any part of the Services;

22.1.3	a Regulatory Body has advised the DFE that exercise by the DFE of its rights under this clause 22 is necessary;

22.1.4	a serious risk exists to the health and safety of persons, property or the environment;

22.1.5	it is necessary to discharge a statutory duty; or

22.1.6	the Contractor becomes insolvent.

22.2	If the DFE has a Step-In Right it may serve notice on the Supplier (a “Step-In Notice”) that it will take action under this clause 22 either itself or with the assistance of a third party.

22.3	The Step-In Notice shall set out:

22.3.1	the action the DFE wishes to take and in particular the Services that it wishes to control (the “Required Action”);

22.3.2	the event triggering the Step-In Rights and whether the DFE believes that the Required Action is due to the Contractor's Default;

22.3.3	the date on which it wishes to commence the Required Action;

22.3.4	the time period which it believes will be necessary for the Required Action;

22.3.5	whether the DFE will require access to the Contractor’s premises; and

22.3.6	to the extent practicable, the effect the DFE anticipates the Required Action will have on the Contractor’s obligations to provide the Services during the period that the Required Action is being taken.

22.4	 Following service of a Step-In Notice, the DFE shall:

22.4.1	take the Required Action set out in the Step-In Notice and any consequential

additional action as it reasonably believes is necessary to achieve the Required Action;

22.4.2	keep records of the Required Action taken and provide information about the Required Action to the Contractor;

22.4.3	co-operate wherever reasonable with the Contractor in order to enable the Contractor to continue to provide those Services of which the DFE is not assuming control; and

22.4.5	act reasonably in mitigating the cost that the Contractor will incur as a result

of the exercise of the Step-In Rights.

.

22.5	For as long as and to the extent that the Required Action continues:

22.5.1	the Contractor shall not be obliged to provide the Services to the extent that

they are the subject of the Required Action; and

22.5.2	the DFE shall pay the Contractor the Charges after subtracting any applicable Clawback and the DFE’s costs of taking the Required Action.

22.6	If the Contractor demonstrates to the DFE’s reasonable satisfaction that the Required Action has resulted in the degradation of any Services not subject to the Required Action beyond that which would have been the case had the DFE not taken the Required Action, the DFE may adjust the Charges.

22.7	Before ceasing to exercise its Step-In Rights the DFE shall deliver a written notice to the Contractor (a “Step-Out Notice”), specifying:

22.7.1	the Required Action it has taken; and

22.7.2	the date on which the DFE plans to end the Required Action subject to the DFE being satisfied with the Contractor’s ability to resume the provision of the Services and the Contractor’s plan developed in accordance with clause 22.8.

22.8	The Contractor shall, following receipt of a Step-Out Notice and not less than 20 Business Days prior to the date specified in clause 22.7.2, develop for the DFE’s approval a draft plan relating to the resumption by the Contractor of the Services, including any action the Contractor proposes to take to ensure that the affected Services satisfy the requirements of the Contract.

22.9	If the DFE does not approve the draft plan, it shall inform the Contractor of its reasons for not approving it and the Contractor shall then revise the draft plan taking those reasons into account and shall re-submit the revised plan to the DFE for approval. The DFE shall not withhold or delay its approval of the draft plan unreasonably.

22.10	The Contractor shall bear its own costs in connection with any Step-In under this clause 22, provided that the DFE shall reimburse the Contractor’s reasonable additional expenses incurred directly as a result of any Step-In action taken by the DFE under clauses 22.1.2 to 22.1.5 (insofar as the primary cause of the DFE serving the Step-In Notice is identified as not being the result of a Contractor’s Default).

23.	TERMINATION

23.1	The DFE may terminate the Contract with immediate effect and without paying compensation to the Contractor where the Contractor is a company and in respect of the Contractor:

23.1.1	a proposal is made for a voluntary arrangement within Part I of the Insolvency Act 1986 or of any other composition scheme or arrangement with, or assignment for the benefit of, its creditors;

23.1.2	a shareholders’ meeting is convened for the purpose of considering a resolution that it be wound up or a resolution for its winding-up is passed (other than as part of, and exclusively for the purpose of, a bona fide reconstruction or amalgamation);

23.1.3	a petition is presented for its winding up (which is not dismissed within 14 days of its service) or an application is made for the appointment of a provisional liquidator or a creditors’ meeting is convened pursuant to section 98 of the Insolvency Act 1986;

23.1.4	a receiver, administrative receiver or similar officer is appointed over the whole or any part of its business or assets;

23.1.5	an application order is made either for the appointment of an administrator or for an administration order, an administrator is appointed, or notice of intention to appoint an administrator is given;

23.1.6	it is or becomes insolvent within the meaning of section 123 of the Insolvency Act 1986;

23.1.7	being a “small company” within the meaning of section 247(3) of the Companies Act 1985, a moratorium comes into force pursuant to Schedule A1 of the Insolvency Act 1986; or

23.1.8	any event similar to those listed in clauses 23.1.1 to 23.1.7 occurs under the law of any other jurisdiction.

23.2	The DFE may terminate the Contract with immediate effect by notice and without paying compensation to the Contractor where the Contractor is an individual and:

23.2.1	an application for an interim order is made pursuant to sections 252–253 of the Insolvency Act 1986 or a proposal is made for any composition scheme or arrangement with, or assignment for the benefit of, the Contractor’s creditors;

23.2.2	a petition is presented and not dismissed within 14 days or order made for the Contractor’s bankruptcy;

23.2.3	a receiver, or similar officer is appointed over the whole or any part of the Contractor’s assets or a person becomes entitled to appoint a receiver, or similar officer over the whole or any part of his assets;

23.2.4	the Contractor is unable to pay his debts or has no reasonable prospect of doing so, in either case within the meaning of section 268 of the Insolvency Act 1986;

23.2.5	a creditor or encumbrancer attaches or takes possession of, or a distress, execution, sequestration or other such process is levied or enforced on or sued against, the whole or any part of the Contractor’s assets and such attachment or process is not discharged within 14 days;

23.2.6	he dies or is adjudged incapable of managing his affairs within the meaning of Part VII of the Mental Capacity Act 2005;

23.2.7	he suspends or ceases, or threatens to suspend or cease, to carry on all or a substantial part of his business; or

23.2.8	any event similar to those listed in clauses 23.2.1 to 23.2.7 occurs under the law of any other jurisdiction.

23.3	The Contractor shall notify the DFE immediately in writing of any proposal or negotiations which will or may result in a merger, take-over, change of control, change of name or status including if the Contractor undergoes a change of control within the meaning of section 1124 of the Corporation Taxes Act 2010 (“Change of Control”). The DFE may terminate the Contract with immediate effect by notice and without compensation to the Contractor within 6 months of:

23.3.1	being notified that a Change of Control has occurred; or

23.3.2	where no notification has been made, the date that the DFE becomes aware of the Change of Control

but shall not be permitted to terminate where approval was granted prior to the Change of Control.

23.4	The DFE may terminate the Contract with immediate effect and without paying compensation to the Contractor where the Contractor is a partnership and:

23.4.1	a proposal is made for a voluntary arrangement within Article 4 of the Insolvent Partnerships Order 1994 or a proposal is made for any other composition, scheme or arrangement with, or assignment for the benefit of, its creditors;

23.4.2	it is for any reason dissolved;

23.4.3	a petition is presented for its winding up or for the making of any administration order, or an application is made for the appointment of a provisional liquidator;

23.4.4	a receiver, or similar officer is appointed over the whole or any part of its assets;

23.4.5	the partnership is deemed unable to pay its debts within the meaning of sections 222 or 223 of the Insolvency Act 1986 as applied and modified by the Insolvent Partnerships Order 1994; or

23.4.6	any of the following occurs in relation to any of its partners:

23.4.6.1	an application for an interim order is made pursuant to sections 252–253 of the Insolvency Act 1986 or a proposal is made for any composition scheme or arrangement with, or assignment for the benefit of, his creditors;

23.4.6.2	a petition is presented for his bankruptcy;

23.4.6.3	a receiver, or similar officer is appointed over the whole or any part of his assets; or

23.4.6.4.	any event similar to those listed in clauses 23.4.1 to 23.4.6 occurs under the law of any other jurisdiction.

23.5	The DFE may terminate the Contract with immediate effect and without paying compensation to the Contractor where the Contractor is a limited liability partnership and:

23.5.1	a proposal is made for a voluntary arrangement within Part I of the Insolvency Act 1986 or a proposal is made for any other composition, scheme or arrangement with, or assignment for the benefit of, its creditors;

23.5.2	it is for any reason dissolved;

23.5.3	an application is made either for the appointment of an administrator or for an administration order, an administrator is appointed, or notice of intention to appoint an administrator is given within Part II of the Insolvency Act 1986;

23.5.4	any step is taken with a view to it being determined that it be wound up (other than as part of, and exclusively for the purpose of, a bona fide reconstruction or amalgamation) within Part IV of the Insolvency Act 1986;

23.5.5	a petition is presented for its winding up (which is not dismissed within 14 days of its service) or an application is made for the appointment of a provisional liquidator within Part IV of the Insolvency Act 1986;

23.5.6	a receiver, or similar officer is appointed over the whole or any part of its assets; or

23.5.7	it is or becomes unable to pay its debts within the meaning of section 123 of the Insolvency Act 1986;

23.5.8	a moratorium comes into force pursuant to Schedule A1 of the Insolvency Act 1986; or

23.5.9	any event similar to those listed in clauses 23.5.1 to 23.5.8 occurs under the law of any other jurisdiction.

23.6	References to the Insolvency Act 1986 in clause 23.5.1 shall be construed as being references to that Act as applied under the Limited Liability Partnerships Act 2000 subordinate legislation.

23.7	The DFE may terminate the Contract with immediate effect and without paying compensation to the Contractor if the Contractor commits a Default and:

23.7.1	the Contractor has not remedied the Default to the satisfaction of the DFE within 21 Business Days or such other period as may be specified by the DFE, after issue of a notice specifying the Default and requesting it to be remedied

23.7.2	the Default is not, in the opinion of the DFE, capable of remedy; or

23.7.3	the Default is a Material Breach.

23.8	The DFE may terminate the Contract with immediate effect and without paying compensation to the Contractor if:

23.8.1	the Contractor’s warranty in clause 19 is materially untrue;

23.8.2	the Contractor commits a material breach of its obligation to notify the DFE of any Occasion of Non-Tax Compliance;

23.8.3	the Contractor fails to provide details of proposed mitigating factors which, in the DFE’s reasonable opinion are acceptable; or

23.8.4	the Contractor has not, in performing the Services, complied with its legal obligations in respect of environmental, social or labour law.

23.9	The DFE may terminate the Contract with immediate effect and without paying compensation to the Contractor if:

23.9.1	the Contract has been subject to a substantial modification which requires a new procurement procedure pursuant to regulation 72(9) of the Regulations;

23.9.2	the Contractor was, at the time the Contract was awarded, in one of the situations specified in regulation 57(1) of the Regulations, including as a result of the application of regulation 57(2), and should therefore have been excluded from the procurement procedure which resulted in the award of the Contract; or

23.9.3	the Contract should not have been awarded to the Contractor in view of a serious infringement of the obligations under the Treaties and the Regulations which has been declared by the Court of Justice of the European Union in a procedure under Article 258 of the TFEU.

23.10	If the DFE terminates the Contract under clauses 23.7, 23.8 or 23.9:

23.10.1	and makes other arrangements for the supply of the Services, the DFE may recover from the Contractor the cost reasonably incurred in making those other arrangements; and

23.10.2	the DFE shall make no further payments to the Contractor (for Services supplied by the Contractor prior to termination and in accordance with the Contract but where the payment has yet to be made by the DFE), until the DFE has established the final cost of making the other arrangements envisaged under this clause 23.

23.11	The DFE may terminate the Contract (or any part of it) at any time by giving at least 3 months’ prior written notice to the Contractor.

23.12	If the DFE terminates the Contract under clause 23.11 the DFE shall make no further payments to the Contractor except for Services reasonably and appropriately supplied by the Contractor or committed to by the Contractor prior to termination and in accordance with the Contract but where the payment has yet to be made by the DFE. The Contractor shall use all reasonable endeavours to mitigate the amount of such costs and shall provide written evidence of the reasonableness and unavoidability of such costs.

23.13	If any funding from governmental or other sources for the provision of the Services, or for a programme or a project to which the provision of the Services relates is withdrawn, reallocated or no longer available in such a way that the Contract cannot reasonably continue the DFE may terminate the Contract (or any part of it) by serving 3 months’ written notice on the Contractor.

23.14	If the DFE terminates the Contract under clause 23.13 the DFE shall pay to the Contractor for Services supplied prior to the termination and in accordance with the Contract, and any disengagement costs and other costs reasonably incurred by the Contractor as a direct consequence of such termination (excluding any loss of profit and any possible redundancy costs), provided that the Contractor shall use all reasonable endeavours to mitigate the amount of such costs and has provided written evidence of the reasonableness and unavoidability of such costs.

23.15	If, through any Default of the Contractor, data transmitted or processed in connection with the Contract is either lost or sufficiently degraded as to be unusable, the Contractor shall be liable for the cost of reconstitution of that data and shall reimburse the DFE in respect of any charge levied for its transmission and any other costs charged in connection with such Default.

23.16	If the DFE fails to pay the Contractor undisputed sums of money when due the Contractor shall give notice to the DFE of its failure to pay. If the DFE fails to pay such undisputed sums within 90 Business Days of the date of such notice, the Contractor may terminate the Contract in writing with immediate effect, save that such right of termination shall not apply where the failure to pay is due to the DFE exercising its rights under clause 8.6 or to Force Majeure.

23.17	Save as otherwise expressly provided in the Contract:

23.17.1	termination or expiry of the Contract shall be without prejudice to any rights, remedies or obligations accrued under the Contract prior to termination or expiration and nothing in the Contract shall prejudice the right of either Party to recover any amount outstanding at such termination or expiry; and

23.17.2	termination of the Contract shall not affect the continuing rights, remedies or obligations of the DFE or the Contractor under clauses 8 (Charges), 9 (Tax and VAT), 10 (Prevention of Corruption), 12 (Intellectual Property), 13 (Data Systems, Handing and Security), 15 (Confidentiality), 16 (Freedom of Information), 17 (Official Secrets Act and Finance Act), 18 (Liability), 19 (Warranties and Representations), 23 (Termination), 24 (Retendering and Handover), 25 (Exit Management), 26 (Audit), and 37 (Governing Law and Jurisdiction).

24.	RETENDERING AND HANDOVER

24.1	Within 30 days of being requested by the DFE, the Contractor shall provide without charge, and thereafter keep updated, in a fully indexed and catalogued format, all the information reasonably necessary to enable the DFE to issue tender documents for the future provision of replacement services. Updates shall be subject to reimbursement by the DFE of the Contractor’s reasonable costs incurred in the provision thereof, such costs to be agreed between the Parties in advance. For the avoidance of doubt, this shall exclude updates for which provision is made under clause 7.3, for which no charge shall be payable.

24.2	The DFE shall take reasonable precautions to ensure that the information referred to in clause 24.1 is given only to potential contractors who have qualified to tender for the future provision of the replacement services.

24.3	The DFE shall require that all potential contractors treat the information in confidence; that they do not communicate it except to such persons within their organisation and to such extent as may be necessary for the purpose of preparing a response to an invitation to tender issued by the DFE; and that they shall not use it for any other purpose.

24.4	The Contractor shall allow access to the Premises in the presence of DFE’s authorised representative, to any person representing any potential contractor whom the DFE has selected to tender for the future provision of the Services.

24.5	If access is required to the Contractor’s Premises for the purposes of clause 24.4, the DFE shall give the Contractor 7 days’ notice of a proposed visit together with the names of all persons who will be visiting.

24.6	The Contractor shall co-operate fully with the DFE during any handover at the end of the Contract including allowing full access to, and providing copies of, all documents, reports, summaries and any other information necessary in order to achieve an effective transition without disruption to routine operational requirements.

24.7	Within 10 Business Days of being requested by the DFE, the Contractor shall transfer to the DFE, or any person designated by the DFE, free of charge, all computerised filing, recording, documentation, planning and drawing held on software and utilised in the provision of the Services. The transfer shall be made in a fully indexed and catalogued disk format, to operate on a proprietary software package identical to that used by the DFE.

25.	EXIT MANAGEMENT

25.1	If the DFE requires a continuation of all or any of the Services at the end of the Term, either by performing them itself or by engaging a third party to perform them, the Contractor shall co-operate fully with the DFE and any such third party and shall take all reasonable steps to ensure the timely and effective transfer of the Services without disruption to routine operational requirements.

25.2	The Contractor will, within 3 months of the Effective Date, deliver to the DFE, a plan which sets out the Contractor’s proposals for achieving an orderly transition of Services from the Contractor to the DFE and/or its Replacement Contractor at the end of the Term (an “Exit Plan”).

25.3	Within 30 days of the submission of the Exit Plan, both Parties will use reasonable endeavours to agree the Exit Plan. If the Parties are unable to agree the Exit Plan the dispute shall be referred to the dispute resolution procedure in clause 36.

25.4	The Contractor will review and (if appropriate) update the Exit Plan in the first month of each year of the Term to reflect changes to the Services. Following such update the Contractor will submit the revised Exit Plan to the DFE for review. Within 30 days following submission of the revised Exit Plan, the Parties shall meet and use reasonable endeavours to agree the revised Exit Plan and the changes that have occurred in the Services since the Exit Plan was last agreed. If the Parties are unable to agree the revised Exit Plan within 30 days, such dispute shall be referred to the dispute resolution procedure in clause 36.

25.5	If the Contractor reasonably incurs additional costs in delivering the Services prior to termination or expiry (including as a consequence of being required to use resources for exit management in addition to those which are normally used to deliver the Services), the Parties shall agree a variation of the Charges. In all other circumstances, there shall be no change to the Charges.

25.6	If the DFE requests, the Contractor shall deliver to the DFE details of all licences for software used in the provision of the Services including the software licence agreements.

25.7	Within one month of receiving the software licence information described above, the DFE shall notify the Contractor of the licences it wishes to be transferred, and the Contractor shall provide for the approval of the DFE a plan for licence transfer.

25.8	The Contractor shall co-operate fully with the DFE in order to enable an efficient and detailed knowledge transfer from the Contractor to the DFE at the end of the Term and shall provide the DFE free of charge with full access to Personnel, copies of all documents, reports, summaries and any other information requested by the DFE. The Contractor shall comply with the DFE’s request for information no later than 15 Business Days from the date that that request was made.

26.	AUDIT

26.1	The Contractor shall keep and maintain until 6 years after the end of the Term, or as long a period as may be agreed between the Parties, full and accurate records of the Contract including the Services supplied under it and all Charges.

26.2	The Contractor agrees to make available to the DFE, free of charge, whenever requested, copies of audit reports obtained by the Contractor in relation to the Services

26.3	The Contractor shall permit duly authorised representatives of the DFE and/or the National Audit Office to examine the Contractor’s records and documents relating to the Contract and to provide such copies and oral or written explanations as may reasonably be required.

26.4	The Contractor (and its agents) shall permit the Comptroller and Auditor General (and his appointed representatives) access free of charge during normal business hours on reasonable notice to all such documents (including computerised documents and data) and other information as the Comptroller and Auditor General may reasonably require for the purposes of his financial audit of the DFE and for carrying out examinations into the economy, efficiency and effectiveness with which the DFE has used its resources. The Contractor shall provide such explanations as are reasonably required for these purposes.

27.	ENTIRE AGREEMENT

27.1	The Contract contains all the terms which the Parties have agreed in relation to the subject matter of the Contract and supersedes any prior written or oral agreements, representations or understandings between the Parties.

27.2	Nothing in this clause 27 shall exclude any liability which one Party would otherwise have to the other Party in respect of any statements made fraudulently.

28.	PARTNERSHIP

28.1	Nothing in the Contract is intended to or shall operate to create a legal partnership between the Parties or to authorise either Party to act as an agent for the other, and neither Party shall have authority to act in the name or on behalf of or otherwise to bind the other in any way (including making any representation or warranty, the assumption of any obligation or liability and the exercise of any right or power).

29.	WAIVER

29.1	No failure or delay by any Party to exercise any right, power or remedy will operate as a waiver of it nor will any partial exercise preclude any further exercise of the same, or of some other right, power or remedy.

30.	CHANGE CONTROL

30.1	Either Party may at any time request in writing a Variation in accordance with the change control procedure set out in schedule 6 (the “Change Control Procedure”). No Variation shall be effective unless made in accordance with the Change Control Procedure.

31.	COUNTERPARTS

31.1	The Contract may be executed in any number of counterparts, each of which so executed and delivered shall constitute an original, but together shall constitute one and the same instrument.

32.	CONTRACTS (RIGHTS OF THIRD PARTIES) ACT 1999

32.1	The provisions of clauses 7.5 and 12.6 confer benefits on a Replacement Contractor and are intended to be enforceable by a Replacement Contractor by virtue of the Contracts (Rights of Third Parties ) Act 1999 (“CRTPA”).

32.2	Subject to clause 32.1, a person who is not a Party has no right under CRTPA to enforce provisions of the Contract but this does not affect any right or remedy of any person which exists or is available otherwise than pursuant to the CRTPA and does not apply to the Crown.

32.3	A Replacement Contractor may not enforce or take steps to enforce the provisions of clauses 7.5 or 12.6 without DFE’s prior written consent.

32.4	The Parties may amend the Contract without the consent of any Replacement Contractor.

33.	CONFLICTS OF INTEREST

33.1	The Contractor shall:

33.1.1	not permit its obligations to its other clients and third parties (including other governmental bodies and organisations providing services to other governmental bodies) to interfere or conflict in any material way with its duty (which the Contractor hereby acknowledges) to comply with its obligations under the Contract to the required standards; and

33.1.2	take appropriate steps to ensure that neither the Contractor nor any of the Personnel is placed in a position where, in the reasonable opinion of the DFE, there is or may be an actual conflict, or a potential conflict, between the pecuniary or personal interests of the Contractor or any of the Personnel and the duties owed to the DFE under the provisions of the Contract in either case, referred to in this clause 33 as a “Conflict of Interest”.

33.2	If the Contractor becomes aware of any Conflict of Interest (or potential Conflict of Interest) or other situation which has arisen or may arise and which may cause a breach of this clause 33 the Contractor shall forthwith provide full particulars to the DFE.

33.3	In performing its obligations under the Contract the Contractor shall conduct its business, operations and activities in a politically neutral fashion.

33.4	Without prejudice to the foregoing provisions of this clause 33, if any Conflict of Interest (or potential Conflict of Interest) arises or is likely to arise, the Contractor shall:

33.4.1	take all reasonable steps to remove or avoid the Conflict of Interest or to prevent it occurring in each case, or to manage the conflict to the satisfaction of the DFE (acting reasonably); and

33.4.2	give the DFE a comprehensive and detailed written statement of the action it had taken.

33.5	If the DFE is not satisfied with the Contractor’s actions, the Contractor shall, on request by the DFE promptly end any relationship it may have with any third party, where that relationship has given rise to the Conflict of Interest (or potential Conflict of Interest).

33.6	Without prejudice to any other right or remedy it may have, the DFE may terminate the Contract with immediate effect by notice in writing and/or to take such other steps it deems necessary where, in the reasonable opinion of the DFE, there is any continuing breach by the Contractor of the provisions of this clause 33.

34.	FURTHER ASSURANCE

34.1	The Parties shall do or procure the doing of all such acts and things and will execute or procure the execution of all such documents as may be reasonably required including on or subsequent to the end of the Contract to vest in the relevant Party all rights granted under the Contract and otherwise to comply with its terms.

35.	NOTICES

35.1	Any notice, demand or communication in connection with the Contract shall be in writing and may be delivered by hand, prepaid first class post or (where being sent to an address in a different country to where posted) airmail, facsimile or e-mail, addressed to the recipient at its registered office or its address (or such other address, facsimile number or e-mail address as may be notified in writing from time to time).

35.2	The notice, demand or communication shall be deemed to have been duly served:

35.2.1	if delivered by hand, when left at the proper address for service;

35.2.2	if given or made by prepaid unregistered first class post 48 hours after being posted or in the case of unregistered airmail 14 days after being posted;

35.2.3	if given or made by prepaid registered first-class post or registered airmail, on the day on which the notice, demand or communication is successfully delivered as evidenced by postal service records or, if that day is not a Business Day, on the next following Business Day;

35.2.4	if given or made by facsimile or e-mail, at the time of transmission, provided that a confirming copy is sent by first class pre-paid post or (where being sent to an address in a different country to where posted) airmail to the other Party within 24 hours after transmission and that, in the case of transmission by e-mail where the time of transmission is not between 9.00 am and 5.00 pm, service shall be deemed to occur at 9.00 am on the next following Business Day (such times being local time at the address of the recipient).

35.3	If proceedings to which the Civil Procedure Rules apply have been issued, the provisions of Civil Procedure Rule 6 must be complied with in respect of the service of documents in connection with those proceedings.

36.	DISPUTE RESOLUTION

36.1	Any Dispute shall be dealt with in accordance with this clause 36.

36.2	In the first instance, a representative of each Party will each use their reasonable endeavours to resolve the Dispute. If the Dispute cannot be resolved by such representatives within 15 days of the Dispute arising, it will be referred to a senior representative of each Party, who shall each use their reasonable endeavours to resolve the Dispute.

36.3	If a Dispute cannot be resolved by negotiation as referred to in clause 36.2 within 30 days of the Dispute arising, either Party may refer the Dispute for determination in accordance with the mediation procedure administered by the Centre for Effective Dispute Resolution, the costs of the mediator being split equally between the Parties, who shall otherwise bear their own costs.

37.	GOVERNING LAW AND JURISDICTION

37.1	The Contract and any non-contractual obligations arising out of or connection with it will be governed by and construed in accordance with English Law.

37.2	The courts of England shall have exclusive jurisdiction to settle any dispute which arises out of or in connection with the Contract.

37.3	If any provision of the Contract is held by any court or other competent authority to be void or unenforceable in whole or part, the other provisions of the Contract and the remainder of the affected provisions shall continue to be valid.

Schedule 3

- Financials

- 1.	The DFE shall pay the Contractor the Charges in accordance with the Contract, subject to successful delivery of the Services against the KPIs set out in schedule 4. The Charges are inclusive of all expenses incurred by the Contractor in relation to its provision of the Services and unless agreed otherwise between the Contractor and the DFE, the Contractor shall not be entitled to claim any expenses in addition to the Charges.

- 2.	Subject to VAT legislation and VAT rates prevailing on the Effective Date being maintained, the total Charge payable to the Contractor in respect of the Services shall not exceed £4,734,000 for the Initial Term of the Contract, (to 31st march 2021)including any VAT that may apply. The Contractor shall be entitled to invoice the Charges monthly on the basis of the budget profile set out in the Table[s] below:

TABLE OF CHARGES

INVOICING PROFILE

- 3.	Indexation shall not apply to the Charges.

- 4.	Funds allocated to a particular expenditure heading in the Tables are available for that expenditure heading only. Funds allocated to a particular accounting year are available for that accounting year only.

- 5.	The Contractor shall during the term of the Contract co-operate with the DFE to provide complete and accurate open book financial and non-financial information which is sufficient to enable the DFE to verify the Charges already paid or payable and Charges forecast to be paid during the remainder of the Contract, including details and all assumptions relating to, but not limited to:

5.1	the Contractor’s Costs and operating expenditure relating to the provision of the Services;

5.2	any overhead related costs;

5.3	the level of profit achieved over the Contract; and

5.4	an explanation of the type and value of risk and contingencies associated with the

provision of the Services, including the amount of money attributed to each risk and/or contingency.

Schedule 4

- Key Performance Indicators (KPIs)

- KEY PERFORMANCE INDICATORS (KPIs)

- The objectives of the Key Performance Indicators (KPIs) are to:

- 1.1 	ensure that the Services are of a consistently high quality and meet the requirements of the DFE;

- 1.2	incentivise the Contractor to meet the Key Performance Indicators (KPIs) and to remedy any failure to meet them expeditiously.

- This schedule 4 sets out the Key Performance Indicators (KPIs) against which the Contractor shall measure its performance.

- The Contractor shall monitor its performance against of each of the Key Performance Indicators (KPIs) in Table 1 and send the DFE a report detailing the Key Performance Indicators (KPIs) which have been achieved and progress against those which have not yet been achieved in accordance with the provisions of this schedule 4 in advance of each service review meeting. The Contractor shall also notify the DFE of any failure to comply with the Key Performance Indicators (KPIs) and what remedial action it has taken as soon as it becomes aware of the failure.

- The Contractor must meet the Key Performance Indicators (KPIs) as set out in Table 1 below. In the event that the Contractor fails to meet the Key Performance Indicators (KPIs):

- 4.1	DFE may, at its discretion, demand that Clawback be applied by the Contractor to the next invoice submitted for payment or another invoice of its choosing; or

- 4.2	if the Contractor is not due to submit any further invoices, DFE may issue to the Contractor an invoice with respect to the Clawback, which shall be payable by the Contractor within 30 days.

- The maximum applicable Clawback with respect to the Key Performance Indicators (KPIs) in any given Performance Reporting Year shall be 15% of the Charges payable in such Performance Reporting Year (the “Maximum Clawback”). The maximum applicable Clawback payable in respect of each individual Key Performance Indicator (KPI) shall be the percentage of the Maximum Clawback indicated in Table 1 below. Where the Contractor has failed to achieve a KPI, the Clawback payable will be calculated as follows:

  - for a [Non-Numerical KPI] (such KPIs are detailed within Table 1 below) a failure shall attract the maximum Clawback attributable to such KPI;

  - for a [Numerical KPI] (such KPIs are detailed within Table 1 below) a rate of 5% of the maximum Clawback attributable to such KPI shall be applied per percentage point that performance has fallen below the relevant numerical target. As a worked example:

    - the KPI to secure 90% of positive feedback from a survey of teachers in relation to leadership training attracts a 5% proportion of the maximum Clawback for a relevant Performance Reporting Year (see Table 1). As such, the maximum Clawback attributable to this KPI would be: the Maximum Clawback x 0.05. For the sake of this worked example, we will say the Maximum Clawback x 0.05 = £12,000;

    - if the Contractor has secured 86% of positive feedback from a survey of teachers. This represents 96% of the target (86/90 * 100); therefore the DFE would apply Clawback of £2,400 (12,000 * 0.05 * 4) for that Performance Reporting Year.

- DFE may, at its sole discretion, determine that Clawback should not be applied with respect to an incident of failure to meet the Key Performance Indicators (KPIs) detailed in Table 1, or determine that the Clawback to be applied should be in an amount lower than the maximum applicable as calculated in accordance with clause 5. Any such determination shall not affect DFE’s right to apply Clawback with respect to future instances in which the Contractor fails to meet the Key Performance Indicators (KPIs), whether in relation to the same Key Performance Indicator (KPI) or others, subject to not exceeding the maximum applicable Clawback in relation to any individual Key Performance Indicator (KPI) in any given Performance Reporting Year as calculated in accordance with clause 5.

- The DFE shall, in determining whether to apply Clawback and the level of that Clawback, take full account of any evidence presented by the Contractor which suggests that the Contractor’s failure to meet the Key Performance Indicators (KPIs) is a consequence of any decision to appoint other contractors for the Services in the Area as provided for under clause 3.2 of schedule 2. In such circumstances, the Parties shall agree a reduction in the maximum level of Clawback which is commensurate with the extent to which the evidence presented to the DFE by the Contractor indicates that the Contractor’s ability to meet the Key Performance Indicators (KPIs) has been impeded or otherwise compromised as a result of such an appointment of other contractors.

- Any decision by DFE to apply Clawback shall not affect DFE’s future right to additionally exercise any other right for which provision is made in this Contract, including in the event of a Default or Material Breach.

- The Parties shall use all reasonable endeavours to resolve any dispute relating to the application of the provisions of this schedule within 10 Business Days of the dispute being raised, after which period either Party may refer the matter for resolution in accordance with clause 36 of schedule 2.

- The Contractor confirms that it has taken the Key Performance Indicators (KPIs) into account in calculating the Charges.

- If, in any given Performance Reporting Year, the Contractor fails:

  - three or more KPIs; and/or

  - a [Numerical KPI] by 10% or more;

- (a “KPI Failure”), the DFE may require that the Contractor undertake the remediation process outlined in Clause 21 of Schedule 2.

- During the Term, if the Contractor commits two or more KPI Failures (regardless of whether previous KPI Failures have been remedied) this shall constitute a “Material KPI Failure”.

Table 1: Key Performance Indicators (KPIs)

| KPI # | Description | Annual Minimum Target Required and Proportion of Maximum Charges Rebate |  |  |  |  |  |  |  | Method of assessment |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Y1 (October 2018 – 31 March 2019) | Y1 Proportion of Maximum Charges Rebate | Y2 (1 April 2019 – 31 March 2020) | Y2 Proportion of Maximum Charges Rebate | Y3 (1 April 2020 – 31 March 2021) |  | Y3 Proportion of Maximum Charges Rebate |  |  |
| KPI 1 | Managing Centre Action Plans 100% of action plans to be developed to a pre-agreed template, to a high standard, in line with ESFA funding condition requirements and to agreed timescales for every financial year of the programme. | 100% | 30% | 100% | 20% | 100% |  | 20% |  | Monitored on a monthly basis; assessed annually. |
| KPI 2 | Research Reports will be approved as ready for publication by DfE by 14 August 2019, be deemed to be of high quality and of a publishable standard by DFE officials and be considered of value in the design of the teaching approach trials and teaching resources used within the Centres and across the sector in general. |  |  | Achieved | 10% | - |  |  |  | Monitored and assessed by the end of financial year 2 |
|  | By the end of financial year 2 (by 31 March 2020), 80% of attendees of the Centres for Excellence Forum will feedback positively to the question: Has the Delivery Partner developed and shared with you practical evidence and guidance that has supported your Centre to trial new and improved maths teaching methods? Yes or no. | - |  | 80% | 10% | - |  |  |  | Monitored and assessed by the end of financial year 2 |
| KPI 3 | Evaluation The report will be developed and published from financial year 2 onwards (by 31 March 2020 and 31 March 2021). The report will be deemed accurate and of a high quality by DFE officials on the teaching approaches being tested and an analysis of progress to date linked to improved performance of maths attainment for students within Centres and across the Maths Networks | - |  | Achieved | 5% | Achieved |  | 5% |  | Monitored and assessed by the end of financial years 2 and 3 |
|  | By the end of financial year 2 (by 31 March 2020) and financial year 3 (by 31 March 2021), 80% of attendees of the Centres for Excellence Forum will feedback positively to the question: Has the Delivery Partner and Evaluation Partner supported your Centre for Excellence to effectively trial, monitor and evaluate whether your teaching approaches are enhancing the quality of maths teaching? Yes or no. | - |  | 80% | 5% | 80% |  | 5% |  | Monitored and assessed by the end of financial years 2 and 3 |
| KPI 4 | Leadership training 100% of centres will attend leadership training by 31 May 2019 |  |  | 100% of Centres in attendance. | 20% | - |  |  |  | Monitored monthly and assessed at the end of financial year 1. |
|  | Leadership training evaluation questionnaires will achieve a minimum positive response of 90% to the question: Has this training supported you in the leadership of your Centre for Excellence? |  |  | 90% positive survey response | 20% | - |  |  |  |  |
| KPI 5 | Teacher Training By the end of financial year 2 (by 31 March 2020), the Delivery Partner will develop and deliver high quality teacher training directly to over 100 teachers across the Centres or Maths Networks on how to successfully develop and deliver the new teaching approaches. By the end of financial year 3 (by 31 March 2021), the Delivery Partner will develop and deliver high quality teacher training to directly over 400 teachers across the Centres or Maths Networks. N.B. this is a scaled, cumulative figure. | - |  | 100 | 10% | 400 |  | 10% |  | Monitored monthly and assessed at the end of financial years 2 and 3. |
|  | Teacher training evaluation questionnaires will achieve a minimum positive response of 90% to the question for each financial year: Has this training supported you in the development of your understanding and delivery of the new teaching approaches? Yes or no. | - |  | 90% | 10% | 90% |  | 10% |  |  |
| KPI 6 | Resources At the Centre for Excellence Forum in financial year 3 (by March 2021), evaluation questionaires from a minimum of 50% of Centres will achieve a positive response of 80% to the question: Is the Delivery Partner adequately supporting Centres to identify, use or develop the appropriate and relevant teaching materials & resources required to deliver effective teaching of the new teaching approaches? Yes or no. | - |  | - |  | 80% |  | 10% |  | Monitored and assessed at the end of financial year 3. |
|  | The Delivery Partner in financial year 3 (by March 2021) will survey a minimum, random sample of 25 students per Centre to identify whether the teaching resources and materials are supporting their needs. 80% of all students surveyed will feedback positively to the question: Are the teaching resources and materials being used of good quality and supporting you to improve at maths? Yes or no. | - |  | - |  | 80% |  | 10% |  | Monitored and assessed at the end of financial year 3 |
| KPI 7 | Centre for Excellence Forum For each financial year of the contract, the Delivery Partner will coordinate a termly Centre for Excellence Forum, with three forums delivered in the period January - July 2019 to mitigate for delayed contract start. This will be attended by the leadership of a minimum of 90% of all Centres, | 90% attendance | 5% | 90% attendance | 5% | 90% attendance |  | 5% |  | Monitored termly and assessed annually. |
|  | Evaluation questionnaires will achieve a minimum positive response of 90% to the question: Has the Forum furthered your understanding of the Centres for Excellence programme? | 90% positive response | 5% | 90% positive response | 5% | 90% positive response |  | 5% |  |  |
| KPI 8 | Maths Networks By the end of financial year 1 (by 31 March 2019) the Delivery Partner will ensure that every Centre has established a Maths Network and is supporting and sharing best practice with a minimum of 5 other institutions. By the end of financial year 2 (by 31 March 2020) and 3 (by 31 March 2021), the Delivery Partner will ensure that every Centre has established a Maths Network and is supporting and sharing best practice with a minimum of 10 other institutions. | 5 institutions per network | 10% | 10 institutions per network | 10% | 10 institutions per network |  | 10% |  | Monitored monthly and assessed annually |
|  | By July 2019, and then by the end of financial year 2 (by 31 March 2020) and financial year 3 (by 31 March 2021) the programme’s outputs (new resources, new teaching methods or teachers who’ve engaged in maths teaching CPD) should indirectly have reached and benefited the required number of maths resit students across the Centres and their Maths Networks. Year; Centres – Students indirectly reached; Partner providers – Students indirectly reached; Indicative student cumulative reach to be updated against learner census data. 1; 100%; 0; 11,500. 2; 100%; 33%; 41,500 10,000+20,000+(Yr 1 11,500). 3; 100%; 66%; 91,500 10,000+40,000 +(Yr 1 & 2 41,500). 4; 100%; 100%; 161,500 10,000+60,000 + (Yr 1 – 3 91,500). | 10,000 | 10% | 25,000 | 10% | 50,000 |  | 10% |  | Monitored and assessed annually |
| Additional KPIs – to be agreed with the successful bidder |  |  |  |  |  |  |  |  |  |  |
| KPI 9 | Improvement in the percentage point GCSE mathematics resit pass rate in Centres and Maths Networks within targeted student groups supported by Trials or other activities. | - |  | - |  | - |  |  |  | Assessed with Ofqual data / UMS scores by the Authority or its designated agents. Assessed annually. |
|  | Improvement in percentage point improvement of student attaining level 2 mathematics qualifications in Centre and Maths Network within targeted student groups supported by Trials or other activities. | - |  | - |  | - |  |  |  | Assessed with Ofqual data / UMS scores by the Authority or its designated agents. Assessed annually. |
|  | Improvement in the percentage point in the level 2 mathematics progression rate in Centres and Maths Network within targeted student groups supported by Trials or other activities. | - |  | - |  |  | - |  |  | Assessed with Ofqual data / UMS scores by the Authority or its designated agents. Assessed annually. |

KPI 1 – Managing Centre Action Plans

- For each financial year of the contract (i.e. by 31st March 2019, 31st March 2020 and 31st March 2021), the Delivery Partner will support, advise and challenge all of the Centres for Excellence leadership teams to plan, prioritise, deliver and evaluate their work to ensure they meet the government’s maths education priorities.

- The Delivery Partner will provide a named key contact for all Centres and will successfully support all Centres to develop standardised action plans outlining how they will resource and deliver the programme. For October 2018 to March 2019, the Delivery Partner should ensure that all action plans are submitted to DfE for approval by 18 January 2018. For April – July 2019, the Delivery Partner should ensure that all action plans are submitted to DfE for approval by 15 March 2019. Thereafter, action plans for each academic year should be submitted to DfE for approval by 30 June, on an annual basis.

- This Centres action plan will include a breakdown of financial spending, key objectives, a project plan and key milestones, a risk analysis and information relating to their teaching approach trials, evaluation and dissemination plans. This action plan will also include any proposals for additional grant funding, based on the factors identified in our specification.

- In order to achieve this KPI:

The Delivery Partner will manage the Centres to develop 100% of action plans to a pre-agreed template, to a high standard in line with ESFA funding condition requirements and approved by DfE to the agreed timescales for every financial year of the programme.

KPI 2 - Scoping Research

- By 31st July 2019, the Delivery Partner will build on existing understanding of this policy area and the teaching approaches identified to conduct a high quality review of existing research, good practice and resources and interviews with key stakeholders and users, as set out in Schedule 1, to determine how best to enhance the teaching and delivery of basic maths to the Post-16 re-sit cohort.

- This research will cover each of the four teaching approaches identified (and possibly any other pedagogical themes that the Delivery Partner and DfE considers appropriate).

- The research will need to demonstrate use of best practice; underpinned by high-level expertise in evaluation techniques, and knowledge of the appropriate evaluation guidance and frameworks as appropriate.

- The research must adhere where relevant to the guidance set out in the Magenta Book. The HM Treasury Magenta Book: Quality in policy impact evaluation  was published by the government as supplementary guidance to its evaluation guidance. The document sets out the strengths and weaknesses of evaluation designs.

- The research will also be accountable to the Government Social Research (GSR) five principles for publishing research and analysis in government.

- In order to achieve this KPI:

The reports will be developed and approved as ready for publication by DfE by 14 August 2019.

  - They will be deemed to be of high quality and of a publishable standard by DfE’s Basic Skills Board and be considered of value in the design of the teaching approach trials and teaching resources used within the Centres and across the sector in general.

  - By the end of financial year 2 (by 31 March 2020), 80% of all attendees of the Centres for Excellence Forum will feedback positively to the question:
Has the Delivery Partner developed and shared with you practical evidence and guidance that has supported your Centre to trial new and improved maths teaching methods? Yes or no.

KPI 3 – Evaluation Partner

- By the 31 May 2019 , the Delivery Partner will commission an independent Evaluation Partner. This Evaluation Partner will support the research methodology of the trials of the teaching approaches and use quantitative and qualitative analysis to determine whether the teaching approaches are having an impact.

- The evaluation reports must adhere to the guidance set out in the Magenta Book. The HM Treasury Magenta Book: Quality in policy impact evaluation was published by the government as supplementary guidance to its evaluation guidance. The document sets out the strengths and weaknesses of evaluation designs.

- The reports will also be accountable to the Government Social Research (GSR) five principles for publishing research and analysis in government .

- In order to achieve this KPI:

  - The report will be developed and published from financial year 2 onwards (by 31 March 2020 and 31 March 2021). The report will be deemed accurate and of a high quality by DfE’s Basic Skills Board on the impact of the teaching approaches being tested.

  - By the end of financial year 2 (by 31 March 2020) and financial year 3 (by 31 March 2021), 80% of all attendees of the Centres for Excellence Forum will feedback positively to the question:
Has the Delivery Partner and Evaluation Partner supported your Centre for Excellence to effectively trial, monitor and evaluate whether your teaching approaches are enhancing the quality of maths teaching? Yes or no.

KPI 4 – Leadership Training

- The Delivery Partner will be required to deliver high quality leadership training to the Centres for Excellence. This will cover:

  - How to effectively plan the programme & resources

  - How to develop networks that drive improvements across a range of institutions

  - Researching & trialling the teaching approaches

  - Developing curriculum and resources

- In order to achieve this KPI:

  - By 31 May 2019, the Delivery Partner will develop and deliver leadership training to 100% of maths leadership teams across 100% of Centres.

  - By 31 October 2019, training evaluation questionnaires (from a minimum of 50% of Centres) will achieve a minimum positive response of 90% to the question: 
Has this training supported you in the leadership of your Centre for Excellence? Yes or no.

KPI 5 Teacher Training

- The Delivery Partner will be required to develop and deliver high quality teacher training on how to successfully deliver the teaching approaches. This will cover:

  - Understanding & delivering the Teaching Approaches

  - Developing and delivering effective curriculum and teaching resources

  - Networking, collaborating and sharing best practice

- In order to achieve this KPI, the Delivery Partner will be required to:

  - By the end of financial year 2 (by 31 March 2020), the Delivery Partner will develop and deliver teacher training directly to over 100 teachers across the Centres or Maths Networks on how to successfully develop and deliver the new teaching approaches.

  - By the end of financial year 3 (by 31 March 2021), the Delivery Partner will develop and deliver teacher training to directly over 400 teachers across the Centres or Maths Networks. N.B. this is a scaled, cumulative figure.

  - By the end of financial year 2 (by 31 March 2020) and financial year 3 (by 31 March 2021), Training evaluation questionnaires (from a minimum of 50% of Centres) will achieve a minimum positive response of 90% to the question: 
Has this training supported you in the development of your understanding and delivery of the new teaching approaches? Yes or no.

KPI 6 – Developing Resources and Best Practice

- In financial years 2 (by 31 March 2020) and 3 (by 31 March 2021), the Delivery Partner will develop, identify (if existing already) and coordinate high quality teaching resources and materials relating to the teaching approaches and research undertaken. The resources will be deemed of high quality and useful by the Centres in trialling and embedding the teaching approaches.

- In order to achieve this KPI, the Delivery Partner will be required to:

  - At the Centre for Excellence Forum in financial year 3 (by March 2021), evaluation questionaires from a minimum of 50% of Centres will achieve a positive response of 80% to the question:
Is the Delivery Partner adequately supporting Centres to identify, use or develop the appropriate and relevant teaching materials & resources required to deliver effective teaching of the new teaching approaches? Yes or no.

  - The Delivery Partner in financial year 3 (by March 2021) will survey a minimum, random sample of 25 students per Centre to identify whether the teaching resources and materials are supporting their needs. 80% of all students surveyed will feedback positively to the question:
Are the teaching resources and materials being used of good quality and supporting you to improve at maths? Yes or no.

KPI 7 – Networking between Centres

- For each financial year of the contract, the Delivery Partner will coordinate a termly Centres for Excellence Forum, with three forums to be held in the period from contract signature to end July 2019.

- In order to achieve this KPI:

  - The Centres for Excellence Forum will be attended by nominated representatives of a minimum of 90% of all Centres

  - Evaluation questionnaires will achieve a minimum positive response of 90% to the question:
Has the Forum furthered your ability to network, share good practice and drive forward priorities to improve maths outcomes?

KPI 8 – Establishing Maths Networks

- The Delivery Partner is required to support the Centres for Excellence to develop wide reaching Maths Networks that facilitate the spreading and embedding of best practice.

- In order to achieve this KPI:

  - By the end of financial year 1 (by 31 March 2019) the Delivery Partner will ensure that every Centre has established a Maths Network and is supporting and sharing best practice with a minimum of 5 other institutions on (at least) a termly basis. This should include a mix of institution types.

  - By the end of financial year 2 (by March 2020) and 3 (by 31 March 2021), the Delivery Partner will ensure that every Centre has established a Maths Network and is supporting and sharing best practice with a minimum of 10 other institutions. This should include a mix of institution types.

| Year | Centres – Students indirectly reached | Partner providers – Students indirectly reached | Indicative student cumulative reach to be updated against learner census data |
| --- | --- | --- | --- |
| 1 | 100% | 0 | 11,500 |
| 2 | 100% | 33% | 41,500 10,000+20,000+(Yr 1 11,500) |
| 3 | 100% | 66% | 91,500 10,000+40,000 +(Yr 1 & 2 41,500) |
| 4 | 100% | 100% | 161,500 10,000+60,000 + (Yr 1 – 3 91,500) |

  - By financial year 1 (by 31 March 2019) the programme’s outputs (new resources, new teaching approaches or teachers who have engaged in maths training and support) should cumulatively, indirectly have reached the proportion of students indicated in the table above across the Centres and their Maths Networks.

  - By financial year 2 (by 31 March 2020) the programme’s outputs (new resources, new teaching methods or teachers who’ve engaged in maths teaching CPD) should cumulatively, indirectly have reached over the proportion of students indicated in the table above across the Centres and their maths networks.

  - By financial year 3 (by 31 March 2021) the programme’s outputs (new resources, new teaching methods or teachers who’ve engaged in maths teaching CPD) should cumulatively, indirectly have reached the proportion of students in the table above across the Centres and their maths networks.

Additional KPIs

- By the end of financial year 1 (by 31 March 2019), the Delivery Partner will agree with DfE additional KPIs linked to improved performance of maths attainment for students within Centres and across the Maths Networks. These KPIs will then be used in financial years 2 and 3 as a measure of impact.

- In addition, we would expect bids to include other KPIs linked to quality of provision and the measureable impact of activities and evidence of improved leadership (this is not an exhaustive list). We reserve the right to develop additional KPIs to the ones outlined above throughout the contracting process.

- Bidders are encouraged to propose KPIs in addition to those set out above. These KPIs should be measurable in a similar manner to those developed by DfE.

- For the purposes of this tender, DfE will only evaluate bids against the KPIs that are currently specified.

Charges Rebate

- Bidders must link payment of up to 15% of the total contract value per annum (see indicative figures at paragraph 5) (Maximum Charges Rebate) to the successful achievement of their KPIs split across the range of KPIs proposed on a sliding scale relative to the extent to which the KPI failed to be met.

- KPIs will be reviewed on an annual basis at the end of each financial year (by 31 March).

- Performance against KPIs will be reviewed at the end of each financial year. The review will ensure that future KPIs remain current and challenging. All changes to KPIs are to be agreed with ETF no later than end of May in each annual cycle.

- Failure to meet a KPI will not, of itself, be considered a breach of Contract. However, failure to achieve a KPI will indicate that the quality of the Services delivered has fallen short of the requirements and that consequently the charges should be reduced by a corresponding amount to reflect the loss of enjoyment of the services.

- Where there are multiple or significant failures, this will indicate particular cause for concern and in addition to any rebate due for non-achievement of a KPI, the DfE may implement a Remediation Process aimed at agreeing an action plan to improve performance to the required standard.

- This Remediation Process will be triggered where the Delivery Partner fails to deliver the annual target of three or more KPIs or misses a KPI by more than 10%. This Remediation Process is set out in Schedule 4 and Clause  21 of Schedule 2 of the Contract.

- Each KPI is assigned a proportion of the Maximum Charges Rebate, as detailed in the table below (the Charges Rebate). This represents the full Charges Rebate that could be applied in the event of non-performance of that KPI.

- For example, if the Maximum Charges Rebate is £200,000 for each Financial  Year, a KPI assigned 30% of the Charges Rebate would indicate that up to £60,000 could be subject to a Charges Rebate for underperformance against this KPI annually.

- Performance against KPIs will be monitored on a monthly basis (at the monthly meeting between DfE and the Delivery Partner), and discussed to determine if a Charges Rebate is likely to be applied at the end of each financial year. The KPIs will also be fully reviewed on an annual basis.

- If a KPI has not been met, the DfE will calculate the value of the Charges Rebate to be applied. This amount will be calculated on the following basis:

  - for any KPI with a binary, pass/fail outcome (i.e. was it delivered or not) shall automatically trigger the full [Charges Rebate] due for that KPI for that Contract Year (as detailed in the table below); and

  - for all other KPIs, a rate of 5% of the Maximum Charges Rebate for that Contract Year for that KPI per percentage point that performance has fallen below the relevant KPI. This applies to both targets expressed as percentage figures and absolute values.

- As a worked example, for the KPI to secure 90% of positive feedback from a survey of teachers by a given year which is given a maximum of £300,000 of annual Maximum Charges Rebate. At that year’s Assessment Point, the Delivery Partner secured 86% of positive feedback from teachers. This represents 96% of the target (86/90 * 100); therefore the DfE would apply a Charges Rebate of £60,000 (300,000 * 0.05 * 4) for that Contract Year.

- As a second worked example, the KPI to train a cumulative total of 100 teachers by a given year which is given a maximum of £525,000 of the annual Maximum Charges Rebate. At that year’s Assessment Point, the Delivery Partner trained 84 teachers. This represents 84% of the target; therefore the DfE would apply a Charges Rebate of £420,000 (525,000 * 0.05 * 16) for that Contract Year.

- Application of a Charges Rebate for failure to meet one or more KPIs will be done by payment of a KPI Credit by the Delivery Partner. Applicable KPI Credits will be either

  - deducted from the Supplier’s next monthly invoice; or

  - in the event that applicable KPI Credits exceed the value of the next monthly invoice or if no further Supplier invoices are due, the Supplier will be invoiced for payment of the difference by the DfE.

- The Delivery Partner may not pass on any element of the Charges Rebates to the Centres for Excellence or the Evaluaton Partner, with the exception of those relating to KPI3 and quality of evaluation. The DfE will monitor this through the monthly reporting process (and, if necessary, auditing procedure).

Underperformance and Remediation

- In addition to any KPI Credits where a Charges Rebate is due, if the Delivery Partner fails to meet the annual target of three or more KPIs (whether or not these are KPIs) at any Assessment Point, the Supplier will be expected to follow the Remediation Process set out in Schedule 4 and Clause 21 of Schedule 2 of the Contract:

- The Supplier should note that, if it has successfully completed a Remediation Plan but, at a later Assessment Point, again fails to meet the annual target of three or more KPIs (regardless of whether these particular KPIs have been missed previously or not), the DfE may enforce the Remediation Process again or may choose to terminate the Contract on written notice with immediate effect.

This page is intentionally blank

Schedule 5

Implementation and Project Plan

- The Contractor shall provide the Services in accordance with the Implementation and Project Plan set out below.

- The Implementation and Project Plan shall be sufficiently detailed as is necessary to manage the Services and any proposed changes are subject to the Change Control Procedure.

- The Contractor shall be responsible for implementing and managing the Services and for taking all such steps as may be necessary so as to ensure that from the Service Commencement Date the Contractor is able to provide the Services:

- 3.1	in accordance with the provisions of the Contract; and

- 3.2 	in a manner that maintains the continuity of Services to the DFE.

- The Contractor shall monitor its performance against the Implementation and Project Plan and report to the DFE monthly (or more frequently if so required by the DFE) on its performance.

- The Parties recognise that details of the Implementation and Project plan will need to be finalised after contract award.  As changes are agreed this Schedule 5 will be updated.

Implementation and Project Plan

Schedule 5  CfEM, ETF. All project plans and risk register are to be further clarified post contract award

Redacted – Commercial in Confidence

Schedule 6

Change Control Procedure

- 1.	The Parties acknowledge that minor changes to the Contract may be necessary to reflect operational and administrative procedures during the Term and that such minor changes may be agreed in writing between the Parties’ respective contract managers.

- 2.	The Contractor shall use reasonable endeavours to incorporate minor changes requested by the DFE within the current Charges and shall not serve a Contractor Notice of Change unless the change involves a demonstrable material increase to its costs or requires a material change to the Contract.

- 3.	Either Party may request a Variation provided that such Variation does not amount to a material change.

- 4.	The DFE may request a Variation by completing the Change Control Note and giving the Contractor sufficient information to assess the extent of the Variation and consider whether any change to the Charges are required in order to implement the Variation within a reasonable time limit specified by the DFE. If the Contractor accepts the Variation it shall confirm it in writing within 21 days of receiving the Change Control Note.

- 5.	If the Contractor is unable to accept the Variation or where the Parties are unable to agree a change to the Charges, the DFE may allow the Contractor to fulfil its obligations under the Contract without Variation or if the Parties cannot agree to the Variation the Dispute will be determined in accordance with clause 36.

- 6.	If the Contractor wishes to introduce a change to the Contract it may request a Variation by serving the Change Control Note on DFE.

- 7.	The DFE shall evaluate the Contractor’s proposed Variation in good faith, taking into account all relevant issues.

- 8.	The DFE shall confirm in writing within 21 days of receiving the Change Control Note if it accepts or rejects the Variation.

- 9.	The DFE may at its absolute discretion reject any request for a Variation proposed by the Contractor.

Change Control Note:

| Contract Number Change Control Number |  | DFE Contract / Programme Manager |  |
| --- | --- | --- | --- |
| Contractor |  | Original Contract Value (£) |  |
| Contract Start Date |  | Contract Expiry Date |  |

| Variation Requested |  |
| --- | --- |
| Originator of Variation (tick as appropriate) | DFE  Contractor  |
| Date |  |
| Reason for Variation |  |
| Summary of Variation (e.g. specification, finances, contract period) |  |
| Date of Variation commencement |  |
| Date of Variation expiry (if applicable) |  |
| Total Value of Variation £ (if applicable) |  |
| Payment Profile (if applicable) e.g. milestone payments |  |
| Revised daily rate (if applicable) |  |
| Impact on original contract (if applicable) |  |
| Supporting Information (please attach all supporting documentation for this Change Control) |  |
| Terms and Conditions | Save as herein amended all other terms and conditions of the Original Contract shall remain in full force and effect. |
| Variation Agreed For the Contractor: For the DFE: Signature……………………………….. Signature……………………………………….. Full Name………………………………. Full Name……………………………………… Title……………………………………… Title……………………………………………. Date……………………………………… Date…………………………………………… |  |

Please note that no works/services described in this form should be undertaken, and no invoices will be paid until both copies of the CCN are signed, returned and counter-signed.

| To be entered by the Commercial department: |  |  |  |
| --- | --- | --- | --- |
| Commercial Contact |  | Reference Number |  |
| Date received |  | EC Reference |  |

Schedule 7

Key Personnel and Key Sub-Contractors

N.B. ALL information contained within Schedule 7 is considered to be commercially or personally sensitive and is to be redacted in all published copies of this contract.

Key Sub-Contractors

- The Contractor may sub-contract its obligations under the Contract to the Sub-Contractors listed in the table below.

Schedule 8

[Not used]

Schedule 9

Departmental Security Standards

| “BPSS” “Baseline Personnel Security Standard” | is a level of security clearance described as pre-employment checks in the National Vetting Policy. Further information can be found at: https://www.gov.uk/government/publications/government-baseline-personnel-security-standard |
| --- | --- |
| “CCSC” “Certified Cyber Security Consultancy” | is NCSC’s approach to assessing the services provided by consultancies and confirming that they meet NCSC’s standards. This approach builds on the strength of CESG Listed Adviser Scheme (CLAS) and certifies the competence of suppliers to deliver a wide and complex range of cyber security consultancy services to both the public and private sectors. See website: https://www.ncsc.gov.uk/scheme/certified-cyber-consultancy |
| “CCP” “Certified Professional” | is a NCSC scheme in consultation with government, industry and academia to address the growing need for specialists in the cyber security profession and is building a community of recognised professionals in both the UK public and private sectors. See website: https://www.ncsc.gov.uk/scheme/certified-professional |
| “CC” “Common Criteria” | The Common Criteria scheme provides assurance that a developer’s claims about the security features of its product are valid and have been independently tested against recognised criteria. |
| “CPA” “Commercial Product Assurance” [formerly called “CESG Product Assurance”] | is an ‘information assurance scheme’ which evaluates commercial off the shelf (COTS) products and their developers against published security and development standards. These CPA certified products can be used by government, the wider public sector and industry. See website: https://www.ncsc.gov.uk/scheme/commercial-product-assurance-cpa |
| “Cyber Essentials” “Cyber Essentials Plus” | Cyber Essentials is the government backed, industry supported scheme to help organisations protect themselves against common cyber-attacks. Cyber Essentials and Cyber Essentials Plus are levels within the scheme. There are a number of certification bodies that can be approached for further advice on the scheme; the link below points to one of these providers: https://www.iasme.co.uk/apply-for-self-assessment/ |
| “Data” “Data Controller” “Data Processor” “Personal Data” “Sensitive Personal Data” “Data Subject”, “Process” and “Processing” | - shall have the meanings given to those terms by the Data Protection Act 1998, the GDPR, the LED and any applicable national implementing Laws as amended from time to time, and the DPA 2018 subject to Royal Assent to the extent that it relates to processing of personal data and privacy; (iii) all applicable Law about the processing of personal data and privacy. |
| “Department’s Data” “Department’s Information” | is any data or information owned or retained in order to meet departmental business objectives and tasks, including: (a) any data, text, drawings, diagrams, images or sounds (together with any repository or database made up of any of these components) which are embodied in any electronic, magnetic, optical or tangible media, and which are: (i) supplied to the Contractor by or on behalf of the Department; or (ii) which the Contractor is required to generate, process, store or transmit pursuant to this Contract; or (b) any Personal Data for which the Department is the Data Controller. |
| “DFE” “Department” | means the Department for Education. |
| “Departmental Security Standards” | means the Department’s security policy or any standards, procedures, process or specification for security that the Contractor is required to deliver. |
| “Digital Marketplace / GCloud” | The Digital Marketplace is the online framework for identifying and procuring cloud technology and people for digital projects. Cloud services (e.g. web hosting or IT health checks) are on the G-Cloud framework. |
| “FIPS 140-2” | is the Federal Information Processing Standard (FIPS) Publication 140-2, (FIPS PUB 140-2), entitled ‘Security Requirements for Cryptographic Modules’. This document is the de facto security standard used for the accreditation of cryptographic modules. |
| “Good Industry Practice” “Industry Good Practice” | means the exercise of that degree of skill, care, prudence, efficiency, foresight and timeliness as would be expected from a leading company within the relevant industry or business sector. |
| “Good Industry Standard” “Industry Good Standard” | means the implementation of products and solutions, and the exercise of that degree of skill, care, prudence, efficiency, foresight and timeliness as would be expected from a leading company within the relevant industry or business sector. |
| “GSC” “GSCP” | means the Government Security Classification Policy which establishes the rules for classifying HMG information. The policy is available at: https://www.gov.uk/government/publications/government-security-classifications |
| “HMG” | means Her Majesty’s Government. |
| “ICT” | means information and communications technology (ICT) and is used as an extended synonym for information technology (IT), used to describe the bringing together of enabling technologies used to deliver the end-to-end solution. |
| “ISO/IEC 27001” “ISO 27001” | is the International Standard for Information Security Management Systems Requirements. |
| “ISO/IEC 27002” “ISO 27002” | is the International Standard describing the Code of Practice for Information Security Controls. |
| “ISO 22301” | is the International Standard describing for Business Continuity. |
| “IT Security Health Check (ITSHC)” “IT Health Check (ITHC)” “Penetration Testing” | means an assessment to identify risks and vulnerabilities in systems, applications and networks which may compromise the confidentiality, integrity or availability of information held on that IT system. |
| “Need-to-Know” | the Need-to-Know principle is employed within HMG to limit the distribution of classified information to those people with a clear ‘need to know’ in order to carry out their duties. |
| “NCSC” | The National Cyber Security Centre (NCSC), formerly CESG, is the UK government’s National Technical Authority for Information Assurance. The NCSC website is https://www.ncsc.gov.uk. |
| “OFFICIAL” “OFFICIAL-SENSITIVE” | The term ‘OFFICIAL’ is used to describe the baseline level of ‘security classification’ described within the Government Security Classification Policy (GSCP) which details the level of protection to be afforded to information by HMG, for all routine public sector business, operations and services. The ‘OFFICIAL–SENSITIVE’ caveat is used to identify a limited subset of OFFICIAL information that could have more damaging consequences (for individuals, an organisation or government generally) if it were lost, stolen or published in the media, as described in the Government Security Classification Policy. |
| “Secure Sanitisation” | Secure sanitisation is the process of treating data held on storage media to reduce the likelihood of retrieval and reconstruction to an acceptable level. Some forms of sanitisation will allow you to re-use the media, while others are destructive in nature and render the media unusable. Secure sanitisation was previously covered by “Information Assurance Standard No. 5 – Secure Sanitisation” (“IS5”) issued by the former CESG. Guidance can now be found at: https://www.ncsc.gov.uk/guidance/secure-sanitisation-storage-media The disposal of physical documents and hardcopy materials advice can be found at: https://www.cpni.gov.uk/secure-destruction |
| “Security and Information Risk Advisor” “CCP SIRA” “SIRA” | The Security and Information Risk Advisor (SIRA) is a role defined under the NCSC Certified Professional (CCP) Scheme. See also: https://www.ncsc.gov.uk/articles/about-certified-professional-scheme. |
| “SPF” “HMG Security Policy Framework” | This is the definitive HMG Security Policy which describes the expectations of the Cabinet Secretary and Government’s Official Committee on Security on how HMG organisations and third parties handling HMG information and other assets will apply protective security to ensure HMG can function effectively, efficiently and securely. It is published online at: https://www.gov.uk/government/publications/security-policy-framework. |
| “Tailored Assurance” [formerly called “CTAS”, or, “CESG Tailored Assurance”] | is an ‘information assurance scheme’ which provides assurance for a wide range of HMG, MOD, Critical National Infrastructure (CNI) and public sector customers procuring IT systems, products and services, ranging from simple software components to national infrastructure networks. Further details are available online at https://www.ncsc.gov.uk/documents/ctas-principles-and-methodology. |

  - The Contractor shall comply with Departmental Security Standards for Contractors which include but are not constrained to the following clauses.

  - Where the Contractor will provide ICT products or services or otherwise handle information at OFFICIAL level on behalf of the Department, the requirements under Cabinet Office Procurement Policy Note – Use of Cyber Essentials Scheme or Cyber Essentials Plus certification – Action Note 09/14 dated 25 May 2016 (https://www.gov.uk/government/publications/procurement-policy-note-0914-cyber-essentials-scheme-certification), or any subsequent updated document, are mandated; that “contractors supplying products or services to HMG shall have achieved, and retain certification at the appropriate level, under the HMG Cyber Essentials Scheme”. The certification scope must be relevant to the services supplied to, or on behalf of, the Department.

  - The Contractor shall have achieved, and be able to maintain, independent certification to ISO/IEC 27001 (Information Security Management Systems Requirements). The ISO/IEC 27001 certification must have a scope relevant to the services supplied to, or on behalf of, the Department. The scope of certification and the statement of applicability must be acceptable, following review, to the Department, including the application of controls from ISO/IEC 27002 (Code of Practice for Information Security Controls).

  - The Contractor shall follow the UK Government Security Classification Policy (GSCP) in respect of any Departmental Data being handled in the course of providing this service, and will handle this data in accordance with its security classification. (In the event that the Contractor has an existing Protective Marking Scheme then the Contractor may continue to use this but must map the HMG security classifications against it to ensure the correct controls are applied to the Departmental Data).

  - Departmental Data being handled in the course of providing an ICT solution or service must be segregated from all other data on the Contractor’s or sub-contractor’s own IT equipment to protect the Departmental Data and enable the data to be identified and securely deleted when required. In the event that it is not possible to segregate any Departmental Data then the Contractor and any sub-contractor shall be required to ensure that it is stored in such a way that it is possible to securely delete the data in line with Clause 1.15.

  - The Contractor shall have in place and maintain physical security, in line with those outlined in ISO/IEC 27002 including, but not limited to, entry control mechanisms (e.g. door access) to premises and sensitive areas.

  - The Contractor shall have in place and maintain an access control policy and process for the logical access (e.g. identification and authentication) to ICT systems to ensure only authorised personnel have access to Departmental Data.

  - The Contractor shall have in place and shall maintain procedural, personnel, physical and technical safeguards to protect Departmental Data, including but not limited to: physical security controls; good industry standard policies and process; anti-virus and firewalls; security updates and up-to-date patching regimes for anti-virus solutions; operating systems, network devices, and application software, user access controls and the creation and retention of audit logs of system use.

  - Any data in transit using either physical or electronic transfer methods across public space or cyberspace, including mail and courier systems, or third party provider networks must be protected via encryption which has been certified to FIPS 140-2 standard or a similar method approved by the Department prior to being used for the transfer of any Departmental Data.

  - Storage of Departmental Data on any portable devices or media shall be limited to the absolute minimum required to deliver the stated business requirement and shall be subject to Clause 1.11 and 1.12 below.

  - Any portable removable media (including but not constrained to pen drives, flash drives, memory sticks, CDs, DVDs, or other devices) which handle, store or process Departmental Data to deliver and support the service, shall be under the control and configuration management of the Contractor or sub-contractors providing the service, shall be both necessary to deliver the service and shall be encrypted using a product which has been certified to FIPS140-2 standard or another encryption standard that is acceptable to the Department.

  - All portable ICT devices, including but not limited to laptops, tablets, smartphones or other devices, such as smart watches, which handle, store or process Departmental Data to deliver and support the service, shall be under the control and configuration management of the Contractor or sub-contractors providing the service, and shall be necessary to deliver the service. These devices shall be full-disk encrypted using a product which has been certified to FIPS140-2 standard or another encryption standard that is acceptable to the Department.

  - Whilst in the Contractor’s care all removable media and hardcopy paper documents containing Departmental Data must be handled securely and secured under lock and key when not in use and shall be securely destroyed when no longer required, using either a cross-cut shredder or a professional secure disposal organisation.

  - When necessary to hand carry removable media and/or hardcopy paper documents containing Departmental Data, the media or documents being carried shall be kept under cover and transported in such a way as to ensure that no unauthorised person has either visual or physical access to the material being carried. This clause shall apply equally regardless of whether the material is being carried inside or outside of company premises.

  - At the end of the Contract or in the event of equipment failure or obsolescence, all Departmental information and data, in either hardcopy or electronic format, that is physically held or logically stored on the Contractor’s ICT infrastructure must be securely sanitised or destroyed and accounted for in accordance with the current HMG policy using a NCSC approved product or method. Where sanitisation or destruction is not possible for legal, regulatory or technical reasons, such as a Storage Area Network (SAN) or shared backup tapes, then the Contractor or sub-contractors shall protect the Department’s information and data until the time, which may be long after the end of the Contract, when it can be securely cleansed or destroyed.

  - Access by Contractor or sub-contractor staff to Departmental Data shall be confined to those individuals who have a “need to know” in order to carry out their role; and have undergone mandatory pre-employment screening, to a minimum of HMG Baseline Personnel Security Standard (BPSS); or hold an appropriate National Security Vetting clearance as required by the Department. All Contractor or sub-contractor staff must complete this process before access to Departmental Data is permitted.

  - All Contractor or sub-contractor employees who handle Departmental Data must have annual awareness training in protecting information.

  - The Contractor shall, as a minimum, have in place robust Business Continuity arrangements and processes including IT disaster recovery plans and procedures that conform to ISO 22301 to ensure that the delivery of the contract is not adversely affected in the event of an incident. An incident shall be defined as any situation that might, or could lead to, a disruption, loss, emergency or crisis to the services delivered. If an ISO 22301 certificate is not available the supplier will provide evidence of the effectiveness of their ISO 22301 conformant Business Continuity arrangements and processes including IT disaster recovery plans and procedures. This should include evidence that the Contractor has tested or exercised these plans within the last 12 months and produced a written report of the outcome, including required actions.

  - Any suspected or actual breach of the confidentiality, integrity or availability of Departmental Data being handled in the course of providing this service, or any non-compliance with these Departmental Security Standards for Contractors, or other Security Standards pertaining to the solution, shall be investigated immediately and escalated to the Department by a method agreed by both parties.

  - The Contractor shall ensure that any IT systems and hosting environments that are used to handle, store or process Departmental Data shall be subject to independent IT Health Checks (ITHC) using a NCSC approved ITHC provider before go-live and periodically (at least annually) thereafter. The findings of the ITHC relevant to the service being provided are to be shared with the Department and all necessary remedial work carried out. In the event of significant security issues being identified, a follow up remediation test may be required.

  - The Contractor or sub-contractors providing the service will provide the Department with full details of any storage of Departmental Data outside of the UK or any future intention to host Departmental Data outside the UK or to perform any form of ICT management, support or development function from outside the UK. The Contractor or sub-contractors will not go ahead with any such proposal without the prior written agreement from the Department.

  - The Department reserves the right to audit the Contractor or sub-contractors providing the service within a mutually agreed timeframe but always within seven days of notice of a request to audit being given. The audit shall cover the overall scope of the service being supplied and the Contractor’s, and any sub-contractors’, compliance with the clauses contained in this Section.

  - The Contractor shall contractually enforce all these Departmental Security Standards for Contractors onto any third-party suppliers, sub-contractors or partners who could potentially access Departmental Data in the course of providing this service.

  - The Contractor and sub-contractors shall undergo appropriate security assurance activities as determined by the Department. The Contractor and sub-contractors shall support the provision of appropriate evidence of assurance and the production of the necessary security documentation such as completing the DFE Security Assurance Model (DSAM) process or the Business Service Assurance Model (BSAM). This will include obtaining any necessary professional security resources required to support the Contractor’s and sub-contractors’ security assurance activities such as: a NCSC Certified Cyber Security Consultancy (CCSC) or NCSC Certified Professional (CCP) Security and Information Risk Advisor (SIRA).

  - Where the Contractor is delivering an ICT solution to the Department they shall design and deliver solutions and services that are compliant with the HMG Security Policy Framework in conjunction with current NCSC Information Assurance Guidance and Departmental Policy. The Contractor will provide the Department with evidence of compliance for the solutions and services to be delivered. The Department’s expectation is that the Contractor shall provide written evidence of:

- Existing security assurance for the services to be delivered, such as: PSN Compliance as a PSN Customer and/or as a PSN Service; NCSC (formerly CESG) Tailored Assurance (CTAS); inclusion in the Common Criteria (CC) or Commercial Product Assurance Schemes (CPA); ISO/IEC 27001 / 27002 or an equivalent industry level certification. Documented evidence of any existing security assurance or certification shall be required.

- Existing HMG security accreditations or assurance that are still valid including: details of the body awarding the accreditation; the scope of the accreditation; any caveats or restrictions to the accreditation; the date awarded, plus a copy of the residual risk statement. Documented evidence of any existing security accreditation shall be required.

- Documented progress in achieving any security assurance or accreditation activities including whether documentation has been produced and submitted. The Contractor shall provide details of who the awarding body or organisation will be and date expected.

Schedule 10

Data Processing, Personal Data and Data Subjects

- The Contractor shall process and store personal data in accordance with the schedule below, as amended from time to time with the agreement of the Parties.

- The Contractor shall comply with any further written instruction with respect to processing given by DFE, and the Parties shall incorporate any such further instructions into this schedule.

| Description | Details |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Subject matter of the processing | Centres for Excellence Action Plans | Training and support for teachers and leaders | Resources evaluation | Ongoing evaluation of the effectiveness of the teaching approaches by the Evaluation Partner | Maths Networks support |
| Duration of the processing | Throughout the contract | Throughout the contract | To be processed in financial year 3 (by 31 March 2021). | Throughout the contract. | Throughout the contract |
| Nature and purposes of the processing | To identify contact information and details of the institution’s actions and budget. | To communicate with Centres and Maths Networks about training and to complete evaluation surveys. | To survey students on the effectiveness of the resources being developed and trialled across the Centres and Maths Networks. | To collate data and information to determine whether the new teaching approaches and resources are having an impact on the quality of teaching across the Centres and Maths Networks. | To communicate with institutions within each Centre’s Maths Network. |
| Type of Personal Data | Contact details of key personnel (e-mail, phone numbers, addresses and names) and their roles within the Centre for Excellence. | Contact details of teachers and leaders across the Centres and Maths Networks (name, e-mail, phone number, address). Survey responses from teachers and leaders to be anonymised. | Survey responses on the effectiveness of the teaching resources being used from students to be anonymised at source. | Student attainment, attendance records, teacher satisfaction information and any other agreed data to monitor and evaluate the impact of the teaching approaches on the quality of teaching. | Contact details of teachers and leaders across the Centres and Maths Networks (name, e-mail, phone number, address). |
| Categories of Data Subject | Third party individuals relevant to the wider programme, relevant students / pupils |  |  |  |  |
| Plan for return and destruction of the data once the processing is complete UNLESS requirement under union or member state law to preserve that type of data | Data to be held securely throughout the lifetime of the Contract and to be destroyed at the end of the Contract. | Data to be held securely throughout the lifetime of the Contract and to be destroyed at the end of the Contract. | Survey data should be anonymised. Data to be held securely throughout the lifetime of the Contract and to be destroyed at the end of the Contract. | Data should be anonymised, held securely and destroyed at the end of the contract. | Data to be held securely throughout the lifetime of the Contract and to be destroyed at the end of the Contract. |
| Approved sub-processors | University of Nottingham B.I.T., Eedi, Evaluation partner (TBC) | Touchconsulting, AoC, University of Nottingham, PET-Xi, Evaluation partner (TBC) | University of Nottingham, Pearson, Evaluation Partner (TBC) | University of Nottingham, B.I.T., Eedi, Evaluation Partner (TBC) | AoC, PET-Xi, Evaluation Partner (TBC) |

- In the event that the Parties agree that they are joint data controllers for the purposes of Data Protection Legislation, the data protection provisions in the Contract shall be amended in accordance with the Change Control Procedure set out in the Contract.

Schedule 11

Redacted – Commercial in Confidence

Schedule 12

Redacted – Commercial in Confidence

Smith Review (2017) https://www.gov.uk/government/publications/smith-review-of-post-16-maths-report-and-government-response

Industrial Strategy – BEIS (2017) https://www.gov.uk/government/publications/industrial-strategy-building-a-britain-fit-for-the-future

Attainment Data – DFE (2018) https://www.gov.uk/government/statistics/level-2-and-3-attainment-by-young-people-aged-19-in-2017

Attainment Data – DFE (2018) https://www.gov.uk/government/statistics/level-2-and-3-attainment-by-young-people-aged-19-in-2017

? CFE Research - https://www.gov.uk/government/publications/english-and-maths-for-16-to-18-year-olds-effective-teaching

BIT Research - https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/683822/Improving_engagement_and_attainment_in_maths_and_English_courses.pdf

EEF - https://educationendowmentfoundation.org.uk/projects-and-evaluation/projects/mathematics-mastery

EEF - https://educationendowmentfoundation.org.uk/projects-and-evaluation/projects/embedding-contextualisation-in-english-and-mathematics-gcse-teaching/

University of Nottinham and EEF - https://www.nottingham.ac.uk/research/groups/crme/projects/maths-for-life/index.aspx

MEI and EEF - Embedding contextualisation in English and mathematics GCSE teaching https://educationendowmentfoundation.org.uk/projects-and-evaluation/projects/embedding-contextualisation-in-english-and-mathematics-gcse-teaching/

Where no minimum level is specified, the Bidder should propose a value.

https://www.gov.uk/government/publications/the-magenta-book

https://www.gov.uk/government/publications/government-social-research-publication-protocols