## Section 3 - Primary School
3 | SCHEDULE OF WORKS
SECTION THREE
3.1 | Scope Of Works
The works comprise of all building works necessary for the replacement of the roof coverings and upgrading of insulation to the Andre Malraux Primary School Building. The scope of works also includes for other associated repairs at roof level and those internal works resultant from intrusive works.
The construction period is anticipated to commence on the 7th July 2017, during the schools summer holiday break. Works are to be completed within approximately 12 weeks.
Refer to the preliminaries for sectional completion dates.
3.2 | Notes Generally
No hot works or asphalting will be permitted when the school is in operation.
The Contractor is to price each item separately. It is important that prices are not grouped together for works common to all roofs as the Client requires to have a complete itemised schedule on a roof by roof basis.
Where the clause numbers or sections are referred to, all of these numbers refer to the relevant clauses/sections in Section 2 of this specification and the Contractor is deemed to have included in his price, all those works necessary and contained within the standard clauses where referred to.
Where quantities of various elements have been provided within the schedule of works, these are for the Contractor’s guidance only, except where specifically stated otherwise. The Contractor should check all quantities themselves.
The Contractor should supply the Contract Administrator with a telephone number where he may be contacted 24 hours a day and at weekends during the works.
It is the Contractor’s responsibility to maintain close liaison with the Contract Administrator, the Headteacher and Ms Justine Pare, Property Manager for Lycée Français Charles De Gaulle, to ensure full co-operation to carry out the works. In this respect, the Contractor should appoint a Site Manager for the works to be present at all times throughout the duration of the project.
Where buildings are opened to the elements during roof replacement/repair works, this should be undertaken in bays/sections which shall allow the contractor to provide adequate protection to ensure weather tightness until work recommences.
No allowance has been made for temporary roofs. The contractor will be responsible for ensuring the building is in a watertight condition at the end of every working day. Water damage caused by the contractor not making adequate provisions will be rectified at the contractors cost.
Replacement of skylights/roof lights and lantern lights over student/school areas shall only be permitted when the school is closed (Out of Hours) or within the holiday period.
Deliveries are not permitted between 8.00 to 10.00am, and between 2.30 am to 4.30pm when the school is in operation.
The contractor shall make every effort to ensure the majority of waste and materials are delivered during the holiday period. Vehicle movements during school operation will be restricted during the start of the day, playtimes, lunch times and end of the day.
3.3 | General Items Applicable to all Works
3.3.1 | Temporary Protection
The Contractor shall provide sheeting over all openings where works are in progress and seal to prevent dust etc., from percolating through to the occupied space at all levels, together with outer areas of the building and maintain for the duration of the project. If this occurs, then the Contractor is to clean up all affected areas as soon as possible, to the satisfaction of the Contract Administrator and the Property Manager.
All existing glazing, roof lights, walls, doors and other parts of the building fabric and services are to be adequately protected against damage.
The Contractor, either by himself or staff, shall not obstruct any rights of way, entrance or anything that might amount to a nuisance or annoyance. Any complaint must be communicated at once to the Contract Administrator.
3.3.2 | Cleanliness
The Contractor is to ensure that the site is kept clean at all times. The contractor must maintain and keep all access routes clear at all times
On completion clear away all builder’s rubbish and materials and leave clean and ready for occupation at handover.
3.4 | Primary School Building
3.4.1 | Scaffolding and Temporary Works
The erection and striking of scaffolding shall only be undertaken during the Schools holiday period or during weekends.
Where minor alterations are required to scaffolding during the works where clashes/over sailing occurs the project team accept this can occur during term time when students are off site (Early morning / Late afternoon).
Contractor is to include for all required gantries to enable scaffolding to over sail roofs below where replacement of roof coverings is required. Contractor is also to over sail items that are to remain in place such as entrance canopies etc.
Provide, erect, maintain and dismantle on completion, all necessary scaffolding and temporary access required to undertake the works all as indicated within the specification.
Allow for garden clearance as required to safety erect scaffolding. Including cutting back of trees and shrubbery, and temporarily relocating items.
Scaffolding should be erected in accordance with BS EN 12811-1.
Means of access should be suitable for the full refurbishment at roof level and other associated works as outlined within the Specification. Particular attention should be paid to:
a) | All entrances surrounding the premises are to be maintained at all times and adequately protected etc.
b) | Tying in to avoid or reduce damage to the faces of masonry units.
c) | Avoiding physical damage during erection and striking.
d) | Use of base plates to isolate stones or other services from scaffold standards.
e) | Avoiding rust staining to the building.
f) | Capping pole ends.
g) | A scaffold alarm is to be provided on the first lift for the duration of the project. These are to be monitored 24hr by an off site provider.
h) | The existing fire escapes should be maintained during the construction phase at all times without exception.
I) | The lower sections of scaffolding are to be double boarded and sheeted with reinforced sheeting for the duration.
j) | All standards are to be foamed and cable tied.
k) | Adequate fans are to be provided to provide full protection to the surrounding playground areas, which are to remain in full use.
l) | Provide all necessary warning notices.
m) | The contractor is to also include for all necessary access towers/material hoists and skips/chutes for disposal from site.
The contractor is to state here the separate additional cost for the provision of a temporary roof over Roof 10 only. Do not carry the inserted cost through to the summary.
£………………………………
3.4.2 | Contractors Compound
This compound shall serve all works and will be the only compound on site.
The contractor shall be provided the area has highlighted on Drawing 17.334.103. This will be the only area permitted for the site compound.
Prior to using areas for compounds and welfare the Contractor will be required to undertake and submit a photographic schedule of the area.
Adequate protection to existing surfaces, trees, shrubs and services must be afforded.
The compound shall comply with the CDM Regulations. In additional an Office and Meeting room shall be provided. The meeting room can also be the canteen.
No drainage is available in this area of the site. The contractor shall allow for their own disposal of waste. It is assumed the contractor will install temporary site WC's.
All materials, scaffolding etc. must be stored neatly.
The contractor shall be permitted to use water and electric from the school. However, the contractor shall bear the full cost of installing such supplies. All cabling / pipework routes must be fully clipped to boundaries to avoid damage.
3.4.3 | External Hoarding
The contractors compound shall be fully hoarded with access gates as required.
Provide 100 x 50mm timber posts, locate within surface mounted steel base plates, resin fixed using M12 bolts / or set within concrete.
Provide hoarding / plywood 18mm WBP to height of 2.4m. At low level provide and fix 200mm plywood skirting detail and head detail.
Provide two large Perspex windows to enable pupils to safely view the compound to prevent a rush of pupils during opening of the gates.
Prepare and decorate hoarding using white egg shell, in accordance with Part 2B.
Allow for ledged and braced access doors and gates, fully ply lined. Provide and fit digital lock or similar to all hoarding doors and gates as required to secure work areas etc.
Roof replacement
Refer to drawings:
17.334.001 - Existing site plan and roof plan
17.334.002 - Not issued
17.334.003 - Not issued
17.334.004 - Proposed Roof Plan
17.334.100 - Existing plans and elevations
17.334.101 - Proposed plans and elevations
17.334.102 - Proposed sections and details
17.334.103 - Contractors compound
3.6 | Roof 01
3.6.1 | Replacement of Flat Roof Covering
Refer to Permanite Specification included in Section 2A
Strip existing asphalt roof coverings, stones, debris and all associated details and clear from site. Take back to concrete roof deck.
Contractor to note that no temporary roof is being provided and the roof is to remain watertight for the duration of the project. In this respect the works are to be undertaken in manageable bays in an approved manner to ensure that the building remains watertight at all times.
| See preliminaries for Provision Sum for repairs to screed to existing roof decking. | Inc
Contractor is to allow for scheduling and programming the attendance of the CA to view the exposed roof structure and advise if further works are required.
Provide and lay new insulated asphalt roof coverings in accordance with Section 2A. The Main Contractor is to note that the client wishes to take advantage of the 20 year Permanite IKO Single Point insurance backed guarantee. In this respect the installation of new asphalt finishes are only to be carried out by an approved Permanite installer.
Provide and install min 150mm thick (Thickness dependant on location) IKO enertherm PIR ALU cut to falls insulation. Contractor to obtain cut to falls drawings for approval prior to ordering.
The existing outlets are being retained, allow to form sumps around these outlets as required.
To the perimeter of the roof install IKO termination trim / upstand trim. Lead flashings are not to be used due to theft.
The Main Contractor is not to alter the scope of the works from the specification provided by Permanite without the express permission with both the CA and IKO PLC.
Provide and lay new insulated asphalt roof system complete as indicated on the drawings and as detailed in the specification provided by Permanite.(section 2A)
3.6.2 | Works to Parapets
Carefully remove all redundant fixings, brackets etc. to parapets and clear away.
Carefully remove all existing copings to the parapet wall and put to one side for reuse. Allow for mechanical removal due to weight, existing copings are not to be cut down.
To all parapets allow to carefully remove the existing render (where existing), ensuring that damage to the brick face is minimised and the render is removed in its entirety.
Install an stainless steel expanded metal larvae to the brickwork and secure at 100mm centres with stainless steel masonry fixings.
Using a 1:1:4 mortar, render the parapet walls to smooth finish.
Re lay coping stones on a level bed of 1:1:6 mortar, on a new ICOPAL polyethylene DPC in accordance with the Manufactures guidelines and fully point in all joints on completion.
PQ | Allow a provisional quantity of 10no 500mm sandstone replacement coping stones to replace those damaged or severely weathered. The replacements are to match existing, C.A to approve prior to installation.
PQ | Allow a provisional quantity of 40lm of pointing replacement. Rake out defective pointing to the external face of the parapet and re point with a 1:1:6 ratio mortar. Colour: To match existing. C.A to measure and instruct prior to undertaking.
3.6.3 | Outlets through parapet
Allow to remove the existing lead work that passes through the brickwork parapets and clear away.
Replace the lead on a like for like basis using code 4 lead in accordance with the LSA guidelines. Where required allow to line the bottom of the outlet using WBP 18mm plywood.
Lead to be cut into the brickwork matching the stepped detail currently provided. Upon completion, wedge using lead and seal using a grey low modulus silicone.
3.6.3 | Works to Chimney Stack
The chimney is operational. For the duration of the works to the chimney, the boiler much be shut down and locked off. The contractor is to liaise with site staff to ensure this is carried out.
The contractor is to ensure minimal debris enters the chimney by installing a temporary cover and balloons to the flues. Any debris entering the chimney must be removed and cleaned.
Carefully remove the existing flaunching's and debris to the chimney crown.
To the uppermost 15no brickwork courses, carefully rake out the mortar bed to depth at least twice the width of the joint, not more than 20mm. The joints to the creasing tiles should also be raked out.
To all to raked out joints allow to re-point in a 1:1:6 ratio mortar. Colour: To match existing. C.A to approve prior to installation.
To the chimney crown, allow to replace the flaunching using a 1:1:6 ratio mortar.
PQ | Allow a for the provisional quantity of 30no replacement bricks. Rake out and remove bricks as instructed by C.A, bed in using 1:1:6 mortar. Colour: To match existing. C.A to measure and instruct prior to undertaking.
3.6.4 | Heli-Bar Repair to Chimney Stack
PQ | Allow a provisional quantity of 10lm of Heli-bar repair. The mortar beds of 1000mm in length should be raked out to a minimum depth of 40mm. Wash out joint and leave clear of debris.
Inject a bead of Heli bond along the back of the mortar bed and push in the Heli bar into place.
Inject a further bead of Heli bond over the Heli bar finishing 12mm from the face of the brickwork.
Allow to point with a 1:3:6 ratio mortar, colour to match existing. Sample area to be approved by the C.A.
3.6.5 | Overhaul of cast Iron Rainwater Goods
Allow to carefully remove gutters, downpipes, hoppers and bracketry to all elevations.
Using mechanical means, clear debris and corrosion from the surface. Particular attention is to be paid to the internal faces of the joints.
Where the cast iron is cracked, the sections are to be retained and repaired using a liquid metal system. Once repaired allow to file down liquid metal, flush with original surface.
Include for replacing all defective brackets, clips and fittings, with a cast iron replacement.
Provide and install min 150mm thick (Thickness dependant on location) IKO enertherm PIR ALU cut to falls insulation. Contractor to obtain cut to falls drawings for approval prior to ordering.
A black low modulus silicone or flexible caulking should be used applied to the joints upon reinstatement. Replacement stainless steel nuts, bolts and washers should be used.
Decorate all cast iron rainwater goods in accordance with the Paint Specification in Section 2B. Colour: Black
Water test upon completion.
3.6.6 | Replacement of PVCu Rainwater Goods
Remove all PVCu rainwater goods, clips and bracketry and clear away.
Replace all rainwater goods with black PVCu heritage products to match the existing cast iron products in size and appearance. C.A to approve prior to ordering.
Seal all joints using a black low modulus silicone.
All brackets, clips and hoppers to be screwed with stainless steel screws and washers.
Water test upon completion.
3.6.7 | Services
Allowance should be made to test the cables/services to establish whether they are live or redundant. All redundant cables should be removed and disposed of, whilst those that are live should be carefully unclipped and set aside.
Upon completion of the works all live cables should be adequately clipped to the inner parapet walls using Stainless Steel P clips.
3.7 | Roof 02
Below clauses to include for new roof covering and roof light to extension under Section 5
3.7.1 | Replacement of Flat Roof Covering
Refer to Permanite Specification included in Section 2A
Strip existing asphalt roof coverings, debris, stone and all associated details and clear from site. Take back to concrete roof deck.
Contractor to note that no temporary roof is being provided and the roof is to remain watertight for the duration of the project. In this respect the works are to be undertaken in manageable bays in an approved manner to ensure that the building remains watertight at all times.
See preliminaries for Provision Sum for repairs to screed to existing roof decking.
Contractor is to allow for scheduling and programming the attendance of the CA to view the exposed roof structure and advise if further works are required.
Provide and lay new insulated asphalt roof coverings in accordance with Section 2A. The Main Contractor is to note that the client wishes to take advantage of the 20 year Permanite IKO Single Point insurance backed guarantee. In this respect the installation of new asphalt finishes are only to be carried out by an approved Permanite installer.
Provide and install min 150mm thick (Thickness dependant on location) IKO enertherm PIR ALU cut to falls insulation. Contractor to obtain cut to falls drawings for approval prior to ordering.
The existing outlets are being retained, allow to form sumps around these outlets as required.
To the perimeter of the roof install IKO termination trim / upstand trim. Lead flashings are not to be used due to theft.
Where existing services penetrate the roof covering allow to install lead code 4 collars and seal with grey silicon sealant.
The Main Contractor is not to alter the scope of the works from the specification provided by Permanite without the express permission with both the CA and IKO PLC.
Provide and lay new insulated asphalt roof system complete as indicated on the drawings and as detailed in the specification provided by Permanite within Section 2A
3.7.2 | Works to Parapets
Carefully remove all redundant fixings, brackets etc. to parapets and clear away.
Carefully remove all existing copings to the parapet wall and put to one side for reuse. Allow for mechanical removal due to weight, existing copings are not to be cut down.
To all parapets allow to carefully remove the existing render (where existing), ensuring that damage to the brick face is minimised and the render is removed in its entirety.
Install an stainless steel expanded metal larvae to the brickwork and secure at 100mm centres with stainless steel masonry fixings.
Using a 1:1:4 mortar, render the parapet walls to smooth finish.
Re lay coping stones on a level bed of 1:1:6 mortar, on a new ICOPAL polyethylene DPC in accordance with the Manufactures guidelines and fully point in all joints on completion.
PQ | Allow a provisional quantity of 15no 500mm sandstone replacement coping stones to replace those damaged or severely weathered. The replacements are to match existing, C.A to approve prior to installation.
PQ | Allow a provisional quantity of 80lm of pointing replacement. Rake out defective pointing to the external face of the parapet and re point with a 1:1:6 ratio mortar. Colour: To match existing. C.A to measure and instruct prior to undertaking.
3.7.3 | Lead works
Allow to remove the existing lead work that passes through the brickwork parapets and clear away.
Replace the lead on a like for like basis using code 4 lead in accordance with the LSA guidelines. Where required allow to line the bottom of the outlet using WBP 18mm plywood.
Lead to be cut into the brickwork matching the stepped detail currently provided. Upon completion, wedge using lead and seal using a grey low modulus silicone.
3.7.4 | Roof Lights to be removed
Refer to Drawings to confirm roof light removal.
Remove existing roof lights and clear away. Refer to the asbestos survey within the PCI, asbestos containing gaskets / rope is known to exist. The contractor shall be responsible to removal and disposal.
Allow to dismantle roof light and clear away.
Allow to cut back the upstands ensuring they are left level with the roof deck. Make good any defects and ensure any protruding reinforcement bars are cut back and receive a coating of red-oxide primer.
Allow to trim out the opening with pressure treated timber (minimum 100mm x 50mm) and affix with Fischer Stainless steel concrete screws. Install noggins, ensuring installation at 400mm centres.
Install an 22mm WBP Plywood deck ensuring a tight and flush fitment with the existing roof deck. Leave ready to receive new insulation and roof covering.
Internally allow to install timber counter battens as required to take new plasterboard finish 25mm higher than the existing ceiling finishes. This will leave the outline of the original roof light. Install two layers of tapered edge 15mm fire line over new battens. Fill and sand as required. Decorate in accordance with Section 2B. White in colour.
3.7.5 | Roof Lights to be replaced
Refer to Drawings to confirm roof light replacement.
Remove existing roof lights and clear away. Refer to the asbestos survey within the PCI, asbestos containing gaskets / rope is known to exist. The contractor shall be responsible to removal and disposal.
Refer to Appendix C to confirm what window need to be electronically openable.
Internally, allow to remove vertical linings taking back to concrete structure.
Allow for raising of the perimeter upstands in tantalised timber to give a minimum 150mm upstand above the level of the new roof coverings.
Allow to install Em-Glaze Modular Flat Glazed Aluminium roof lights as per Appendix B. Installation should be carried out in accordance with the manufactures instructions.
Ensure the asphalt can be taken up the new upstands and terminated correctly prior to roof light installation.
Appendix C Roof light schedule, details those roof lights that should be fixed/electronically openable. The installation should be carried out in accordance with this schedule.
The contractor is responsible for measuring the aperture of the upstand to ensure correct fitment prior to ordering. Due to lead time on bespoke products these should be immediately after the pre-start meeting.
Line opening internally using 18mm moisture resistant MDF as required. Vertical MDF to drop 15mm below the existing ceiling finish and be routered to form a chamfer to both sides. Allow to repair ceiling, fill screw holes and sand back. Decorate in accordance with Section 2B. Colour White.
3.7.6 | Electrical Supply (Roof Windows)
The contractor shall be responsible for ascertaining all routes and BWIC, full allowance shall be made within this clause.
Allow for a NICEIC/ELECSA electrician to install a fused electrical supply adjacent to the roof window (where required) taken from a local supply.
All wiring should be carried out in accordance with BS7671 Amd. 3 and manufactures instructions.
Cables are to be concealed within the buildings fabric where possible however, where the cables are to be seen, white conduit with saddles at 500mm centres should be used.
The window control module is to be located adjacent to the main entrance door to the room at a height of 1200mm from floor level.
Allow for an electrical installation certificate to be provided upon completion.
3.12.7 | Electrical Binds
Electrically operated blinds are to be installed to all roof windows except those in the WC. Colours are to be selected from the standard range.
Within the kitchen areas a vinyl fabric is to be selected. Colours are to be selected from the standard range.
Remotes are to be mounted next to light switches at a height of 1.8m
3.7.8 | Overhaul of cast Iron Rainwater Goods
Allow to carefully remove gutters, downpipes, hoppers and bracketry to all elevations.
Using mechanical means, clear debris and corrosion from the surface. Particular attention is to be paid to the internal faces of the joints.
Where the cast iron is cracked, the sections are to be retained and repaired using a liquid metal system. Once repaired allow to file down liquid metal, flush with original surface.
Include for replacing all defective brackets, clips and fittings, with a cast iron replacement.
Reinstate rainwater goods on completion of elevation and roof works, ensuring all falls are correct.
A black low modulus silicone or flexible caulking should be used applied to the joints upon reinstatement. Replacement stainless steel nuts, bolts and washers should be used.
Decorate all cast iron rainwater goods in accordance with the Paint Specification in Section 2B. Colour: Black
Water test upon completion.
3.7.9 | Replacement of PVCu Rainwater Goods
Remove all PVCu rainwater goods, clips and bracketry and clear away.
Replace all rainwater goods with black PVCu heritage products to match the existing cast iron products in size and appearance. C.A to approve prior to ordering.
Seal all joints using a black low modulus silicone.
All brackets, clips and hoppers to be screwed with stainless steel screws and washers.
Water test upon completion.
3.7.10 | Soil and Vent Pipes
To soil and vent pipes at roof level, overhaul as required, including sealing of all joints and leave in full working order on completion. Provide wire balloon gratings or cowlings as appropriate.
Decorate all soils and vent pipes at roof level in accordance with the Paint Specification (Section 2B). Colour Black.
3.7.11 | Extractor Fans
The contractor shall be responsible for ascertaining all routes and BWIC, full allowance shall be made within this clause.
Remove all existing fans and isolate as required. Where fans pass through walls hole can be re-used if appropriate.
To all WC's, allowance should be made to install a 220mm extractor to each. Four in total.
Allow for a NICEIC/ELECSA electrician to install a fused electrical supply with a triple pole isolator to the fan, taken from a local lighting supply.
A 9" core hole should be drilled through the main elevation, ensuring that other services are not present. (CA to approve positioning prior to drilling)
Install a Vent Axia Lo Carbon 9" Commercial Panel Fan with an external cowling. The fan should have a minimum of 5 minutes overrun.
3.7.12 | Services (Gas, water, AC etc.)
The contractor shall be responsible for ascertaining all routes and BWIC, full allowance shall be made within this clause.
Allowance should be made to test the cables/services to establish whether they are live or redundant. All redundant cables should be removed and disposed of, whilst those that are live should be carefully unclipped, labelled and set aside.
There are a number of services upon the existing roof that will require re-rooting to accommodate the increased roof heights. These include Gas, Water and air-conditioning along with other associated building services.
Include for all necessary work to raise pipe work on roof in an approved manner to take account of the raised height of the roof. Include for forming new openings as required and for making good on completion.
Loosing these pipes within the roof covering will not be permitted.
Include for all necessary shut downs, draw off etc. to allow works to be undertaken.
Remove the existing pipe supports and clear away. Provide new pipe supports to be TAB-P System by Roof Pro (Tel: 01234 843790) or similar approved, installed strictly in accordance with manufacturers instructions.
All pipework should be clipped and sat upon Metsec flexi-feet. Where possible the pipework is to run adjacent to the cable tray for neatness.
All services should be tested/commissioned upon completion and a certificate issued.
3.8 | Roof 03 and Roof 08
3.8.1 | Replacement of Flat Roof Covering
Refer to Permanite Specification included in Section 2A
Strip existing asphalt roof coverings, debris and all associated details and clear from site. Take back to roof deck.
Contractor to note that no temporary roof is being provided and the roof is to remain watertight for the duration of the project. In this respect the works are to be undertaken in manageable bays in an approved manner to ensure that the building remains watertight at all times.
Strip the timber roof deck and dispose. Expose void and vacuum voids.
Contractor is to allow for scheduling and programming the attendance of the CA to view the exposed roof structure and advise if further works are required.
Install an 22mm WBP Plywood deck fixed at ≤ 300mm intervals using stainless steel screws. The board joints are to be staggered, leaving a 3mm expansion gap between the boards. Leave ready to receive new roof covering.
The increased height of this roof will reduce the height below the window sills to less than 150mm. This is not of concern as these windows are protected by the roof above. The upstand height shall be directly below the window sill level.
Provide and lay new insulated asphalt roof coverings in accordance with Section 2A. The Main Contractor is to note that the client wishes to take advantage of the 20 year Permanite IKO Single Point insurance backed guarantee. In this respect the installation of new asphalt finishes are only to be carried out by an approved Permanite installer.
Provide and install min 150mm thick (Thickness dependant on location) IKO enertherm PIR ALU cut to falls insulation. Contractor to obtain cut to falls drawings for approval prior to ordering.
To the perimeter of the roof install IKO termination trim / upstand trim. Lead cover flashings are not to be used due to theft.
Where the asphalt runs into the gutter, provide and install new code 4 lead trip detail in accordance with LSA guidance.
The Main Contractor is not to alter the scope of the works from the specification provided by Permanite without the express permission with both the CA and IKO PLC.
Provide and lay new insulated asphalt roof system complete as indicated on the drawings and as detailed in the specification provided by Permanite within Section 2A
3.9 | Roof 04
3.9.1 | Replacement of Flat Roof Covering
Refer to Permanite Specification included in Section 2A
Strip existing asphalt roof coverings, debris, stone and all associated details and clear from site. Take back to concrete roof deck.
Contractor to note that no temporary roof is being provided and the roof is to remain watertight for the duration of the project. In this respect the works are to be undertaken in manageable bays in an approved manner to ensure that the building remains watertight at all times.
See preliminaries for Provision Sum for repairs to screed to existing roof decking.
Contractor is to allow for scheduling and programming the attendance of the CA to view the exposed roof structure and advise if further works are required.
Provide and lay new insulated asphalt roof coverings in accordance with Section 2A. The Main Contractor is to note that the client wishes to take advantage of the 20 year Permanite IKO Single Point insurance backed guarantee. In this respect the installation of new asphalt finishes are only to be carried out by an approved Permanite installer.
Provide and install min 150mm thick (Thickness dependant on location) IKO enertherm PIR ALU cut to falls insulation. Contractor to obtain cut to falls drawings for approval prior to ordering.
The existing outlets are being retained, allow to form sumps around these outlets as required.
To the perimeter of the roof install IKO termination trim / upstand trim. Lead flashings are not to be used due to theft.
The Main Contractor is not to alter the scope of the works from the specification provided by Permanite without the express permission with both the CA and IKO PLC.
Provide and lay new insulated asphalt roof system complete as indicated on the drawings and as detailed in the specification provided by Permanite within Section 2A
3.9.2 | Works to Parapets
Carefully remove all redundant fixings, brackets etc. to parapets and clear away.
Carefully remove all existing copings to the parapet wall and put to one side for reuse. Allow for mechanical removal due to weight, existing copings are not to be cut down.
To all parapets allow to carefully remove the existing render (where existing), ensuring that damage to the brick face is minimised and the render is removed in its entirety.
Install an stainless steel expanded metal larvae to the brickwork and secure at 100mm centres with stainless steel masonry fixings.
Using a 1:1:4 mortar, render the parapet walls to smooth finish.
Re lay coping stones on a level bed of 1:1:6 mortar, on a new ICOPAL polyethylene DPC in accordance with the Manufactures guidelines and fully point in all joints on completion.
PQ | Allow a provisional quantity of 5no 500mm sandstone replacement coping stones to replace those damaged or severely weathered. The replacements are to match existing, C.A to approve prior to installation.
PQ | Allow a provisional quantity of 20lm of pointing replacement. Rake out defective pointing to the external face of the parapet and re point with a 1:1:6 ratio mortar. Colour: To match existing. C.A to measure and instruct prior to undertaking.
3.9.3 | Lead works
Allow to remove the existing lead work that passes through the brickwork parapets and clear away.
Replace the lead on a like for like basis using code 4 lead in accordance with the LSA guidelines. Where required allow to line the bottom of the outlet using WBP 18mm plywood.
Lead to be cut into the brickwork matching the stepped detail currently provided. Upon completion, wedge using lead and seal using a grey low modulus silicone.
3.9.4 | Roof Lights Removal
Remove existing roof light and clear away. Refer to the asbestos survey within the PCI, asbestos containing gaskets / rope is known to exist. The contractor shall be responsible to removal and disposal.
Allow to dismantle roof light and clear away.
Allow to cut back the upstands ensuring they are left level with the roof deck. Make good any defects and ensure any protruding reinforcement bars are cut back and receive a coating of red-oxide primer.
Allow to trim out the opening with pressure treated timber (minimum 100mm x 50mm) and affix with Fischer Stainless steel concrete screws. Install noggins, ensuring installation at 400mm centres.
Install an 22mm WBP Plywood deck ensuring a tight and flush fitment with the existing roof deck. Leave ready to receive new insulation and roof covering.
Internally allow to install timber counter battens as required to take new plasterboard finish 25mm higher than the existing ceiling finishes. This will leave the outline of the original roof light. Install two layers of tapered edge 15mm fire line over new battens. Fill and sand as required. Decorate in accordance with Section 2B. White in colour.
3.1 | Roof 05
3.10.1 | Replacement of Flat Roof Covering
Refer to Permanite Specification included in Section 2A
Strip existing asphalt roof coverings, debris, stone and all associated details and clear from site. Take back to concrete roof deck.
Contractor to note that no temporary roof is being provided and the roof is to remain watertight for the duration of the project. In this respect the works are to be undertaken in manageable bays in an approved manner to ensure that the building remains watertight at all times.
See preliminaries for Provision Sum for repairs to screed to existing roof decking.
Contractor is to allow for scheduling and programming the attendance of the CA to view the exposed roof structure and advise if further works are required.
Provide and lay new insulated asphalt roof coverings in accordance with Section 2A. The Main Contractor is to note that the client wishes to take advantage of the 20 year Permanite IKO Single Point insurance backed guarantee. In this respect the installation of new asphalt finishes are only to be carried out by an approved Permanite installer.
Provide and install min 150mm thick (Thickness dependant on location) IKO enertherm PIR ALU cut to falls insulation. Contractor to obtain cut to falls drawings for approval prior to ordering.
The existing outlets are being retained, allow to form sumps around these outlets as required.
To the perimeter of the roof install IKO termination trim / upstand trim. Lead flashings are not to be used due to theft.
The Main Contractor is not to alter the scope of the works from the specification provided by Permanite without the express permission with both the CA and IKO PLC.
Provide and lay new insulated asphalt roof system complete as indicated on the drawings and as detailed in the specification provided by Permanite within Section 2A
3.10.2 | Works to Parapets
Carefully remove all redundant fixings, brackets etc. to parapets and clear away.
Carefully remove all existing copings to the parapet wall and put to one side for reuse. Allow for mechanical removal due to weight, existing copings are not to be cut down.
To all parapets allow to carefully remove the existing render (where existing), ensuring that damage to the brick face is minimised and the render is removed in its entirety.
Install an stainless steel expanded metal larvae to the brickwork and secure at 100mm centres with stainless steel masonry fixings.
Using a 1:1:4 mortar, render the parapet walls to smooth finish.
Re lay coping stones on a level bed of 1:1:6 mortar, on a new ICOPAL polyethylene DPC in accordance with the Manufactures guidelines and fully point in all joints on completion.
PQ | Allow a provisional quantity of 5no 500mm sandstone replacement coping stones to replace those damaged or severely weathered. The replacements are to match existing, C.A to approve prior to installation.
PQ | Allow a provisional quantity of 20lm of pointing replacement. Rake out defective pointing to the external face of the parapet and re point with a 1:1:6 ratio mortar. Colour: To match existing. C.A to measure and instruct prior to undertaking.
3.10.3 | Lead works
Allow to remove the existing lead work that passes through the brickwork parapets and clear away.
Replace the lead on a like for like basis using code 4 lead in accordance with the LSA guidelines. Where required allow to line the bottom of the outlet using WBP 18mm plywood.
Lead to be cut into the brickwork matching the stepped detail currently provided. Upon completion, wedge using lead and seal using a grey low modulus silicone.
3.10.4 | Abutment with Roof 10
There is a back gutter to roof 5. Where this is formed the new insulation will require the asphalt to be taken further up the pitched roof.
In conjunction with roof covering replacement to roof 10, allow to extend and install new WBP 18mm plywood and asphalt up the pitched roof slope.
3.11 | Roof 06, 07 & 14
3.11.1 | Replacement of Flat Roof Covering
Refer to Permanite Specification included in Section 2A
Strip existing asphalt roof coverings, debris and all associated details and clear from site. Take back to concrete roof deck.
Contractor is to allow for scheduling and programming the attendance of the CA to view the exposed roof deck and advise if further works are required.
A provisional sum has been included within the preliminaries for concrete repair.
Provide and lay new asphalt roof coverings in accordance with Section 2A. The Main Contractor is to note that the client wishes to take advantage of the 20 year Permanite IKO Single Point insurance backed guarantee. In this respect the installation of new asphalt finishes are only to be carried out by an approved Permanite installer.
To the perimeter of the roof install IKO termination trim / upstand trim. Lead flashings are not to be used due to theft.
The Main Contractor is not to alter the scope of the works from the specification provided by Permanite without the express permission with both the CA and IKO PLC.
Provide and lay new asphalt roof system complete as indicated on the drawings and as detailed in the specification provided by Permanite.(section 2A)
3.11.2 | Brickwork Repair
Where the concrete roof decks have expanded they have caused brickwork locally to crack.
PQ | Allow a provisional quantity of 20no replacement bricks as instructed by the C.A. Bricks to match the existing. Bed and point in using 1:3:6 ratio mortar.
3.11.3 | Cleaning
The contractor is to deploy the use of steam based cleaning system by DOFF, Torick or Hot Box. Clean down the canopies. Leave ready for decoration
3.11.4 | Decoration
Prepare and decorate concrete canopies to Paint Specification in Section 2B. Colour White. (Including masonry and supporting poles.
3.11.5 | Repair of feature above Roof 14
A provisional sum has been included within the preliminaries for concrete repair.
3.12 | Roof 10
3.12.1 | Replacement of Pitched Roof Covering
Contractor is to allow for scheduling and programming the attendance of the CA to view the exposed roof structure and advise if further works are required.
Strip off and cart away all tiling, battens, asphalt to parapet gutters and any under felt and all associated details.
PQ | Due to suspected timber decay to sections of close boarding, allow a provisional quantity of 25m2m of replacement boarding. The timber is to be tantalised and of matching dimensions to the existing.
Provide extra over cost for removal of all close boarding and clearing away. This would remove the requirement for vertical battens
Provide and install 38 x 38mm counter battens running in the same direction of the rafters.
Starting at the bottom of the roof, pull taut Tyvek Supro (or similar approved) across the battens (horizontally), and hold in place with stainless steel staples. Reference should be made to the manufactures instructions. The contractor is to ensure the minimum air gap and product overlap is achieved.
Provide and install 38 x 25mm tile battens running across the top of the counter battens in the opposite direction to the entire roof fixed to BS5534.
Recover the pitched roof in Marley Burnt Flame clay tiles to be laid to appropriate lap and gauge in accordance with manufacturer’s instructions and BS 5534:2003.
Provide and fix new Marley Burnt Flame half round clay ridge tiles (Terracotta) and bed on mortar of 1.3 ratio. Furthermore mechanical fixings should be utilised.
Provide and fix new lead stepped flashing and soakers to adjoining brickwork in accordance with LSA guidance.
3.12.2 | Verges
To the verges, allow to remove existing creasing tiles back to top of brickwork and clear away. Provide and install new clay creasing tiles using mortar of 1.3 ratio, three ties deep.
Creasing tiles to be gauged to ensure increased height of roof due to additional batten is accommodated.
Provide and fix new Marley Burnt Flame Plain tile cloak verge system in accordance with manufacturer’s instructions.
3.12.3 | Lead works
Provide new flashings to the chimneys, flues and other services penetrating the roof covering. The flashings are to be in code 4 lead and installed in accordance with the LSA guidelines.
Where the tiled roofs meet the parapets Code 4 lead cover flashing are to be installed in accordance with LSA guidelines.
There is a valley parapet gutter to this roof behind roof 14. This parapet is to be lined and detailed with Code 5 lead in accordance with LSA guidelines.
3.12.4 | Abutment with Roof 5
Where the tiled roof meets roof 5 there is a lead valley which allows rainwater to discharge from the asphalt gutter down the side of roof 10 and then onto roof 3.
Allow to improve this lead valley by increasing its width to 150mm. Allow to form in Code 5 lead. Line with WBP plywood as required and clad in lead in accordance with LSA guidance.
Where roof abuts brickwork, provide stepped lead flashings to match existing arrangement.
3.12.5 | Roof lights
Remove existing roof lights and clear away. See R&D survey within PCI in Appendix D. Asbestos rope and gaskets known to exist, contractor to make full allowance for removal and disposal.
Refer to Appendix C to confirm what window need to be electronically openable.
The contractor is responsible for measuring the opening to ensure correct fitment prior to ordering. Due to lead time on bespoke products these should be ordered immediately after the pre-start meeting.
The current arrangement with the roof windows extending beyond the eaves is to be altered to enable the fitment of Velux roof windows.
Using tantalised timber and WBP 18mm Plywood allow to increase the height of the bottom sill to accommodate a Velux window.
Install top hung polyurethane Velux roof windows (or similar approved). Colour: White internally. The installation should be carried out in accordance with the manufactures instructions.
The contractor is to design and manufacture a zinc cover flashing to extend from the bottom of the Velux window down into the gutter to create a weather tight detail. This needs to extend 400mm past the width of the window and allow tiled battens to extend over except where directly below the window. The design and installation is to be agreed with the project team using VM Quartz Zinc. (Lead may be considered).
Provide and install Velux flashing kit.
Line opening internally using 18mm moisture resistant MDF as required. Vertical MDF to drop 15mm below the ceiling and skeiling finish and be routered to form a chamfer to both sides.
Allow to repair ceiling and infill ceiling / skeiling as required, fill screw holes and sand back. Decorate in accordance with Section 2B. Colour White.
3.12.6 | Replacement of Soffits and Fascia's
Carefully remove all fascia's and soffits clear away from site taking back to rafter feet. Vacuum and clean out voids.
Allow to frame out using tanalised timber from existing rafter feet to ensure new fascias and soffits are straight and plumb.
Provide and install new white 18mm PVCu facias and vented soffits. Vented soffits to have pre-fitted mesh.
Provide all relevant , trims, brackets and caps where required. All fixings are to be stainless steel.
Prepare and decorate concrete soffits to Paint Specification in Section 2B.
3.12.7 | Replacement of PVCu Rainwater Goods
Remove all PVCu rainwater goods, clips and bracketry and clear away.
Replace all rainwater goods with black PVCu heritage products to match the existing cast iron products in size and appearance. C.A to approve prior to ordering.
Seal all joints using a black low modulus silicone.
All brackets, clips and hoppers to be screwed with stainless steel screws and washers.
Water test upon completion.
3.12.8 | Electrical Supply to roof lights
Allow for a NICEIC/ELECSA electrician to install a fused electrical supply adjacent to the roof window (where required) taken from a local supply.
All wiring should be carried out in accordance with BS7671 Amd. 3 and manufactures instructions.
Cables are to be concealed within the buildings fabric where possible however where the cables are to be seen, white conduit with saddles at 500mm centres should be used.
The window control module is to be located adjacent to the main entrance door to the room at a height of 1200mm from floor level.
Allow for an electrical installation certificate to be provided upon completion.
3.12.9 | Electrical Blinds
Electrically operated Velux blinds are to be installed to all roof windows except those in the WC. Colours are to be selected from the standard range.
Within the kitchen areas a vinyl fabric is to be selected. Colours are to be selected from the standard range.
Remotes are to be mounted next to light switches at a height of 1.8m
3.13 | Roof 10 Void
3.13.1 | Insulation of Roof Void
Works must be undertaken during holidays or during weekends.
Prior to carrying out these works please see Asbestos R&D Survey within PCI. See Appendix D.
Externally, allow to carefully remove a section of close boarding and trim out rafters as required to allow access into the pitched roof voids. The aperture should allow for the removal of redundant tanks and services within the roof void.
Allow to remove all existing insulation, waste, disused M&E and debris to all pitched roof sections. All voids should be vacuumed and left clean.
Remove and dispose of the redundant water tank ensuring that all associated redundant pipework is also pipework is also removed.
Remove all duck boards and clear away. Allow to install new tanalised timber noggins to allow for new 1000mm width duck boards. Noggins to be fixed to every ceiling joist to ensure adequate support to duck boards.
Insulate the voids with 100mm of Knauf Earthwool between the joists. A further 170mm of Knauf Earthwool should be cross laid in the opposite direction to the joists.
To new noggins / trimmers install new 18mm WBP plywood, screwed to every noggin. Duck boards to be a total width of 1000mm with a 50 x 50mm section of tanalised timber fixed to either side.
To the internal access hatch, accessing this roof void, allow to provide and fix a new heavy duty aluminium loft ladder suitable for high ceiling height.
3.13.2 | Lighting to Roof Void
The contractor shall be responsible for ascertaining all routes and BWIC, full allowance shall be made within this clause.
Remove all existing lighting, clear away and isolate as required.
Allow for a NICEIC/ELECSA electrician to install a fused electrical supply. All wiring should be carried out in accordance with BS7671.
Install new 5ft 50w LED Non Corrosive Weatherproof Fitting - IP65 strip lights to ridge board at every 5m.
Lighting to be switched from the estate office and next to the loft access ladder within the roof void. Switch plates to be MK with indicator light.
Cables are to be concealed within the buildings fabric where possible however where the cables are to be seen, white conduit with saddles at 500mm centres should be used.
Allow for an electrical installation certificate to be provided upon completion.
3.13.3 | Cable control
Provide and install new galvanised medium gauge cable tray next to the duck boards.
All cables should be moved and secured to new cable tray. Where this is not possible cables are to be either clipped to the joists or laid directly upon the ceiling. Cables should not be 'sandwiched' between layers of insulation.
To all cables with exposed connections, allow to tighten the connections and contain with a Wago box or similar.
3.14 | Completion
On completion clear away all builder’s rubbish and materials and leave clean and ready for occupation at handover.
Provide the Client / Contract Administrator with copies of all necessary handover documentation including all Statutory Compliances, test certification, guarantees and warranties for O&M and H&S file.
COLLECTION PAGE
Collection from page 1
Collection from page 2
Collection from page 3
Collection from page 4
Collection from page 5
Collection from page 6
Collection from page 7
Collection from page 8
Collection from page 9
Collection from page 10
Collection from page 11
Collection from page 12
Collection from page 13
Collection from page 14
Collection from page 15
Collection from page 16
Collection from page 17
Collection from page 18
Collection from page 19
Collection from page 20
Collection from page 21
Collection from page 22
Collection from page 23
Collection from page 24
Collection from page 25
Collection from page 26
Collection from page 27
Collection from page 28
Total to Summary

## Section 4 - Nursery
4 | SCHEDULE OF WORKS
SECTION FOUR
4.1 | Scope Of Works
The works comprise of all building works necessary for the replacement of the roof coverings and upgrading of insulation to the Andre Malraux Nursery School Building. The scope of works also includes for other associated repairs at roof level and those internal works resultant from intrusive works.
The construction period is anticipated to commence on the 7th July 2017 and are to complete within the schools summer holiday break. The works are to be carried out concurrently to those in Section 3 & 5 with a construction period of 6 weeks.
Refer to the preliminaries for sectional completion dates.
4.2 | Notes Generally
No hot works or asphalting will be permitted when the school is in operation.
It should be noted that access to this building is restricted due to the width of access between the main building and the boundary being reduced to approximataly 1500mm. The contactor is to make full allowance for this.
The Contractor is to price each item separately. It is important that prices are not grouped together for works common to all roofs as the Client requires to have a complete itemised schedule on a roof by roof basis.
Where the clause numbers or sections are referred to, all of these numbers refer to the relevant clauses/sections in Section 2 of this specification and the Contractor is deemed to have included in his price, all those works necessary and contained within the standard clauses where referred to.
Where quantities of various elements have been provided within the schedule of works, these are for the Contractor’s guidance only, except where specifically stated otherwise. The Contractor should check all quantities themselves.
The Contractor should supply the Contract Administrator with a telephone number where he may be contacted 24 hours a day and at weekends during the works.
It is the Contractor’s responsibility to maintain close liaison with the Contract Administrator, the Headteacher and Ms Justine Pare, Property Manager for Lycée Français Charles De Gaulle, to ensure full co-operation to carry out the works. In this respect, the Contractor should appoint a Site Manager for the works to be present at all times throughout the duration of the project.
Where buildings are opened to the elements during roof replacement/repair works, this should be undertaken in bays/sections which shall allow the contractor to provide adequate protection to ensure weather tightness until work recommences.
Replacement of skylights/roof lights and lantern lights over student/school areas shall only be permitted when the school is closed (Out of Hours) or within the holiday period.
No allowance has been made for temporary roofs. The contractor will be responsible for ensuring the building is in a watertight condition at the end of every working day. Water damage caused by the contractor not making adequate provisions will be rectified at the contractors cost.
Replacement of skylights/roof lights and lantern lights over student/school areas shall only be permitted when the school is closed (Out of Hours) or within the holiday period.
Deliveries are not permitted between 8.00 to 10.00am, and between 2.30 am to 4.30pm when the school is in operation.
The contractor shall make every effort to ensure the majority of waste and materials are delivered during the holiday period. Vehicle movements during school operation will be restricted during the start of the day, playtimes, lunch times and end of the day.
4.3 | General Items Applicable to all Works
4.3.1 | Temporary Protection
The Contractor shall provide sheeting over all openings where works are in progress and seal to prevent dust etc., from percolating through to the occupied space at all levels, together with outer areas of the building and maintain for the duration of the project. If this occurs, then the Contractor is to clean up all affected areas as soon as possible, to the satisfaction of the Contract Administrator and the Property Manager.
All existing glazing, roof lights, walls, doors and other parts of the building fabric and services are to be adequately protected against damage.
The Contractor, either by himself or staff, shall not obstruct any rights of way, entrance or anything that might amount to a nuisance or annoyance. Any complaint must be communicated at once to the Contract Administrator.
4.3.2 | Cleanliness
The Contractor is to ensure that the site is kept clean at all times. The contractor must maintain and keep all access routes clear at all times
On completion clear away all builder’s rubbish and materials and leave clean and ready for occupation at handover.
4.4 | Nursery School Building
4.4.1 | Scaffolding and Temporary Works
The erection and striking of scaffolding shall only be undertaken during the Schools holiday period or during weekends.
Where minor alterations are required to scaffolding during the works where clashes/over sailing occurs the project team accept this can occur during term time when students are off site (Early morning / Late afternoon).
Contractor is to include for all required gantries to enable scaffolding to over sail roofs below where replacement of roof coverings is required. Contractor is also to over sail items that are to remain in place such as entrance canopies etc.
Provide, erect, maintain and dismantle on completion, all necessary scaffolding and temporary access required to undertake the works all as indicated within the specification.
Allow for garden clearance as required to safety erect scaffolding. Including cutting back of trees and shrubbery, and temporarily relocating items.
Scaffolding should be erected in accordance with BS EN 12811-1.
Means of access should be suitable for the full refurbishment at roof level and other associated works as outlined within the Specification. Particular attention should be paid to:
a) | All entrances surrounding the premises are to be maintained at all times and adequately protected etc.
b) | Tying in to avoid or reduce damage to the faces of masonry units.
c) | Avoiding physical damage during erection and striking.
d) | Use of base plates to isolate stones or other services from scaffold standards.
e) | Avoiding rust staining to the building.
f) | Capping pole ends.
g) | A scaffold alarm is to be provided on the first lift for the duration of the project. These are to be monitored 24hr by an off site provider.
h) | The existing fire escapes should be maintained during the construction phase at all times without exception.
i) | The lower sections of scaffolding are to be double boarded and sheeted with reinforced sheeting for the duration.
j) | All standards are to be foamed and cable tied.
k) | Adequate fans are to be provided to provide full protection to the surrounding playground areas, which are to remain in full use.
l) | Provide all necessary warning notices.
m) | The contractor is to also include for all necessary access towers/material hoists and skips/chutes for disposal from site.
The contractor is to state here the separate additional cost for the provision of a temporary roof over Roof 11 only. Do not carry the inserted cost through to the summary.
£………………………………
4.4.2 | Contractors Compound
Included in Section 3.
Roof replacement
Refer to drawings:
17.334.001 - Existing site plan and roof plan
17.334.002 - Not issued
17.334.003 - Not issued
17.334.004 - Proposed Roof Plan
17.334.100 - Existing plans and elevations
17.334.101 - Proposed plans and elevations
17.334.102 - Proposed sections and details
17.334.103 - Contractors compound
4.5 | Roof 09
4.5.1 | Replacement of Flat Roof Covering
Refer to Permanite Specification included in Section 2A
Strip existing asphalt roof coverings, debris, stone and all associated details and clear from site. Take back to concrete roof deck.
Contractor to note that no temporary roof is being provided and the roof is to remain watertight for the duration of the project. In this respect the works are to be undertaken in manageable bays in an approved manner to ensure that the building remains watertight at all times.
See preliminaries for Provisional Sum for repairs to screed to existing roof decking.
Contractor is to allow for scheduling and programming the attendance of the CA to view the exposed roof structure and advise if further works are required.
Provide and lay new insulated asphalt roof coverings in accordance with Section 2A. The Main Contractor is to note that the client wishes to take advantage of the 20 year Permanite IKO Single Point insurance backed guarantee. In this respect the installation of new asphalt finishes are only to be carried out by an approved Permanite installer.
Provide and install min 150mm thick (Thickness dependant on location) IKO enertherm PIR ALU cut to falls insulation. Contractor to obtain cut to falls drawings for approval prior to ordering.
The existing outlets are being retained, allow to form sumps around these outlets as required.
To the perimeter of the roof install IKO termination trim / upstand trim. Lead flashings are not to be used due to theft.
Where existing services penetrate the roof covering allow to install lead code 4 collars and seal with grey silicon sealant.
The Main Contractor is not to alter the scope of the works from the specification provided by Permanite without the express permission with both the CA and IKO PLC.
Provide and lay new insulated asphalt roof system complete as indicated on the drawings and as detailed in the specification provided by Permanite within Section 2A
4.5.2 | Works to Parapets
Carefully remove all redundant fixings, brackets etc. to parapets and clear away.
Carefully remove all existing copings to the parapet wall and put to one side for reuse. Allow for mechanical removal due to weight, existing copings are not to be cut down.
To all parapets allow to carefully remove the existing render (where existing), ensuring that damage to the brick face is minimised and the render is removed in its entirety.
Install an stainless steel expanded metal larvae to the brickwork and secure at 100mm centres with stainless steel masonry fixings.
Using a 1:1:4 mortar, render the parapet walls to smooth finish.
Re lay coping stones on a level bed of 1:1:6 mortar, on a new ICOPAL polyethylene DPC in accordance with the Manufactures guidelines and fully point in all joints on completion.
PQ | Allow a provisional quantity of 15no 500mm sandstone replacement coping stones to replace those damaged or severely weathered. The replacements are to match existing, C.A to approve prior to installation.
PQ | Allow a provisional quantity of 80lm of pointing replacement. Rake out defective pointing to the external face of the parapet and re point with a 1:1:6 ratio mortar. Colour: To match existing. C.A to measure and instruct prior to undertaking.
4.5.3 | Lead works
Allow to remove the existing lead work that passes through the brickwork parapets and clear away.
Replace the lead on a like for like basis using code 4 lead in accordance with the LSA guidelines. Where required allow to line the bottom of the outlet using WBP 18mm plywood.
Lead to be cut into the brickwork matching the stepped detail currently provided. Upon completion, wedge using lead and seal using a grey low modulus silicone.
4.5.4 | Roof Lights to be removed
Refer to Drawings to confirm roof light removal.
Remove existing roof lights and clear away. Refer to the asbestos survey within the PCI, asbestos containing gaskets / rope is known to exist. The contractor shall be responsible to removal and disposal.
Allow to dismantle roof light and clear away.
Allow to cut back the upstands ensuring they are left level with the roof deck. Make good any defects and ensure any protruding reinforcement bars are cut back and receive a coating of red-oxide primer.
Allow to trim out the opening with pressure treated timber (minimum 100mm x 50mm) and affix with Fischer Stainless steel concrete screws. Install noggins, ensuring installation at 400mm centres.
Install an 22mm WBP Plywood deck ensuring a tight and flush fitment with the existing roof deck. Leave ready to receive new insulation and roof covering.
Internally allow to install timber counter battens as required to take new plasterboard finish 25mm higher than the existing ceiling finishes. This will leave the outline of the original roof light. Install two layers of tapered edge 15mm fire line over new battens. Fill and sand as required. Decorate in accordance with Section 2B. White in colour.
4.5.5 | Roof Lights to be replaced
Refer to Drawings to confirm roof light replacement.
Remove existing roof lights and clear away. Refer to the asbestos survey within the PCI, asbestos containing gaskets / rope is known to exist. The contractor shall be responsible to removal and disposal.
Refer to Appendix C to confirm what window need to be electronically openable.
Internally, allow to remove vertical linings taking back to concrete structure.
Allow for raising of the perimeter upstands in tantalised timber to give a minimum 150mm upstand above the level of the new roof coverings.
Allow to install Em-Glaze Modular Flat Glazed Aluminium roof lights as per Appendix B. Installation should be carried out in accordance with the manufactures instructions.
Ensure the asphalt can be taken up the new upstands and terminated correctly prior to roof light installation.
Appendix C Roof light schedule, details those roof lights that should be fixed/electronically openable. The installation should be carried out in accordance with this schedule.
The contractor is responsible for measuring the aperture of the upstand to ensure correct fitment prior to ordering. Due to lead time on bespoke products these should be immediately after the pre-start meeting.
Line opening internally using 18mm moisture resistant MDF as required. Vertical MDF to drop 15mm below the existing ceiling finish and be routered to form a chamfer to both sides. Allow to repair ceiling, fill screw holes and sand back. Decorate in accordance with Section 2B. Colour White.
4.5.6 | Electrical Supply (Roof Windows)
The contractor shall be responsible for ascertaining all routes and BWIC, full allowance shall be made within this clause.
Allow for a NICEIC/ELECSA electrician to install a fused electrical supply adjacent to the roof window (where required) taken from a local supply.
All wiring should be carried out in accordance with BS7671 Amd. 3 and manufactures instructions.
Cables are to be concealed within the buildings fabric where possible however, where the cables are to be seen, white conduit with saddles at 500mm centres should be used.
The window control module is to be located adjacent to the main entrance door to the room at a height of 1200mm from floor level.
Allow for an electrical installation certificate to be provided upon completion.
4.5.7 | Electrical Blinds
Electrically operated blinds are to be installed to all roof windows except those in the WC. Colours are to be selected from the standard range.
Within the kitchen areas a vinyl fabric is to be selected. Colours are to be selected from the standard range.
Remotes are to be mounted next to light switches at a height of 1.8m
4.5.8 | Overhaul of cast Iron Rainwater Goods
Allow to carefully remove gutters, downpipes, hoppers and bracketry to all elevations.
Using mechanical means, clear debris and corrosion from the surface. Particular attention is to be paid to the internal faces of the joints.
Where the cast iron is cracked, the sections are to be retained and repaired using a liquid metal system. Once repaired allow to file down liquid metal, flush with original surface.
Include for replacing all defective brackets, clips and fittings, with a cast iron replacement.
Reinstate rainwater goods on completion of elevation and roof works, ensuring all falls are correct.
A black low modulus silicone or flexible caulking should be used applied to the joints upon reinstatement. Replacement stainless steel nuts, bolts and washers should be used.
Decorate all cast iron rainwater goods in accordance with the Paint Specification in Section 2B. Colour: Black
Water test upon completion.
4.5.9 | Replacement of PVCu Rainwater Goods
Remove all PVCu rainwater goods, clips and bracketry and clear away.
Replace all rainwater goods with black PVCu heritage products to match the existing cast iron products in size and appearance. C.A to approve prior to ordering.
Seal all joints using a black low modulus silicone.
All brackets, clips and hoppers to be screwed with stainless steel screws and washers.
Water test upon completion.
4.5.10 | Soil and Vent Pipes
To soil and vent pipes at roof level, overhaul as required, including sealing of all joints and leave in full working order on completion. Provide wire balloon gratings or cowlings as appropriate.
Decorate all soils and vent pipes at roof level in accordance with the Paint Specification (Section 2B). Colour Black.
4.5.11 | Services
Allowance should be made to test the cables/services to establish whether they are live or redundant. All redundant cables should be removed and disposed of.
Where cables are retained, allow to clip to parapets using stainless steel P-Clips and fixings.
4.6 | Roof 11
4.6.1 | Replacement of Pitched Roof Covering
Contractor is to allow for scheduling and programming the attendance of the CA to view the exposed roof structure and advise if further works are required.
Strip off and cart away all tiling, battens, asphalt to parapet gutters and any under felt and all associated details.
PQ | Due to suspected timber decay to sections of close boarding, allow a provisional quantity of 15m2m of replacement boarding. The timber is to be tantalised and of matching dimensions to the existing.
Provide extra over cost for removal of all close boarding and clearing away. This would remove the requirement for vertical battens
Provide and install 38 x 38mm counter battens running in the same direction of the rafters.
Starting at the bottom of the roof, pull taut Tyvek Supro (or similar approved) across the battens (horizontally), and hold in place with stainless steel staples. Reference should be made to the manufactures instructions. The contractor is to ensure the minimum air gap and product overlap is achieved.
Provide and install 38 x 25mm tile battens running across the top of the counter batters in the opposite direction to the entire roof fixed to BS5534.
Recover the pitched roof in Marley Burnt Flame clay tiles to be laid to appropriate lap and gauge in accordance with manufacturer’s instructions and BS 5534:2003.
Provide and fix new Marley Burnt Flame half round clay ridge and hip tiles (Terracotta) and bed on mortar of 1.3 ratio. Furthermore mechanical fixings should be utilised.
Provide and fix new lead stepped flashing and soakers to adjoining brickwork in accordance with LSA guidance.
4.6.2 | Works to Chimney Stacks
Carefully remove the existing flaunching's and debris to the chimney capping.
To the chimney, allow to replace the flaunching using a 1:3 ratio mortar.
Carefully rake out the mortar bed to depth at least twice the width of the joint, not more than 20mm. The joints to the creasing tiles should also be raked out.
To all to raked out joints allow to re-point in a 1:1:6 ratio mortar. Colour: To match existing. C.A to approve prior to installation bricks as required to complete the works.
PQ | Allow a provisional quantity of 15lm of repointing to the chimney stacks. | 15lm
4.6.3 | Lead works
Removal existing lead work to chimneys. Provide new stepped flashings etc. to the chimneys. The flashings are to be in code 4 lead and installed in accordance with the LSA guidelines.
Where the tiled roofs meet the parapets Code 4 lead cover flashing are to be installed in accordance with LSA guidelines.
4.6.4 | Roof lights
Remove existing roof lights and clear away. See R&D survey within PCI in Appendix D. Asbestos rope and gaskets known to exist, contractor to make full allowance for removal and disposal.
Refer to Appendix C to confirm what window need to be electronically openable.
The contractor is responsible for measuring the opening to ensure correct fitment prior to ordering. Due to lead time on bespoke products these should be ordered immediately after the pre-start meeting.
The current arrangement with the roof windows extending beyond the eaves is to be altered to enable the fitment of Velux roof windows.
Using tantalised timber and WBP 18mm Plywood allow to increase the height of the bottom sill to accommodate a Velux window.
Install top hung polyurethane Velux roof windows (or similar approved). Colour: White internally. The installation should be carried out in accordance with the manufactures instructions.
The contractor is to design and manufacture a zinc cover flashing to extend from the bottom of the Velux window down into the gutter to create a weather tight detail. This needs to extend 400mm past the width of the window and allow tiled battens to extend over except where directly below the window. The design and installation is to be agreed with the project team using VM Quartz Zinc. (Lead may be considered).
Provide and install Velux flashing kit.
Line opening internally using 18mm moisture resistant MDF as required. Vertical MDF to drop 15mm below the ceiling and skeiling finish and be routered to form a chamfer to both sides.
Allow to repair ceiling and infill ceiling / skeiling as required, fill screw holes and sand back. Decorate in accordance with Section 2B. Colour White.
4.6.5 | Replacement of Soffits and Fascia's
Carefully remove all fascia's and soffits clear away from site taking back to rafter feet. Vacuum and clean out voids.
Allow to frame out using tanalised timber from existing rafter feet to ensure new fascias and soffits are straight and plumb.
Provide and install new white 18mm PVCu facias and vented soffits. Vented soffits to have pre-fitted mesh.
Provide all relevant , trims, brackets and caps where required. All fixings are to be stainless steel.
Prepare and decorate concrete soffits to Paint Specification in Section 2B.
4.6.6 | Replacement of PVCu Rainwater Goods
Remove all PVCu rainwater goods, clips and bracketry and clear away.
Replace all rainwater goods with black PVCu heritage products to match the existing cast iron products in size and appearance. C.A to approve prior to ordering.
Seal all joints using a black low modulus silicone.
All brackets, clips and hoppers to be screwed with stainless steel screws and washers.
Water test upon completion.
4.6.7 | Electrical Supply to roof lights
Allow for a NICEIC/ELECSA electrician to install a fused electrical supply adjacent to the roof window (where required) taken from a local supply.
All wiring should be carried out in accordance with BS7671 Amd. 3 and manufactures instructions.
Cables are to be concealed within the buildings fabric where possible however where the cables are to be seen, white conduit with saddles at 500mm centres should be used.
The window control module is to be located adjacent to the main entrance door to the room at a height of 1200mm from floor level.
Allow for an electrical installation certificate to be provided upon completion.
4.7 | Roof 11 Void
4.7.1 | Insulation of Roof Void
Prior to carrying out these works please see Asbestos R&D Survey within PCI. See Appendix D.
Externally, allow to carefully remove a section of close boarding and trim out rafters as required to allow access into the pitched roof voids. The aperture should allow for the removal of redundant tanks and services within the roof void.
Allow to remove all existing insulation, waste, disused M&E and debris to all pitched roof sections. All voids should be vacuumed and left clean.
Remove and dispose of the redundant water tank ensuring that all associated redundant pipework is also pipework is also removed.
Remove all duck boards and clear away. Allow to install new tanalised timber noggins to allow for new 1000mm width duck boards. Noggins to be fixed to every ceiling joist to ensure adequate support to duck boards.
Insulate the voids with 100mm of Knauf Earthwool between the joists. A further 170mm of Knauf Earthwool should be cross laid in the opposite direction to the joists.
To new noggins / trimmers install new 18mm WBP plywood, screwed to every noggin. Duck boards to be a total width of 1000mm with a 50 x 50mm section of tanalised timber fixed to either side.
To the internal access hatch, accessing this roof void, allow to provide and fix a new heavy duty aluminium loft ladder suitable for high ceiling height.
4.7.2 | Lighting to Roof Void
The contractor shall be responsible for ascertaining all routes and BWIC, full allowance shall be made within this clause.
Remove all existing lighting, clear away and isolate as required.
Allow for a NICEIC/ELECSA electrician to install a fused electrical supply. All wiring should be carried out in accordance with BS7671.
Install new 5ft 50w LED Non Corrosive Weatherproof Fitting - IP65 strip lights to ridge board at every 5m.
Lighting to be switched from the estate office and next to the loft access ladder within the roof void. Switch plates to be MK with indicator light.
Cables are to be concealed within the buildings fabric where possible however where the cables are to be seen, white conduit with saddles at 500mm centres should be used.
Allow for an electrical installation certificate to be provided upon completion.
4.7.3 | Cable control
Provide and install new galvanised medium gauge cable tray next to the duck boards.
All cables should be moved and secured to new cable tray. Where this is not possible cables are to be either clipped to the joists or laid directly upon the ceiling. Cables should not be 'sandwiched' between layers of insulation.
To all cables with exposed connections, allow to tighten the connections and contain with a Wago box or similar.
4.8 | Roof 12 & 13
4.8.1 | Replacement of flash band trim
Allow to careful remove and dispose of the existing flashing tape to the perimeter upstand in its entirety.
In Code 4 lead allow to dress the entire perimeter upstand in accordance with LSA guidance. Include for forming curved sections of WBP 18mm plywood etc. as required to correctly detail.
4.9 | Completion
On completion clear away all builder’s rubbish and materials and leave clean and ready for occupation at handover.
Provide the Client / Contract Administrator with copies of all necessary handover documentation including all Statutory Compliances, test certification, guarantees and warranties for O&M and H&S file.
COLLECTION PAGE
Collection from page 1
Collection from page 2
Collection from page 3
Collection from page 4
Collection from page 5
Collection from page 6
Collection from page 7
Collection from page 8
Collection from page 9
Collection from page 10
Collection from page 11
Collection from page 12
Collection from page 13
Collection from page 14
Total to Summary

## Section 5 - Extension
5 | SCHEDULE OF WORKS
SECTION FIVE
5.1 | Scope Of Works
The works comprise of all building works necessary for the construction of an extension to the West Elevation of the Primary School Building. The extension is to be used as a catering store room.
In addition to the extension, works include for a slope to be formed to the doorway in the corridor adjacent to the extension. This is to allow the use of wheeled trolleys.
The construction period is anticipated to commence on the 7th July 2017, during the schools summer holiday break. Works are to be completed within approximately 12 weeks. The works are to be carried out concurrently to those in Section 3 & 4.
Refer to the preliminaries for sectional completion dates.
5.2 | Notes Generally
No hot works or asphalting will be permitted when the school is in operation.
The Contractor is to price each item separately. It is important that prices are not grouped together as the Client requires to have a complete itemised schedule.
Where the clause numbers or sections are referred to, all of these numbers refer to the relevant clauses/sections in Section 2 of this specification and the Contractor is deemed to have included in his price, all those works necessary and contained within the standard clauses where referred to.
Where quantities of various elements have been provided within the schedule of works, these are for the Contractor’s guidance only, except where specifically stated otherwise. The Contractor should check all quantities himself.
The Contractor should supply the Contract Administrator with a telephone number where he may be contacted 24 hours a day and at weekends during the works.
It is the Contractor’s responsibility to maintain close liaison with the Contract Administrator, the Headteacher and Ms Justine Pare, Property Manager for Lycée Français Charles De Gaulle, to ensure full co-operation to carry out the works. In this respect, the Contractor should appoint a Site Manager for the works to be present at all times throughout the duration of the project.
Where buildings are opened to the elements during roof replacement/repair works, this should be undertaken in bays/sections which shall allow the contractor to provide adequate protection to ensure weather tightness until work recommences.
Internal works shall only be permitted when the school is closed (Out of Hours) or within the holiday period.
Deliveries are not permitted between 8.15 to 8.45am, and between 11.30 am to 2.00pm.
The contractor shall be responsible for liaising with the Approved Inspector / Building Inspector throughout the works. Their fees have been paid by the Client.
The contractor will be afforded all details regarding the full plans submission and contact details of the Approved Inspector / Building Inspector once they have been appointed.
The contractor will be responsible for ensuring the C.A is made aware of when attendance/site visits are required by the Approved Inspector / Building Control.
5.3 | General Items Applicable to all Works
5.3.1 | Temporary Protection
The Contractor shall provide sheeting over all openings where works are in progress and seal to prevent dust etc., from percolating through to the occupied space at all levels, together with outer areas of the building and maintain for the duration of the project. If this occurs, then the Contractor is to clean up all affected areas as soon as possible, to the satisfaction of the Contract Administrator and the Property Manager.
All existing glazing, roof lights, walls, doors and other parts of the building fabric and services are to be adequately protected against damage.
The Contractor, either by himself or staff, shall not obstruct any rights of way, entrance or anything that might amount to a nuisance or annoyance. Any complaint must be communicated at once to the Contract Administrator.
5.3.2 | Cleanliness
The Contractor is to ensure that the site is kept clean at all times. The contractor must maintain and keep all access routes clear at all times
On completion clear away all builder’s rubbish and materials and leave clean and ready for occupation at handover.
5.3.3 | External Hoarding
The external works shall be completed before the School recommences in early September.
If the external works overrun, the contractor shall be fully responsible for costs associated to providing temporary heras fencing until completion.
5.3.4 | Internal Hoarding
The contractor shall install internal hoarding to separate the existing window opening extending 1000mm into the existing corridor. This is required regardless of when works are completed.
Provide and erect a timber stud wall using 100 x 50mm timber to close off the work area.
Provide full fill glass wool fibre insulation between studs. Line both sides with 18mm WBP plywood.
At low level provide and fix 200mm plywood skirting detail and head detail using 18mm WBP plywood.
Seal perimeter / services using expanding foam. It is important the work are is fully sealed off from the works and outside.
Prepare and decorate hoarding facing into the corridor using Egg Shell White in colour in accordance with Part 2B.
Corridor extension
The contractor is to include for all works on the drawings whether stated or implied.
Refer to drawings:
17.334.100 - Existing plans and elevations
17.334.101 - Proposed plans and elevations
17.334.102 - Proposed sections and details
17.334.103 - Contractors compound
5.4 | Ground & Civil Works
5.4.1 | CCTV & CAT Scan
Undertake CAT Scan of playground prior to any excavations to establish if any unknown services are located above the work area. If any anomalies found notify C.A and stop works until further notice.
The contractor shall undertake a full CCTV survey of the drainage within the area of the extension and beyond as required to complete the extension. Once completed provide drainage map and CCTV report to C.A for review.
5.4.2 | Underground Drainage
To be read in conjunction with Drawing 17.334.101
N.B a number of the inspection chambers and runs that require altering are located within the live playground area. These works must be undertaken as part of the externals within the holiday period.
The contractor will be required to locate all drainage runs and report to the C.A.
Carefully excavate and break out existing surface water drainage as indicated and clear away.
Provide and lay new 100mm plastic pipe surface water drainage system as indicated running to new soak away 5m from extension.
Provide and install new deep flow Aco drainage channel with galvanised steel grating connected to below ground surface water drainage system as indicated, bed in using lean mix concrete.
Supply and fit new gully traps and covers as required to all new and existing rainwater down pipes within new tarmac area.
Install new soak away system by Polystorm or similar 1000 x 2000mm x 800mm. Rap in geotextile as required and back fill using pee shingle and type 1. Leave ready to receive new tarmacadam finish.
Prior to back fill under take drop test on surface water drainage system and record results. Client / C.A & Approved Inspector / Building Control to be in attendance.
Back fill as required using pee shingle and type 1. Leave ready to receive new tarmacadam finish to match existing. Levels to match existing.
5.4.3 | Foundations
To be read in conjunction with Drawing Nr 17.334.101
Excavate for new deep mass concrete strip foundations. Provide formwork and cast new mass concrete foundations as Drawing Nr 17.334.101
The foundations are to be of 600mm x 1600mm however, this will require confirmation from the Building Control Officers upon excavation.
Allow for all reinforced concrete lintels as required to over sail new and existing drainage runs. Allow for over sailing one drainage run.
Psum | A provisional sum shall be included under this Section for additional foundation works subject to ground conditions. | 2000
5.4.4 | PCC Block and Beam Floor
To be read in conjunction with Drawing Nr 17.334.101
Install a Forterra (or Similar Approved) precast concrete beam and block floor in accordance with Drawing Nr 17.334.101 and the manufactures details. Ensure 150mm of cleared ground beneath the floor structure.
Install a 1200 gauge polythene DPM/vapour barrier above the block and beam floor but below the insulation and screed.
The floor should be insulated with ≥150mm Celotex F15000 to achieve a U value of 0.22 W/m2k.
Install a 75mm sand/cement screed finished 25 mm below the existing floor finish of the connecting corridor. Leave screed ready to receive vinyl floor covering.
5.5 | Main walls
5.5.1 | Existing elevation works
Allow to remove existing rainwater goods and hoppers and set aside for re-use.
Remove the extractor fan from the adjacent WC. Allow to brick up the opening and make good internally within the WC.
Allow to carefully remove the existing exterior metal shelving. This is to be set aside and either re-fixed in an alternative location. Make allowance for re-fixing in location to be confirmed by Client.
5.5.2 | Block work / Brickwork walls
To be read in conjunction with Drawing Nr 17.334.101
The walls are to be cavity in type with the internal skin of blockwork whilst the external skin is to be of matching brickwork.
Provide an ICOPAL damp roof course to manufactures recommendations and Drawing Nr 17.334.101 horizontally at a minimum of 150mm from the finished external ground level.
Provide engineering brickwork below DPC level and infill with a lean mix of sand and cement.
Provide and install four buff telescopic air vents to ventilate new floor void as required.
The contractor is responsible for inviting an Ibstock representative to provide a choice of 4no matching brick types. The contractor is to present the options to the Client & C.A for approval prior to ordering.
Brickwork detailing to match that indicated on elevation drawings.
Install catnic lintel to window opening full insulated. Allow for all required wall ties, DPC's and red weep holes.
The internal skin is to be constructed of Thermalite Hi strength 7 blocks.
To the cavity install 75mm of Celotex CG5000 partial fill insulation leaving a 25mm airgap. All mortar snots should be removed at regular intervals ensuring the cavity is kept clear of debris.
All opening / cavity ends to window and door reveals allow to supply and fix into position Thermarator or similar insulated cavity closers to the manufactures recommendations.
Below the window provide a recessed section of render. This detail is to allow for the later installation of double doors. Brickwork is therefore to be terminated correctly with a blockwork infill. Render blockwork using sand cement with stainless steel fixtures and fittings.
5.5.3 | Parapet
To be read in conjunction with Drawing Nr 17.334.101
Carefully dismantle the parapet to Roof No.2 as indicated on Drawing Nr 17.334.101. Clean and set aside bricks and coping stones to be used elsewhere for repair replacement.
Take existing parapet down to roof deck level as indicated on drawings.
The parapet wall to the extension is to be toothed into the existing where possible or with the use of stainless steel starter bars.
A soldier course is to be installed at parapet level as per Drawing Nr 17.334.101 to match existing.
Install new sandstone coping stones on a level bed of 1:1:6 mortar, on a ICOPAL polyethylene DPC and cavity trays in accordance with the Manufactures guidelines and fully point in all joints on completion.
Allow for forming outlet through parapet to match those found throughout the school. Outlets to be fully detailed in Code 4 Lead in accordance with LSA guidance.
5.6 | Roof
5.6.1 | Roof Structure
To be read in conjunction with Drawing Nr 17.334.101
Install timber joists as per Drawing Nr 17.334.101. Allow for all roof light and junction details as required.
Joists to be a minimum of 38 x 170 C16 at 400mm centres and all noggins required for building control approval.
Provide tantalised timber firings as required to provide 5 degree minimum pitch. Provide and fit 22mm WBP Plywood deck. Leave ready to receive insulation and roof covering.
The level of the deck is to match the level of the surrounding concrete deck of Roof No. 2.
Roof covering costs to be included under Roof 2 within Section 3.
5.6.2 | Roof light
Roof light installation and costs to be included under Roof 2 within Section 3.
5.6.3 | Roof Covering
The Installation of Asphalt is to be carried out concurrently with that of Roof No. 2, creating a seamless roof covering.
5.6.4 | Rainwater goods
To be read in conjunction with Drawing Nr 17.334.101
As indicated on the drawing, allow to re-fix the previously set aside cast iron hopper and down pipe.
Using mechanical means, clear debris and corrosion from the surface. Particular attention is to be paid to the internal faces of the joints.
Where the cast iron is cracked, the sections are to be retained and repaired using a liquid metal system. Once repaired allow to file down liquid metal, flush with original surface.
Include for replacing all defective brackets, clips and fittings, with a cast iron replacement.
A black low modulus silicone or flexible caulking should be used applied to the joints upon reinstatement. Replacement stainless steel nuts, bolts and washers should be used.
Decorate all cast iron rainwater goods in accordance with the Paint Specification in Section 2B. Colour: Black
Water test upon completion.
5.7 | Windows and Doors
5.7.1 | Aluminium Windows
Provide and install new double glazed Schuco white polyester powder coated aluminium windows as indicated.
Glazing to provide minimum U-value of 1.7 Argon filled. Glazing to be Pilkington Artic Blue 6mm Toughened with low E coating to surface #3 (Inner pane).
The window is to be installed with two side hung opening casements.
External window sill to over sail render finish below.
Provide clear mastic sealant to junction of new frames with surrounding reveals.
Contractor to obtain 10 year guarantee from manufacture for windows / doors.
5.7.2 | Aluminium Doors within existing corridor
Carefully remove the existing single door and frame as indicated and clear away to full width of structural opening.
Provide and install new Schuco white polyester powder coated aluminium glazed doors as indicated.
To either side of the door, provide and fit as part of the door frame infill panels. Side panels to be powder coated white fully insulated.
Glazing to provide minimum U value of 1.7 Argon filled. Glazing to be Pilkington Artic Blue 6mm Toughened with low E coating to surface #3 (Inner pane).
Double doors within Glazed system to be provided with 20mm Part M level thresholds.
Doors to be provided with panic push bar door furniture. Externally provide euro lock barrel. Provide 3nr keys to Client upon completion.
Provide clear mastic sealant to junction of new frames with surrounding reveals.
Provide and fit 4nr stainless steel hooks externally to allow doors to be held open. Screw fix using stainless steel screws.
Contractor to obtain 10 year guarantee from manufacture for windows / doors.
5.7.3 | Blinds
Allow to provide and fit black out blinds to all new window manually operated. Blinds to be adequate / robust enough for school environment.
Blinds to be grey in colour
5.8 | Internal Works
5.8.1 | Remove existing window
Remove the existing window as required to form new door opening and clear away.
Below window opening allow to cut down and remove masonry as required.
Take down to below concrete floor level as required. Make good and raise levels as required using concrete.
Take new DPM and insulation from extension, extending into opening. Screed as required matching levels and leave ready for Vinyl floor finishes.
5.8.2 | Adjusting double door opening
Allow to decrease the width of the existing opening as indicated to access new double doors.
Provide and install new blockwork on a DPC as required and leave ready to receive new plasterboard finish.
Ensure blockwork is set correctly to allow for plasterboard and skim / fill to be flush with the existing internal corridor finishes.
5.8.3 | Internal wall finish
To be read in conjunction with Drawing Nr 17.334.101
Provide and fit new 12.5mm tape and jointed plasterboard to all walls and return around opening.
Fill and sand back as required. Include for making good around new opening in existing corridor. Leave ready to receive decoration.
5.8.4 | Ceiling linings
Provide and fix new tape and jointed 12.5mm plasterboard ceiling to beneath flat roof as indicated. Tape and joint and leave to receive decoration.
Allow for trimming around new roof light and lining with plasterboard.
Allow for all trims, beads and fixings as required.
5.8.5 | Floor coverings
Remove metal trolley ramp and clear away as indicated on drawings. Remove and break out concrete ramp to kitchen.
Remove all vinyl floor finishes as indicated on drawings. Where vinyl cut back allow to protect until re-jointed.
As indicated on drawings cast new reinforced screeded ramp. Allow to cut out existing floor / screed as required to ensure new ramp thickness does not go below 40mm.
When casting install formwork as required as not to allow screed to push up to internal plastic corridor windows.
Provide and lay latex self levelling screed by Sika to ensure as required to repair existing floors where vinyl removed.
Provide new Altro Vinyl as indicated on drawings - Provisionally allow for £55.00 per metre for material cost. Client to confirm manufacture in due course.
Include for all threshold strips, fittings and fixings. If possible allow to weld new vinyl to existing.
5.8.6 | New double door set
Provide new FD30S internal grade plywood flush door set to new opening. Doors to have top and bottom vision panels using clear fire rated glass.
Provide new lock and latch case complete with internal thumb turn. Provide 3nr keys per lock and hand to client.
Provide combined intumescent cold smoke seals by Lorient or similar.
1mm thick interdens intumescent gaskets are to be fitted under all hinge blades, lock forends and keeps.
Provide and fit 1 and 1/2 pairs of hinges to each door leaf. Hinges to be stainless steel parliament type to allow doors to be open flush with corridor walls.
Provide and fit stainless steel hooks to allow the doors to be hooked in an open position during operation.
Provide and fit stainless steel Kick Plates to each side of the doors.
Provide and fit 4no stainless steel D-Handles 22mm thick bolt through.
Provide and fit 2no stainless steel Push Plates internal face.
Leave ready for decoration.
5.8.7 | 2nd Fix and retained Joinery
Supply and fit half round skirting to all new and existing walls / partitions as required, 200mm high 18mm thick. Screw fix, counter sink and fill. Leave ready to receive decoration.
Supply and fit half round architraves to all new and existing doors and screens as required, 150mm x 18mm thick. Leave ready to receive decoration.
Provide and fit new MDF window boards 24mm thick to all new and existing windows.
5.8.8 | Internal decoration
All decoration to be undertaken in accordance with Section 2A - Dulux Paint Specification.
Decorate new joinery with white egg shell.
Decorate all walls with vinyl matt emulsion colour white.
Decorate all ceilings with vinyl matt emulsion.
Silicon window/door frames to window reveals upon completion.
5.8.9 | Sundries
Provide and fit fire door keep shut aluminium signage to external face of new double doors.
5.9 | Services
5.9.1 | Power Installation
The existing small power is of age. Allow to provide one new MK distribution board mounted at high level within the store room.
The new distribution board will need to be connected back to the incoming main for the school. The contractor will need to allow for this new connection and all required building works.
Provide and install all MK switch gear and face plates from the standard range. Colour white.
All new wiring to be concealed within walls. All face plates to be flush with wall finish (Not surface mounted)
Provide the following, final locations to be agreed on site:
* 6no double sockets to perimeter of room at low level, not in banks
* 6no double sockets to perimeter of room at high level, not in banks
5.9.2 | Lighting
Provide 6 recessed LED down light fittings white in colour.
Lighting to be activated on PIRs. Also allow for an override switch.
Provide 4no external bulkhead black fittings IP65 for the playground areas. External lighting to be activated on PIR's.
5.9.3 | Emergency Lighting
Provide and install Emergency lighting in accordance with BS5266 Part 1.
Include for installing one emergency light fitting close to the double doors.
5.9.4 | Smoke and Heat Detectors
Provide and install interlinked one smoke and one heat detector with audio sounders as indicated on the drawings to satisfy building control.
| Include a provisional sum of £1,500.00 for connection to existing fire alarm panel. | 1500
5.1 | External hard standing
5.10.1 | Tarmacadam finishes
Allow to grub out all existing tarmacadam and grass surfaces as indicated on drawings.
Excavate 200mm and clear away spoil. Provide 100mm of type 1 aggregate mechanically compacted
Scrap back subsoil as required to ensure falls are directed to new Aco drainage channel to North East Elevation.
Allow to replace inspection chamber covers within work area with cast iron replacements. Allow to raise / lower manhole covers as required.
Provide and lay Asphalt Concrete (100mm Base, 60mm Binder Course & 40mm Surface Course), mechanically compacted and rolled.
5.1 | Completion
On completion clear away all builder’s rubbish and materials and leave clean and ready for occupation at handover.
Provide the Client / Contract Administrator with copies of all necessary handover documentation including all Statutory Compliances, test certification, guarantees and warranties for O&M and H&S file.
COLLECTION PAGE
Collection from page 1
Collection from page 2
Collection from page 3
Collection from page 4
Collection from page 5
Collection from page 6
Collection from page 7
Collection from page 8
Collection from page 9
Collection from page 10
Collection from page 11
Collection from page 12
Total to Summary

## Section 6 - ER
6 | Schedule of Rates
DO NOT INCLUDE WITHIN PRICED SUMMARY
6.1 | Concrete Repairs
Break out all loose and defective concrete marked for removal and repair with Fosroc repair system.
MIGRATING CORROSION INHIBITOR: Apply MCI to selected areas identified following survey.
Allow provisional quantity of 20 sq.m.
Repairs not exceeding 25mm deep.
| Repairs not exceeding 0.01m² | 10nr
| Repairs exceeding 0.01m² but not exceeding 0.05m² | 10nr
| Repairs exceeding 0.05m² but not exceeding 0.10m² | 10nr
| Repairs exceeding 0.10m² but not exceeding 0.25m² | 10nr
| Repairs exceeding 0.20m² but not exceeding 0.50m² | 10nr
Repairs exceeding 25mm & not exceeding 50mm deep.
| Repairs not exceeding 0.01m² | 10nr
| Repairs exceeding 0.01m² but not exceeding 0.05m² | 10nr
| Repairs exceeding 0.05m² but not exceeding 0.10m² | 10nr
| Repairs exceeding 0.10m² but not exceeding 0.25m² | 10nr
| Repairs exceeding 0.20m² but not exceeding 0.50m² | 10nr
Repairs exceeding 50mm & not exceeding 75mm deep.
| Repairs not exceeding 0.01m² | 10nr
| Repairs exceeding 0.01m² but not exceeding 0.05m² | 10nr
| Repairs exceeding 0.05m² but not exceeding 0.10m² | 10nr
| Repairs exceeding 0.10m² but not exceeding 0.25m² | 10nr
| Repairs exceeding 0.20m² but not exceeding 0.50m² | 10nr
6.2 | Timber Deck replacement
Allow to remove existing 3/4 inch timber boards to timber joists and clear away.
De-nail joists as required and leave ready to receive new boarding.
Provide and fit new 18mm plywood to Clause K11/515, screwed down to all joists at 300 C/C.
Allow for 20m2 in isolated areas of 2m2.

## Summary
GENERAL SUMMARY
Section 1 | Preliminaries/General Conditions
| Provisional Sums & Contingency | 10000
| Contingency | 30000
Section 2 | Workmanship & Materials
Section 3 | Schedule of Works - Section 3 Primary School
Section 4 | Schedule of Works - Section 4 Nursery
Section 5 | Schedule of Works - Section 5 Extension
Section 6 | SOR - Do not include
TOTAL CARRIED FORWARD TO FORM OF TENDER:
Contractor | ...............................................................
Address | ...............................................................
Signed | ...............................................................
Date | ...............................................................