## Setup (hidden)
DOCUMENT SETUP PAGE
Workbook Setup
|  | Document Title: |  | 1ST STAGE TENDER DOCUMENT
|  | Project Title: |  | New Sports and Community Pavilion, Edmonds Park, Didcot
|  | Client Name: |  | Didcot Town Council
|  | Date Issue: |  | 2026-07-30 00:24 |  |  |  | 2022-06-10
|  | Report nr: |  | Version 2 |  |  |  | Version 1
|  | RIDGE Office: |  | OX
|  | Report Section: |  | Main Contract Works
|  | Contractors Name: |  | {Contractors Name}
Document Revision: |  |  | 15 | 2016-05-20
Do Not Print This Page Out
Notes : (Please Read Before using the Speadsheets)
• | All items in { } are to be inputted as part of the setup of the workbook
• | All items in 'Green' text are titles and should not be altered
• | The data inputted above is linked and transferred to the headers on the each workbook sheet
• | Within the Workbook the following conventions apply;
| • | Any items in 'Blue' text are the results of formulas or linked items - Do Not amend
| • | Any areas in 'Orange' are for the input of data which is used elsewhere for automatic calculations
| • | Any areas in 'Yellow' are for Side calculations and should be hidden before printing
• | Always Print out in Black & White. Only Covers should be printed in colour
• | The Spreadsheet are generally set up of the central printer, please check page lengths & widths before
printing.
• | Always set at 100% print. Adjust the last column to fit on a page.
• | Never adjust the Header rows 1 to 5.
• | RIDGE Office Addresses (Look-up table)
| BM | 2 Cranbrook Way | Solihull Business Park | Solihull | B90 4GT | Tel: 0121 713 8000
| BR | Eden Office Park | 65 Macrae Road | Ham Green | Bristol | BS20 0DD | Tel: 01275 813500
| CA | Sophia House | 28 Cathedral Road | Cardiff | CF11 9LJ | Tel: 029 2002 0015
| LE | Jupiter Court | 1A Dominus Way | Meridian Business Park | Leicester | LE19 1RP | Tel: 0116 245 6600
| LI | 8th Floor | Horton House | Exchange Flags | Liverpool | L2 3YL | Tel: 0151 243 3500
| LO | Harling House | 47-51 Great Suffolk Street | London | SE1 0BS | Tel: 020 7593 3400
| OX | The Cowyards | Blenheim Park | Oxford Road | Woodstock | OX20 1QR | Tel: 01993 815000
| MA | 1B Abito | 85 Greengate | Manchester | M3 7NA | Tel: 0161 833 9579
| RD | Beaumont House | 59 High Street | Theale | Reading | RG7 5AL | Tel: 0118 932 3088
| WI | Partnership House | Moorside Road | Winchester | SO23 7RX | Tel: 01962 834400
Note on E5: Information: Document Title Should Not be amended
Note on E12: Information: Dark Orange denotes "Selection from a drop down list"
Note on F12: Ref Key: BM = Birmingham BR = Bristol CA = Cardiff LE = Leicester LI = Liverpool LO = London MA = Manchester OX = Oxford RE = Reading WI = Winchester

## Cover-Print (hidden)
{Insert Client Logo}
1ST STAGE TENDER DOCUMENT
New Sports and Community Pavilion, Edmonds Park, Didcot
2026-07-30 00:24
Version 2
Prepared for | Prepared by
A Sample Client | Ridge and Partners LLP
A building | The Cowyards
A Road | Blenheim Park
A Town | Oxford Road
A County | Woodstock
Postcode | OX20 1QR
Tel: 01993 000000 | Tel: 01993 815000
Note on C9: Note: Enter Ridge office ref on the setup page. The Address will change

## Front Cover (A4-P)
1ST STAGE TENDER DOCUMENT
New Sports and Community Pavilion, Edmonds Park, Didcot
Didcot Town Council
2026-07-30 00:24

## Version
1ST STAGE TENDER DOCUMENT
New Sports and Community Pavilion, Edmonds Park, Didcot
New Sports and Community Pavilion, Edmonds Park, Didcot
Didcot Town Council
2026-07-30 00:24
Prepared for
Didcot Town Council
Didcot Civic Hall
Britwell Road
Didcot
Oxfordshire
OX11 7HN
Prepared by | Contact
Ridge and Partners LLP | Simon Keen
The Cowyards | Associate
Blenheim Park | 01993 815068
Oxford Road | skeen@ridge.co.uk
Woodstock
OX20 1QR
Tel: 01993 815000

## Content
1ST STAGE TENDER DOCUMENT
New Sports and Community Pavilion, Edmonds Park, Didcot
VERSION CONTROL
Project Name |  | New Sports and Community Pavilion, Edmonds Park, Didcot
Project No. |  | 5018614
VERSION | DATE | DESCRIPTION | CREATED BY | REVIEWED BY
1 | 10.06.2022 | Draft Issue | TP | SK
2 | 2026-07-30 00:24 | Final issue | TP | SK
CONTENTS
1. PRELIMINARIES/GENERAL CONDITIONS
| 1.1 - Introduction |  |  | 1.1/1
| 1.2 - Preliminaries |  |  | 1.2/1
| 1.3 - Preliminaries Pricing Schedules |  |  | 1.3/1
| 1.4 - Responsibility Matrix |  |  | 1.4/1
2. PROVISIONAL ITEMS
| 2.1 - Notes on Cost Plan |  |  | 2.1/1
| 2.2 - Cost Plan Summary (Elemental Provisional Sums) |  |  | 2.2/1
| 2.3 - Dayworks |  |  | 2.3/1
3. CONTRACT SUM ANALYSIS/WORK PACKAGES
| 3.1 - Element/Package Prices |  |  | 3.1/1
4. MAIN SUMMARY |  |  |  | 4/1
5. FORM OF TENDER |  |  |  | 5/1
APPENDICES
A. DOCUMENT REGISTER |  |  |  | A/1
B. CONTRACT CONDITIONS |  |  |  | B/1
| B.1 JCT Design and Build Building Contract 2016 |  |  | B.1/1
| B.2 Specific Schedule of Amendments |  |  | B.1/2
C. WARRANTIES, BONDS AND GUARANTEES |  |  |  | C/1
| C.1 Collateral Warranties/ Third Party Rights |  |  | C.1/1
| C.2 Performance Bond |  |  | C.2/1
D. PRE CONSTRUCTION SERVICES AGREEMENT (PCSA) |  |  |  | D/1
| D.1 PCSA Pricing Schedule |  |  | D.1/1
| D.2 PCSA Form of Tender |  |  | D.2/1
| D.3 PCSA Contract Particulars |  |  | D.3/1
E. COST PLAN |  |  |  | E/1
F. PROGRAMME |  |  |  | F/1
CONTENTS
G. PLANNING DECISSION AND PLANNING CONDITION TRACKER |  |  |  | G/1
H. PRE-CONSTRUCTION INFORMATION |  |  |  | H/1
I. BREEAM TRACKER |  |  |  | I/1
J. TENDER EVALUATION |  |  |  | J/1

## Fly1.1
1. PRELIMINARIES/GENERAL CONDITIONS | 1.1 - Introduction

## Flysheet (hidden)
1ST STAGE TENDER DOCUMENT
New Sports and Community Pavilion, Edmonds Park, Didcot
1. PRELIMINARIES/GENERAL CONDITIONS
1.1 - Introduction
1. PRELIMINARIES/GENERAL CONDITIONS
1.2 - Peliminaries
1. PRELIMINARIES/GENERAL CONDITIONS
1.3 - Peliminaries Pricing Schedules
1. PRELIMINARIES/GENERAL CONDITIONS
1.4 - Responsibility Matrix
2. CONTRACT SUM ANALYSIS
2.1 - Notes on the Cost Plan
2. CONTRACT SUM ANALYSIS
2.2 - Cost Plan Summary
3. MAIN SUMMARY
4. FORM OF TENDER
A. DOCUMENT REGISTER
APPENDIX
B. CONTRACT CONDITIONS
B. CONTRACT CONDITIONS
B.1 - JCT Design and build Contract 2011
B. CONTRACT CONDITIONS
B.2 - JCT Design and Build Contract Amendment 1 (CDM)
B. CONTRACT CONDITIONS
B.3 - Special Conditions
B. CONTRACT CONDITIONS
B.4 - Stage 1 Agreement
C. WARRANTIES, BONDS AND GUARANTEES
C. WARRANTIES, BONDS AND GUARANTEES
C.1 - Collateral Warranties
C. WARRANTIES, BONDS AND GUARANTEES
C.2 - Performance Bond
D. CONSULTANT APPOINTMENT AND NOVATION AGREEMENTS
D.1 - Letter of Appointment for Design Consultant Services
D. CONSULTANT APPOINTMENT AND NOVATION AGREEMENTS
D.2 - Architectural Consultant Services
D. CONSULTANT APPOINTMENT AND NOVATION AGREEMENTS
D.3 - Civil & Structural Consultant Services
E. PRE CONSTRUCTION INFORMATION
E.1 - PCSA Pricing Schedule
E. PRE CONSTRUCTION INFORMATION
E.2 - PCSA Form of Tender
E. PRE CONSTRUCTION INFORMATION
E.3 - PCSA Contract particulars
F. PROJECT DIRECTORY
G. PLANNING DOCUMENTS

## Fly1.2
1. PRELIMINARIES/GENERAL CONDITIONS | 1.2 - Preliminaries

## Fly1.3
1. PRELIMINARIES/GENERAL CONDITIONS | 1.3 - Preliminaries Pricing Schedules

## 1.3 Prelims Pricing Schedul
1ST STAGE TENDER DOCUMENT | [5 empty] | Data Entry
New Sports and Community Pavilion, Edmonds Park, Didcot
1. PRELIMINARIES/GENERAL CONDITIONS
1.3 | Preliminaries Pricing Schedules |  |  |  |  | Fixed Related |  |  | Time Related
Ref. | Description |  |  | F £ | TR £ | Start | Stage | End
1 | Main Contractor's Cost Items
• | Not withstanding the conditions set out in the ‘National Building
Specification’ guidelines and the ‘Standard Method of
Measurement’ 7th Edition. The Contractor’s general cost items are
to be priced in accordance with the ‘RICS New Rules of
Measurement’ volume 2, 1st edition, (RICS:NRM-2 v1)
• | Costs relating to preliminaries items that are not specifically
identified in the contractor’s full and detailed breakdown shall be
deemed to have no cost implications or have been included
elsewhere within the contractor’s rates and prices.
• | Costs of all site facilities including Scaffolding and Skips for work
package contractors should be priced in this section not under Work
packages section.
1.1 | Employer's requirements
1.1.1 | Site accommodation
| 1 | Site accommodation |  | 0 | 0
| 2 | Temporary works in connection with site establishment |  | 0 | 0
| 3 | Furniture and equipment |  | 0 | 0
| 4 | IT systems |  | 0 | 0
| 5 | Consumables & services |  | 0 | 0
| 6 | Brought-in services |  | 0 | 0
| 7 | Sundries |  | 0 | 0
1.1.2 | Site records
| 1 | Operation and maintenance manuals. |  | 0 | 0
| 2 | Compilation of health and safety file. |  | 0 | 0
1.2 | Main Contractor's Cost Items
1.2.1 | Management & Staff
1.2.1.1 | Project Specific Management & Staff:
| 1 | Project manager/director |  | 0 | 0
| 2 | Construction manager/Supervisors |  | 0 | 0
| 3 | Health & Safety manager/officer |  | 0 | 0
| 4 | Commissioning manager (building engineering services) |  | 0 | 0
| 5 | Planning/programming manager and staff. |  | 0 | 0
| 6 | Senior/managing quantity surveyor. |  | 0 | 0
| 7 | Project/package quantity surveyors. |  | 0 | 0
| 8 | Administrative staff |  | 0 | 0
| 9 | Other management and staff. |  | 0 | 0
|  |  | To Collection £ | 0 | 0
1.2 | Main Contractor's Cost Items
1.2.1 | Management & Staff
1.2.1.2 | Visiting Management & Staff
| 1 | Managing/regional directors & the like |  | 0 | 0
| 2 | Quality manager |  | 0 | 0
| 3 | Contracts/commercial manager |  | 0 | 0
| 4 | Health & Safety Manager/Officer |  | 0 | 0
| 5 | Other visiting management & staff |  | 0 | 0
1.2.1.3 | Extraordinary Support Costs
| 1 | Other extraordinary support costs |  | 0 | 0
| 2 | Day transport |  | 0 | 0
| 3 | Personnel transport |  | 0 | 0
| 4 | Temporary living accommodation |  | 0 | 0
| 5 | Subsistence payments |  | 0 | 0
| 6 | Out of Hours working |  | 0 | 0
1.2.2 | Site establishment
1.2.2.1 | Site facilities
| 1 | Site accommodation |  | 0 | 0
| 2 | Temporary works in connection with site establishment |  | 0 | 0
| 3 | Furniture and equipment |  | 0 | 0
| 4 | IT systems |  | 0 | 0
| 5 | Consumables & services |  | 0 | 0
| 6 | Brought-in services |  | 0 | 0
| 7 | Sundries |  | 0 | 0
1.2.3 | Temporary services
1.2.3.1 | Site facilities
| 1 | Temporary water supply |  | 0 | 0
| 2 | Temporary gas supply |  | 0 | 0
| 3 | Temporary electricity supply |  | 0 | 0
| 4 | Temporary telecommunication systems |  | 0 | 0
| 5 | Temporary drainage |  | 0 | 0
|  |  | To Collection £ | 0 | 0
1.2 | Main Contractor's Cost Items
1.2.4 | Security
1.2.4.1 | Site facilities
| 1 | Security staff |  | 0 | 0
| 2 | Security equipment |  | 0 | 0
| 3 | Hoardings, fences and gates |  | 0 | 0
1.2.5 | Safety and environmental protection
1.2.5.1 | Site facilities
| 1 | Safety programme |  | 0 | 0
| 2 | Barriers & safety scaffolding |  | 0 | 0
| 3 | Environmental protection measures |  | 0 | 0
| 4 | Skips for work package contractors |  | 0 | 0
1.2.6 | Control and protection
1.2.6.1 | Site facilities
| 1 | Survey, inspections & monitoring |  | 0 | 0
| 2 | Setting out |  | 0 | 0
| 3 | Protection of works |  | 0 | 0
| 4 | Samples |  | 0 | 0
| 5 | Environmental control of building |  | 0 | 0
1.2.7 | Mechanical plant
1.2.7.1 | Site facilities
| 1 | Generally |  | 0 | 0
| 2 | Tower cranes |  | 0 | 0
| 3 | Mobile cranes |  | 0 | 0
| 4 | Hoists |  | 0 | 0
| 5 | Access plant |  | 0 | 0
| 6 | Concrete plant |  | 0 | 0
| 7 | Other plant |  | 0 | 0
1.2.8 | Temporary works
1.2.8.1 | Site facilities
| 1 | Access scaffolding |  | 0 | 0
| 2 | Temporary works |  | 0 | 0
|  |  | To Collection £ | 0 | 0
1.2 | Main Contractor's Cost Items
1.2.9 | Site records
1.2.9.1 | Site records
| 1 | Photography |  | 0 | 0
| 2 | Works records |  | 0 | 0
1.2.10 | Completion and post-completion requirements
1.2.10.1 | Requirements
| 1 | Testing and commissioning plan |  | 0 | 0
| 2 | Handover |  | 0 | 0
| 3 | Post-completion services |  | 0 | 0
1.2.11 | Cleaning
1.2.11.1 | Requirements
| 1 | Site tidy |  | 0 | 0
| 2 | Maintenance of roads, paths and pavings |  | 0 | 0
| 3 | Building clean |  | 0 | 0
1.2.12 | Fees and charges
1.2.12.1 | Fees & Charges
| 1 | Rates on temporary accommodation. |  | 0 | 0
| 2 | Licences in connection with hoardings, scaffolding,
|  | gantries & the like. |  | 0 | 0
1.2.13 | Site services
1.2.13.1 | Temporary works
| 1 | Temporary works that are not specific to an element. |  | 0 | 0
1.2.13.2 | Multi-service gang
| 1 | Ganger |  | 0 | 0
| 2 | Labour |  | 0 | 0
| 3 | Fork lift driver. |  | 0 | 0
| 4 | Service gang plant and transport. |  | 0 | 0
|  |  | To Collection £ | 0 | 0
1.2 | Main Contractor's Cost Items
1.2.14 | Insurance, bonds, guarantees and warranties
1.2.14.1 | Works insurance
| 1 | Contractor’s ‘all risks’ (CAR) insurance. |  | 0 | 0
| 2 | Contractor’s plant and equipment insurance. |  | 0 | 0
| 3 | Temporary buildings insurance. |  | 0 | 0
| 4 | Terrorism insurance. |  | 0 | 0
| 5 | Other insurances in connection with the works. |  | 0 | 0
1.2.14.2 | Public liability insurance
| 1 | Non-negligence insurance. |  | 0 | 0
| 2 | Professional indemnity insurance. |  | 0 | 0
1.2.14.3 | Employer’s (main contractor’s) liability insurance
| 1 | Management and staff, including administrative staff. |  | 0 | 0
| 2 | Works operatives. |  | 0 | 0
1.2.14.4 | Other insurances
| 1 | Employer’s loss of liquidated damages. |  | 0 | 0
| 2 | Latent defects cover. |  | 0 | 0
| 3 | Motor vehicles. |  | 0 | 0
| 4 | Other insurances. |  | 0 | 0
| 5 | Insurance premium tax (IPT). |  | 0 | 0
| 6 | Allowance for recovery of all or part of premium excess. |  | 0 | 0
1.2.14.5 | Bonds
| 1 | Tender bonds (if applicable). |  | 0 | 0
| 2 | Performance bonds. |  | 0 | 0
1.2.14.6 | Guarantees
| 1 | Parent company guarantees. |  | 0 | 0
| 2 | Product guarantees, insurance backed guarantees. |  | 0 | 0
1.2.14.7 | Warranties
| 1 | Collateral warranties. |  | 0 | 0
| 2 | Funder’s warranties. |  | 0 | 0
| 3 | Purchaser’s and tenant’s warranties. |  | 0 | 0
| 4 | Other warranties. |  | 0 | 0
|  |  | To Collection £ | 0 | 0
1.2 | Main Contractor's Cost Items
1.2.14.8 | Design Fees
| 1 | Architectural |  | 0 | 0
| 2 | Structural |  | 0 | 0
| 3 | Civil Engineering |  | 0 | 0
| 4 | MEP Engineer |  | 0 | 0
| 5 | Landscaping Architect |  | 0 | 0
| 6 | Fire Consultant |  | 0 | 0
| 7 | Acoustic Consultant |  | 0 | 0
| 8 | BREEAM Advisor |  | 0 | 0
| 9 | Principal Designer |  | 0 | 0
| 10 | Ecologist |  | 0 | 0
| 11 | Temporary Works Designer |  | 0 | 0
| 12 | Technical support / clash detection |  | 0 | 0
| 13 | Other Fees and charges |  | 0 | 0
|  |  | To Collection £ | 0 | 0
Collection
|  | 1.3/1 |  | 0 | 0
|  | 1.3/2 |  | 0 | 0
|  | 1.3/3 |  | 0 | 0
|  | 1.3/4 |  | 0 | 0
|  | 1.3/5 |  | 0 | 0
|  | 1.3/6 |  | 0 | 0
|  |  | £ | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | £ | 0 |  |  | 0
|  |  |  | Total to main summary £ | 0 |  | Check totals?: | P | P
Instruction:
Insert figures in the ORANGE sections of the sheet

## Fly1.4
1. PRELIMINARIES/GENERAL CONDITIONS | 1.4 - Responsibility Matrix

## 1.4 Responsibility Matrix
EMPLOYERS REQUIREMENTS
New Sports and Community Pavilion, Edmonds Park, Didcot
1. PRELIMINARIES/GENERAL CONDITIONS
1.4 | Preliminaries Responsibility Matrix
Ref. | Description |  | Employer | Main Contractor | Sub Contractor | Comments/ Guidance
Quality Standards/ Control
| ▪ | Samples |  | P | P
| ▪ | Mock ups |  | P | P
| ▪ | Off site testing |  | P | P
| ▪ | On site testing |  | P | P
| ▪ | Sample storage/ room |  | P
| ▪ | Factory visits/ witness testing |  | P | P | As required for specific materials or installations
| ▪ | Site quality/ environmental signage |  | P
Security/ Safety/ Protection
| ▪ | Day time site security |  | P
| ▪ | Security of the site outside operational hours. |  | P
| ▪ | Radios |  | P | P
| ▪ | Temporary CCTV |  | P
| ▪ | ID card installations |  | P
| ▪ | Hutting - see site accommodation |  | P
| ▪ | Security gates/ barriers |  | P
| ▪ | Safety/ Protection |  | P | P
Specific limitations on method/sequence/timing/use of site
| ▪ | Working hours |  | P |  | Main Contractor to adhere to the limits imposed by the Employer/ Local Authority
| ▪ | Occupied buildings/ site |  | P
| ▪ | Safety of occupants |  | P
| ▪ | Safety of customers |  | P
| ▪ | Temp generators for power outages/ shut downs |  | P
| ▪ | Occupants access/ egress |  | P
| ▪ | Customer access/ egress |  | P
| ▪ | Temporary fire alarms etc. |  | P
| ▪ | Noise control |  | P
| ▪ | Dust control |  | P
| ▪ | Out of hours working requirements. |  | P
| ▪ | Maintain phones/ IT |  | P
| ▪ | Crane over sail licence/ permissions |  | P |  | Contractor to include for any notices or permissions
| ▪ | Special induction requirements |  | P
Operation/Maintenance of the finished building
| ▪ | O&M's + As-built drawings |  | P | P | Contractor to also include for the co-ordination of O&M's
| ▪ | Asset coding |  | P
| ▪ | Requirement to engage technical author.
| ▪ | Health & Safety File |  | P
| ▪ | Building Log |  | P
| ▪ | Training of the Employers staff |  | P | P
| ▪ | Provision of Spares |  | P | P
Contractor's general cost items.
Management and staff
| ▪ | Project Managers |  | P | P | Sub-contractor staff and management dependent on the nature of works required
| ▪ | APM's / Package Managers |  | P | P | Sub-contractor staff and management dependent on the nature of works required
| ▪ | Cost Managers |  | P | P | Sub-contractor staff and management dependent on the nature of works required
| ▪ | Estimators |  | P | P | Sub-contractor staff and management dependent on the nature of works required
| ▪ | Buyers |  | P | P | Sub-contractor staff and management dependent on the nature of works required
| ▪ | Construction / Section Managers |  | P | P | Sub-contractor staff and management dependent on the nature of works required
| ▪ | Building services managers |  | P | P | Sub-contractor staff and management dependent on the nature of works required
| ▪ | Design Manager |  | P | P | Sub-contractor staff and management dependent on the nature of works required
| ▪ | H&S manager |  | P | P | Sub-contractor staff and management dependent on the nature of works required
| ▪ | Planner |  | P | P | Sub-contractor staff and management dependent on the nature of works required
| ▪ | Document control |  | P | P | Sub-contractor staff and management dependent on the nature of works required
| ▪ | IT manager |  | P | P | Sub-contractor staff and management dependent on the nature of works required
| ▪ | Project Engineer |  | P | P | Sub-contractor staff and management dependent on the nature of works required
| ▪ | Secretarial staff |  | P | P | Sub-contractor staff and management dependent on the nature of works required
| ▪ | Commissioning manager |  | P | P | Sub-contractor staff and management dependent on the nature of works required
| ▪ | Travel allowances. |  | P | P | Travel to Employer's, Consultants' & Sub-contractors offices/ works in the UK to be included
| ▪ | Other resource required but not listed above to carry out the
|  | works |  | P | P | As required to suit the project requirements for the Contractor and Sub-contractor
Site accommodation
| ▪ | Temporary accommodation for site based staff prior to main
|  | site establishment. |  | P |  | As required to suit the project requirements for the Contractor and Sub-contractor
| ▪ | Employer offices
| ▪ | Contractors offices |  | P |  | As required to suit the project requirements for the Contractor and Sub-contractor
| ▪ | Site conference room |  | P |  | As required to suit the project requirements for the Contractor and Sub-contractor
| ▪ | Security huts |  | P |  | As required to suit the project requirements for the Contractor and Sub-contractor
| ▪ | Welfare facilities |  | P |  | As required to suit the project requirements for the Contractor and Sub-contractor
| ▪ | Drying room |  | P |  | As required to suit the project requirements for the Contractor and Sub-contractor
| ▪ | Canteen |  | P |  | As required to suit the project requirements for the Contractor and Sub-contractor
| ▪ | First Aid hut |  | P |  | As required to suit the project requirements for the Contractor and Sub-contractor
| ▪ | Induction hut |  | P |  | As required to suit the project requirements for the Contractor and Sub-contractor
| ▪ | Site toilets |  | P |  | As required to suit the project requirements for the Contractor and Sub-contractor
| ▪ | Site showers |  | P |  | As required to suit the project requirements for the Contractor and Sub-contractor
| ▪ | Fencing to main site compound |  | P |  | As required to suit the project requirements for the Contractor and Sub-contractor
| ▪ | Hard standing to site compound |  | P |  | As required to suit the project requirements for the Contractor and Sub-contractor
| ▪ | Temporary car parks |  | P
| ▪ | Paved footpaths to site compound |  | P
| ▪ | Hoarding / fencing to site perimeter |  | P | P | As required to suit the project requirements for the Contractor and Sub-contractor
| ▪ | Hoarding licence |  | P |  | As required to suit the project requirements for the Contractor and Sub-contractor
| ▪ | Moving site accommodation during the project
Accommodation Equipment
| ▪ | Canteen kitchen equipment |  | P |  | Contractor to provide to own Staff and Sub-Contractors
| ▪ | Crockery / cutlery |  | P |  | Contractor to provide to own Staff and Sub-Contractors
| ▪ | Furniture etc. |  | P |  | Contractor to provide to own Staff and Sub-Contractors
| ▪ | Boot racks |  | P |  | Contractor to provide to own Staff and Sub-Contractors
Contractor's general cost items.
Computers & special equipment
| ▪ | Project extranet/intranet |  | P
| ▪ | Computers |  | P | P
| ▪ | Printers |  | P | P
| ▪ | TV & video for site inductions |  | P
| ▪ | Software incl user licences |  | P | P
| ▪ | System maintenance & reconfiguration |  | P | P
Services and facilities
Communications
| ▪ | Phone lines, site, canteen, security |  | P |  | Contractor to provide to own Staff and Sub-Contractors
| ▪ | IT line installation. |  | P |  | Contractor to provide to own Staff and Sub-Contractors
| ▪ | IT line subscription. |  | P |  | Contractor to provide to own Staff and Sub-Contractors
| ▪ | Telephone system wiring |  | P |  | Contractor to provide to own Staff and Sub-Contractors
| ▪ | Handsets incl. security huts |  | P | P | Contractor to provide to own Staff and Sub-Contractors
| ▪ | Plain paper fax machine |  | P | P | Contractor to provide to own Staff and Sub-Contractors
| ▪ | Maintenance & adaptation of phone system during project |  | P |  | Contractor to provide to own Staff and Sub-Contractors
| ▪ | Site radios |  | P | P | Contractor to provide to own Staff and Sub-Contractors
| ▪ | Call charges |  | P | P | Contractor to provide to own Staff and Sub-Contractors
Safety
| ▪ | First Aid kit incl. topping up |  | P | P
| ▪ | First Aid @ Work training |  | P | P
| ▪ | Site visitors - hard hats, hi-vis vests, Wellington boots,
|  | gloves, ear defenders etc. |  | P | P
| ▪ | Contractors site staff full PPE sets |  | P | P
| ▪ | Replacement PPE for long term resident site team & visitors. |  | P | P
| ▪ | Health & safety equipment |  | P | P
| ▪ | Induction video / facility |  | P
| ▪ | Temporary barriers / hoardings |  | P
| ▪ | Site safety signage |  | P
| ▪ | Mansafe systems |  | P
| ▪ | Temporary ramps / stairs |  | P
Stationery & Postage
| ▪ | Project archiving |  | P | P
| ▪ | Couriers |  | P | P
| ▪ | Parcel postage |  | P | P
| ▪ | Letter postage |  | P | P
| ▪ | Site stationery |  | P | P
Photocopying
| ▪ | Site copier |  | P
| ▪ | Maintain/ service copiers |  | P
| ▪ | Colour copier |  | P | P
Services and facilities
Reprographics
| ▪ | CAD charges for logistics drawings etc. |  | P
| ▪ | Copy documents for subcontract tenders / contracts |  | P
| ▪ | Colour printing / copying programmes etc. |  | P
| ▪ | Copy S/C's drawings for issue to Design Team / other S/C's |  | P
| ▪ | Copy construction issue drawings / revisions to S/C's |  | P
Site Photography
| ▪ | Regular site progress photos |  | P
| ▪ | Professional photography |  | P
Waste Management & Removal
| ▪ | Waste removal from site accommodation |  | P
| ▪ | Waste removal from canteen |  | P
| ▪ | Skips / general waste removal from site |  | P
| ▪ | On floor bins for waste collection |  | P
Multi-service & Site Logistics Gang
| ▪ | Site catering staff |  | P
| ▪ | Cleaning site welfare, toilets and offices |  | P
| ▪ | Fire points |  | P
| ▪ | Small tools & plant |  | P
| ▪ | Materials off loading / horizontal distribution. |  | P | P
Consumables & sundry items
| ▪ | Noise monitoring equipment |  | P
| ▪ | Vibration monitoring equipment |  | P
| ▪ | S/C credit checks |  | P
| ▪ | Project social functions - Topping out | P | P
| ▪ | Site consumables incl. WC rolls, hand towels, sundry |  | P
cleaning consumables etc.
Final Clean
| ▪ | Phased cleaning |  | P
| ▪ | Pre-snag cleaning |  | P
| ▪ | Final clean |  | P
| ▪ | Deep clean to catering areas |  | P
| ▪ | Special clean to IT areas. |  | P
P
Mechanical plant
Hoisting
| ▪ | Erect and test hoist |  | P
| ▪ | Hoist base - install & remove |  | P
| ▪ | Hoist tower with run off's |  | P
| ▪ | Protect building openings to each hoist |  | P
| ▪ | Hoist hire |  | P
| ▪ | Hoist drivers |  | P
| ▪ | Dismantle hoist |  | P
| ▪ | Forklift excl driver |  | P
| ▪ | Forklift drivers |  | P
Cranage
| ▪ | Tower cranes, driver & banksman |  | P
| ▪ | Mobile cranes |  | P
Wheel wash facility
| ▪ | Wheel wash installation |  | P
| ▪ | Wheel wash maintenance |  | P
| ▪ | Allowance for relocation |  | P
| ▪ | Wheel wash removal |  | P
Temporary works
Temporary Plumbing & Drainage
| ▪ | Temporary foul drainage - site + site accommodation |  | P
| ▪ | Temporary surface water drainage - site + site accom |  | P
| ▪ | Discharge licences |  | P
| ▪ | Temporary water supplies - Potable to accom / welfare |  | P
| ▪ | Temporary water supplies - Non-portable to accommodation
|  | / welfare / the works |  | P
| ▪ | Wheel wash water supply. |  | P
| ▪ | Temporary ground water control. |  | P
Scaffolding / access equipment
| ▪ | External perimeter scaffold |  | P |  | Including alarming and adaptions as necessary to carry out the works
| ▪ | Common user birdcage scaffolds |  | P |  | Including alarming and adaptions as necessary to carry out the works
| ▪ | Perimeter / void handrails |  | P |  | Including alarming and adaptions as necessary to carry out the works
| ▪ | Temporary staircases |  | P |  | Including alarming and adaptions as necessary to carry out the works
| ▪ | Temporary roof's / roof opening protection |  | P |  | Including alarming and adaptions as necessary to carry out the works
| ▪ | Powered access platforms /scissor lifts etc. |  | P | P | Including alarming and adaptions as necessary to carry out the works
| ▪ | Trestles / tower scaffolds etc. |  | P | P | Including alarming and adaptions as necessary to carry out the works
| ▪ | Crash decks |  | P | P | Including alarming and adaptions as necessary to carry out the works
Protection
| ▪ | Protection of the works |  | P
| ▪ | Protection of stored materials |  | P
Temporary works
Temporary Signage
| ▪ | Site quality / environmental signage |  | P
| ▪ | Directional signage to the site |  | P
| ▪ | Site safety signage |  | P
| ▪ | General information signage |  | P
| ▪ | Main site sign board |  | P
Temporary electrics
| ▪ | Temporary HV feed |  | P
| ▪ | Temporary power - site accommodation |  | P
| ▪ | Temporary electrics |  | P
| ▪ | Temporary external lighting |  | P
| ▪ | CCTV installation - see security |  | P
| ▪ | Temporary supplies to building lifts for early use or
|  | commissioning |  | P
| ▪ | Temporary supplies to other items of permanent plant for
|  | early use or commissioning. |  | P
| ▪ | Welding points / 3 phase supplies |  | P
| ▪ | Hoist supplies |  | P
| ▪ | Tower crane supplies |  | P
| ▪ | Tower crane floodlighting |  | P
| ▪ | Temporary site power to the works |  | P
| ▪ | Temporary fire alarm system to the works |  | P
| ▪ | Temporary lighting - safety |  | P
| ▪ | Temporary lighting - task |  |  | P
| ▪ | Lighting to hoardings |  | P
| ▪ | Ongoing maintenance & adaptation |  | P
| ▪ | Testing, commissioning and strip out of temporary electrics |  | P
Statutory supplies
| ▪ | Temporary water & drainage charges |  | P
| ▪ | Temporary electricity consumption charges for site & welfare |  | P
| ▪ | Rates on site set-up |  | P
| ▪ | Water consumption for testing / commissioning |  | P
| ▪ | Electricity consumption for testing / commissioning |  | P
| ▪ | Gas consumption for running up heating / commissioning |  | P
Cleaning
| ▪ | Road cleaning to site & adjacent roads |  | P
Traffic Control
| ▪ | Traffic lights etc. |  | P
| ▪ | Road closures |  | P
| ▪ | Banksmen (as required) |  | P

## Fly2.1
2. PROVISIONAL ITEMS | 2. PROVISIONAL ITEMS | 2.1 - Notes on Cost Plan

## 2.1 Notes on Cost Plan
1ST STAGE TENDER DOCUMENT
New Sports and Community Pavilion, Edmonds Park, Didcot
2. PROVISIONAL ITEMS
2.1 | Notes on Cost Plan
1 | This schedule has been prepared to show the anticipated elemental allocation of expenditure to be
defined in the second stage procurement.
2 | The Contractor is to comment with their Stage 1 tender on the adequacy of the elemental Cost Plan
detailing any areas that they have concerns over.
3 | Prior to commencement of the second stage sub-contract tendering activity the Contractor is to
allocate the elemental costs/ provisional sums to the agreed work packages for reconciliation with
the tender returns.
4 | The Provisional Sums are Defined sums and relate to the scope of the works set out in the
documents. The Contractor is deemed to have made due allowance in programming, planning and
pricing preliminaries, for undertaking all the work required or necessary
5 | The values in this section are deemed to be net sub-contract values. Main Contract allowances for
preliminaries, general attendances, overheads and profits are to be included elsewhere.

## Fly2.2
2. PROVISIONAL ITEMS | 2. PROVISIONAL ITEMS | 2.2 - Cost Plan Summary (Elemental Provisional Sums)

## 2.2 Cost Plan Summary
1ST STAGE TENDER DOCUMENT
New Sports and Community Pavilion, Edmonds Park, Didcot
2. PROVISIONAL ITEMS
2.2 | Elemental Provisional Sums
Ref |  | Description |  | Total
0 | Facilitating works
| 0.1 | Toxic/hazardous material removal | 0
| 0.2 | Major demolition works | 2000
| 0.3 | Specialist Groundworks | 0
| 0.4 | Temporary diversion works | 0
| 0.5 | Extraordinary site investigation works | 0
2000
1 | Substructure
| 1.1 | Foundations | 150800
150800
2 | Superstructure
| 2.1 | Frame | 73900
| 2.2 | Upper floors | 0
| 2.3 | Roof | 168100
| 2.4 | Stairs and ramps | 1800
| 2.5 | External walls | 168700
| 2.6 | Windows and external doors | 38000
| 2.7 | Internal walls and partitions | 58500
| 2.8 | Internal doors | 29800
538800
3 | Internal finishes
| 3.1 | Wall finishes | 39600
| 3.2 | Floor finishes | 26600
| 3.3 | Ceiling finishes | 50700
116900
4 | Fittings, furnishings and equipment
| 4.1 | General fittings, furnishings and equipment | 22600
22600
5 | Services
| 5.1 | Sanitary Installations | 41500
| 5.2 | Mechanical Installations | 102700
| 5.8 | Electrical installations | 180100
| 5.14 | BWIC | 16200
340500
6 | Complete buildings and building units |  | 0 | 0
7 | Work to existing buildings |  | 0 | 0
8 | External works
| 8.1 | Site preparation works | 6500
| 8.2 | Roads, paths and paving | 142500
| 8.3 | Planting | 19400
| 8.4 | Fencing, railings and walls | 6600
| 8.5 | Site/street furniture and equipment | 32100
| 8.6 | External drainage | 47900
| 8.7 | External services | 21000
| 8.8 | Minor building works and ancillary buildings | 0
276000
| Total: Facilitating works and Building Works |  |  | 1447600
Note: Values rounded to the nearest hundred

## Fly2.3
2. PROVISIONAL ITEMS | 2. PROVISIONAL ITEMS | 2.3 - Dayworks

## 2.3 dayworks
1ST STAGE TENDER DOCUMENT
New Sports and Community Pavilion, Edmonds Park, Didcot
2. PROVISIONAL ITEMS
2.3 | Dayworks
REF | DESCRIPTION | [5 empty] | £
2.3.1 | Authorised Overtime/All-in Labour Constants
2.3.1.1 | Works carried out, outside of normal working hours
For prime cost incurred at any time during the Contract. Any such
extra cost will be calculated using Rates of Basic Pay, Additional
Payments, for use with the Working Rule Agreement for the
Construction Industry, published by the Construction Industry Joint
Council, current when the work is carried out, together with additional
payments for continuous extra skill or responsibility or intermittent
responsibility, as appropriate.
Provisional Sum: Allow for the following amount of resources, all in rates
|  | by a Labourer: | 50 | hours @ £ |  | /hr Item | 0
|  | by a Craftsman: | 50 | hours @ £ |  | /hr Item | 0
Add for percentage addition to cover the cost of the non productive
element only of overtime, incidental costs, overheads and profit,
|  | at time and a half |  |  |  | % | 0
|  | at double time |  |  |  | % | 0
Insert rates/percentages in highlighted yellow cells
[6 empty] | To Collection £ | 0
2.3.2 | DAYWORKS (A55)
General Notes
• | If in the opinion of the CA any work cannot be properly valued from the Pricing
Document, instructions shall be confirmed in writing that the works to be carried out
on a dayworks account basis.
• | The Contractor is to insert rates in the following schedule of dayworks and these
rates shall be extended into the cash column, totalled and carried to the Main
Summary.
• | The rates shall be "all-inclusive" and shall allow for all fluctuations in labour rates,
insurances and expenses in connection with labour including allowing for the use of
hand tools and maintenance of same, superintendence, travelling time and fares,
profit, overheads, protection, incidental costs and the like.
Labour
2.3.2.1 | Labourer or mate |  | 50 | hrs |  | /hr Item | 0
2.3.2.2 | Groundworker |  | 30 | hrs |  | /hr Item | 0
2.3.2.3 | Piling operative |  | 30 | hrs |  | /hr Item | 0
2.3.2.4 | Banksman |  | 30 | hrs |  | /hr Item | 0
2.3.2.5 | Scaffolder |  | 30 | hrs |  | /hr Item | 0
2.3.2.6 | Concretor |  | 30 | hrs |  | /hr Item | 0
2.3.2.7 | Reinforcement fixer |  | 30 | hrs |  | /hr Item | 0
2.3.2.8 | Bricklayer |  | 30 | hrs |  | /hr Item | 0
2.3.2.9 | Stonemason |  | 30 | hrs |  | /hr Item | 0
2.3.2.10 | Renderer |  | 30 | hrs |  | /hr Item | 0
2.3.2.11 | Metal roofing and metal cladding fixer |  | 30 | hrs |  | /hr Item | 0
2.3.2.12 | Sheet membrane roofing layer |  | 30 | hrs |  | /hr Item | 0
2.3.2.13 | Carpenter |  | 30 | hrs |  | /hr Item | 0
[6 empty] | To Collection £ | 0
2.3.2 | DAYWORKS (A55)
Labour (cont)
2.3.2.14 | Joiner |  | 30 | hrs |  | /hr Item | 0
2.3.2.15 | Structural steelworker |  | 30 | hrs |  | /hr Item | 0
2.3.2.16 | Metalworker |  | 30 | hrs |  | /hr Item | 0
2.3.2.17 | Plasterer |  | 30 | hrs |  | /hr Item | 0
2.3.2.18 | Carpet layer |  | 30 | hrs |  | /hr Item | 0
2.3.2.19 | Floor layer |  | 30 | hrs |  | /hr Item | 0
2.3.2.20 | Tiler |  | 30 | hrs |  | /hr Item | 0
2.3.2.21 | Glazier |  | 30 | hrs |  | /hr Item | 0
2.3.2.22 | Glazed curtain walling operative |  | 30 | hrs |  | /hr Item | 0
2.3.2.23 | Framed ceiling installer |  | 30 | hrs |  | /hr Item | 0
2.3.2.24 | Mastic sealant operative |  | 30 | hrs |  | /hr Item | 0
2.3.2.25 | Painter |  | 30 | hrs |  | /hr Item | 0
2.3.2.26 | Competent Electrician |  | 30 | hrs |  | /hr Item | 0
2.3.2.27 | Electrician's mate |  | 30 | hrs |  | /hr Item | 0
2.3.2.28 | Registered plumber |  | 30 | hrs |  | /hr Item | 0
2.3.2.29 | Plumber's mate |  | 30 | hrs |  | /hr Item | 0
2.3.2.30 | Registered heating and ventillating engineer |  | 30 | hrs |  | /hr Item | 0
2.3.2.31 | Heating and venilating engineer's mate |  | 30 | hrs |  | /hr Item | 0
[6 empty] | To Collection £ | 0
2.3.3 | Materials & Goods
2.3.3.1 | Provide for the prime cost of materials and goods |  |  |  |  | item | 2000
2.3.3.2 | Add the percentage addition for incidental costs,
| overheads and profit |  |  |  | % |  | 0
Plant
2.3.3.3 | Provide for the prime cost of plant hired by the Contractor |  |  |  |  | item | 2000
2.3.3.4 | Add the percentage addition for incidental costs,
| overheads and profit |  |  |  | % |  | 0
[6 empty] | To Collection £ | 4000
Collection
|  | 2.3/1 |  |  |  |  | 0
|  | 2.3/2 |  |  |  |  | 0
|  | 2.3/3 |  |  |  |  | 0
|  | 2.3/4 |  |  |  |  | 4000
[6 empty] | Total to main summary £ | 4000
1

## Fly3.1
3. CONTRACT SUM ANALYSIS/WORK PACKAGES | 3.1 - Element/Package Prices

## 3.1 CSA-Work Packages
1ST STAGE TENDER DOCUMENT
New Sports and Community Pavilion, Edmonds Park, Didcot
3. CONTRACT SUM ANALYSIS/WORK PACKAGES
3.1 | Element/ Package Prices
Ref. | Description |  |  | Total
General Notes
• | This Contract Sum Analysis is to be completed during the second
stage tender and shall be amended by the Contractor to show the
agreed packages of work.
• | The values in this section are deemed to be net sub-contract values.
| Main Contract allowances for preliminaries, general attendances, |  |  |  | • | Balustrades
| overheads and profits are to be included elsewhere. |  |  |  | • | Stairs
Work packages are to include but are not limited to:
| • | Site clearance and alteration worrks
| • | Groundworks
| • | Insitu concrete
| • | Precast/ composite concrete
| • | Masonry external walls
| • | Structural steel
| • | Structural timber
| • | Fire protection
| • | Carpentry
| • | Composite slate roof coverings
| • | Composite slate wall coverings
| • | Canopies and covered terraces
| • | Waterproofing
| • | Proprietary linings and partitions
| • | Joinery
| • | Rooflights - aluminium
| • | Windows - aluminium
| • | External doors and louvres - aluminium
| • | Internal glazing
| • | Floor finishes (screeds, sheeting, tiles)
| • | Wall finishes (plaster, decoration, tiles, acoustic panels, sheeting)
| • | Ceiling finishes (suspended grid, plasterboard, decoration)
| • | Furniture, fittings and equipment
| • | Safety systems/ mansafe
| • | Signage
| • | Above ground drainage
| • | Below ground drainage (under building footprint)
| • | Sanitary installations
| • | Mechanical installations
| • | Rainwater harvesting
| • | Electrical installations
| • | Photovoltaic panels
| • | Specialist installations
| • | Communication, security and control systems
| • | Utility supplies
| • | Builder's work in connection with services
| • | Sustainable solutions/ renewables
| • | Roads, paths and paving
| • | Planting
| • | Fencing, railings and walls
| • | Site/street furniture and equipment
| • | External drainage
| • | External services
| • | Minor building works and ancillary buildings
|  |  | Total to main summary £ | 0

## Fly4
4. MAIN SUMMARY | 4. MAIN SUMMARY

## 4. Main Summary
1ST STAGE TENDER DOCUMENT
New Sports and Community Pavilion, Edmonds Park, Didcot
4. MAIN SUMMARY
Ref. | Description |  |  | £
1 | PRELIMINARIES/GENERAL CONDITIONS
1.1 - Introduction
1.2 - Preliminaries
|  | 1.3 - Preliminaries Pricing Schedules |  | 0
1.4 - Responsibility Matrix
2 | PROVISIONAL ITEMS
2.1 - Notes on Cost Plan
|  | 2.2 - Cost Plan Summary |  | 1447600
|  | 2.3 - Dayworks |  | 4000
3 | CONTRACT SUM ANALYSIS
|  | 3.1 - Element/ Package tenders |  | Nil
3 | MAIN CONTRACTOR OVERHEADS AND PROFIT
Add a percentage to cover all Main Contractor overheads and profits based on the
| value of this tender Submission. The percentage is to allow for all adjustments to the |  |  |  | % Addition | Element Code | Total (exc. Section 2)
net value of work (including Main Contractor Discount). No other adjustments shall
apply.
|  |  | % |  |  | 10.1 | 1451600
Contractor :
Address :
Date :
|  |  | Total Tender £ | 1451600

## Fly5
5. FORM OF TENDER | 5. FORM OF TENDER

## 5. Form of Tender
1ST STAGE TENDER DOCUMENT
New Sports and Community Pavilion, Edmonds Park, Didcot
5. FORM OF TENDER
Tender for: |  | New Sports and Community Pavilion, Edmonds Park, Didcot
To: |  | Ridge and Partners LLP
The Cowyards
Blenheim Park
Oxford Road
Woodstock
OX20 1QR
From: |  | …………………………………………….
…………………………………………….
…………………………………………….
…………………………………………….
We have examined the following documents:
• Drawings listed in the Invitation to Tender;
• The JCT Form and other Conditions of Contract specified in the Pricing Document;
• Pre-Construction Information
Option A - period as stipulated by tender documents
We offer to carry out the whole of the Works described in accordance with the documents referred to
above;
for the sum of |  |  | £ …………………………………………………………………………………….... (in words)
£ ……………………………………………..… (in figures) exclusive of any VAT chargeable
within | 34 | weeks from acceptance of our second stage tender, comprising a period of:
• | 4 | weeks from acceptance to the Date of Possession and
• | 30 | weeks from the Date of Possession to the Date for Completion.
Option B - period to be stipulated by contractor
We offer to carry out the whole of the Works described in accordance with the documents referred to
above;
for the sum of |  |  | £ …………………………………………………………………………………….... (in words)
£ ……………………………………………..… (in figures) exclusive of any VAT chargeable
within | 0 | weeks from acceptance of our second stage tender, comprising a period of:
• |  | weeks from acceptance to the Date of Possession and
• |  | weeks from the Date of Possession to the Date for Completion.
For the purposes of the contract, pre-construction agreement, warranties and guarantee requirements
mentioned in the Pricing Document, We have reviewed the contents of the Pricing Document and accept,
without amendment, the wording set out in the appendices.
We enclose our fully priced document in the separate envelope provided and marked with our name.
We agree that if any obvious errors in pricing or errors in arithmetic are discovered in the priced
document[s] before acceptance of this offer, they shall be dealt with in accordance with the Alternative 2
procedure set out in JCT Practice Note 6 - Main Contract Tendering.
We undertake in the event of your acceptance to execute with you a formal contract embodying all the
conditions and terms contained in this offer within 21 days of being required to do so by the Employer.
This tender remains open for acceptance for 56 days from the latest date fixed for the submission of
the second stage tenders.
We confirm that this tender is submitted at our expense and agree that the Employer need not necessarily
accept the lowest or any other tender.
Certificate of Bona Fide Tender
The essence of selective tendering is that the client shall receive bona fide competitive tenders from all
those tendering. In recognition of the principle, I certify that this is a bona fide tender, intended to be
competitive, and that we have not fixed or adjusted the amount of the tender by or under or in accordance
with any agreement or arrangement with any other person. I also certify that we have not done and we
undertake that will not do at any time before the hour and date specified for return of this tender any of the
following acts:-
a. | Communication to a person other than the person calling for those tenders the amount or
approximate amount of the proposed tender, except where the disclosure, in confidence, of the
approximate amount of the tender was necessary to obtain insurance premium quotations required
for the preparation of the tender.
b. | entering into any agreement or arrangement with any other person that he shall refrain from
tendering or as to the amount of any tender to be submitted.
c. | offering or paying or giving or agreeing to pay or give any sum of money or valuable consideration
directly or indirectly to any person for doing or having done or causing or having caused to be done
in relation to any other tender or proposed tender for the said work any act or thing or sort
described above.
In this certificate the word "person" includes any person any body or association, corporate or
unincorporate and "any agreement or arrangement" includes any such transaction, formal or informal, and
whether legally binding or not.
Signed by or on
behalf of : |  |  | …………………………………………………………………………………….
Signature : |  |  | …………………………………………………………………………………….
duly authorised to sign
Position : |  |  | …………………………………………………………………………………….
Date : |  |  | ………………………………………….. 2022
Note: The completed form of tender together with the information requested must be
received by Ridge at the above address no later than 12:00 hours on the date set out in the
tender invitation.

## FlyA
A. DOCUMENT REGISTER | A. DOCUMENT REGISTER

## A. Register
1ST STAGE TENDER DOCUMENT
New Sports and Community Pavilion, Edmonds Park, Didcot
A. DOCUMENT REGISTER
REF | DESCRIPTION |  |  |  |  | REVISION
Consultant Name : |  |  | RIDGE | Project Ref : | 5018614
Documents:
PD |  | Pricing Document
PCI |  | Pre-Construction Information Pack
5018614-001 |  | Site Logistic Plan
RDS |  | RDG-XX-XX-XX-A-9080 - Room Data Sheets - for information only
Consultant Name : |  |  | RPA ARCHITECTS | Project Ref : | 2186
Drawings :
A-001 |  | Block and location plan |  |  |  | -
A-002 |  | Existing Site Plan |  |  |  | -
A-003 |  | Proposed site plan |  |  |  | A
A-100 |  | Proposed changing and community building plan |  |  |  | A
A-200 |  | Proposed elevations |  |  |  | -
A-201 |  | Proposed elevations |  |  |  | -
A-202 |  | Proposed street elevations |  |  |  | -
Other Documents:
|  | Planning application form |  |  |  | 2021-06-04
|  | Design, access and planning statement - May 2021 |  |  |  | -
|  | Visualisation proposals |  |  |  | -
Consultant Name : |  |  | The Landscape Studio | Project Ref : | Edmonds Park
Drawings :
TLS.1 |  | Landscape layout plan |  |  |  | A
TLS.2 |  | Planting plan |  |  |  | -
Other Documents:
|  | Landscape statement |  |  |  | 2021-03-22
Consultant Name : |  |  | Sylva Consultancy | Project Ref : | 21046
Other Documents:
|  | Arboricultural Report - March 2021 |  |  |  | 2021-03-05
Consultant Name : |  |  | STM Environmental | Project Ref : | PH1-2021-000083
Other Documents:
|  | Contaminated land risk assessment - Phase 1 Desk Study Report |  |  |  | 1
Consultant Name : |  |  | Other Documents | Project Ref : | n/a
Other Documents:
|  | Site waste management plan |  |  |  | June 2021
|  | Transport assessment |  |  |  | June 2021
|  | Geosynthetics Cellweb TRP Technical Support Package |  |  |  | -
|  | Configuration of football pitches - Edmonds Park |  |  |  | -
|  | Letter to Sport England and SODC re Edmonds Park community pavilion |  |  |  | 2021-08-02
|  | Thames Water Asset location search - ALS/ALS Standard/2021_4511529 |  |  |  | 2021-09-27
|  | County Series Map - Groundsure Insights |  |  |  | 2021-07-30
Consultant Name : |  |  | South Oxfordshire District Council | Project Ref : | P21/S2646/FUL
Other Documents:
|  | Planning Decision Notice |  |  |  | 2021-10-22
|  | Delegated Report |  |  |  | -
Consultant Name : |  |  | Blewburton Ltd | Project Ref : | n/a
Other Documents:
|  | BREEAM New Construction 2018 Evidence Tracker |  |  |  | V1 | Check if further update will be issued by the 10th June?
Consultant Name : |  |  | Survey Solutions | Project Ref :
Other Documents:
42308NGLS-01 Topographical Survey
|  | 42308NGUG-01 Utilities and Drainage Survey |  |  |  | -
BELOW SUBJECT TO BEING ISSUED
Consultant Name : |  |  | Forge Engineering | Project Ref :
Other Documents:
Flood risk assessment including SUDS design
Consultant Name : |  |  | GIS | Project Ref :
Other Documents:
Ground Investigation Survey
Consultant Name : |  |  | AAE-Ltd | Project Ref :
Other Documents:
Ecology Survey
RDS |  | RDG-XX-XX-XX-A-9080 - Room Data Sheets |  |  |  | - |  | 5018614-RDG-XX-XX-XX-A-9080 -
Consultant Name : |  |  | DTA Transport | Project Ref :
Other Documents:
Transport Survey
Consultant Name : |  |  | MK Surveys | Project Ref :
Drawings :
-

## FlyB
B. CONTRACT CONDITIONS | B. CONTRACT CONDITIONS

## B.1 Contract
1ST STAGE TENDER DOCUMENT
New Sports and Community Pavilion, Edmonds Park, Didcot
B. CONTRACT CONDITIONS
Document Ref | Description |  | Revision
CONTRACT CONDITIONS
Documents:
B.1 |  | JCT Design and Build Contract 2016 - separate document | DRAFT

## B. 2 Contract Amendments
1ST STAGE TENDER DOCUMENT
New Sports and Community Pavilion, Edmonds Park, Didcot
B. CONTRACT CONDITIONS
Document Ref | Description |  |  | Revision
CONTRACT CONDITIONS
Documents:
B.2 |  | Specific Schedule of Amendments
SCHEDULE OF AMENDMENTS TO JCT DESIGN AND BUILD CONTRACT
2016 EDITION
|  | 1. | Contract Particulars
Clause 4.9 Interim and final Payments - final date and amount
Amend clause 4.9.1 as following;
Change '14 days' to '30 days'

## FlyC
C. WARRANTIES, BONDS AND GUARANTEES

## C. Warranties
1ST STAGE TENDER DOCUMENT
New Sports and Community Pavilion, Edmonds Park, Didcot
C. WARRANTIES, BONDS AND GUARANTEES
Document Ref | Description |  |  | Revision
WARRANTIES, BONDS AND GUARANTEES
Documents:
C.1 |  | Collateral Warranties/ Third Party Rights |  | Draft
|  | ▪ | SCWa/E - Sub-Contractor Collateral Warranty for Employer 2016 - Separate document
refer to preliminaries clause A30/320 for details of sub-contractors required to
provide warranties and level/type of PI insurance required.
|  | ▪ | CWa/F - Contractor Collateral Warranty for Funder 2016 - Separate document
|  | ▪ | CWa/P&T - Contractor Collateral Warranty for Purchaser or Tenant 2016.
|  | ▪ | SCwa/F - Sub- Contractor Collateral Warranty for Funder 2016 - Separate document
Comments- as for SCWa/E for sub-contractors to provide this type of warranty
|  | ▪ | SCwa/P&T- Sub- Contractor Collateral Warranty for Purchaser or Tenant
2016 - comments as for SCWa/E for sub-contractors to provide this type of
warranty
|  | ▪ | Designers Collateral Warranty for Employer - Refer ro A30/315
C.2 |  | Performance Bond

## FlyC.1
C.1 Collateral Warranties/ Third Party Rights

## FlyC.2
C.2 Performance Bond

## FlyD
D. PRE CONSTRUCTION SERVICES AGREEMENT (PCSA)

## D. PCSA
1ST STAGE TENDER DOCUMENT
New Sports and Community Pavilion, Edmonds Park, Didcot
D. PRE CONSTRUCTION INFORMATION
Document Ref | Description |  | Revision
PRE CONSTRUCTION SERVICES AGREEMENT (PCSA)
Documents:
D.1 |  | PCSA Pricing Schedule
D.2 |  | PCSA Form of Tender
D.3 |  | PCSA Contract Particulars - Separate Document | Draft

## FlyD.1
D. PRE CONSTRUCTION SERVICES AGREEMENT (PCSA) | D.1 PCSA Pricing Schedule

## D1 PCSA Pricing Sched
1ST STAGE TENDER DOCUMENT | [5 empty] | Data Entry
New Sports and Community Pavilion, Edmonds Park, Didcot
D. PRE CONSTRUCTION INFORMATION
D/1 | PCSA Pricing Schedule |  |  |  |  | Fixed Related |  |  | Time Related
Ref. | Description |  |  | F £ | TR £ | Start | Stage | End
1 | Main Contractor's Cost Items
• | Not withstanding the conditions set out in the ‘National Building
Specification’ guidelines and the ‘Standard Method of
Measurement’ 7th Edition. The Contractor’s general cost items are
to be priced in accordance with the ‘RICS New Rules of
Measurement’ volume 2, 1st edition, (RICS:NRM-2 v1)
• | Costs relating to preliminaries items that are not specifically
identified in the contractor’s full and detailed breakdown shall be
deemed to have no cost implications or have been included
elsewhere within the contractor’s rates and prices.
1.1 | Employer's requirements
1.1.1 | Site accommodation
| 1 | Site accommodation |  | 0 | 0
| 2 | Temporary works in connection with site establishment |  | 0 | 0
| 3 | Furniture and equipment |  | 0 | 0
| 4 | IT systems |  | 0 | 0
| 5 | Consumables & services |  | 0 | 0
| 6 | Brought-in services |  | 0 | 0
| 7 | Sundries |  | 0 | 0
1.1.2 | Site records
| 1 | Operation and maintenance manuals. |  | 0 | 0
| 2 | Compilation of health and safety file. |  | 0 | 0
|  |  | To Collection £ | 0 | 0
1.2 | Main Contractor's Cost Items
1.2.1 | Management & Staff
1.2.1.1 | Project Specific Management & Staff:
| 1 | Project manager/director |  | 0 | 0
| 2 | Construction manager/Supervisors |  | 0 | 0
| 3 | Health & Safety manager/officer |  | 0 | 0
| 4 | Commissioning manager (building engineering services) |  | 0 | 0
| 5 | Planning/programming manager and staff. |  | 0 | 0
| 6 | Senior/managing quantity surveyor. |  | 0 | 0
| 7 | Project/package quantity surveyors. |  | 0 | 0
| 8 | Administrative staff |  | 0 | 0
| 9 | Other management and staff. |  | 0 | 0
1.2.1.2 | Visiting Management & Staff
| 1 | Managing/regional directors & the like |  | 0 | 0
| 2 | Quality manager |  | 0 | 0
| 3 | Contracts/commercial manager |  | 0 | 0
| 4 | Health & Safety Manager/Officer |  | 0 | 0
| 5 | Other visiting management & staff |  | 0 | 0
1.2.1.3 | Extraordinary Support Costs
| 1 | Other extraordinary support costs |  | 0 | 0
| 2 | Day transport |  | 0 | 0
| 3 | Personnel transport |  | 0 | 0
| 4 | Temporary living accommodation |  | 0 | 0
| 5 | Subsistence payments |  | 0 | 0
| 6 | Out of Hours working |  | 0 | 0
1.2.2 | Site establishment
1.2.2.1 | Site facilities
| 1 | Site accommodation |  | 0 | 0
| 2 | Temporary works in connection with site establishment |  | 0 | 0
| 3 | Furniture and equipment |  | 0 | 0
| 4 | IT systems |  | 0 | 0
| 5 | Consumables & services |  | 0 | 0
| 6 | Brought-in services |  | 0 | 0
| 7 | Sundries |  | 0 | 0
|  |  | To Collection £ | 0 | 0
1.2.3 | Temporary services
1.2.3.1 | Site facilities
| 1 | Temporary water supply |  | 0 | 0
| 2 | Temporary gas supply |  | 0 | 0
| 3 | Temporary electricity supply |  | 0 | 0
| 4 | Temporary telecommunication systems |  | 0 | 0
| 5 | Temporary drainage |  | 0 | 0
1.2.4 | Security
1.2.4.1 | Site facilities
| 1 | Security staff |  | 0 | 0
| 2 | Security equipment |  | 0 | 0
| 3 | Hoardings, fences and gates |  | 0 | 0
1.2 | Main Contractor's Cost Items
1.2.5 | Safety and environmental protection
1.2.5.1 | Site facilities
| 1 | Safety programme |  | 0 | 0
| 2 | Barriers & safety scaffolding |  | 0 | 0
| 3 | Environmental protection measures |  | 0 | 0
1.2.6 | Control and protection
1.2.6.1 | Site facilities
| 1 | Survey, inspections & monitoring |  | 0 | 0
| 2 | Setting out |  | 0 | 0
| 3 | Protection of works |  | 0 | 0
| 4 | Samples |  | 0 | 0
| 5 | Environmental control of building |  | 0 | 0
|  |  | To Collection £ | 0 | 0
1.2.7 | Mechanical plant
1.2.7.1 | Site facilities
| 1 | Generally |  | 0 | 0
| 2 | Tower cranes |  | 0 | 0
| 3 | Mobile cranes |  | 0 | 0
| 4 | Hoists |  | 0 | 0
| 5 | Access plant |  | 0 | 0
| 6 | Concrete plant |  | 0 | 0
| 7 | Other plant |  | 0 | 0
1.2.8 | Temporary works
1.2.8.1 | Site facilities
| 1 | Access scaffolding |  | 0 | 0
| 2 | Temporary works |  | 0 | 0
1.2.9 | Site records
1.2.9.1 | Site records
| 1 | Photography |  | 0 | 0
| 2 | Works records |  | 0 | 0
1.2.10 | Completion and post-completion requirements
1.2.10.1 | Requirements
| 1 | Testing and commissioning plan |  | 0 | 0
| 2 | Handover |  | 0 | 0
| 3 | Post-completion services |  | 0 | 0
1.2.11 | Cleaning
1.2.11.1 | Requirements
| 1 | Site tidy |  | 0 | 0
| 2 | Maintenance of roads, paths and pavings |  | 0 | 0
| 3 | Building clean |  | 0 | 0
|  |  | To Collection £ | 0 | 0
1.2.12 | Fees and charges
1.2.12.1 | Fees & Charges
| 1 | Rates on temporary accommodation. |  | 0 | 0
| 2 | Licences in connection with hoardings, scaffolding,
|  | gantries & the like. |  | 0 | 0
1.2.13 | Site services
1.2.13.1 | Temporary works
| 1 | Temporary works that are not specific to an element. |  | 0 | 0
1.2.13.2 | Multi-service gang
| 1 | Ganger |  | 0 | 0
| 2 | Labour |  | 0 | 0
| 3 | Fork lift driver. |  | 0 | 0
| 4 | Service gang plant and transport. |  | 0 | 0
1.2.14 | Insurance, bonds, guarantees and warranties
1.2.14.1 | Works insurance
| 1 | Contractor’s ‘all risks’ (CAR) insurance. |  | 0 | 0
| 2 | Contractor’s plant and equipment insurance. |  | 0 | 0
| 3 | Temporary buildings insurance. |  | 0 | 0
| 4 | Terrorism insurance. |  | 0 | 0
| 5 | Other insurances in connection with the works. |  | 0 | 0
1.2.14.2 | Public liability insurance
| 1 | Non-negligence insurance. |  | 0 | 0
| 2 | Professional indemnity insurance. |  | 0 | 0
1.2.14.3 | Employer’s (main contractor’s) liability insurance
| 1 | Management and staff, including administrative staff. |  | 0 | 0
| 2 | Works operatives. |  | 0 | 0
|  |  | To Collection £ | 0 | 0
1.2.14.4 | Other insurances
| 1 | Employer’s loss of liquidated damages. |  | 0 | 0
| 2 | Latent defects cover. |  | 0 | 0
| 3 | Motor vehicles. |  | 0 | 0
| 4 | Other insurances. |  | 0 | 0
| 5 | Insurance premium tax (IPT). |  | 0 | 0
| 6 | Allowance for recovery of all or part of premium excess. |  | 0 | 0
1.2.14.5 | Bonds
| 1 | Tender bonds (if applicable). |  | 0 | 0
| 2 | Performance bonds. |  | 0 | 0
1.2.14.6 | Guarantees
| 1 | Parent company guarantees. |  | 0 | 0
| 2 | Product guarantees, insurance backed guarantees. |  | 0 | 0
1.2.14.7 | Warranties
| 1 | Collateral warranties. |  | 0 | 0
| 2 | Funder’s warranties. |  | 0 | 0
| 3 | Purchaser’s and tenant’s warranties. |  | 0 | 0
| 4 | Other warranties. |  | 0 | 0
1.2.14.8 | Design Fees
| 1 | Architectural |  | 0 | 0
| 2 | Structural |  | 0 | 0
| 3 | Civil Engineering |  | 0 | 0
| 4 | MEP Engineer |  | 0 | 0
| 5 | Landscaping Architect |  | 0 | 0
| 6 | Fire Consultant |  | 0 | 0
| 7 | Acoustic Consultant |  | 0 | 0
| 8 | BREEAM Advisor |  | 0 | 0
| 9 | Principal Designer |  | 0 | 0
| 10 | Ecologist |  | 0 | 0
| 11 | Temporary Works Designer |  | 0 | 0
| 12 | Technical support / clash detection |  | 0 | 0
| 13 | Other Fees and charges |  | 0 | 0
|  |  | To Collection £ | 0 | 0
Collection
|  | 1.4/1 |  | 0 | 0
|  | 1.4/2 |  | 0 | 0
|  | 1.4/3 |  | 0 | 0
|  | 1.4/4 |  | 0 | 0
|  | 1.4/5 |  | 0 | 0
|  |  | £ | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | £ | 0 |  |  | 0
|  |  |  | Total to main summary £ | 0 |  | Check totals?: | P | P
Instruction:
Insert figures in the ORANGE sections of the sheet

## D1 PCSA Pricing Sched PR
1ST STAGE TENDER DOCUMENT | [6 empty] | Data Entry
New Sports and Community Pavilion, Edmonds Park, Didcot
D. PRE CONSTRUCTION INFORMATION
D/2 | PCSA Contractor's Project Staff Rates | [5 empty] | Fixed Related
REF | ROLE |  | QTY | UNIT | RATE £ | TOTAL £ | £/hr | Element Code
D/2.1 | CONTRACTOR'S PROJECT STAFF RATES
Please enter rates for the following Contractor Project Staff for inclusion in Annex A
of the Pre-Construction Agreement
D/2.1.1 | Management & Staff:
| 1 | Project Director | 8 | hrs | 0 | 0 | 0 |  | Management & Staff: Project Director | 0
| 2 | Senior Project Manager | 8 | hrs | 0 | 0 | 0 |  | Management & Staff: Senior Project Manager | 0
| 3 | Project Manager | 8 | hrs | 0 | 0 | 0 |  | Management & Staff: Project Manager | 0
| 4 | Assistant Project Manager | 8 | hrs | 0 | 0 | 0 |  | Management & Staff: Assistant Project Manager | 0
| 5 | Senior Commercial Manager | 8 | hrs | 0 | 0 | 0 |  | Management & Staff: Senior Commercial Manager | 0
| 6 | Commercial Manager | 8 | hrs | 0 | 0 | 0 |  | Management & Staff: Commercial Manager | 0
| 7 | Procurement Manager | 8 | hrs | 0 | 0 | 0 |  | Management & Staff: Procurement Manager | 0
| 8 | Senior Quantity Surveyor | 8 | hrs | 0 | 0 | 0 |  | Management & Staff: Senior Quantity Surveyor | 0
| 9 | Quantity Surveyor | 8 | hrs | 0 | 0 | 0 |  | Management & Staff: Quantity Surveyor | 0
| 10 | Assistant / Technician Quantity Surveyor | 8 | hrs | 0 | 0 | 0 |  | Management & Staff: Assistant / Technician Quantity Surveyor | 0
| 11 | Trainee Quantity Surveyor | 8 | hrs | 0 | 0 | 0 |  | Management & Staff: Trainee Quantity Surveyor | 0
| 12 | Cost Clerk | 8 | hrs | 0 | 0 | 0 |  | Management & Staff: Cost Clerk | 0
| 13 | Senior M&E Manager | 8 | hrs | 0 | 0 | 0 |  | Management & Staff: Senior M&E Manager | 0
| 14 | Security Systems Manager | 8 | hrs | 0 | 0 | 0 |  | Management & Staff: Security Systems Manager | 0
| 15 | Logistics Manager | 8 | hrs | 0 | 0 | 0 |  | Management & Staff: Logistics Manager | 0
| 16 | Construction Director | 8 | hrs | 0 | 0 | 0 |  | Management & Staff: Construction Director | 0
| 17 | Senior Construction Manager | 8 | hrs | 0 | 0 | 0 |  | Management & Staff: Senior Construction Manager | 0
| 18 | Construction Manager | 8 | hrs | 0 | 0 | 0 |  | Management & Staff: Construction Manager | 0
| 19 | Assistant Construction Manager | 8 | hrs | 0 | 0 | 0 |  | Management & Staff: Assistant Construction Manager | 0
| 20 | Design Manager | 8 | hrs | 0 | 0 | 0 |  | Management & Staff: Design Manager | 0
| 21 | BIM Manager | 8 | hrs | 0 | 0 | 0 |  | Management & Staff: BIM Manager | 0
| 22 | Planning Manager | 8 | hrs | 0 | 0 | 0 |  | Management & Staff: Planning Manager | 0
| 23 | Senior Planner/Project Controller | 8 | hrs | 0 | 0 | 0 |  | Management & Staff: Senior Planner/Project Controller | 0
| 24 | Planner/Project Controller | 8 | hrs | 0 | 0 | 0 |  | Management & Staff: Planner/Project Controller | 0
| 25 | Assistant / Trainee Planner/Project Controller | 8 | hrs | 0 | 0 | 0 |  | Management & Staff: Assistant / Trainee Planner/Project Controller | 0
| 26 | Principal Designer | 8 | hrs | 0 | 0 | 0 |  | Management & Staff: Principal Designer | 0
| 27 | H&S Manager | 8 | hrs | 0 | 0 | 0 |  | Management & Staff: H&S Manager | 0
| 28 | Training Manager | 8 | hrs | 0 | 0 | 0 |  | Management & Staff: Training Manager | 0
| 29 | Quality Management Systems Manager | 8 | hrs | 0 | 0 | 0 |  | Management & Staff: Quality Management Systems Manager | 0
| 30 | Office Manager | 8 | hrs | 0 | 0 | 0 |  | Management & Staff: Office Manager | 0
| 31 | Document Controller | 8 | hrs | 0 | 0 | 0 |  | Management & Staff: Document Controller | 0
| 32 | Reception/Admin support | 8 | hrs | 0 | 0 | 0 |  | Management & Staff: Reception/Admin support | 0
|  | 1.2/1 |  |  | To Collection £ | 0
2.1.1.2 | Design
Architect:
| 1 | Senior | 8 | hrs | 0 | 0 | 0 |  | Design - Architect: Senior | 0
| 2 | Qualified | 8 | hrs | 0 | 0 | 0 |  | Design - Architect: Qualified | 0
| 3 | Assistant/Technician | 8 | hrs | 0 | 0 | 0 |  | Design - Architect: Assistant/Technician | 0
| 4 | Trainee | 8 | hrs | 0 | 0 | 0 |  | Design - Architect: Trainee | 0
Civil / Structural Engineer:
| 5 | Senior | 8 | hrs | 0 | 0 | 0 |  | Design - Civil / Structural Engineer: Senior | 0
| 6 | Qualified | 8 | hrs | 0 | 0 | 0 |  | Design - Civil / Structural Engineer: Qualified | 0
| 7 | Assistant/Technician | 8 | hrs | 0 | 0 | 0 |  | Design - Civil / Structural Engineer: Assistant/Technician | 0
| 8 | Trainee | 8 | hrs | 0 | 0 | 0 |  | Design - Civil / Structural Engineer: Trainee | 0
Mechanical Engineer:
| 9 | Senior | 8 | hrs | 0 | 0 | 0 |  | Design - Mechanical Engineer: Senior | 0
| 10 | Qualified | 8 | hrs | 0 | 0 | 0 |  | Design - Mechanical Engineer: Qualified | 0
| 11 | Assistant/Technician | 8 | hrs | 0 | 0 | 0 |  | Design - Mechanical Engineer: Assistant/Technician | 0
| 12 | Trainee | 8 | hrs | 0 | 0 | 0 |  | Design - Mechanical Engineer: Trainee | 0
Electrical Engineer:
| 13 | Senior | 8 | hrs | 0 | 0 | 0 |  | Design - Electrical Engineer: Senior | 0
| 14 | Qualified | 8 | hrs | 0 | 0 | 0 |  | Design - Electrical Engineer: Qualified | 0
| 15 | Assistant/Technician | 8 | hrs | 0 | 0 | 0 |  | Design - Electrical Engineer: Assistant/Technician | 0
| 16 | Trainee | 8 | hrs | 0 | 0 | 0 |  | Design - Electrical Engineer: Trainee | 0
Environmental Services:
| 17 | Senior | 8 | hrs | 0 | 0 | 0 |  | Design - Environmental Services: Senior | 0
| 18 | Qualified | 8 | hrs | 0 | 0 | 0 |  | Design - Environmental Services: Qualified | 0
| 19 | Assistant/Technician | 8 | hrs | 0 | 0 | 0 |  | Design - Environmental Services: Assistant/Technician | 0
| 20 | Trainee | 8 | hrs | 0 | 0 | 0 |  | Design - Environmental Services: Trainee | 0
|  | 1.2/2 |  |  | To Collection £ | 0
Collection
|  | 1.2/1 |  |  |  | 0
|  | 1.2/2 |  |  |  | 0
[5 empty] | Total to main summary £ | 0
MEP Total - Breakdown on separate Tab
Instruction:
Insert figures in the ORANGE sections of the sheet

## FlyD.2
D. PRE CONSTRUCTION SERVICES AGREEMENT (PCSA) | D.2 PCSA Form of Tender

## D2 PCSA Form of Tender
1ST STAGE TENDER DOCUMENT
New Sports and Community Pavilion, Edmonds Park, Didcot
D. FORM OF TENDER
D/2 | PCSA Form of Tender
To: |  | Ridge and Partners LLP
The Cowyards
Blenheim Park
Oxford Road
Woodstock
OX20 1QR
From: |  | …………………………………………….
…………………………………………….
…………………………………………….
…………………………………………….
…………………………………………….
We have examined the tender documents and offer to provide the Pre Construction Services described
(inclusive of all expenses, disbursements and the like) in accordance with the documents;
Option A - period as stipulated by tender documents
for the sum of |  |  | £ …………………………………………………………………………………….... (in words)
£ ……………………………………………..… (in figures) exclusive of any VAT chargeable
within | 12 | weeks from acceptance of our tender, comprising a period of:
• | 4 | weeks from appointment as 2nd stage contractor to start the design
period/procurement period, and
• | 8 | weeks for the second procurement period.
Option B - period to be stipulated by contractor
We offer to carry out the whole of the Works described in accordance with the documents referred to
above;
for the sum of |  |  | £ …………………………………………………………………………………….... (in words)
£ ……………………………………………..… (in figures) exclusive of any VAT chargeable
within | 0 | weeks from acceptance of our tender, comprising a period of:
• |  | weeks from appointment as 2nd stage contractor to start the design
period/procurement period, and
• |  | weeks for the second procurement period.
We enclose our priced PCSA fee and preliminaires document for each option.
We agree that if any obvious errors in pricing or errors in arithmetic are discovered in the priced
document[s] before acceptance of this offer, they shall be dealt with in accordance with the Alternative 2
procedure set out in JCT Practice Note 6 - Main Contract Tendering.
We undertake in the event of your acceptance to execute with you a formal contract embodying all the
conditions and terms contained in this offer within 21 days of being required to do so by the Employer.
This tender remains open for acceptance for 56 days from the latest date fixed for the submission of
tenders.
We confirm that this tender is submitted at our expense and agree that the Employer need not necessarily
accept the lowest or any other tender.
Certificate of Bona Fide Tender
The essence of selective tendering is that the client shall receive bona fide competitive tenders from all
those tendering. In recognition of the principle, I certify that this is a bona fide tender, intended to be
competitive, and that we have not fixed or adjusted the amount of the tender by or under or in accordance
with any agreement or arrangement with any other person. I also certify that we have not done and we
undertake that will not do at any time before the hour and date specified for return of this tender any of the
following acts:-
a. | Communication to a person other than the person calling for those tenders the amount or
approximate amount of the proposed tender, except where the disclosure, in confidence, of the
approximate amount of the tender was necessary to obtain insurance premium quotations required
for the preparation of the tender.
b. | entering into any agreement or arrangement with any other person that he shall refrain from
tendering or as to the amount of any tender to be submitted.
c. | offering or paying or giving or agreeing to pay or give any sum of money or valuable consideration
directly or indirectly to any person for doing or having done or causing or having caused to be done
in relation to any other tender or proposed tender for the said work any act or thing or sort
described above.
In this certificate the word "person" includes any person any body or association, corporate or
unincorporate and "any agreement or arrangement" includes any such transaction, formal or informal, and
whether legally binding or not.
Signed by or on
behalf of : |  |  | …………………………………………………………………………………….
Signature : |  |  | …………………………………………………………………………………….
duly authorised to sign
Position : |  |  | …………………………………………………………………………………….
Date : |  |  | ………………………………………….. 20…..
Note: The completed form of tender together with the information requested must be received
at the above address no later than 12:00 hours on the date set out in the tender invitation.

## FlyD.3
D. PRE CONSTRUCTION SERVICES AGREEMENT (PCSA) | D.3 PCSA Contract Particulars

## FlyE
E. COST PLAN | E. COST PLAN

## cost plan
1ST STAGE TENDER DOCUMENT
New Sports and Community Pavilion, Edmonds Park, Didcot
E. COST PLAN
REF | DESCRIPTION |  | QUANTITY |  | RATE | ITEM TOTAL | GROUP TOTAL
0 | Facilitating works
0.1 | Toxic/hazardous material removal
| • | Asbestos survey and removal
| • | Contaminated ground land; removal
| • | Eradication of plant growth; removal / chemical treatment
0
0.2 | Major demolition works
| • | Demolition works
| • | Soft strip works | 1 | item |  | 0
0
0.3 | Specialist groundworks
| • | Site dewatering and pumping
| • | Soil stabilisation measures
| • | Ground gas venting measures
0
0.4 | Temporary diversion works
| • | Temporary diversion of drains
| • | Temporary diversion of services
0
0.5 | Extraordinary site investigation works
| • | Archaeological investigation
| • | Reptile/wildlife mitigation measures
| • | Other extraordinary investigation works
0
|  | Element Group Total |  |  |  | £ | 0
1 | Substructure
1.1 | Substructure
• | Standard Foundations (assumption)
| • | Strip foundation, including excavation, earthwork support, disposal, backfilling, compact base of foundation, concrete, reinforcement, formwork, compressible materials, clayboard; strip foundation estimated up to 1m deep (subject to ground investigation) | 433 | m² |  | 0
| • | Isolated pad foundation; for column base, excavate pit in firm ground, partial backfill, partial disposal, support, compact base of pit; in-situ concrete; reinforced. | 5 | nr |  | 0
| • | Assume 150mm wide x 300mm deep concrete upstand with reinforcement for external walls | 122 | m |  | 0
| • | Assume 150mm wide x 300mm deep concrete upstand with reinforcement for internal walls | 87 | m |  | 0
0
• | External Walls Up to DPC
| • | Assumption: 100 thick block outer skin, 60 wide lean concrete infilled; concrete block inner skin at slab level; 350 high block wall plus 100 high brick wall; overall 450 high; DPC; cavity tray and associated weepholes | 122 | m |  | 0
0
1.2 | Ground floor construction (assumption in-situ concrete)
| • | Ground floor construction: blinded hardcore bed; 150 thick reinforced ground bearing slab with A393 mesh reinforcement top and bottom; DPM; 85 thick floor grade insulation; vapour control layer, 75 thick screed | 433 | m2 |  | 0
| • | Design joints | 433 | m2 |  | 0
0
|  | Element Group Total |  |  |  | £ | 0
2 | Superstructure
2.1 | Frame
| • | Steel frames | 433 | m2 |  | 0
| • | Fire protection to steel frame | 433 | m2 |  | 0
| • | Porch column | 5 | nr |  | 0
0
2.2 | Upper floors
| • | Upper floors |  |  |  | Not Applicable
0
2.3 | Roof
• | Roof Structure
| • | Roof structure - pitched roof - Roof truss by specialist; ceiling joist as part of the roof truss (area considered GIA plus covered terrace) | 499 | m2 |  | 0
• | Roof Coverings
| • | Roof coverings - Pitched roofs composite slate roof; breather membrane, battens and counter battens | 723 | m2 |  | 0
| • | Extra over for ridge | 48 | m |  | 0
| • | Extra over for double course of slates at eaves | 95 | m |  | 0
| • | Extra over for eaves; facia/soffits | 95 | m |  | 0
| • | Extra over for verge & barge board | 60 | m |  | 0
| • | Extra over for valley gutter/ flashings | 16 | m |  | 0
| • | Roof insulation board between rafters; vapour control barriers (assume 100 thick between rafters and 200 thick over rafters) | 611 | m2 |  | 0
| • | Roof insulation to sloping ceiling with insulation between rafters 100 thick; vapour control barriers. (insulated plasterboard measured under ceiling) | 112 | m2 |  | 0
• | Roof Drainage
| • | Gutters | 95 | m |  | 0
| • | Rainwater pipes & fittings | 30 | m |  | 0
| • | Extra over for connecting below ground drainage | 10 | nr |  | 0
• | Rooflights/ openings
| • | Forming recess to high level windows to community space; including roof tiles, flashings etc | 1 | item |  | 0
| • | Roof lights | 12 | m2 |  | 0
0
2.4 | Stairs and ramps
| • | Forming ramps to main entrance | 1 | nr |  | 0
| • | Forming ramps to Plant/ Bins | 1 | nr |  | 0
| • | Forming ramps to fire escape | 1 | nr |  | 0
0
2.5 | External walls
| • | External walls; facing brickwork (various colours of brick) | 415 | m2 |  | 0
| • | Extra over for forming cavities | 415 | m2 |  | 0
| • | Extra over for dpc | 109 | m |  | 0
| • | Extra over for cavity tray at base of cavity wall; weep holes; jointing to dpc under timber stud to ground floor slab | 109 | m |  | 0
| • | Extra over for finishing at top of wall | 122 | m |  | 0
| • | Extra over for slate cladding to gable to east elevation | 19 | m2 |  | 0
| • | Extra over for brick banding (approx. 300 wide projection) | 30 | m |  | 0
| • | Extra over for forming entrance/canopy to south elevation | 1 | item |  | 0
| • | Extra over for forming opening to external doors | 5 | nr |  | 0
| • | Extra over for forming opening for windows | 6 | nr |  | 0
| • | Timber frame to inner skin including insulation and plasterboard | 415 | m2 |  | 0
0
2.6 | Windows and external doors
External Windows
| • | Windows (6 number of various sizes) | 35 | m2 |  | 0
| • | Window film to windows | 35 | m2 |  | 0
| • | Glazed sliding door to entrance (approx. 2550 x 2500) | 1 | nr |  | 0
| • | Sliding/folding door to community space (approx. 6500 x 2500) | 1 | nr |  | 0
| • | Single door to changing area (approx. 1000 x 2500) | 1 | nr |  | 0
| • | Single door to fire escape (approx. 900 x 2500) | 1 | nr |  | 0
| • | Double door including louvre to Plant/Bins | 1 | nr |  | 0
0
2.7 | Internal walls and partitions
• | Wall and partitions
| • | Timber stud, plasterboard partitions; sole & head plates; 12.5 thick plasterboard both sides; 50 thick insulation | 431 | m2 |  | 0
| • | Extra over for pattressing to wall | 65 | m2 |  | 0
| • | Extra over for forming openings in walls for internal doors; single door | 19 | nr |  | 0
| • | Extra over for forming openings in walls for internal doors; double door | 3 | nr |  | 0
| • | Extra over for 15mm Fireline board to wall (assume 20% of internal partition) | 86 | m2 |  | 0
| • | Cubicles: Shower & WC cubicles | 8 | nr |  | 0
0
2.8 | Internal doors
| • | Internal doors; single | 19 | nr |  | 0
| • | Internal doors; double | 2 | nr |  | 0
| • | Internal doors; double to hall | 1 | nr |  | 0
| • | Internal doors; roller shutter to kitchen servery | 1 | nr |  | 0
| • | Architraves mdf (both sides of the door) & paint | 236 | m |  | 0
0
|  | Element Group Total |  |  |  | £ | 0
3 | Internal Finishes
3.1 | Wall Finishes
| • | Skim finish to walls | 968 | m2 |  | 0
| • | Emulsion paint; Dimond mat linen white | 716 | m2 |  | 0
| • | Emulsion paint; light grey | 133 | m2 |  | 0
| • | Emulsion paint; washable linen white (moisture resistant) | 119 | m2 |  | 0
| • | White rock finish | 105 | m2 |  | 0
| • | Tile splashback | 6 | m |  | 0
| • | Hygienic wall finish to kitchen areas | 46 | m2 |  | 0
| • | Acoustic treatment to walls | 1 | item |  | 0
| • | Corner protectors | 8 | nr |  | 0
0
3.2 | Floor finishes
| • | Cement sand floor screed |  |  |  | included in floor construction
| • | Forbo De Luxe Decibel; including latex screed | 220 | m2 |  | 0
| • | Anti-slip altro classic; including latex screed | 16 | m2 |  | 0
| • | Anti-slip stone effect; including latex screed | 13 | m2 |  | 0
| • | Altro marine 20 vinyl; including latex screed | 45 | m2 |  | 0
| • | Altro Atlas 40 vinyl; including latex screed | 83 | m2 |  | 0
| • | Anti slip floor to kitchen; including latex screed | 20 | m2 |  | 0
| • | Concrete sealed floor | 11 | m2 |  | 0
| • | Matting suitable for football boots | 9 | m2 |  | 0
| • | Matting to covered entrance | 12 | m2 |  | 0
| • | Matting to covered terrace | 15 | m2 |  | 0
| • | Skirtings; Timber skirting | 114 | m |  | 0
| • | Skirtings; Altro classic | 17 | m |  | 0
| • | Skirtings; anti-slip stone effect | 29 | m |  | 0
| • | Skirtings; altro, marine 20 | 53 | m |  | 0
| • | Skirtings; Altro atlus 40 | 100 | m |  | 0
| • | Skirtings; Anti-slip to kitchen | 18 | m |  | 0
| • | Floor trim/finishes to single internal doors | 19 | nr |  | 0
| • | Floor trim/finishes to double internal doors | 3 | nr |  | 0
0
3.3 | Ceiling Finishes
| • | Standard plasterboard ceiling | 143 | m2 |  | 0
| • | Moisture resistant plasterboard ceiling | 150 | m2 |  | 0
| • | Insulated plasterboard slope ceiling to community space; high level | 112 | m2 |  | 0
| • | Sound absorption rafting; to Foyer & community space(assumed 60% area to cover) | 91 | m2 |  | 0
| • | Finishes to ceiling; skim coat | 405 | m2 |  | 0
| • | Finishes to ceiling; matt white | 143 | m2 |  | 0
| • | Finishes to community space ceiling | 112 | m2 |  | 0
| • | Finishes to ceiling; washable white (moisture resistant) | 150 | m2 |  | 0
| • | Acoustic treatment to ceiling | 1 | item |  | 0
| • | Access hatch | 1 | item |  | 0
| • | Covered terrace, entrance & benching area ceiling (assumed timber cladding) | 66 | m2 |  | 0
0
0
|  | Element Group Total |  |  |  | £ | 0
4 | Fittings, furnishings and equipment
4.1 | General fittings, furnishings and equipment
• | General fittings
| • | Changing room bench with hooks | 19 | m |  | 0
| • | Locker; to changing lobby | 24 | nr |  | 0
| • | Locker to official change | 10 | nr |  | 0
| • | Tables & chairs |  |  |  | Excluded
| • | First aid/ examination set | 1 | nr |  | 0
• | Kitchen fittings and equipment
| • | Kitchen unit/counter (approximate 630 wide) including servery, cutout for sink & washbasin | 14 | m |  | 0
| • | Kitchen appliances; Hob+Oven + cooker hood | 1 | nr |  | 0
| • | Kitchen appliances; Under counter dishwasher | 1 | nr |  | 0
| • | Kitchen appliances; Under counter fridge/freezer | 1 | nr |  | 0
| • | Waste bins, towel rails, storage racks and other accessories | 1 | item |  | 0
0
• | Sign/ Notices
| • | Statutory signage | 433 | m2 |  | 0
| • | General internal signage | 433 | m2 |  | 0
0
• | Bird and Vermin Control
| • | Wires, nets, spikes etc | 1 | item |  | 0
0
|  | Element Group Total |  |  |  | £ | 0
5 | Services
5.1 | Sanitary installations
• | Sanitary appliances
| • | Kitchen sink, taps and waste | 1 | nr |  | 0
| • | Kitchen WHB, including taps and waste | 1 | nr |  | 0
| • | WHB, including taps and waste | 9 | nr |  | 0
| • | WC including seat & cover | 9 | nr |  | 0
| • | Urinals |  |  |  | None
| • | Shower tray & shower screen | 9 | nr |  | 0
| • | Shower tray & shower screen to Accessible changing | 1 | nr |  | 0
| • | Thermostatic shower valve & head | 9 | nr |  | 0
| • | Thermostatic shower valve & head to accessible changing | 1 | nr |  | 0
| • | Cleaner's sink | 1 | nr |  | 0
| • | Accessible WC suite/ baby changing; including WC, WHB, mirror, grab rail, baby changing seat etc. | 1 | item |  | 0
| • | Accessible changing room/ first aid; including WC, WHB, mirror, grab rail etc. | 1 | item |  | 0
| • | Testing of installations |  | % |  | 0
| • | Commissioning of installations |  | % |  | 0
0
• | Sanitary ancillaries
| • | Fittings; Mirrors to toilet, allow 1 per WHB (for accessible included in WC suite above) | 9 | nr |  | 0
| • | Fittings; Hand driers (allowed to some WC's only) | 6 | nr |  | 0
| • | Fittings; toilet roll holders (for accessible included in WC suite above) | 9 | nr |  | 0
| • | Fittings; soap dispensers (for accessible included in WC suite above) | 9 | nr |  | 0
0
5.2 | Mechanical installations
• | Service equipment |  |  |  |  | Excluded
5.3 | Disposal installations
| • | Drainage to sanitary appliances; above ground soil and waste | 35 | nr |  | 0
| • | Testing of installations |  | % |  | 0
| • | Commissioning of installations |  | % |  | 0
0
5.4 | Water installation
| • | Mains water supply; hot & cold water services and thermal insulation | 433 | m2 |  | 0
| • | Testing of installations |  | % |  | 0
| • | Commissioning of installations |  | % |  | 0
0
5.5 | Heat source
| • | Heat source | 433 | m2 |  | 0
| • | Testing of installations |  | % |  | 0
| • | Commissioning of installations |  | % |  | 0
0
5.6 | Space heating
| • | Central heating system & controls | 433 | m2 |  | 0
| • | Testing of installations |  | % |  | 0
| • | Commissioning of installations |  | % |  | 0
0
5.7 | Ventilation systems
| • | Toilet/Shower/Kitchen ventilation units | 433 | m2 |  | 0
| • | Testing of installations |  | % |  | 0
| • | Commissioning of installations |  | % |  | 0
0
5.8 | Electrical installations
• | Electrical mains/submains distributions
| • | Electrical mains sub-mains | 433 | m2 |  | 0
| • | Testing of installations |  | % |  | 0
| • | Commissioning of installations |  | % |  | 0
0
• | Power installations
| • | Power installations | 433 | m2 |  | 0
| • | Testing of installations |  | % |  | 0
| • | Commissioning of installations |  | % |  | 0
0
• | Lighting installations
| • | Lighting installations | 433 | m2 |  | 0
| • | Testing of installations |  | % |  | 0
| • | Commissioning of installations |  | % |  | 0
0
• | Earthing & Bonding Systems
| • | Earthing & bonding systems | 433 | m2 |  | 0
| • | Testing of installations |  | % |  | 0
| • | Commissioning of installations |  | % |  | 0
0
• | Solar PV Installations
| • | Solar Panel | 1 | item |  | 0
| • | Testing of installations |  | % |  | 0
| • | Commissioning of installations |  | % |  | 0
0
5.9 | Gas and other fuel installations
• | Gas and other fuel installations |  |  |  |  | Excluded
5.1 | Lift and conveyor installations
• | Lift & conveyor installations |  |  |  |  | Not Applicable
5.11 | Fire and Lightning protection
| • | Fire fighting system (lightning, fire detection & alarm) | 433 | m2 |  | 0
| • | Testing of installations |  | % |  | 0
| • | Commissioning of installations |  | % |  | 0
0
5.12 | Communication, security and control systems
• | Communication /data system
| • | Telecommunication system | 433 | m2 |  | 0
| • | Testing of installations |  | % |  | 0
| • | Commissioning of installations |  | % |  | 0
0
• | Burglar and security alarms; security lighting
| • | Burglar & security alarms | 433 | m2 |  | 0
| • | Security lights & lighting system | 433 | m2 |  | 0
| • | Testing of installations |  | % |  | 0
| • | Commissioning of installations |  | % |  | 0
0
• | CCTV
| • | CCTV System | 433 | m2 |  | 0
| • | Testing of installations |  | % |  | 0
| • | Commissioning of installations |  | % |  | 0
0
5.13 | Specialist installations
• | Specialist installations |  |  |  |  | Excluded
5.14 | Builder's work in connection with services
• |  | Builder's work in connection with services & fire stopping |  | % |  | 0
0
|  | Element Group Total |  |  |  | £ | 0
6 | Complete buildings and building units
6.1 | Prefabricated buildings |  |  |  |  | Not applicable
|  | Element Group Total |  |  |  | £ | 0
7 | Work to existing buildings
7.1 | Minor demolition works and alteration works |  |  |  |  | Not Applicable
|  | Element Group Total |  |  |  | £ | 0
8 | External works
8.1 | Site preparation works
| • | Site strip | 6475 | m2 |  | 0
0
8.2 | Roads, paths and pavings
| • | Stone slab paving | 22 | m2 |  | 0
| • | Resin bound gravel permeable paving with black powder coated metal edge | 711 | m2 |  | 0
| • | Extra over for specialist sports paving to areas around table tennis tables - say 26m2 per Table tennis table | 79 | m2 |  | 0
| • | Gravel path | 21 | m2 |  | 0
| • | Timber edge | 36 | m |  | 0
| • | Grass Crete system with grass seed over | 80 | m2 |  | 0
| • | Making good existing carpark; replace wearing course | 1172 | m2 |  | 0
| • | Repairing, replacing existing kerbing | 181 | m |  | 0
| • | Line marking to existing carpark | 66 | nr |  | 0
0
8.3 | Planting
| • | Topsoil for planting bed | 114 | m2 |  | 0
| • | Planting as proposed herbaceous planting schedule with fine bark mulch | 114 | m2 |  | 0
| • | Existing grass allowed to grow long with a maximum of 2 cuts per year to encourage wild flower growth | 680 | m2 |  | 0
| • | Existing grass retained and patched where necessary | 4311 | m2 |  | 0
0
8.4 | Fencing, railings and walls
| • | Removing existing fencing and make good for new access | 1 | item |  | 0
| • | Entrance gate - Pedestrian gate | 1 | nr |  | 0
| • | Pedestrian gate from carpark | 2 | nr |  | 0
| • | Timber and metal pole kick rail with gates for emergency vehicle access | 1 | nr |  | 0
0
8.5 | Site/street furniture and equipment
| • | Cycle shelter for 8nr cycle stand | 1 | item |  | 0
| • | Table tennis tables & specialist matting | 3 | nr |  | 0
| • | Bollards (assumed 3nr) | 3 | nr |  | 0
| • | Outdoor tables 4nr & chairs 16nr | 4 | set |  | 0
| • | Timber benches/seating area (re-use existing 2nr) | 7 | nr |  | 0
| • | Bin (re-use 2nr existing bin) | 4 | nr |  | 0
| • | Nesting boxes, bat boxes etc | 1 | item |  | 0
0
8.6 | External drainage
| • | Site drainage hardstanding | 834 | m2 |  | 0
| • | Building drainage | 433 | m2 |  | 0
| • | Connection to existing foul drainage system in Park Road | 1 | item |  | 0
0
8.7 | External services
| • | Water main supply | 1 | PS |  | 0
| • | Electricity mains supply | 1 | PS |  | 0
| • | Gas main supply |  |  |  | excluded
| • | Telecommunication connection | 1 | PS |  | 0
| • | Services trenching | 1 | item |  | 0
| • | External lighting | 1 | item |  | 0
| • | Bases of external lighting | 1 | item |  | 0
0
8.8 | Minor building works and ancillary buildings |  |  |  |  | excluded
excluded
|  | Element Group Total |  |  |  | £ | 0
|  | Sub Total: Facilitating works and Building Works |  |  |  | £ | 0

## FlyF
F. PROGRAMME | F. PROGRAMME

## FlyG
G. PLANNING DECISSION AND PLANNING CONDITION TRACKER | F. PROGRAMME

## FlyH
H. PRE-CONSTRUCTION INFORMATION | F. PROGRAMME

## FlyI
I. BREEAM TRACKER | F. PROGRAMME

## FlyJ
J. TENDER EVALUATION | F. PROGRAMME