## COVER PAGE
SCHEDULES OF WORK
-in respect of-
REPAIR AND RE-ROOFING WORKS
-to-
THE CUE BUILDING
-at-
100 LONDON ROAD, FOREST HILL, LONDON, SE23 3PQ
-for-
THE HORNIMAN PUBLIC MUSEUM &
PUBLIC PARK TRUST
Chartered Quantity Surveyors
Unit 83, Capital Business Centre
22 Carlton Road
South Croydon
June 2023 |  | Surrey, CR2 0BS

## CONTENTS
Schedules of Work
-in respect of-
Repair and re-roofing works
-to-
The Cue Building
-at-
100 London Road, Forest Hill, London, SE23 3PQ
-for-
The Horniman Public Museum &
Public Park Trust
- comprising -
Section No. 1 | - | Conditions of Contract / Preliminaries
Section No. 2 | - | Temporary access / Survey
Section No. 3 | - | Work to the main roof
Section No. 4 | - | Work to the front balcony (All Provisional)
Section No. 5 | - | Dayworks
Section No. 6 | - | Schedule of fixed rate charges for possible additional works
Summary
Appendix A | - | Detailed terms of the Conditions of Contract
Appendix B | - | Detailed terms of the Preliminaries
Appendix C | - | Design information

## SECTION No. 1
HORNIMAN MUSEUM
100 LONDON ROAD, FOREST HILL, LONDON, SE23 3PQ
CUE BUILDING - REPAIR AND RE-ROOFING WORKS
SECTION No. 1
CONDITIONS OF CONTRACT / PRELIMINARIES
£ p
Following review of Appendix "A" and Appendix "B" the Contractor is to insert below his proposed costs in respect of the "Conditions of Contract" and "Preliminaries". In the event that no specific allowance is stated below the Contractor will be deemed to have covered elsewhere within the body of the pricing for the cost of fully complying with the terms detailed in Appendix "A" and "B".
1.01
1.02
1.03
1.04
1.05
1.06
1.07
1.08
1.09
1.1
1.11
1.12
1.13
1.14
1.15
SECTION No. 1 - CONDITIONS OF CONTRACT / PRELIMINARIES
|  |  | To Summary £ | 0

## SECTION No. 2
HORNIMAN MUSEUM
100 LONDON ROAD, FOREST HILL, LONDON, SE23 3PQ
CUE BUILDING - REPAIR AND RE-ROOFING WORKS
= Contractor to insert pricing
SECTION No. 2
TEMPORARY ACCESS / SURVEY
£ p
2.0.1 | In pricing the items that follow, the Contractor shall be deemed to have thoroughly inspected the tender documents and have acquainted himself with the site and the full extent / character of the items. The items have been split into the following priceable areas of work: | 0 | 0 | 0 | 0
2.1 - Temporary access works
2.2 - Survey / report
2.0.2 | The Contractor is requested to price and submit this document electronically. In the event that the Contractor elects not to submit the tender electronically then it is requested, for ease of checking, that each printed page is individually totalled and carried forward to a summary. | 0 | 0 | 0 | 0
0
| 2.1 - TEMPORARY ACCESS WORKS |  |  |  | 0
0
2.1.1 | Contractor Designed Portion: Provide alarmed scaffold in gaining access to the areas of works so described in this document. Include for all necessary costs in respect of hoists, safety netting, fans etc. Allow for altering and adapting the scaffold as required and remove upon completion. In designing the scaffold the contractor is to take due regard of the following: 1) The alarm is to be designed such that the security personnel in the clock tower are alerted if triggered 2) Access ladders at ground level are to be removed whenever the scaffold is not in use 3) Fire escape routes from the museum to remain unobstructed at all times 4) The design is to be approved by the CA prior to commencement. | 1 | Item |  | 0
0
2.1.2 | in pricing the item above, given the scope of works so described in this document, the Contractor is requested to state how many weeks hire has been duly allowed for. |  | weeks |  | 0
0
2.1.3 | in the event that the CA instructs additional works (over and above that described) thereby requiring the extended hire of the scaffold then the Contractor is requested to quote here his additional cost per week for such an eventuality. Should the Contractor elect to claim prolongation costs on this basis then he is reminded that the Contract provisions are to be followed and as such due 'cause and affect' will need to be demonstrated before the inclusion of costs will be considered. |  | / week |  | 0
0
| _______________________________________ |  |  |  | 0
0
| The Contractor is requested to insert below the details / costs of any additional items which are not covered by the headings of cost above but are deemed necessary in complying with the information provided: |  |  |  | 0
0
2.1.4 |  | 1 | Item |  | 0
0
2.1.5 |  | 1 | Item |  | 0
0
2.1.6 |  | 1 | Item |  | 0
0
2.1.7 |  | 1 | Item |  | 0
0
2.1.8 |  | 1 | Item |  | 0
0
0
0
| 2.2 - SURVEY / REPORT |  |  |  | 0
0
2.2.1 | Following completion of the demolition / works on site items described in Section 3.1 allow for undertaking an existing condition survey. The report is to be undertaken by a suitably qualified professional to all elements of the existing roof structure in identifying where repair works are necessary. Upon completion of the survey allow for producing a detailed written report for subsequent handing to the CA / Employer. | 1 | Item |  | 0
0
0
0
0
SECTION No. 2 - TEMPORARY ACCESS / SURVEY
|  |  |  | To Summary £ | 0

## SECTION No. 3
HORNIMAN MUSEUM
100 LONDON ROAD, FOREST HILL, LONDON, SE23 3PQ
CUE BUILDING - REPAIR AND RE-ROOFING WORKS
= Contractor to insert pricing
SECTION No. 3
WORK TO THE MAIN ROOF
£ p
3.0.1 | In pricing the items that follow, the Contractor shall be deemed to have thoroughly inspected the tender documents and have acquainted himself with the site and the full extent / character of the items. The items have been split into the following priceable areas of work: | 0 | 0 | 0 | 0
3.1 - Removal of existing roof systems
3.2 - Temporary protection works
3.3 - Site survey
3.4 - Work to the existing roof structure
3.5 - New roofing works
3.6 - Roofing accessories
3.7 - Mechanical installations
3.0.2 | The Contractor is requested to price and submit this document electronically. In the event that the Contractor elects not to submit the tender electronically then it is requested, for ease of checking, that each printed page is individually totalled and carried forward to a summary. | 0 | 0 | 0 | 0
0
| 3.1 - REMOVAL OF EXISTING ROOF SYSTEMS |  |  |  | 0
0
| ALT-01: Removal of existing roof systems |  |  |  | 0
0
| Allow for undertaking the following demolition works to the North and South pitches of the existing roof that is located above the Cue Building; all as indicated on drawings LAB-687-DR-0111, 0112, 0120, 0130, 0211 & 0212 and within Architect's specification clause C90 - 1.2.3 (ALT-01): |  |  |  | 0
0
3.1.1 | Carefully remove the existing green roof systems, inclusive of all green roof components; in exposing the existing roof membrane | 1 | Item |  | 0
0
3.1.2 | Carefully remove the existing roof membranes and all associated perimeter trims, flashings, cappings, fixtures and timber profiles; in exposing the existing timber roof deck structure | 1 | Item |  | 0
0
0
0
| 3.2 - TEMPORARY PROTECTION WORKS |  |  |  | 0
0
3.2.1 | Allow for all necessary temporary protection measures, or for carefully removing and setting aside for reuse, all retained elements on the roof - i.e. vent cowls, rooflights, clerestory windows, roof lightning protection tapes etc. | 1 | Item |  | 0
0
3.2.2 | Following the removal of the existing roof membranes allow for all necessary temporary protection measures to the Cue Building in maintaining adequate weather protection; the Contractor's methodology in this regard is to be made clear within the covering correspondence to the tender return and comprise part of the tender review process. | 1 | Item |  | 0
0
0
0
| 3.3 - SITE SURVEY |  |  |  | 0
0
| ALT-01: Inspection of existing timbers |  |  |  | 0
0
3.3.1 | Following completion of the demolition works allow for undertaking an existing condition survey. The report is to be undertaken by a suitably qualified professional to all elements of the existing roof structure in identifying where repair works are necessary. Upon completion of the survey allow for producing a detailed written report for subsequent handing to the CA / Employer. | 1 | Item |  | 0
0
0
0
| 3.4 - WORK TO THE EXISTING ROOF STRUCTURE |  |  |  | 0
0
| ALT-02: Removal works |  |  |  | 0
0
| Allow for the following work to the existing Northern pitch; all as indicated on drawings LAB-687-DR-0120, 0211, 0212, 4011, 4012, SK-01 & SK-02 and within Architect's specification clause C90 - 1.2.4 (ALT-02): |  |  |  | 0
0
3.4.1 | Carefully remove the existing timber fascia, projecting rafters and drainage spouts to the lower eaves; exposed timber face to receive new work (measured separately) | 1 | Item |  | 0
0
0
| Allow for the following work to the existing Southern pitch - extent to be limited to the reduced roof pitch length above the balcony; all as indicated on drawings LAB-687-DR-0120 & SK-03 and within Architect's specification clause C90 - 1.2.4 (ALT-02): |  |  |  | 0
0
3.4.2 | Carefully remove the existing timber fascia, projecting rafters and drainage spouts to the lower eaves; exposed timber face to receive new work (measured separately) | 1 | Item |  | 0
0
0
| ALT-02: Remedial work to the existing timber structures |  |  |  | 0
0
3.4.3 | As detailed at item 3.3.1 the Contractor is to keep a detailed schedule of the repair works and this will serve as the basis of adjusting the following Provisional Sum. The method of valuing the works will be in accordance with the rates provided at Section 6 unless it is agreed the works will be progressed on dayworks basis, in which the case the rates provided at Section 5 will apply. | 0 | 0 | 0 | 0
0
3.4.4 | Provide the Provisional Sum of £10,000.00 for repair work to the existing roof structure | 1 | Item | 10000 | 10000
0
0
| ALT-02: New carpentry works to the Northern pitch |  |  |  | 0
0
3.4.5 | Allow for all carpentry works in reforming the lower eaves to the Northern pitched roof; all as indicated on Architect's drawings LAB-687-DR-4011, 4012, 4051 & SK-02, Structural Engineer's drawing 230237-CON-X-XX-DR-S-0004 and within Architect's specification clause C90 - 1.2.4 (ALT-02); scope to include the following: |  |  |  | 0
| [1] Fascia board; include for forming circular ventilation holes and for installing steel vermin control mesh to rear face |  |  |  | 0
| [2] Eaves board |  |  |  | 0
| [3] Stiffener plates to the eaves board |  |  |  | 0
| [4] Spout board - 5No |  |  |  | 0
| [5] Stiffener plates to either side of the spout board | 1 | Item |  | 0
0
3.4.6 | extra for 100 x 100mm galvanised steel angle | 1 | Item |  | 0
0
3.4.7 | extra cleaning all new and existing timber and sealing with matt transparent weather sealer | 1 | Item |  | 0
0
3.4.8 | extra for providing a mock up of the eaves installation for approval by the Contract Administrator | 1 | Item |  | 0
0
0
3.4.9 | Allow for all carpentry works in reforming the verges to the Eastern / Western edges of the Northern pitched roof; all as indicated on Architect's drawings LAB-687-DR-4013, Structural Engineer's drawing 230237-CON-X-XX-DR-S-004 and within Architect's specification clause C90 - 1.2.4 (ALT-02); scope to include the following: |  |  |  | 0
| [1] Fascia board |  |  |  | 0
| [2] Timber edge batten | 1 | Item |  | 0
0
3.4.10 | extra for 100 x 100mm galvanised steel angle | 1 | Item |  | 0
0
3.4.11 | extra cleaning all new and existing timber and sealing with matt transparent weather sealer | 1 | Item |  | 0
0
0
3.4.12 | Allow for all carpentry works in reforming the upper eaves to the Northern pitched roof; all as indicated on Architect's drawings LAB-687-DR-4015 and within Architect's specification clause C90 - 1.2.4 (ALT-02); scope to include the following: |  |  |  | 0
| [1] 500mm wide strip of plywood in reinforcing the existing roof deck |  |  |  | 0
| [2] Timber block; 75 x 129mm |  |  |  | 0
| [3] Timber block; 75 x 175mm |  |  |  | 0
| [4] Fascia board to external face (upper section) |  |  |  | 0
| [5] Fascia board to external face (lower section) |  |  |  | 0
| [6] Steel vermin control mesh to ventilation gap between the upper and lower fascias; mesh to be surface fixed | 1 | Item |  | 0
0
3.4.13 | extra cleaning all new and existing timber and sealing with matt transparent weather sealer | 1 | Item |  | 0
0
0
| ALT-02: New carpentry works to the Southern pitch |  |  |  | 0
0
3.4.14 | Allow for all carpentry works in reforming the eaves to the Southern pitched roof - extent to be limited to the reduced roof pitch length above the balcony; all as indicated on Architect's drawings LAB-687-DR-6061, 6062, 6063 & SK-03, Structural Engineer's drawing 230237-CON-X-XX-DR-S-003 and within Architect's specification clause C90 - 1.2.4 (ALT-02); scope to include the following: |  |  |  | 0
| [1] Fascia board; include for forming circular ventilation holes and for installing steel vermin control mesh to rear face |  |  |  | 0
| [2] Eaves board |  |  |  | 0
| [3] Stiffener plates to the eaves board |  |  |  | 0
| [4] Spout board - 2No |  |  |  | 0
| [5] Stiffener plates to either side of the spout board | 1 | Item |  | 0
0
3.4.15 | extra for 100 x 100mm galvanised steel angle to inner face of the fascia upstand | 1 | Item |  | 0
0
3.4.16 | extra for 100 x 150mm galvanised steel angle to outer face of the fascia upstand | 1 | Item |  | 0
0
3.4.17 | extra cleaning all new and existing timber and sealing with matt transparent weather sealer | 1 | Item |  | 0
0
0
3.4.18 | Allow for all carpentry works in reforming the verges to the Eastern / Western edges of the Southern pitched roof; all as indicated on Architect's drawings LAB-687-DR-4013, Structural Engineer's drawing 230237-CON-X-XX-DR-S-004 and within Architect's specification clause C90 - 1.2.4 (ALT-02); scope to include the following: |  |  |  | 0
| [1] Fascia board |  |  |  | 0
| [2] Timber edge batten | 1 | Item |  | 0
0
3.4.19 | extra for 100 x 100mm galvanised steel angle | 1 | Item |  | 0
0
3.4.20 | extra cleaning all new and existing timber and sealing with matt transparent weather sealer | 1 | Item |  | 0
0
0
3.4.21 | Allow for all carpentry works in reforming the top edge detail to the Southern pitched roof; all as indicated on Architect's drawings LAB-687-DR-4016 and within Architect's specification clause C90 - 1.2.4 (ALT-02); scope to include the following: |  |  |  | 0
| [1] Fascia board |  |  |  | 0
| [2] Timber fillet | 1 | Item |  | 0
0
3.4.22 | extra cleaning all new and existing timber and sealing with matt transparent weather sealer | 1 | Item |  | 0
0
0
0
| 3.5 - NEW ROOFING WORKS |  |  |  | 0
0
| RFS-03: Leadwork |  |  |  | 0
0
| Allow for supplying and installing the following items of Code 5 leadwork; as Architect's specification clause H71 |  |  |  | 0
0
| Northern pitched roof: |  |  |  | 0
0
3.5.1 | fascia upstand / eaves board weatherings to the lower eaves; install to comprise 2No separate sections of leadwork; as indicated on Architect's drawings LAB-687-DR-4011 & 4051 | 1 | Item |  | 0
0
3.5.2 | extra for forming leadwork to the eaves spouts - 5No; as indicated on Architect's drawings LAB-687-DR-4012 & 4051 | 1 | Item |  | 0
0
3.5.3 | verge upstand weathering to the Eastern and Western edges; as indicated on Architect's drawing LAB-687-DR-4013 | 1 | Item |  | 0
0
3.5.4 | fascia upstand weathering to the upper eaves; as indicated on Architect's drawings LAB-687-DR-4015 | 1 | Item |  | 0
0
0
| Southern pitched roof: |  |  |  | 0
0
3.5.5 | fascia upstand / eaves board weatherings to the eaves of the Southern pitched roof - extent to be limited to the reduced roof pitch length above the balcony; install to comprise 2No separate sections of leadwork; as indicated on Architect's drawings LAB-687-DR-6061, 6062 & 6052 | 1 | Item |  | 0
0
3.5.6 | extra for forming leadwork to the eaves spouts - 2No; as indicated on Architect's drawings LAB-687-DR-6063 & 6052 | 1 | Item |  | 0
0
3.5.7 | verge upstand weathering to the Eastern and Western edges; as indicated on Architect's drawing LAB-687-DR-4013 | 1 | Item |  | 0
0
0
| RFS-01: Reinforced bitumen membrane roof coverings |  |  |  | 0
0
| Allow for supplying and installing the following reinforced bitumen membrane roof coverings; include for all additional work at the roof perimeters and wind tower upstands; all as architect's specification clause J41 |  |  |  | 0
0
3.5.8 | in forming new roof coverings to the Northern pitched roof; as indicated on Architect's drawings LAB-687-DR-2111, 4011, 4012, 4013, 4014 & 4015 | 1 | Item |  | 0
0
3.5.9 | in forming new roof coverings to the Southern pitched roof; as indicated on Architect's drawings LAB-687-DR-2111, 4013, 4014, 4016, 6061, 6062 & 6063 | 1 | Item |  | 0
| ________________________________________ |  |  |  | 0
0
3.5.10 | Allow for testing the watertightness of the roof coverings; as Architect's specification clause J41 - 2.2.3 |  |  |  | 0
0
3.5.11 | Allow for providing a 10-year warranty on the new roof coverings | 1 | Item |  | 0
0
0
| RFS-02: Green roof system |  |  |  | 0
0
3.5.12 | Note: In pricing the items that follow Sky Garden Ltd, or other similar approved, has been referenced in Architect's specification clause Q37; in the event that the Contractor elects to engage the services of an alternative provider the specification provided is to match the bespoke planting mix that has been discussed and agreed between The Museum and Sky Garden | 0 | 0 | 0 | 0
0
0
| Allow for supplying and installing the following in forming the new green roof coverings; all as architect's specification clause Q37 |  |  |  | 0
0
3.5.13 | Northern pitched roof; as indicated on drawings 2113, 2114, 4011, 4012, 4013, 4014 & 4015 |  |  |  | 0
0
3.5.14 | slotted aluminium retention angles in forming stone margins to the eaves, Eastern / Western roof edges and perimeter of the wind towers | 1 | Item |  | 0
0
3.5.15 | galvanised steel gravel retention grille to the 5No water spouts on the lower eaves | 1 | Item |  | 0
0
3.5.16 | green roof build up including protection layer, drainage board with clamp support to top edge; filter membrane, substrate retention system and biodiverse substrate which is to vary between 80 and 150mm | 1 | Item |  | 0
0
3.5.17 | vegetation blanket | 1 | Item |  | 0
0
3.5.18 | river stone drainage margins | 1 | Item |  | 0
0
3.5.19 | irrigation system | 1 | Item |  | 0
0
0
| Southern pitched roof; as indicated on drawings 2113, 2114, 4013, 4014, 4016, 6061, 6062 & 6063 |  |  |  | 0
0
3.5.20 | slotted aluminium edge retention angles in forming stone margins to the eaves, Eastern / Western roof edges and perimeter of the rooflights and wind towers | 1 | Item |  | 0
0
3.5.21 | galvanised steel gravel retention grille to the 8No water spouts | 1 | Item |  | 0
0
3.5.22 | green roof build up including protection layer, drainage board with clamp support to top edge; filter membrane, substrate retention system and biodiverse substrate which is to vary between 80 and 150mm | 1 | Item |  | 0
0
3.5.23 | vegetation blanket | 1 | Item |  | 0
0
3.5.24 | river stone drainage margins | 1 | Item |  | 0
0
3.5.25 | irrigation system | 1 | Item |  | 0
| ________________________________________ |  |  |  | 0
0
3.5.26 | Allow for providing aftercare on the green roof system in Year 1; as specification clause Q37 - 1.2.5/C/xii (PROVISIONAL) | 1 | Item |  | 0
0
0
0
| 3.6 - ROOF ACCESSORIES |  |  |  | 0
0
| ALT-02: Lightning protection |  |  |  | 0
0
3.6.1 | Allow for reinstalling the existing lightning protection installation using the existing earth rod; as indicated on drawing LAB-687-DR-4015 | 1 | Item |  | 0
0
0
| ASE-01: Galvanised steel guarding |  |  |  | 0
0
3.6.2 | Allow for providing and installing, to the Eastern edge of the Southern roof, a new galvanised steel edge protection guardrail by High Access Solution Ltd; guardrail to be provided at 1m height above the roof level with support posts securely fixed to the primary timbers via steel plates; all as indicated on drawings LAB-687-DR-2141 & 2142 and Architect's specification clause N25 - 1.2.3 (ASE-01) | 1 | Item |  | 0
0
0
| ASE-02: Ladder installations |  |  |  | 0
0
3.6.3 | Allow for providing D ring wall anchor to the East elevation; anchor to be fixed to the triangular beam end at approximately 2m above the landing level; anchor to be used as tethering point for Client supplied ladder, in gaining access between the upper steel grille landing and lower roof level | 1 | Item |  | 0
0
3.6.4 | Allow for providing 4.5m long stowable aluminium ladder; ladder to be fixed to the underside of the eaves with galvanised steel proprietary hanging brackets and lockable cables ties; as indicated on drawings LAB-687-DR-2141 & 2142 and Architect's specification clause N25 - 1.2.4 (ASE-02) | 1 | Item |  | 0
0
0
| ASE-03: Existing fall arrest system |  |  |  | 0
0
3.6.5 | Allow for 'pull testing' the existing mansafe systems located on the Northern and Southern pitched roofs; provide written report to the Contract Administrator; as indicated on drawings LAB-687-DR-2141 & 2142 and Architect's specification clause N25 - 1.2.5 (ASE-03) | 1 | Item |  | 0
0
0
0
| 3.7 - MECHANICAL INSTALLATIONS |  |  |  | 0
0
3.7.1 | Allow for retaining the existing UPVC water pipe that currently terminates the foot of one of the Northern roof wind towers; allow for all necessary adaptation works to the pipework to enable it to serve the new green roof irrigation system inclusive of extending the pipework to the Southern roof; as indicated on drawings LAB-687-DR-2141 & 2142 | 1 | Item |  | 0
0
0
0
0
SECTION No. 3 - WORK TO THE MAIN ROOF
|  |  |  | To Summary £ | 10000

## SECTION No. 4
HORNIMAN MUSEUM
100 LONDON ROAD, FOREST HILL, LONDON, SE23 3PQ
CUE BUILDING - REPAIR AND RE-ROOFING WORKS
= Contractor to insert pricing
SECTION No. 4
WORK TO THE FRONT BALCONY (ALL PROVISIONAL)
£ p
4.0.1 | In pricing the items that follow, the Contractor shall be deemed to have thoroughly inspected the tender documents and have acquainted himself with the site and the full extent / character of the items. The items have been split into the following priceable areas of work: | 0 | 0 | 0 | 0
4.1 - Demolition work
4.2 - Substructure works
4.3 - Superstructure work
4.0.2 | The Contractor is requested to price and submit this document electronically. In the event that the Contractor elects not to submit the tender electronically then it is requested, for ease of checking, that each printed page is individually totalled and carried forward to a summary. | 0 | 0 | 0 | 0
0
| 4.1 - DEMOLITION WORKS |  |  |  | 0
0
4.1.1 | Allow for demolishing the existing balcony structure that is located on the South elevation of the Cue Building; as indicated on drawings LAB-687-DR-0111, 0120 and SK-03; scope to include the following: |  |  |  | 0
| [1] upright posts and horizontal timbers fixed thereto |  |  |  | 0
| [2] Balustrading |  |  |  | 0
| [3] Floor deck and joists under |  |  |  | 0
| [4] Secondary floor beams - part only; section next to the building to be retained for subsequent re-use | 1 | Item |  | 0
0
0
0
| 4.2 - SUBSTRUCTURE WORK |  |  |  | 0
0
| Allow for the following in forming the substructure elements to the new balcony structure; as indicated on drawings LAB-687-DR-6001, 6002, 6004 and structural Engineer's drawing 230237-CON-X-XX-DR-S-0001; scope to include the following: |  |  |  | 0
0
4.2.1 | 3No - 600 x 600 x 500mm deep mass in situ concrete pad base foundations | 1 | Item |  | 0
0
4.2.2 | extra for forming 300mm depth of compacted type 1 granular fill / hardcore sub-base beneath the new pad bases if deemed required by the Structural Engineer | 1 | Item |  | 0
0
4.2.3 | 3No - Simpson Strongtie Pisbmaxi galvanised post base stand with stand off; include for bolting to the new foundation and for grouting under base plate with non-shrink grout | 1 | Item |  | 0
0
0
0
| 4.3 - SUPERSTRUCTURE WORK |  |  |  | 0
0
| Allow for the following in forming the superstructure elements to the new balcony structure; as indicated on drawings LAB-687-DR-6001, 6002, 6003, 6004, 6014, 6015, 6016, 6017, 6041, 6051, 6052, 6053, 6061, 6062, 6063 & SK-03 and structural Engineer's drawing 230237-CON-X-XX-DR-S-0001, 002 & 003; scope to include the following: |  |  |  | 0
0
4.3.1 | 3No - 150 x 150mm C24 timber columns; column bolted to post stand at base and column cap at head; as detail 1 on 230237-CON-X-XX-DR-S-0001 | 1 | Item |  | 0
0
4.3.2 | 3No - Simpson Strongtie galvanised column caps; part code: E CCQ; as detail 1 on 230237-CON-X-XX-DR-S-0001 | 1 | Item |  | 0
0
4.3.3 | primary timber beam set mounted on the column caps; beam to comprise 3No 75 x 225mm C24 timbers bolted together; as detail 1 on 230237-CON-X-XX-DR-S-0001 | 1 | Item |  | 0
0
4.3.4 | 6No - "Rafter A" secondary beams - referenced "RA's" on drawings LAB-687-SK-03; each beam to comprise 2No 50 x 225mm C24 timbers with 3No sets of plywood packers between; timbers to be bolted together at packer locations; where the new secondary beam abuts the existing retained beam allow for forming a scarf joint and for installing a 10 x 200 x 450mm steel plate each side; as details 2 - 3 on 230237-CON-X-XX-DR-S-0002 | 1 | Item |  | 0
0
4.3.5 | extra for installing 8mm thick inverted tee bracket between the RA secondary beam and the primary timber beam; bracket to be secured with M12 coach screws - minimum embedment of 100mm; as details 2 - 3 on 230237-CON-X-XX-DR-S-0002 | 1 | Item |  | 0
0
4.3.6 | 12No - "Rafter B" secondary beams - referenced "RB's" on drawings LAB-687-SK-03; each beam to comprise 2No 50 x 225mm C24 timbers with 3No sets of plywood packers between; timbers to be bolted together at packer locations; where the new secondary beam abuts the existing retained beam allow for forming a scarf joint and for installing a 10 x 200 x 450mm steel plate each side; as details 2 - 3 on 230237-CON-X-XX-DR-S-0002 | 1 | Item |  | 0
0
4.3.7 | extra for installing 8mm thick inverted tee bracket between the RB secondary beam and the primary timber beam; bracket to be secured with M12 coach screws - minimum embedment of 100mm; as details 2 - 3 on 230237-CON-X-XX-DR-S-0002 | 1 | Item |  | 0
0
4.3.8 | 5No - 50 x 205mm timber joists; joists secured to rafters "RA" and "RB" | 1 | Item |  | 0
0
4.3.9 | 19 x 140mm approved treated softwood external decking | 1 | Item |  | 0
0
4.3.10 | extra for perimeter board (next building) scribed to suit the elevational alignment; as indicated on drawings LAB-687-DR-6001 | 1 | Item |  | 0
0
4.3.11 | 12No - 50 x 100mm treated timber upright posts; in connecting rafters (RA's) to the eaves | 1 | Item |  | 0
0
4.3.12 | vertical balustrading to 2No sides of the balcony; comprising: 50 x 150mm bottom rail, 24 x 50mm balusters at 50mm spacings, solid infill panels at balustrade ends / external corner and 50 x 150mm top rail | 1 | Item |  | 0
0
4.3.13 | 5No - lines of 24 x 50mm horizontal timbers; fixed at high level to the main vertical upright posts in forming feature just below eaves level | 1 | Item |  | 0
0
0
| Weatherproofing |  |  |  | 0
0
4.3.14 | Allow for sealing all exposed surfaces of the new timbers with matt transparent weather sealer | 1 | Item |  | 0
0
0
0
0
SECTION No. 4 - WORK TO THE FRONT BALCONY (ALL PROVISIONAL)
|  |  |  | To Summary £ | 0

## SECTION No. 5
HORNIMAN MUSEUM
100 LONDON ROAD, FOREST HILL, LONDON, SE23 3PQ
CUE BUILDING - REPAIR AND RE-ROOFING WORKS
SECTION No. 5 |  |  | = Contractor to insert pricing
DAYWORKS
£ p
5.01 | In the event of the Contract Administrator ordering in writing the work to be executed on a daywork basis, the rate of payment is to be as quoted by the Contractor below. |  | 0 | 0 | 0 | 0
5.02 | All sheets are to be consecutively numbered and are to give full details of the following:- the references of the Architect’s authority to carry out the work, the work executed, the date, or dates, of carrying out the work, each day being shown separately where more than one day’s work is required, the name and trade of the workpersons employed on the work, the rates of labour (as entered below), full details of materials and plant giving quantities and cost in accordance with supporting invoices, and the percentage additions on material and plant (as entered below). The sheets are to be signed by the Contractor’s foreman or authorised representative, and submitted to the Architect fully priced for his agreement and signature, within 7 days of the work being completed. |  | 0 | 0 | 0 | 0
Labour
5.03 | The hours worked on daywork shall be the hours actually worked on the operation listed on the sheet, and shall exclude time spent travelling to and from the works and meal breaks.
The Contractor shall quote below the rate he requires for payment of labour.
The rate quoted is to be an inclusive rate covering all charges including:-
(a) Wages and all labour on-costs as described in the Preliminaries
(b) All charges in respect of non-productive overtime
(c) All charges in respect of site and office supervision including foreman’s time and extra charges paid to leading or foreman craftsmen and gangers. Charges for general foreman cannot be included on daywork
(d) All overhead charges such as rent, rates, insurances, heating, water, printing, stationery, postage, telephone charges, motor car expenses, fares, transport charges, office repairs, renewals, maintenance and depreciation of premises, machinery, plant, etc.
| (e) Profit |  | 0 | 0 | 0 | 0
Labour within normal working hours:
5.04 | Hours worked between 8.00 a.m. and 6.00 p.m. Monday to Friday (inclusive) excluding meal breaks.
| 1 - Electrician | Rate per hour = |  |  |  | 0
| 2 - Plumber | Rate per hour = |  |  |  | 0
| 3 - Labourer | Rate per hour = |  |  |  | 0
| 4 - Tiler | Rate per hour = |  |  |  | 0
| 5 - Metalworker | Rate per hour = |  |  |  | 0
| 6 - Glazier | Rate per hour = |  |  |  | 0
| 7 - Decorator | Rate per hour = |  |  |  | 0
Labour outside of normal working hours:
In the event work is instructed outside of normal working hours the Contractor is to quote below his percentage mark-up values on the above rates:
5.05 | Hours worked between 6.00 p.m. and 8.00 a.m. Monday to Thursday (inclusive) and between 6.00 p.m. and 12.00 midnight Friday excluding meal breaks. | % uplift = |  |  |  | 0
5.06 | Hours worked between 00.01 a.m. and 12.00 midnight excluding meal breaks. | % uplift = |  |  |  | 0
5.07 | Hours worked between 00.01 a.m. and 8.00 a.m. the following Monday excluding meal breaks. | % uplift = |  |  |  | 0
5.08 | Hours worked between 00.01 a.m. and 12.00 midnight excluding meal breaks. | % uplift = |  |  |  | 0
Materials
5.09 | The Contractor is to quote here the percentage to be added to the nett invoice cost of materials to cover his supervision, overheads and profit. | % uplift = |  |  |  | 0
Plant
5.1 | The Contractor is to quote here the percentage to be added to the nett invoice cost of hire of plant to cover his supervision, overheads and profit. | % uplift = |  |  |  | 0

## SECTION No. 6
HORNIMAN MUSEUM
100 LONDON ROAD, FOREST HILL, LONDON, SE23 3PQ
CUE BUILDING - REPAIR AND RE-ROOFING WORKS
SECTION No. 6 |  | = Contractor to insert pricing
SCHEDULE OF FIXED RATE CHARGES FOR POSSIBLE ADDITIONAL WORKS
£ p
Generally
6.1.1 | The Contractor is requested to price the following items of work which will serve as a basis of valuation in the event that additional works over and above that specified in Section 3 & 4 is instructed. |  | 0
Resin repairs to timber
Carefully remove defective timber and undertake a 2 Pack epoxy resin repair; as Landolt + Brown "Architectural Specification"
6.1.2 | to area of decayed timber; decay less than 50mm in diameter | Rate per item =
Replacement of damaged timbers
Allow for the replacement of damaged timbers to the main roof decks; as indicated on LAB-687-DR-4011 - 4016; include for: removal of components to gain access, cutting out rotten wood, insertion of new timber to match existing and reinstatement all work disturbed
6.1.3 | existing 20mm thick WBP plywood roof deck panel | Rate per m2 =
Allow for the replacement of damaged timbers to the lower eaves of the Northern pitch; as indicated on LAB-687-DR-4011; include for: removal of components to gain access, cutting out rotten wood, insertion of new timber to match existing and reinstatement all work disturbed
6.1.4 | replacement of existing 20mm thick WBP plywood soffit panel; width approximately 550mm | Rate per m =
6.1.5 | replacement of existing 75 x 75mm fascia | Rate per m =
6.1.6 | replacement of existing 50 x 75mm rafter; length not exceeding 0.50m; joint to existing | Rate per item =
6.1.7 | replacement of existing 75 x 175mm fascia | Rate per m =
Allow for the replacement of damaged timbers to the Eastern / Western edges of the North and South pitches; as indicated on LAB-687-DR-4013; include for: removal of components to gain access, cutting out rotten wood, insertion of new timber to match existing and reinstatement all work disturbed
6.1.8 | replacement of existing 20mm thick WBP plywood soffit panel; width approximately 800mm | Rate per m =
6.1.9 | replacement of existing 20mm thick WBP plywood bargeboard; width approximately 420mm | Rate per m =
Allow for the replacement of damaged timbers to the upper eaves of the Northern pitch; as indicated on LAB-687-DR-4015; include for: removal of components to gain access, cutting out rotten wood, insertion of new timber to match existing and reinstatement all work disturbed
6.1.10 | replacement of existing 75 x 175mm fascia | Rate per m =
6.1.11 | replacement of existing 20mm thick WBP plywood soffit panel | Rate per m2 =
Allow for the replacement of damaged timbers to the lower eaves of the Northern pitch; as indicated on LAB-687-DR-4011; include for: removal of components to gain access, cutting out rotten wood, insertion of new timber to match existing and reinstatement all work disturbed
6.1.12 | replacement of existing 20mm thick WBP plywood soffit panel | Rate per m2 =
6.1.13 | replacement of existing 50 x 75mm rafter; length not exceeding 0.50m; joint to existing | Rate per item =
6.1.14 | replacement of existing 75 x 75mm fascia | Rate per m =

## SUMMARY
.
HORNIMAN MUSEUM
100 LONDON ROAD, FOREST HILL, LONDON, SE23 3PQ
CUE BUILDING - REPAIR AND RE-ROOFING WORKS
SUMMARY
£ p
| Section No. 1 | - | Conditions of Contract / Preliminaries |  | 0
| Section No. 2 | - | Temporary access / Survey |  | 0
| Section No. 3 | - | Work to the main roof |  | 10000
| Section No. 4 | - | Work to the front balcony (All Provisional) |  | 0
| Section No. 5 | - | Dayworks |  | 0
| Section No. 6 | - | Schedule of fixed rate charges for possible repair works |  | 0
|  |  |  | Sub-total £ | 10000
| - |  | Provide the Provisional sum of £10,000.00 for contingencies |  | 10000
|  |  |  | TOTAL £ | 20000
Name of Contractor:
Address:
Date: