## Sheet1
Brief |  |  | Issue No. |  | Page 1 of 2
Establishment: | Highways England |  | Date: | 2018-04-15
Project Title: | Smart Motorway programme Rapid Engineering Modelling (REM) version 2 |  | BPRN:
Region:
Principal Project Sponsor: |  | Shaun Pidcock
Senior Project Sponsor: |  | Lorraine Butler
Service Providers to be Appointed: |  | Design
Specify services
Cost Model Ref
Consultancy Services Start Date |  | 2018-08-01
Description Of The Project:
Background Rapid Engineering Model ver 1 (to SGAR 1) Highways England are currently working to integrate various strands of innovation to develop new methods of ‘Rapid Engineering’. The team are developing a data driven approach to design that will ultimately allow the rapid creation of data rich BIM models at much earlier project stages that can also generate a range of performance based outputs. The method comprises two distinct stages; 1. Survey data analysis 2. Parametric design, using smart BIM objects It starts with basic survey information - essentially centre line and topography data – to generate analyses of gradient, curvature, embankment, traffic information and environmental conditions. The analysis is carried out within a BIM platform and outputs both ‘BIM ready’ 3D content for use in federated design models, and GIS ready’ 2D content for use in the current HE GIS platform. The second stage of the work flow takes this analysis and uses it to drive a parametric modelling system – again with the BIM platform – that can automatically generate a 3D model that could include major road side assembly items such as gantries, and Emergency Refige Areas, across the full extent of the project. The parametric modelling system uses the HE digital component library – updated to reflect the ongoing development in modular assembly design. As part of this work we are creating new parametric ‘exemplar’ assembly models for the modular gantry and the ERAs. These are being developed for use in proprietary software and disemenation via open BIM standards. The assembly models are being developed with extensive meta-data, as well as geometry, that will integrate with ongoing work of the AIG. So that they may be used in immersive digital environments such as VR/AR. The outputs of this work, which will contribute to the ongoing efforts in modular design and HE BIM requirements, will be; - A documented (and demonstrable) work flow for creating contextual analysis from survey information - A documented (and demonstrable) parametric system to create ‘rapid engineering’ models for early stage design - Updates to the digitnal components library to reflect the modular design developments of ERAs and Gantries - Changes to the EIR to embed these new practices with projects The key aims of the Rapid Engineering Modelling Ver 2 ( to SGAR3/5) is to deliver greater and more efficient project level designs though: • Highways England taking greater control of standardised modular design development • Combined Driven/Drone based Surveying to create an accurate Digital Terrain Map Based asset platform • Rules Based Approach to Design Development derived from the principles demonstrated through the Ops Concept works • Reduction in the level of bespoke design resulting in increased costs due to varied design solutions in construction • Increased safety through greater level of consistency of working practises, methods and procedures. REM 2.0 - SGAR 3 - functionality will include but is not limited to : Development, translation and configuration of the REM 1 application(s) and system(s) • The Integration of the REM application and systems with other required systems including SMP GIS, Tableau, ARVR, Machine readable DMRB and ADMM. • Automatted design in the verge • Automated drainage design • Automated retaining wall design • Self-designing gantries • Bore hole data analysis • Alignment with the SES DMRB (computer readable) • Alignment with the AIG ADDM • Cost Estimation • Product documentation The development of REM 2.0 will be auditable against the DMRB, IAN161/18, the PCF single option process, The SMP Design Guide V3, The Survey Guide V3, ADDM V8.
Pre-Commencement Requirement:
With the key aims of REM in mind the pre-requisites for this project are; Computational Design skillset Highways Engineering knowledge experience in computer coding using Python scripts Experience in the use of Rhino and Grasshopper applications Algorithmic Design + Simulation - Rules based design automation for linear infrastructure. - Rules based design analytics for linear infrastructure. - Use of visual/ node-based programming environments within 3D/ BIM modelling software (e.g Rhino + Grasshopper, Revit + Dynamo). - Creation of custom nodes within visual programming environments using python and/ or C#. - Creation and management of custom desktop applications using C#. - Read/ write connectivity with cloud hosted NoSQL database technologies from within node-based programming environments. - Creation and management of parametric BIM component libraries, for use in automated BIM workflows. - Creation of ‘drive through’ model and data visualisations/ animations. Connected Technologies - Management of NoSQL database technologies (e.g. MongoDB). - Read/ write connectivity with cloud hosted NoSQL database technologies (e.g. MongoDB). Interaction and configuration - Creation of custom, interactive applications - across VR/ AR, Web and mobile platforms - using Unity and C#. - Workflows for integrating geometry and data from multiple sources within custom applications (e.g. JSON). - Creation of visualisations/ interactive environments using both geometric and data content. - Read/ write connectivity with cloud hosted NoSQL database technologies from within custom applications. Modelling and Analytics - Creation of cloud-hosted, interactive data visualisations and dashboards (e.g. Tableau), including charts and maps. - Management of large data sets (e.g. within NoSQL cloud database technologies). Spatial + Big Data - Customisation of open source, desktop GIS platforms (e.g. QGIS + python). - Management of all GIS file formats. - Read/ write connectivity with cloud hosted NoSQL database technologies from within GIS platforms.
Phasing Requirement:
The development of REM V2.0 will followed a structured approach based on the commonly known Technology Readiness Levels (TRLs), these levels have been refined to speak specifically to the requirements of the Highways industry using relevant terminology, this is better known as Product Maturity Levels (PMLs). The PMLs are also aligned to the 4Ds Phases of Discover, Develop, Demonstrate and Deliver. This package of works will commence at at PML 2 (Product concept and/or application is formulated. Output requirements developed) through to PML 7 (Prototype Product's validation testing completed as a part of a wider system on UK Highway infrastructure) in this case the Rapid Engineering Model V2.0 is to be tested on a number of scheme digital models (circa 3 schemes from Tranche 6). Each PML will, as a minimum, have a ‘Red’ review (6 total) will take place at each PML gate to ensure the functional aspects of the tool development align to the outcomes of the previous stage. At the end of each of the 4Ds there will be a Pink (3 in total). Each review will have a review/comment/approve cycle. The success of this development work and testing, will determine the need to extend this work package through to PML 8 (Actual Product ready for integration into a wider system on UK Highway infrastructure) and 9 (Actual Product is successfully integrated and tested as a part of wider system on UK Highway infrastructure). The PML definitions and how they align with the 4Ds phases are attached in Annex G.
Note on H1: To be completed by person requesting service.
Note on H2: To be inserted by person requesting service.
Note on A11: Refer to Cost model Guidance before selecting. To be entered by person requesting service.