## COVER PAGE
SCHEDULES OF WORK
(REVISION A)
-in respect of-
BUTTERFLY HOUSE
DUTY / STANDBY HEATER PROJECT
-at-
100 LONDON ROAD, FOREST HILL, LONDON, SE23 3PQ
-for-
THE HORNIMAN PUBLIC MUSEUM &
PUBLIC PARK TRUST
Chartered Quantity Surveyors
Unit 83, Capital Business Centre
22 Carlton Road
South Croydon
November 2022 |  | Surrey, CR2 0BS

## CONTENTS
Schedules of Work
(Revision A)
-in respect of-
Butterfly House
Duty / Standby Heater Project
-at-
100 London Road, Forest Hill, London, SE23 3PQ
-for-
The Horniman Public Museum &
Public Park Trust
- comprising -
Section No. 1 | - | Conditions of Contract / Preliminaries
Section No. 2 | - | Work to the Butterfly House
Section No. 3 | - | Provisional work to areas outside the Butterfly House
Section No. 4 | - | Errata No. 1
Summary
Appendix A | - | Detailed terms of the Conditions of Contract
Appendix B | - | Detailed terms of the Preliminaries

## SECTION No. 1
HORNIMAN MUSEUM
100 LONDON ROAD, FOREST HILL, LONDON, SE23 3PQ
BUTTERFLY HOUSE - DUTY / STANDBY HEATER PROJECT
SECTION No. 1
CONDITIONS OF CONTRACT / PRELIMINARIES
£ p
Following review of Appendix "A" and Appendix "B" the Contractor is to insert below his proposed costs in respect of the "Conditions of Contract" and "Preliminaries". In the event that no specific allowance is stated below the Contractor will be deemed to have covered elsewhere within the body of the pricing for the cost of fully complying with the terms detailed in Appendix "A" and "B".
1.01
1.02
1.03
1.04
1.05
1.06
1.07
1.08
1.09
1.1
1.11
1.12
1.13
1.14
1.15
SECTION No. 1 - CONDITIONS OF CONTRACT / PRELIMINARIES
|  |  | To Summary £ | 0

## SECTION No. 2
HORNIMAN MUSEUM
100 LONDON ROAD, FOREST HILL, LONDON, SE23 3PQ
BUTTERFLY HOUSE - DUTY / STANDBY HEATER PROJECT
= Contractor to insert pricing
SECTION No. 2
WORK TO THE BUTTERFLY HOUSE
£ p
2.0.1 | In pricing the items that follow, the Contractor shall be deemed to have thoroughly inspected the tender documents and have acquainted himself with the site and the full extent / character of the items. The items have been split into the following priceable areas of work: | 0 | 0 | 0 | 0
2.1 - Temporary access
2.2 - Temporary screens / hoardings
2.3 - Structural works
2.4 - Mechanical works
2.5 - Electrical works
2.6 - Builder's work in connection with the M&E works
2.0.2 | The Contractor is requested to price and submit this document electronically. In the event that the Contractor elects not to submit the tender electronically then it is requested, for ease of checking, that each printed page is individually totalled and carried forward to a summary. | 0 | 0 | 0 | 0
0
| 2.1 - TEMPORARY ACCESS |  |  |  | 0
0
2.1.1 | Allow for providing all necessary temporary access in completing the works so described in this document. In providing access the Contractor is to take due regard that the existing butterflys and vegetation are to remain within the building through the duration of the works, accordingly the Contractor is to take all reasonable steps to ensure no damage is occassioned to them. | 1 | Item |  | 0
0
0
0
| 2.2 - TEMPORARY SCREENS / HOARDINGS |  |  |  | 0
0
2.2.1 | Allow for providing all necessary temporary screens / hoarding throughout the course of the works. The installations are to be sufficient such that the temperature within the butterfly house is maintained at all times and also so that butterflies do not escape arising out of the Contractor's ingress / egress. | 1 | Item |  | 0
0
| 2.3 - STRUCTURAL WORKS |  |  |  | 0
0
2.3.1 | Note: In pricing the items of structural steelwork below the Contractor is to note that the steelwork connections are to form a Contractor Designed Portion of the works; as indicated on drawings 310045-HAH-XX-XX-SK-S-001, 310045-HAH-XX-XX-SK-S-002 and 310045-HAH-XX-XX-SK-S-002 | 0 | 0 | 0 | 0
0
| Allow for the following items of steel framing associated with installing the new AHU installation; in pricing allow for: all new steel columns / beams / PFC's / angles / plates / steelwork fixings etc.; all as indicated on drawings 310045-HAH-XX-XX-SK-S-001, 310045-HAH-XX-XX-SK-S-002, 308468-HAH-XX-XX-DR-S-999 and Harley Haddow's steelwork and preliminary specifications |  |  |  | 0
0
2.3.2 | steel framework in supporting the new AHU plant (located within previous office); frame to formed using 40 x 4 SHS verticals, 100 x 50 x 10 PFC horizontals and 50 x 5mm steel flats for bracing; steels to be finished with two coats of shop applied epoxy zince phosphate primer followed by one coat of shop applied epoxy micaceous iron oxide, touched up on site with epoxy wet iron oxide | 1 | Item |  | 0
0
2.3.3 | extra for 'bigfoot' support feet (NB a minimum of 10No feet sized 600 x 600mm are are to be supplied) | 1 | Item |  | 0
0
2.3.4 | all steelwork located within grid lines B to C for the support of the air handling ductwork; beam refs B1 and B2; steels to be hot-dip galvanised | 1 | Item |  | 0
0
2.3.5 | extra for structural support systems to the new 250mm ductwork along grid lines C, D & E; all as indicated on Detail D on drawing 310045-HAH-XX-XX-SK-S-002 | 1 | Item |  | 0
0
0
0
| 2.4 - MECHANICAL WORKS |  |  |  | 0
0
| Allow for the following mechanical works within the Butterfly House; all as indicated on HH mechanical drawings (5No), the mechanical services equipment schedules and within the "Mechanical Services Specification": |  |  |  | 0
0
2.4.1 | Incoming water supply; as specification clause 55-40-40/110 | 1 | Item |  | 0
0
2.4.2 | Natural Gas Supply System; as specification clause 55-60-55/120 | 1 | Item |  | 0
0
2.4.3 | Mechanical Ventilation Systems; as specification 65-110-95/130 | 1 | Item |  | 0
0
2.4.4 | Mechanical Services Control; as specification 75-75-50/120 |  |  |  | 0
0
2.4.5 | Above-ground internal stack wastewater drainage systems; as specification Ss_50_30_04_97 | 1 | Item |  | 0
0
2.4.6 | Engineering Services Survey; as specification clause 10-20-75/110 | 1 | Item |  | 0
0
2.4.7 | Demolition System - during the course of the main works; as specification 65-110-95/130 | 1 | Item |  | 0
0
2.4.8 | Demolition System - at the end of the rectification period (Powrmatic gas-fired heater removal); as specification 65-110-95/130 | 1 | Item |  | 0
0
| _______________________________________ |  |  |  | 0
0
2.4.9 | Preliminaries / working drawings / loading calculations, etc. | 1 | Item |  | 0
0
2.4.10 | Testing and commissioning | 1 | Item |  | 0
0
2.4.11 | O&M manuals and as fitted drawings | 1 | Item |  | 0
0
| _______________________________________ |  |  |  | 0
0
| The Contractor is requested to insert below the details / costs of any additional items which are not covered by the headings of cost above but are deemed necessary in complying with the information provided on the drawings / specifications: |  |  |  | 0
0
2.4.12 |  | 1 | Item |  | 0
0
2.4.13 |  | 1 | Item |  | 0
0
2.4.14 |  | 1 | Item |  | 0
0
2.4.15 |  | 1 | Item |  | 0
0
2.4.16 |  | 1 | Item |  | 0
0
2.4.17 |  | 1 | Item |  | 0
0
2.4.18 |  | 1 | Item |  | 0
0
2.4.19 |  | 1 | Item |  | 0
0
2.4.20 |  | 1 | Item |  | 0
0
2.4.21 |  | 1 | Item |  | 0
0
0
0
| 2.5 - ELECTRICAL WORKS |  |  |  | 0
0
| Allow for the following electrical works within the Butterfly House; all as indicated on HH electrical drawing 309239-HAH-XX-XX-DR-E-06010 and within the "Electrical Services Specification": |  |  |  | 0
0
2.5.1 | Validation of all existing circuits prior to carrying out the works | 1 | Item
2.5.2 | Low-voltage site connection systems; as specification Ss_70_30_45_40 | 1 | Item |  | 0
0
| Low-voltage distribution systems; as specification Ss_70_30_45_45; include for: protective devices, sub-main cabling, primary containment and secondary containment; the scope of works is to include the following, as defined by HH: |  |  |  | 0
0
2.5.3 | Works Within Enclosure 1: "The existing DB1 supply, located within the SP&N distribution board in the enclosure is to be isolated and relocated to the panel board within enclosure 2. The existing MCB to be stripped out. The existing submains cable is to be cut to size (to suit shorter route from the Panel board)." | 1 | Item |  | 0
0
2.5.4 | Works Within Enclosure 2: "1 no. Single Phase Way on the existing Panel board shall be utilised to feed 'DB1'. A 100A SP&N MCCB shall be installed for protection. The existing submains cable shall be cut to size and reused for this feed, as noted in previous section." + "1 no. 3 Phase Way shall be utilised within the Panel board to feed the proposed 125A isolator in The Butterfly House for back up heater battery. A 125A TP&N MCCB shall be installed for protection. The cable proposed for the feed is a 35mm2 4 core XPLE/SWA cable." | 1 | Item |  | 0
0
2.5.5 | Alterations to Existing DBGEN "As mentioned previously, 'DBGEN' is located internally adjacent 'DB1'. 3No. additional circuits shall be installed within this board for Air Handling Unit Isolator, Mechanical Control Panel, Gas Safety Panel. Refer to the Electrical Services Drawing for breaker and cable types/sizes." | 1 | Item |  | 0
2.5.6 | extra over for completing the following works at the at the end of the rectification period: "The existing mechanical heater supply is to be isolated and stripped out if no longer required." | 1 | Item
0
2.5.7 | Hardwired low-voltage small power systems; as specification Ss_70_30_80_35 | 1 | Item |  | 0
0
2.5.8 | Fire detection and alarm systems; as specification Ss_75_50_28_29 | 1 | Item |  | 0
0
2.5.9 | Fire stopping; as specification Ss_25_60_30_40 and Ss_25_60_30_55 | 1 | Item |  | 0
0
2.5.10 | Earthing and bonding; as specification Ss_25_60_30_55 | 1 | Item |  | 0
0
| _______________________________________ |  |  |  | 0
0
2.5.11 | Preliminaries / working drawings / loading calculations, etc. | 1 | Item |  | 0
0
2.5.12 | Testing and commissioning | 1 | Item |  | 0
0
2.5.13 | O&M manuals and as fitted drawings | 1 | Item |  | 0
0
| _______________________________________ |  |  |  | 0
0
| The Contractor is requested to insert below the details / costs of any additional items which are not covered by the headings of cost above but are deemed necessary in complying with the information provided on the drawings / specifications: |  |  |  | 0
0
2.5.14 |  | 1 | Item |  | 0
0
2.5.16 |  | 1 | Item |  | 0
0
2.5.17 |  | 1 | Item |  | 0
0
2.5.18 |  | 1 | Item |  | 0
0
2.5.19 |  | 1 | Item |  | 0
0
2.5.20 |  | 1 | Item |  | 0
0
2.5.21 |  | 1 | Item |  | 0
0
2.5.22 |  | 1 | Item |  | 0
0
2.5.23 |  | 1 | Item |  | 0
0
2.5.24 |  | 1 | Item |  | 0
0
0
0
| 2.6 - BUILDER'S WORK IN CONNECTION WITH THE M&E WORKS |  |  |  | 0
0
| Cut or form all holes, mortices, sinkings and chases through the structure, coverings and finishings of the existing building and allow for all other above ground builders work in connection to the new Mechanical and Electrical Installations. In addition allow for sealing any pentrations or openings that are caused to the structure in a style to match existing. |  |  |  | 0
0
2.6.1 | BWIC associated with the installation of the new systems | 1 | Item |  | 0
0
2.6.2 | BWIC associated with the removal of the existing Powrmatic gas-fired heater at the end of the rectification period | 1 | Item |  | 0
2.6.3 | BWIC associated with the removal of the existing water recirculation system, standpipes and supply to the misting system | 1 | Item
0
0
0
SECTION No. 2 - WORK AT THE BUTTERFLY HOUSE
|  |  |  | To Summary £ | 0

## SECTION No. 3
HORNIMAN MUSEUM
100 LONDON ROAD, FOREST HILL, LONDON, SE23 3PQ
BUTTERFLY HOUSE - DUTY / STANDBY HEATER PROJECT
= Contractor to insert pricing
SECTION No. 3
PROVISIONAL WORK TO AREAS OUTSIDE THE BUTTERFLY HOUSE
£ p
3.0.1 | In pricing the items that follow, the Contractor shall be deemed to have thoroughly inspected the tender documents and have acquainted himself with the site and the full extent / character of the items. The items have been split into the following priceable areas of work: | 0 | 0 | 0 | 0
3.1 - External timber shed
3.2 - AHU works within Plant Room 3
3.0.2 | The Contractor is requested to price and submit this document electronically. In the event that the Contractor elects not to submit the tender electronically then it is requested, for ease of checking, that each printed page is individually totalled and carried forward to a summary. | 0 | 0 | 0 | 0
3.0.3 | The works measured in this Section of the document relate to possible additional works which may be instructed by the Museum. Prior to the works commencing the Contract Administrator will confirm the scope to be undertaken in a formal Contract Administrator's Instruction. | 0 | 0 | 0 | 0
0
| 3.1 - EXTERNAL TIMBER SHED |  |  |  | 0
0
3.1.1 | Note: The proposed location of the new shed is still to be decided but it will probably be sited in the animal walk, next to the Butterfly house | 0 | 0 | 0 | 0
0
0
3.1.2 | Provide the P.C. Sum of £1,020.30 for the supply of a new timber shed (details as per the weblink below) | 1 | Item | 1020.3 | 1020.3
0
- | https://www.diy.com/departments/10-x-3-pressure-treated-tongue-and-groove-pent-wooden-shed-with-double-doors-10-x-3-10ft-x-3ft-10x3-/0600736070904_BQ.prd | 0 | 0 | 0 | 0
0
0
3.1.3 | Add: for overheads and profit on the nett invoice cost | 1 | Item |  | 0
0
3.1.4 | Allow for all costs in connection with constructing the new timber shed and for installing it on a new concrete base (base measured separately) | 1 | Item |  | 0
0
| Provisional sums |  |  |  | 0
0
3.1.5 | Provide the Provisional Sum of £1,500.00 for the construction of a new insitu concrete base for the shed | 1 | Item | 1500 | 1500
0
0
0
| 3.2 - AHU WORKS WITHIN PLANT ROOM 3 |  |  |  | 0
0
3.2.1 | Note: The works under this heading relate to works within the main museum buildings not the plant room within the Butterfly House those works are included under sections 2.3 and 2.4 | 0 | 0 | 0 | 0
0
0
3.2.2 | Note: The detailed scope of works of the AHU works within Plant Room 3 is still being defined. However the scope of works is likely to include the following to 2No AHU's that serve the Music and Temp Galleries: |  |  |  | 0
0
| 1) Isolate, disconnect and remove the existing ultrasonic humidifier installation including electrical, water and duct work connections |  |  |  | 0
| 2) Safely isolate and retain the electrical and control connections associated with the removed humidifier arrangement |  |  |  | 0
| 3) Supply and install new steam humidifier arrangement within the music hall supply ductwork arrangement complete with new duct section incorporating drain, lance connection and associated supports etc. |  |  |  | 0
| 4) Re-configure as necessary the controls, power, and water connection to the new humidifier arrangement |  |  |  | 0
| 5) Commission the new humidifier arrangement including complete and demonstration of the control’s operation | 0 | 0 | 0 | 0
0
0
| Provisional sums |  |  |  | 0
0
3.2.3 | Provide the Provisional Sum of £30,0000.00 for AHU works within plant room 3 | 1 | Item | 30000 | 30000
0
0
0
0
SECTION No. 3 - PROVISIONAL WORK TO OTHER AREAS
|  |  |  | To Summary £ | 32520.3

## SECTION No. 4
HORNIMAN MUSEUM
100 LONDON ROAD, FOREST HILL, LONDON, SE23 3PQ
BUTTERFLY HOUSE - DUTY / STANDBY HEATER PROJECT
= Contractor to insert pricing
SECTION No. 4
ERRATA No. 1
£ p
4.0.1 | In pricing the items that follow, the Contractor shall be deemed to have thoroughly inspected the tender documents and have acquainted himself with the site and the full extent / character of the items. The items have been split into the following priceable areas of work: | 0 | 0 | 0 | 0
4.1 - Additional electrical works
4.0.2 | This Erratta document has been based on the following additional information issued by Harley Haddow:
| 309239-HAH-XX-XX-DR-E-06010/T03 - Electrical Services Layout | 0 | 0 | 0 | 0
4.0.2 | The Contractor is requested to price and submit this document electronically. In the event that the Contractor elects not to submit the tender electronically then it is requested, for ease of checking, that each printed page is individually totalled and carried forward to a summary. | 0 | 0 | 0 | 0
0
| 4.1 - ADDITIONAL ELECTRICAL WORKS |  |  |  | 0
0
| Allow for the following addiitonal electrical works within the Butterfly House; all as indicated on HH electrical drawing 309239-HAH-XX-XX-DR-E-06010/T03: |  |  |  | 0
0
4.1.1 | Removal of existing submains cable | 1 | Item |  | 0
0
4.1.2 | 10A Three Phase Isolator for AHU (NB Changed from the 32A Single Phase Isolator previously specified) | 1 | Item |  | 0
0
4.1.3 | 6-Way TP&N Board (proposed to replace Existing Single Phase board ‘DB1’) | 1 | Item |  | 0
0
4.1.4 | 4-Way TP&N Board (proposed to replace Existing Single Phase Board ‘DBGEN’) | 1 | Item |  | 0
0
4.1.5 | 20kVA Three Phase Generator (proposed to replace existing Single Phase Generator) | 1 | Item |  | 0
0
4.1.6 | 25mm2 SWA Cable - 1No | 1 | Item |  | 0
0
4.1.7 | Automatic Transfer Switch - 1No (PROVISIONAL) | 1 | Item |  | 0
0
4.1.8 | 10A 3 Phase RCBO (NB Changed from the 32A Single Phase MCB for the AHU) | 1 | Item |  | 0
0
4.1.9 | 63A 3 Phase MCCB (NB Changed from 125A Single Phase MCCB at the panel board for DB1) | 1 | Item |  | 0
0
| _______________________________________ |  |  |  | 0
0
| The Contractor is requested to insert below the details / costs of any additional items which are not covered by the headings of cost above but are deemed necessary in complying with the information provided on the drawings / specifications: |  |  |  | 0
0
4.1.10 |  | 1 | Item |  | 0
0
4.1.11 |  | 1 | Item |  | 0
0
4.1.12 |  | 1 | Item |  | 0
0
4.1.13 |  | 1 | Item |  | 0
0
4.1.14 |  | 1 | Item |  | 0
0
0
0
0
SECTION No. 4 - ERRATA No. 1
|  |  |  | To Summary £ | 0

## SUMMARY
.
HORNIMAN MUSEUM
100 LONDON ROAD, FOREST HILL, LONDON, SE23 3PQ
BUTTERFLY HOUSE - DUTY / STANDBY HEATER PROJECT
SUMMARY
£ p
| Section No. 1 | - | Conditions of Contract / Preliminaries |  | 0
| Section No. 2 | - | Work to the Butterfly House |  | 0
| Section No. 3 | - | Provisional work to areas outside the Butterfly House |  | 32520.3
| Section No. 4 | - | Errata No. 1 |  | 0
|  |  |  | Sub-total £ | 32520.3
| - |  | Provide the Provisional sum of £5,000.00 for contingencies |  | 10000
|  |  |  | OPTION A - TOTAL £ | 42520.3 | #
Name of Contractor:
Address:
Date: