# Annex A

| Title of Project | Ocean Country Partnership Programme: Maldives Marine and Environmental Sector Career Mapping Case Studies |
| --- | --- |
| Date and Time for Return of Bids | Monday 16 September 2024 @ 16:00 hours UK GMT |
| Contract Reference Number | C24-0604-1935 |
| Address for Bid Submission | 1 electronic copy to be sent to TenderResponse@jncc.gov.uk PLEASE DO NOT SEND BIDS DIRECTLY TO JNCC PROJECT MANAGER OR PROCUREMENT VIA THEIR WORK EMAIL ADDRESSES AS THIS WILL INVALIDATE YOUR BID. Bids must be less than 10 MB in size. On receipt of your bid, you will receive an automated e-mail to confirm receipt by the JNCC Support Co. If you do not receive this automated email, please contact the number below: +44 1733 866988 |
| Contacts for Technical Information relating to this Project Specification | Joint Nature Conservation Committee Name: Beth Flavell Email: Beth.Flavell@jncc.gov.uk Phone: +44 (0) 7502 366559 |
| Contact for Queries Regarding the Procurement Procedure | Procurement Team Joint Nature Conservation Committee Email: contractqueries@jncc.gov.uk Telephone: 01733 866894 |
| Proposed Start Date | 30th September 2024 |
| Proposed End Date | 17th March 2025 |

## Joint Nature Conservation Committee

The Joint Nature Conservation Committee (JNCC) is the statutory adviser to the UK Government and devolved administrations on UK and international nature conservation

Our role is to provide scientific evidence, information, and advice to inform decisions to protect the natural environment. Our specific role is to work on nature conservation issues that affect the UK as a whole and internationally, by:

advising Government on the development and implementation of policies for, or affecting, nature conservation in the UK and internationally;

providing advice and disseminating knowledge on nature conservation issues affecting the UK and internationally;

establishing common standards throughout the UK for nature conservation, including monitoring, research, and the analysis of results; and

commissioning or supporting research which it deems relevant to these functions.

Background to JNCC can be found on JNCC’s website at: https://jncc.gov.uk/about-jncc/

## Project Aims

The Maldives is home to a rich environment, and biodiversity supports over 90% of Maldives GDP.  However, the Ministry of Climate Change, Environment and Energy often struggles to fill job vacancies, and Maldives National University often doesn’t have interest in their environmental courses.

This contract focuses on the development of a series of case studies mapping career pathways in the environmental sector in Maldives. The aim is to raise awareness of jobs in the environmental and marine sector in Maldives to encourage students to study environmental courses at Maldives National University. This in turn, aims to then support interest in suitably qualified staff applying for jobs in the sector across the country.

The main deliverable would be a digital leaflet providing the career case studies, focused on 8 job examples. Two versions of the leaflet will be provided, one in English and one in Dhivehi.

## Project Background

The Ocean Country Partnership Programme (OCPP) has been working in partnership with the Government of Maldives to explore opportunities to support effective management of their marine environment. The partnership is providing demand-led technical assistance around two key themes: marine biodiversity and marine pollution.

The Marine Biodiversity strand of the OCPP aims to:

- Increase understanding of the value of Marine Protected Areas (MPAs) in supporting sustainable livelihoods, food security, health and well-being;

- Increase understanding of MPA theory and practice, including evidence gathering, identification, selection, monitoring and assessment of MPAs;

- Increase support and compliance for MPAs with stakeholders; and

- Enhance capability and drive within countries to sustainably manager, monitor and assess conservation activities in the future.

More information on the OCPP programme, can be accessed via this link:: https://www.gov.uk/government/publications/blue-planet-fund/ocean-country-partnership-programme-ocpp.

The OCPP has also been working with Maldives National University to support sustainable human development with knowledge and skills on the development of an MPA short course, providing knowledge on best practice for MPA management. Increasing awareness with communication materials and the provision of training are complimentary activities in this program of support.

This contract is being delivered on behalf of the Government of Maldives Ministry of Climate Change, Environment and Energy (MCCEE) and Maldives National University (MNU).

## Project Objectives

To meet the overall aims of this project (Section 2), the objective is to develop a digital leaflet summarising career pathways into environmental jobs in Maldives.

## Project Objectives: Detailed Tasks

The Contractor will be required to:

Ensure regular communications with JNCC and MNU:

Organise and attend a project start-up meeting with JNCC and MNU as soon as possible after start date.

Organise and attend regular meetings with JNCC and MNU staff for the whole duration of the project (frequency to be decided at kick off).

The contractor will complete the following:

Interview ~8 people currently working in different environmental sector jobs in Maldives (JNCC and MNU will advise on the individuals to contact), collecting information about their training, their skills and experiences, and information about their current job.  Provide a clear outline of the essential requirements for each job, that is, what each job entails and how to get started on that career path. It should provide answers to key questions from a job seeker point of view.

- Write up the results of the interviews into ~8 case studies – approx 1 page of A4 each.

- Work with MNU and JNCC on reviews of the case studies to finalise the text.

- Design the case studies into accessible formats – the case studies should be provided together as one digital leaflet, and should also be provided individually in a format that could be used on social media posts

- Translate the final text into Dhivehi and prepare Dhivehi versions of the products.

Throughout all of these activities, the contractors will need to liaise closely with JNCC (on behalf of the OCPP), and the Maldives National University. Regular meetings will be held to share updates on progress, and sufficient time should be factored into planning to ensure for review and sign off by both JNCC and MNU.

## Potential Follow-On Work

Bidders should be aware that there is the potential for the successful bidder to be requested by JNCC to undertake additional work on this contract into the financial year 2024/2025. Please note however that the potential for additional work to be undertaken is subject to a continuing need, availability of funds and satisfactory contractor performance. For the avoidance of doubt, no guarantee can be given that you will be asked to undertake the potential additional work outlined within this Annex A document. Bidders are not asked to provide detailed project plans for these follow-on aspects at this stage.

## Outputs

Any products or outputs submitted to JNCC [for publication] should adhere to JNCC’s house-style and should be produced in an accessible format (see product specification for more information).

## Product Specification

JNCC is committed to making its publicly available resources and documents accessible, in accordance with the Public Sector Bodies (Websites and Mobile Applications) (No. 2) Accessibility Regulations 2018.

Making material accessible means making sure it can be used by as many people as possible.  This includes those with:

- impaired vision

- motor difficulties

- cognitive impairments or learning disabilities

- deafness or impaired hearing

The outputs and material that JNCC publishes should be compliant with the Web Content Accessibility Guidelines version 2.1 AA standard.

## Dissemination

The products/outputs produced under this contract will be a JNCC product and shall not be published or disseminated without the written permission of JNCC. Outputs may at some point be published on the JNCC website and all material supplied as part of this contract shall remain copyright of JNCC. The findings from this contract will also be made available to staff within JNCC, the UK country nature conservation bodies (name them), Defra and (list other parties) (.

## Timescale

Provisional dates for delivery of the contract outputs are set out below. Exact dates are to be agreed at the start-up meeting based on Contractor and JNCC staff availability.

| Output | Provisional Date |
| --- | --- |
| Start-up meeting (virtual) with JNCC and MNU | Week of 30th September 2024 |
| Proposed workplan developed | Week of 7th October 2024 |
| Milestone 1: Prepare questionnaire, and conduct interviews with ~8 individuals as proposed by JNCC and MNU | 7th November 2024 |
| Milestone 2A: Share first draft of case studies | 18th November 2024 |
| Milestone 2B: Prepare second draft of case studies building in comments from JNCC and MNU | 9th December 2024 |
| Milestone 3: Prepare designed materials in English | 6th January 2025 |
| Milestone 4: Prepare designed materials in Dhivehi | 31st January 2025 |
| Milestone 5: Preparation of materials for use on social media | 10th March 2025 |

In agreeing exact dates, please note that the potential for work under this contract to be funded into 2024/25 is subject to availability of funds.

## Health and Safety

The successful bidder is expected to follow appropriate Health and Safety Procedures including adhering to JNCC’ policy on safeguarding. For further information  https://jncc.gov.uk/about-jncc/corporate-information/safeguarding/ and to be able to undertake appropriate risk assessments, evidence of which should be supplied to JNCC.

Any incidents occurring within the contract period should be immediately reported to JNCC.

## Project Management

The successful Contractor shall nominate a project manager who shall be responsible for ensuring the project is completed satisfactorily and who shall be the main contact point for JNCC.

JNCC’s main contact points will be:

Name: Beth Flavell

Email:  Beth.Flavell@jncc.gov.uk

Telephone: +44 (0) 7502 366559

## Instructions for Bid Submission

The bid submission should include the following:

A brief summary of the bidder’s experience in relation to the requirements of this contract;

A proposed approach for achieving the objectives of the contract and delivering the detailed tasks identified within each objective.

A detailed project plan (including Gantt chart) with proposed work programme and an estimate of time required to achieve each objective;

Details of the Project Team including their roles and experience, an estimate of their time input into each task and CVs of all personnel who will be involved in the contract/project; please ensure all CVs MUST be attached as a separate PDF documentation from the proposal, so that we can meet our JNCC GDPR retention policy requirements.

Overall quote for the contract (in GBP) should include:

  - Attending virtual start-up, interim and final meetings with JNCC project team and EPA staff

  - Costs and time allocation should be clearly allocated to specific tasks within this contract.

The following documentation:

  - If your company includes more than 5 employees, please provide copies of health and safety policy;

  - Copies of current public and employer liability insurance certificates or equivalence which is the legal requirement in your jurisdiction;

  - Copies of any appropriate risk assessments; and

  - Copies of any environmental policies should you have them.

## Evaluation Criteria

JNCC is not bound to accept the lowest priced or any bid. Having the technical expertise and experience to complete the work to a high standard and being able to complete it within the timescale are of the essence for this contract.

The bid evaluation will be undertaken by JNCC staff, but proposals may be shared with Maldives National University for their input to the decision-making process. If you do not consent to bid documentation being shared with MNU, please state in your response

For information on how we handle personal data please see our Privacy Notice at https://jncc.gov.uk/about-jncc/corporate-information/privacy-statement/

Bids will be evaluated using the following criteria:

|  | EVALUATION CRITERIA | Maximum Score | Score |
| --- | --- | --- | --- |
| 1. Quality of Bid (40% of the total for the three assessment categories) |  |  |  |
|  | Clarity of proposal particularly work programme and deliverables | 10 |  |
|  | Understanding of, the requirements in particular the adequacy of outputs and understanding of the context | 10 |  |
|  | Soundness and logicality of methods | 10 |  |
|  | Identification and proposed solutions to potential risks/issues | 5 |  |
|  | Serious weaknesses which threaten success | 5 |  |
|  | Sub Total | 40 |  |
| 2. Details of Contractor (40% of the total for the three assessment categories) |  |  |  |
|  | Ability to work in English and Dhivehi | 10 |  |
|  | Relevant experience of copy writing | 10 |  |
|  | Expertise and experience of working in Maldives | 10 |  |
|  | Relevant experience of working in digital design | 10 |  |
|  | Sub Total | 40 |  |
| 3. Cost (20% of the total for the three assessment categories) |  |  |  |
|  | Transparency and correctness of presentation, including breakdown of cost by task and output. | 10 |  |
|  | Fairness/reasonableness for the level of work and expertise required | 10 |  |
|  | Sub Total | 20 |  |
| Total Score |  | 100 |  |

## Payment

PLEASE NOTE: All quotes and all payments must be based on British Pounds (£) or US Dollars ($). If alternative currency payments are needed, please raise this at the earliest opportunity during the bid process so we can explore options.

Payment will be made on completion of the objectives following the submission of invoice(s) and based on the satisfactory undertaking of the contractual elements to the agreed standard of the JNCC Project Officer.

## Additional Requirements

All bidders are requested to carefully read the Terms and Conditions applying to this contract. Payment will only be made upon delivery of key outputs.

It is assumed that all costs associated with the production of figures, reproduction of photographs and the final report are accounted for within the rates/fees given.

The bidder is expected to supply all necessary equipment, software, licences, etc. to carry out the obligations required under the contract.

17.  Procurement Timetable (which may be subject to change)

| Activity | Date |
| --- | --- |
| Invitation/Request for Quote | 22 August 2024 |
| Last date for receipt of clarification questions | Monday 9 September |
| Final submission date for bids | Monday 16 September @1600 hours |
| Evaluation of bids | 17-20 September 2024 |
| Post-tender negotiation/clarification if required | 17-20 September 2024 |
| Notification letters sent to unsuccessful bidders | 23 September 2024 |
| Contract award | w/b 23 September 2024 |
| Start of project | w/b 30 September 2024 |