## Sheet1
CLARIFICATION LOG
Tender: | Mill Meadows Adventure Playground
Tender Reference:
Clarification deadline: | 3rd November 2023
Published Date: | 20th October 2023
Version number: | 1
Number | Clarification | Response | Reply date
1 | What is the budget cap for the project? | The budget is £125,000 with 10% either way. These are hard limits and should not be exceeded. However, a tenderer is able to provide quotes for optional extras / alternative designs, but these must be clearly marked. | 2023-10-20
2 | Is it possible to see the report on the outcome of the public consultation? | This has been uploaded to Contracts Finder portal | 2023-10-20
3 | Do you intend to consult with the public following the tender submissions? | The tenders will be evaluated by a working group of councillors and staff using the evaluation criteria alone. Once a contractor has been appointed, it is likely that the final scheme will be subject to wider consultation | 2023-10-20
4 | Would you consider an extension to the submission deadline? | The deadline for submissions has been extended to 1pm on Friday 24th November 2023 | 2023-10-20
5 | Should the play equipment footings be steel? | We do not specify how the play equipment should be secured into the ground. However, if no steel footings are used, we would recommend that the tenderer provide details of how they believe this is a robust solution | 2023-10-20
6 | Will the trees be reduced? | We are planning to carry out a crown reduction on the trees. This will not affect the installation work, but should be taken into consideration with the design. | 2023-10-20
7 | Will the monolith (dead tree trunk) be felled? | The monolith will need to be felled. It can either be left in situ to form part of the play equipment, or moved / removed, depending on the preference of the successful contractor. This work will be carried out in-house and does not need to be included in your tender. | 2023-10-20
8 | The link to the guidance on the Social Value Act is missing. | The correct link is here: https://www.gov.uk/government/publications/social-value-act-information-and-resources/social-value-act-information-and-resources#:~:text=1.-,Legislation,social%2C%20economic%20and%20environmental%20benefits. | 2023-10-20
9 | How does the Council foresee the theming being balanced with the play utility? | The play utility is the first and foremost consideration and should not be compromised for the sake of theming. However, there should be a clear sense of 'adventure' when looking at the design. | 2023-10-20
In the event of queries please contact: Sheridan Jacklin-Edward, clerk@henleytowncouncil.gov.uk / 07595 608577.