| Contract Management Guidance – Template #10 CHANGE CONTROL FORM- Extensions – v. 5 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Contract Name: | Provision of Consultancy for Project Seagull |  | Contract Ref. No. | CCS Reference: CCCC17A63 (Variation Ref: CCCC17A63-01) |  |
|  |  | CLIENT CHANGE NOTICE (CCN) |  |  |  |
| REDACTED TEXT CCN 1 CCN Reference: Initiated by: Date CCN Raised by relevant party: Source of change: 6th October 2017 Ministry of Defence : |  |  |  |  |  |
| STAGE 1 – CLIENT |  |  |  |  |  |
| Summary of proposals/ requirements : | This is a variation to the Contract between the Ministry of Defence and Deloitte LLP. The Terms and Conditions of the Contract apply but with the following amendments: - Uplift in Contract Value - The existing Contract value is £583,332 (exc. VAT). The Authority proposes to uplift the Contract value by an additional £291,360 (exc. VAT), this would therefore increase the overall Contract value to a maximum of £874,692 (exc. VAT). - Inclusion of additional deliverables: Timeframe 1 - Support and facilitate monthly 3*/2* Alliance Transition Steering Group meetings, including preparation of supporting material. Ongoing, monthly per Sprint 2 - Support and facilitate regular Governance & Integration working group meetings, including preparation of supporting material. Ongoing weekly to fortnightly per Sprint 3 - Support MOD's facilitation of regular Commercial & Contracting working group, including preparation of supporting material. Ongoing, monthly per Sprint with weekly update calls 4 - Draft view of the programme assurance process, decision-management and change configuration, illustrated through scenarios Within week 6 5 - Draft mapping of new Alliance roles and responsibilities with existing roles of the Parties and particular posts 6 - Updated working documents in support of Reporting and Change Control for the Project Controls Steerco 7 - Detailed role descriptions for "MD minus 1" posts and document outlining more detailed organisational structure within the Alliance team |  |  |  |  |
| Proposed payment: | In line with the existing terms and conditions of Contract and the proposed increased Contract value of £874,692 (exc. VAT). |  |  |  |  |
| Required delivery date, with rationale: | In line with the existing terms and conditions of Contract and the proposed new end date of 14th November 2017. |  |  |  |  |
| REDACTED TEXT REDACTED TEXT REDACTED TEXT Change authorised to proceed to Stage 2 (Customer organisation representative): Signature Print Name & Position Date REDACTED TEXT REDACTED TEXT REDACTED TEXT Change authorised to proceed to Stage 2 (CCS representative) Signature Print Name & Position Date |  |  |  |  |  |
| STAGE 2 – SUPPLIER |  |  |  |  |  |
| Comments/ caveats on requested change: |  |  |  |  |  |
| ABORTIVE COSTS : |  |  |  |  |  |
| Anticipated period from CCN being authorised by client to start of related provision |  |  |  |  |  |
| Deloitte LLP confirms that the costs identified above are the agreed figures that will be payable on CCN implementation |  |  |  |  |  |
| REDACTED TEXT Signed (Supplier Representative): REDACTED TEXT Print Name & Position: REDACTED TEXT Date: |  |  |  |  |  |
| STAGE 3 – CLARIFICATIONS |  |  |  |  |  |
| Clarification/ queries to to supplier regarding Date: their proposals: Supplier response Date: |  |  |  |  |  |
| STAGE 4 - CUSTOMER CCN SIGN-OFF TO PROCEED TO IMPLEMENTATION |  |  |  |  |  |
| Variation Withdrawn |  |  |  |  |  |
| By signing below, unless CCN is withdrawn, the Ministry of Defence agrees to pay Deloitte LLP the costs detailed in Stage 1, by deadlines agreed with the supplier, or as defined in the contract. |  |  |  |  |  |
| REDACTED TEXT REDACTED TEXT Signed (Customer Representative): REDACTED TEXT Date Print Name & Position Signature Change authorised to proceed to implementation (CCS): REDACTED TEXT REDACTED TEXT REDACTED TEXT Date Print Name & Position Signature |  |  |  |  |  |
| STAGE 5 - CCN COMPLETION SIGN-OFF |  |  |  |  |  |
| I confirm that the provision required under the CCN commenced in accordance with the customer requirements and supplier proposals in this CCN. |  |  |  |  |  |
| REDACTED TEXT REDACTED TEXT Date provision required under the CCN commenced: Date Signed by Customer: REDACTED TEXT REDACTED TEXT Signed (Customer representative): Print Name & Position |  |  |  |  |  |