Document 6b: Implementation Plan Template

Planning and Delivery Support for Providers of T Levels, including the T Level Transition Programme and Industry Placements

Tender References:

Lot 1: itt_1939

Lot 2: itt_1940

Lot 3: itt_1941

December 2022

Instructions:

All Potential Suppliers are required to complete this template as part of their Tender Submission for any of the three lots comprising the Planning and Delivery Support for Providers of T Levels, including the T Level Transition Programme and Industry Placements, procurement.

The draft Implementation Plan:

- must contain information at the level of detail necessary to manage the implementation stage effectively and as the Department may otherwise require; and

- it shall take account of all dependencies known to, or which should reasonably be known to, the Supplier.

The Potential Supplier shall complete bulleted lists for each Milestone and its Deliverables, including associated tasks, duration to complete, responsible personnel and assumptions.

The Department will finalise the Implementation Plan with the successful Supplier at Contract Award.

Key points to note:

- The Supplier shall provide each of the Deliverable Items identified in the Implementation Plan by the date assigned to that Deliverable Item in the Implementation Plan so as to ensure that each Milestone identified in the Implementation Plan is achieved on or before its Milestone Date.

- The Supplier shall monitor its performance against the Implementation Plan and Milestones (if any) and report to the Department on such performance.

- The Supplier shall note that it is incumbent upon them to understand the lead-in period for security clearances and ensure that all Supplier Staff have the necessary security clearance in place before the Contract Start Date. The Supplier shall ensure that this is reflected in their Implementation Plans.

Lot 1: T Level Provider Support Implementation Plan

| Milestones | Deliverables | Duration (working days) | Responsible Personnel | Milestone Acceptance Criteria | Milestone Date | DfE Responsibilities | Assumptions |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Contract commencement | Meet with DfE to discuss requirements and refinements to delivery plan. Sign contract | 1 day | Project Manager Strategic Lead | Signed contracts | April 2023 | Agree on delivery plan refinements and sign contract | Contract awarded and received in line with ITT |
| Reporting | Agree reporting mechanisms with DfE | 1 day | Project Manager | Reporting templates agreed and KITs scheduled | May 2023 | Agree reporting mechanisms and confirm KIT dates | Monthly reports and meetings. |
| Supplier collaboration | Agree ways of working and streamlined delivery with supplier(s) of Lots 2 and 3. | 1 day | Strategic Lead | Ways of working agreed. Meeting schedule in place. Streamlined processes. | June 2023 | Sign off on plans | Monthly collaborative meetings. Shared calendar of events. Triage processes designed. |
| Years 1 & 2 Delivery plan | Delivery plan finalised | 3 days | Project Manager Strategic Lead | Final delivery plan submitted to DfE | May 2023 | Sign off on delivery plan | As outlined in ITT response. |
| Quality Assurance Plan | Quality assurance plan developed | 3 days | Project Manager Strategic Lead | Final quality assurance plan submitted to DfE | May 2023 | Sign off on quality assurance plans | Quality processes reviewed annually. |
| Risk Register | Risk Register produced | 2 days | Project Manager Strategic Lead | Risk register submitted to DfE | May 2023 | Sign off risk register | Risks discussed during monthly meetings. |
| Data management system | Implement an effective data management system. | 5 days | Strategic Lead Data Manager | System shared with DfE | July 2023 | N/A | Linked to AoC CRM system. |
| Staffing and resourcing | Staffing and resource in place | 20 days | Director of Projects Strategic Lead | Fully resourced team. Contracts signed. Final organisational charts submitted to DfE | July 2023 | Approval of staffing and resource | Current staff to fill required roles, as appropriate. Any recruitment completed by July 2023. |
| Templates | Prepare provider support templates including communications, support and challenge KITs, provider MOUs, and feedback forms. | 6 days | Manager | Templates created and submitted to DfE | August 2023 | Approval | Update current templates, where appropriate. |
| Eligible provider details | Receive provider details from DfE. | 2 days | Data Manager | Details inputted into data management system | July 2023 | Share provider details | Organisation name and key contact details received (name, email, and telephone number). |
| Strategic planning | Host planning day with staff working across each Lot. | 1 day | All | Joint understanding of programme objectives and effective ways of working established. | August 2023 | Attendance | Attendance from suppliers working across Lots. |
| Provider inception calls | Plan and prepare for provider inception calls/diagnostic sessions. Schedule meetings with providers. | 4 days | Manager Senior Advisor | Key data to collect outlined. All calls scheduled. | August 2023 | N/A | Providers will be available in August to schedule and undertake calls. |
| Assessment of provider support needs | Map support needs across the cohort. Design effective support plans. Include Industry Placements within T Level support. | 5 days | Strategic Lead Manager Senior Advisor | Support plans submitted to DfE. | October 2023 | Review plans | Assessment framework as described in ITT response. Inclusion of Industry Placement support. |
| Guidance Resources | Audit of current resources available on T Level, TLTP and Industry Placements. Deliver provider and employer focus. | 10 days | Strategic Lead Manager Guidance Resource Manager | Proposal for new guidance resources and updates required to existing resources. | September 2023 | Approval | Collaboration with supplier(s) of Lot 2 and 3. |
| T Level planner | Review T Level Planner and update, as required. | 5 days | Manager Data Manager | Updated planning tool | September 2023 | Sign off on updates | Using existing T Level Planner. |
| Mentoring and buddying | Design effective mentoring and buddying scheme | 5 days | Manager Senior Advisor | Scheme outlined and ready for implementation | September 2023 | Sign off on plans | As outlined in ITT response. |
| Networks | Audit existing network infrastructure with ETF and the Gatsby Foundation plus supplier(s) of Lots 2 and 3. Gather feedback from providers. Develop sustainable networking plan. | 12 days | Strategic Lead Manager Senior Advisor | Network proposal | September 2023 | Sign off on network proposal | Collaborative partnership agreed with ETF and Gatsby. |
| Events | Strategic audit of sector events and support requirements. Gather feedback from providers on the type and number of events requested. Collaborate with Lot 2 and 3 supplier(s). | 1 day | Strategic Lead Manager Events team | Delivery plans for annual events Shared calendar of events. Communication and marketing plans produced. | September 2023 | Sign off on delivery plans | As outlined in ITT response. |
| Industry Insights | Develop assessment framework of provider support needs. Integrate support across work strands. Plan for support for 2023 providers. | 12 days | Strategic Lead Manager | Provider support plans | October 2023 | Sign off on support plans | As outlined in ITT response. |
| Exit plan | Create exit plan | 1 day | Project Manager | Exit plan submitted to DfE | September 2023 | Sign off on exit plan | Template provided by DfE. |

Lot 3: T Level Transition Programme Implementation Plan

| Milestones | Deliverables | Duration (working days) | Responsible Personnel | Milestone Acceptance Criteria | Milestone Date | DfE Responsibilities | Assumptions |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Contract commencement | Meet with DfE to discuss requirements and refinements to delivery plan. Sign contract | 1 day | Project Manager Strategic Lead | Signed contracts | April 2023 | Agree on delivery plan refinements and sign contract | Contract awarded and received in line with ITT |
| Reporting | Agree reporting mechanisms with DfE | 1 day | Project Manager | Reporting templates agreed and KITs scheduled | May 2023 | Agree reporting mechanisms and confirm KIT dates | Monthly reports and meetings. |
| Supplier collaboration | Agree ways of working and streamlined delivery with supplier(s) of Lots 1 and 2. | 1 day | Strategic Lead | Ways of working agreed. Meeting schedule in place. Streamlined processes. | June 2023 | Sign off on plans | Monthly collaborative meetings. Shared calendar of events. |
| Years 1 & 2 Delivery plan | Delivery plan finalised | 3 days | Project Manager Strategic Lead | Final delivery plan submitted to DfE | May 2023 | Sign off on delivery plan | As outlined in ITT response. |
| Quality Assurance Plan | Quality assurance plan developed | 3 days | Project Manager Strategic Lead | Final quality assurance plan submitted to DfE | May 2023 | Sign off on quality assurance plans | Quality processes reviewed annually. |
| Risk Register | Risk Register produced | 2 days | Project Manager Strategic Lead | Risk register submitted to DfE | May 2023 | Sign off risk register | Risks discussed during monthly meetings. |
| Data management system | Implement an effective data management system. | 5 days | Strategic Lead Data Manager | System shared with DfE | July 2023 | N/A | Linked to AoC CRM system. |
| Staffing and resourcing | Staffing and resource in place | 20 days | Director of Projects Strategic Lead | Fully resourced team. Contracts signed. Final organisational charts submitted to DfE | July 2023 | Approval of staffing and resource | Current staff to fill required roles, as appropriate. Any recruitment completed by July 2023. |
| Templates | Prepare provider support templates including communications, support and challenge KITs, provider MOUs, and feedback forms. | 6 days | Manager | Templates created and submitted to DfE | August 2023 | Approval | Update current templates, where appropriate. |
| Eligible provider details | Receive provider details from DfE. | 2 days | Data Manager | Details inputted into data management system | July 2023 | Share provider details | Organisation name and key contact details received (name, email, and telephone number). |
| Strategic planning | Host planning day with staff working across each Lot. | 1 day | All | Joint understanding of programme objectives and effective ways of working established. | August 2023 | Attendance | Attendance from suppliers working across Lots. |
| Provider inception calls | Plan and prepare for provider inception calls/diagnostic sessions. Schedule meetings with providers. | 30 days | Manager Senior Advisor Advisors | Key data to collect outlined. All calls scheduled. | August 2023 | N/A | Providers will be available in August to schedule and undertake calls. |
| Assessment of provider support needs | Map support needs across the cohort. Design effective support plans. Input into T Level planner. | 6 days | Strategic Lead Manager Senior Advisor | Support plans submitted to DfE. | October 2023 | Review plans | Assessment framework as described in ITT response. |
| Guidance Resources | Audit of current resources available on T Level, TLTP and Industry Placements. Deliver provider and employer focus. | 10 days | Manager Guidance Resource Manager | Proposal for new guidance resources and updates required to existing resources. | September 2023 | Approval | Collaboration with supplier(s) of Lot 1 and 2. |
| Events and networks | Audit existing event and network offer Gather feedback from providers on the type and number of events requested. Collaborate with Lot 1 and 2 supplier(s). Create events and networking plan for years 1&2. | 5 days | Manager Events Team | Events and network proposal | September 2023 | Sign off | As outlined in ITT response. Estimated 20 events and networks per year covering online, face to face and insight days. To be confirmed based on sector feedback. |
| Exit plan | Create exit plan | 1 day | Project Manager | Exit plan submitted to DfE | September 2023 | Sign off on exit plan | Template provided by DfE. |