## Risk evaluation
OFFICIAL
Risk evaluation table example | [5 empty] | Document no2a
LIKELIHOOD (of risk materialising) | Suggested approximate percentage
Completely mitigated | 0%
Rare | 3%
Unlikely | 10%
Possible | 30%
Likely | 70%
Almost Certain | 90%
IMPACT (loss of programme benefit if the risk materialises | Suggested approximate percentage
Zero impact | 0%
Very Low | 2%
Low | 10%
Medium | 40%
High | 80%
Very High | 90%
EXAMPLES
Risks that could interupt supply |  | Impact to vaccination programme / based on current mitigation measures | Additional supplier mitigation (reduces the likelihood) or additional concerns (increases the likelihood) | Likelihood (adjusted) | Exposure | Additional measures taken by the Authority to reduce exposure and associated costs
MANUFACTURING including likelihood and impact of: |  |  | Example comments
- Potency batch release failure – either internal or OMCL (this may depend on the complexity of the vaccine and the type of assay). |  |  | 2 years of bulk stock are held by manufacturers
- Lack of resources for retest especially animal testing. |  |  | No issues identified
- Sterility test failure. |  |  | No issues identified
- Manufacturing plant failure either primary or secondary manufacture for any reason (e.g.fire etc). |  |  | No issues identified
- Regulatory delays (e.g.approval of licence variations, closure of manufacturing facility) |  |  | Offerer plans the move manufacturing facility for which regulatory approval has not yet been given, no contingency for late approval described in the offer.
- Batch recall |  |  | No issues identified
Overall estimated risk exposure, taking into account any mitigating actions |  | Low |  | Rare | 0%
SUPPLY CHAIN including likelihood and impact of:
- Transportation and cold chain problems. |  |  | No issues identified
- Industrial action. |  |  | No issues identified
- Epidemic, pandemic, plague etc. |  |  | No issues identified
Overall estimated risk exposure, taking into account any mitigating actions |  | Low |  | Rare | 0%
ANY OTHER RISKS |  | Low |  | Rare | 0%
Total risk exposure score |  |  |  |  | 0%