## Understanding the Customer

## Research brief

Usability Testing

(Customer requirements to support Debt Products Testing)III

January 2016

Background, previous research, additional reading

Tax credits is being replaced by Universal Credit (UC) so that eventually all tax credits customers will either have moved to Universal Credit or left the tax credits regime entirely. A large proportion of tax credits customers will have outstanding tax credits debts - involving both single and joint claims. Previous research showed that many customers are unaware of their debts, or the scale of them, as tax credits debts may have been deducted regularly from tax credits payments, without customers being aware that this has happened. When a customer moves to UC, HMRC will transfer any outstanding tax credits debt to UC for recovery.

The transfer of tax credits debts to Universal Credit is new and new IT and products are being developed to support the process. Also new is HMRC’s ability to consolidate debts covering a number of years into one document and to allocate the debts to individuals rather than households.

Earlier research tested the new 'mocked up' customer notifications and found that customers' understanding of these products and their purpose, was mixed. Some customers said they would contact HMRC to enquire about the purpose of the customer notifications. HMRC is keen to reduce this low value contact.

Many of the findings from the research were used to support in the development of the base lined customer notifications.

Further research tested the revised customer notifications to assess their effectiveness in supporting the transfer of tax credits debt to UC or leaving the tax credits regime entirely. Some changes have been made to the products but we remain concerned that customers will require additional supporting guidance.

The proposed testing will assess the effectiveness of draft supporting web based guidance ( i.e.  gov.uk content) and will identify areas that customers find difficult and give an indication of where revised and/or further supporting information is needed. The research and findings need to be completed by the end of January 2016.

Ipsos Mori undertook previous research into this subject, earlier this year:

- March 2015: “Qualitative research to understand customer needs when transferring tax credits debt to Universal Credit”

- July 2015 “Usability Testing research - Customer requirements to support Universal Credit debt transfer”.

Ipsos Mori therefore have access to the most recent information on this subject. We are happy to discuss recent developments with the customer notifications that have come about as a result of this previous research.

Overarching business objective/need

The new customer notifications will be sent to the majority of tax credits customers, once they have left the tax credits regime, from April 2016. We need customers to understand that, in most cases, they will be out of time to appeal or dispute so that their calls for information are minimised

We require the agency to probe for which areas/sections/topics present difficulties for customers and to present suggestions/proposals as to how the draft web-based guidance can be clarified.

Research Objectives

- To test the draft web based guidance with a range of tax credits customers, to determine whether they might prove effective in driving the desired behaviour.

- To explore customers responses to the resurrection of older (historic) debt for recovery and whether the guidance satisfies their need for further information.

- To explore whether customers understand how HMRC is treating their debts as individuals (as opposed to joint) debts and how HMRC have treated these debts where the household has subsequently split up.

Some more detail on the sorts of questions you think you would like to ask

We need answers to the following questions:

- Does the guidance help the customer understand the purpose of the customer notification and the information relayed?

- Does the customer understand what is required and where they can find the information they need?  Do customers know what to do next?

- Do customers understand how much they owe?

- Do customers understand the years these debts relate to?

- Do customers know what has happened to their debts and how they will be recovered (either transferred to UC or the requirement to contact HMRC to make a payment in full)?

- Does the customer understand messages explaining that the debts are out of time and no dispute will be permitted (basically a 'Do Not Call' message) If we do not mention time limits to appeal – is this understood or does it need to be said explicitly?

- What additional information would customers need to clarify their debt position & next steps?

Language and Tone

- Are our proposed messages clear?  If not, which parts are harder for the audience to understand?

- How important is language and tone?

Stimulus/Background documents

We will provide:

- The Individual Debt Statement (final version)

This will be issued to customers who move to UC and will contain all the individual customer's stable live and historic debts, some of which could go back for a number of years. It is possible that the customer will receive a number of these statements.

- Consolidated Notice to Pay (final version)

This will be issued to customers whose tax credits award has come to an end (possibly because of a household breakdown) but who do not go on to claim UC. This product will also contain all the individual customer's debts - which could have been accrued over a number of years.

- Customer Journey

We will explain the touch-points for customers – when and why they will receive the products and what explanatory guidance we are planning to publish. We are hoping also to have screen shots available so that testers comment on these.

- Key messages

These are the key messages around the debt transfer to DWP that we need customers to understand.

- “User Needs”

This document describes what we think customers may need to support them through the change in the way their debts will be recovered. The draft content has been based on these “user needs”.

- Content Plan

This document explains the proposed structure of and connections between content pages.

- Draft content

This is the guidance content that we would like to be tested with customers, to explore whether this will answer their questions/concerns and is easily understood.

Proposed Methodology

We envisage the testing will include:

- Depth interviews with individuals which will focus on the detailed content of the product, as it relates to each customer.

- A focus group to test the effectiveness of the draft content in supporting customers through the process.

Sampling

Current and former tax credit customers with debts - who have a cross section of personal circumstances and levels of income.

Given the time constraints we will not be providing a sampling dataset but we’d like to try and cover a cross-section of customers, generally aligning with the sections of the debt products that the content relates to.

Other issues that may have an impact on this project

Previous projects of this nature found that customers were more reluctant than usual to discuss tax credits debts. This had a negative impact on the eventual numbers of participants.  We would like to discuss how this risk can be mitigated

What we need from you – the deliverables

Project Deliverables

- Screening criteria/questions

- Discussion guide(s) design

- Weekly progress reports

- PowerPoint slides of Topline Findings

- Face to Face debrief meeting

In addition, as part of our publication process, we require a publishable version of the research findings that will be published on the HMRC website. A standard template and guidance will be provided.

Our project timeline

The timings given below are indicative and I understand that the proposal document will include more detailed timings for consideration.

| Date by | Action | HMRC | Ipsos Mori |
| --- | --- | --- | --- |
| 04/12/15 | Discuss high level requirements/introductory conversation with Ipsos Mori | Y | Y |
| 04/12/15 | Deliver Research Brief/Proposal | Y | Y |
| 11/12/15 | Agree proposal | Y | Y |
| 18/12/15 | Develop screening and recruitment documents | Y | Y |
| 18/12/15 | Provide early versions of stimulus material as a guideline for developing Topic Guide for testing with individuals | Y |  |
| 18/12/15 | Provide versions as a guideline for developing Topic Guide for Focus Group (if required) | Y |  |
| 08/01/16 | Recruitment |  | Y |
| 08/01/16 | Meeting/telecon to discuss detail of requirement | Y | Y |
| 13/01/16 | Provide stimulus material for finalising Topic Guide for testing with individuals | Y | Y |
| 13/01/16 | Develop topic guides for interviews with individuals |  | Y |
| 13/01/16 | Develop topic guides for interviews with individuals |  | Y |
| 13/01/16 | Final topic guide for interviews signed off | Y |  |
| 13/01/16 | Provide versions of debt products to be tested in Focus Group to Ipsos Mori (if required) | Y |  |
| 13/01/16 | Final topic guide for Focus Group signed off (if required) | Y |  |
| 29/01/16 | Fieldwork – conduct interviews with individuals (testing debt products from stimulus material) |  | Y |
| 29/01/16 | Fieldwork - conduct Focus Group (testing design/look/feel/drivers of debt products) |  | Y |
| 05/02/16 | Provide top line feedback |  | Y |
| 12/02/16 | Debrief presentation to HMRC (pref. w/e 5/01 if poss.) | Y | Y |
| 29/02/16 | Provide final report to HMRC |  | Y |

Budget

- We are not able to disclose exact budget information.  Please provide a cost for the project design set out above and set out alternatives if you feel these would better meet the research objectives.

Costs must include travel and other expenses, broken down separately. Costs should include all fees and expenses but exclude VAT.

General Terms and conditions

On receipt of a satisfactory proposal, the successful research agency will be awarded a fixed price contract for the project. The Standard Conditions of Contract governing research commissions are laid down by the MR130001 framework agreement and are not negotiable.  HMRC observes the general practice of paying only for work satisfactorily completed. All work should comply with the Code of Conduct of the Market Research Society. The Standard Conditions of Contract are available on request.

Payment terms have been negotiated to split as follows on most projects (however there will always be exceptions – which we will do our best to cater for)

30% on commission

30% on Fieldwork commencement

40% on completion

When costing proposals it would be helpful to ensure we can see these key stages clearly.

Some key elements of our standard terms are below:

Contractual obligations

As a result of government policy to achieve greater transparency in public procurement and help deliver improved value for money, HMRC is obliged to publish tender documents for all contracts with a whole life value of over £10,000.  There is a further obligation to publish all contracts with a whole life value of over £10,000 with effect from January 2011.  It is a condition of bidding for this work that applicants accept these obligations and agree to the subsequent publication of the contract once awarded.

Data handling

In most cases, any data we supply will be encrypted, probably using the highest encryption used by Winzip v9 or above. It is your responsibility to ensure appropriate steps are taken to ensure you are able to receive and decrypt our data.

We also require confirmation at appropriate times of the deletion of customer records from both removable and fixed media within your organisation.

Please note that HMRC does not permit the use of USB sticks and so all electronic versions should be provided on CD.

Once appointed, you should agree with your HMRC contact what security rating any data or documentation you produce should have and how it subsequently should be handled.

As part of our standard data handling requirements, as part of your proposal we will require details of your plan to receive, store and use any data that we may supply to you. In most cases the data we supply to you will contain customers’ personal details and we need to be sure that you will treat this data appropriately.

This should include precise details of the data handling and security procedures you have in place. In particular, please detail how, once we have delivered the data to you, how you will transfer and store it and who in your organisation will be able to access it. You should also detail your processes for archival of and/or destroying the data that has been finished with. As an example this should include, what systems you have that are accessible from the internet, how access to the information is managed, and details of how your data servers are backed-up and maintained.

If you have supplied current information, this does not need to be provided again.

Documentation

HMRC will require the publishable report delivered in both pdf and word formats. The pdf document should include the file size as part of the filename.

In addition, HMRC will require draft copies of all key documents, such as recruitment questionnaires, presentation charts, top line and final report. These are to be submitted in sufficient time for comments to be incorporated into the final version and for our approval to be given for production of the final version to take place.

NB ‘Personal’, ‘Confidential’ and ‘Commercial’ sensitive information has been redacted according to the provisions in the FOI Act (sections 40, 41 & 42).