DPS FRAMEWORK SCHEDULE 4: LETTER OF APPOINTMENT AND CONTRACT TERMS

  - Letter of Appointment

Dear Sirs

Letter of Appointment

This letter of Appointment dated 20th August 2020 is issued in accordance with the provisions of the DPS Agreement (RM6018) between CCS and the Supplier.

Capitalised terms and expressions used in this letter have the same meanings as in the Contract Terms unless the context otherwise requires.

| Order Number: | TBC |
| --- | --- |
| From: | Cabinet Office ("Customer") |
| To: | Atkins Limited ("Supplier") |

| Effective Date: | 1st September 2020 |
| --- | --- |
| Expiry Date: | 28th February 2021 |

| Services required: | Set out in Section 2, Part B (Specification) of the DPS Agreement and refined by: · the Customer’s Project Specification attached at Annex A and the Supplier’s Proposal attached at Annex B |
| --- | --- |

| Key Individuals: | Customer: REDACTED Supplier: REDACTED Subcontractor: FLUXX Ltd - REDACTED |
| --- | --- |
| [Guarantor(s)] | N/A |

| Contract Charges (including any applicable discount(s), but excluding VAT): | £115,990.00 See Part 3 – Supplier Costings of this document for details |
| --- | --- |
| Insurance Requirements | Additional public liability insurance to cover all risks in the performance of the Contract, with a minimum limit of £1 million for each individual claim. |
| Liability Requirements | Suppliers limitation of Liability (Clause 18.2 of the Contract Terms); |
| Customer billing address for invoicing: | REDACTED |

| GDPR | See Schedule 7 (Processing, Personal Data and Data Subjects] |
| --- | --- |
| Alternative and/or additional provisions (including Schedule 8(Additional clauses)): | N/A |

FORMATION OF CONTRACT

BY SIGNING AND RETURNING THIS LETTER OF APPOINTMENT (which may be done by electronic means) the Supplier agrees to enter a Contract with the Customer to provide the Services in accordance with the terms of this letter and the Contract Terms.

The Parties hereby acknowledge and agree that they have read this letter and the Contract Terms.

The Parties hereby acknowledge and agree that this Contract shall be formed when the Customer acknowledges (which may be done by electronic means) the receipt of the signed copy of this letter from the Supplier within two (2) Working Days from such receipt

For and on behalf of the Supplier:                            For and on behalf of the Customer:

Name and Title:                                                           Name and Title:

REDACTED					       REDACTED

Signature:           REDACTED

Signature: REDACTED

Date:                                                                            Date:

Annex A

Customer Project Specification

# PURPOSE

## The purpose of this procurement is to commission a piece of external research to establish what Business as Usual (BAU) processes the National Underground Asset Register (NUAR) platform will be replacing and how these will be phased out. The research will identify which existing processes can be retired and which will need to remain and the process for using the NUAR platform in tandem with any remaining BAU processes in future.

## The outcomes of this research may be included in the competitive tender for the regional build and the national rollout of the NUAR platform.

# BACKGROUND TO THE CONTRACTING AUTHORITY

## The Geospatial Commission was established in 2018 by the government as an independent, expert committee responsible for setting the UK’s geospatial strategy and coordinating public sector geospatial activity. Our aim is to unlock the significant economic, social and environmental opportunities offered by location data and to boost the UK’s global geospatial expertise.

## The Geospatial Commission has a mandate and budget to drive and deliver changes by working in partnership with others. This means they:

### Provide strategic oversight of the geospatial ecosystem in the UK, setting geospatial strategy, policy and standards;

### Hold the budget for the public sector’s largest investment in strategically important geospatial data via the Public Sector Geospatial Agreement;

### Make targeted investments in data projects that accelerate innovation and the adoption of geospatial data applications.

## They have a formal relationship with six partner bodies: The British Geological Survey, Coal Authority, HM Land Registry, Ordnance Survey, UK Hydrographic Office and the Valuation Office Agency.

# BACKGROUND TO REQUIREMENT/OVERVIEW OF REQUIREMENT

## The estimated economic cost of accidental strikes on underground pipes and cables is £1.2 billion a year. Workers who strike gas pipes and electricity cables by mistake can also put themselves and others in danger of death or serious injury.

## The UK does not have a uniform process for asset owners to share their data, which means prior to excavating a site, operators are required to contact all organisations who own or may have owned assets in the area, wait for each to respond, then compile information so it can be read and understood by workers. This process is slow, inefficient and makes inaccuracies leading to accidental damage more likely.

## The Geospatial Commission is tasked with unlocking the economic opportunities offered by geospatial data and estimates £245m in value could be unlocked for the UK economy per annum by creating a national underground asset register (NUAR) where data is shared in a consistent and efficient manner by asset owners and their operators.

## Business as usual (BAU) is highly inefficient - data is hard and slow to access, potentially incomplete, and the inconsistent delivery makes it hard to integrate (Figure 1). This leads to inefficient project planning and makes on-site works more difficult, especially in emergencies. Additionally, there is no procedure for data error reporting so no mechanism for incremental data improvement.

## Figure 1. Example user story that summarises the significant pain-points in the user journey as a result of the lack of a single and coherent data source. This has been developed from 39 stakeholder interviews undertaken during discovery phase in late 2018

## The NUAR Programme aims to increase the understanding of the underground environment and unlock value from utility strike avoidance, project efficiency and data exchange efficiency for utilities and their operators.  The programme also aims to establish more efficient management of the subsurface in general that aligns with government priorities on the digital economy.

## The NUAR pilots were launched in April 2019 to test the feasibility of creating a national data sharing platform for underground asset owners and their operators. The pilots concluded in March 2020 and work is now underway to complete necessary preparation work ahead of launching a competitive tender for a regional build and national rollout.

## As part of the preparation work for the invitation to tender, it is necessary to understand what BAU processes NUAR will be replacing in the national roll out, and how these will be phased out. This procurement therefore aims to commission independent research to determine what these processes are and which processes need to be retained.

# DEFINITIONS

| ## Expression or Acronym | ## Definition |
| --- | --- |
| ## NUAR | ## means National Underground Asset Register |
| ## GC | ## means Geospatial Commission |
| ## BAU | ## means Business as usual |

# SCOPE OF REQUIREMENT

## It is proposed that three work packages are undertaken to gather the BAU process information and map the transition to NUAR:

### A research exercise on existing BAU processes that asset owners and their operators are using to plan and deliver an excavation project, and

### An in-depth analysis on which existing processes NUAR will be replacing and which existing processes will need to be retained.

### A unit-cost based economic analysis of the potential process savings NUAR will generate.

## The geographical scope of this procurement includes England, Wales and Northern Ireland.

## The asset owners that are in scope for this procurement are utility statutory providers (gas, electricity, clean water, sewage and telecommunications) and Local and Highways Authorities. As many of these bodies utilise Tier 1 contractors to plan and execute their works, Tier 1 contractors are also in scope.

## The process mapping will cover both planned excavations and unplanned/emergency works on a site scale.

# THE REQUIREMENT

## Work package A – Research into existing BAU

### The purpose of this work package is to map the existing processes used by utility companies and Local Authorities to plan excavations and collate, share and utilise the underground asset information required for safe digging and avoidance of utility strikes.

### The successful Supplier will be an organisation with existing relationships and/or processes for gathering information from asset owners.

### The Supplier will develop a recommended sampling methodology for the selection of representative asset owners across the sectors (clean water, sewage, gas, electricity, telecommunications, and Local/Highways Authorities), including a small number of Tier 1 contractors in England, Wales and Northern Ireland. The methodology will ensure that the sample would cover a range of asset owners’ size, geographical location and different approaches in their BAU.

### The Supplier will implement the sampling methodology approved by GC to collect information of existing BAU processes across the selected asset owners. The Supplier will then create process maps that identify the most common steps in the process and highlight any outliers and differences between organisations and sectors. The Supplier will also identify the array of options the asset owners use to conduct utility searches. The Supplier will include all the compliance requirements in the process maps (legislative, regulatory and guidance/best practice).

## Work package B – NUAR integration analysis

### The purpose of this work package is to conduct an in-depth analysis on which existing processes NUAR will be replacing and which existing processes will need to be retained. The NUAR platform will be a digital map of all underground assets with an integrated observation tool that provides direct feedback to asset owners.

### The Supplier will identify and report on the processes on the process map created as part of Work package A that will no longer be required when NUAR will be rolled out. The Supplier will also highlight the processes that cannot be replaced.

### The Supplier will make recommendations on how the NUAR platform will be integrated in the remaining processes. The Supplier will also make recommendations on how the observation tool will be added to the process map.

### The Supplier will make recommendations, as appropriate, on what compliance areas the NUAR platform needs to cover in order to fit in with the current legislation and compliance requirements. The Supplier will highlight any identified areas in the integration of NUAR in the BAU processes that might create a risk of compromising compliance.

### The Supplier will compare the processes flow that includes the NUAR platform with the Scottish Roadworks Commission’s Vault System.

## Work package C – Evaluation of savings

### The purpose of this work package is to conduct a unit-cost based economic analysis on the estimated potential process savings that could be generated when the NUAR platform will be rolled out. This will include both the time and cost savings for each process.

### The Supplier will develop a unit-cost estimation of process costs based on the BAU process maps generated as part of Work Package A. The estimation will include the time and unit cost estimates for each of the common process steps and for those processes with specific and key outliers. The unit cost analysis must include all the different approaches asset owners use to conduct utility searches.

### The Supplier will then develop a unit-cost estimation of process costs based on the outcome of Work package B, where some processes will be removed after the NUAR roll out. The Supplier will compare the time and cost estimations of BAU processes to the processes after NUAR roll out -where the time and cost savings for each part of the process is clearly presented.

# KEY MILESTONES AND DELIVERABLES

## The main output of each wok package is expected to take the format of a research report. It is also expected that a spreadsheet detailing each of the processes captured as part of the research and their subsequent time and cost savings will be submitted. Prior to each final report being delivered, a series of presentation outputs and building blocks to the final output are expected to be shared with the Commission, as laid out in the milestones table.

## The following Contract milestones/deliverables shall apply:

| ### Milestone/Deliverable | ### Description | ### Timeframe or Delivery Date |
| --- | --- | --- |
| ### Work package A – Research into existing BAU |  |  |
| ### 1 | ### Kick off meeting | ### Within week 1 of Contract Award |
| ### Gateway point 1 | ### Presentation of proposed methodology for sampling of selected asset owner organisations and Tier 1 contractors | ### Within week 2 of Contract Award |
| ### 2 | ### Presentation (reporting) of participants contacted and response rate (broken down by organisation type and sector), including copy of questionnaires and templates used | ### Within week 6 of Contract Award |
| ### Gateway point 2 | ### Presentation of aggregated process flow maps and outliers, including utilities searches options and compliance requirements | ### Within week 7 of Contract Award |
| ### 3 | ### Draft Work package A report with findings | ### Within week 8 of Contract Award |
| ### Gateway point 3 | ### Final Work package A report with findings | ### Within week 9 of Contract Award |
| ### Work package B - NUAR integration analysis |  |  |
| ### 4 | ### Kick-off meeting – presentation of proposed methodology for conducting the NUAR integration analysis, including integration of the observation tool and compliance risks. | ### Within week 9 of Contract Award |
| ### Gateway point 4 | ### Presentation of initial findings, including progress towards comparison with Vault system | ### Within week 10 of Contract Award |
| ### 5 | ### Draft Work package B report with findings and recommendations | ### Within week 11 of Contract Award and no later than 2nd November 2020 |
| ### Gateway point 5 | ### Final Work package B report with findings and recommendations | ### Within week 13 of Contract Award |
| ### Work package C – Evaluation of savings |  |  |
| ### 6 | ### Kick-off meeting – presentation of proposed methodology for unit-cost analysis | ### Within week 14 of Contract Award |
| ### Gateway point 5 | ### Presentation of initial findings | ### Within week 19 of Contract Award |
| ### 7 | ### Draft Work package C report with findings and recommendations | ### Within week 21 of Contract Award |
| ### Gateway point 6 | ### Final Work package C report with findings and recommendations | ### Within week 23 of Contract Award |

# MANAGEMENT INFORMATION/REPORTING

## The Supplier shall give regular updates on progress through weekly progress review meetings. The Supplier shall provide more detailed updates at key points in the Contract as outlined in the milestones in Section 7, either through Contract Review meetings or other discrete meetings as agreed with the Geospatial Commission.

# CONTINUOUS IMPROVEMENT

## The Supplier will be expected to continually improve the way in which the required Services are to be delivered throughout the Contract duration.

## The Supplier should present new ways of working to the Commission during Contract review meetings.

## Changes to the way in which the Services are to be delivered must be brought to the Commission’s attention and agreed prior to any changes being implemented.

# QUALITY

## The Supplier shall have sound processes for quality assurance of both quantitative and qualitative outputs in place.

## The Supplier shall outline their internal procedures for assurance and quality control in reference to the research, including:

### Procedures for working closely with the Geospatial Commission;

### Procedures for quality assuring proposals, methods and outputs;

### Procedures for data gathering quality assurance, including securing accuracy and eliminating reporting bias;

### Procedures for representative sample selection for the deep dive purposes;

### Interview quality control procedures, how response rates are maximised, and how interviewer and respondent error is managed (if applicable);

### Procedures for qualitative and quantitative analysis and reporting;

### The approach to report writing, ensuring deliverables meet key objectives;

### Procedures for handling complaints.

# STAFF AND CUSTOMER SERVICE

## The Supplier shall have a proven track record of networking and engagement with the utilities sector across the country.

## The Supplier shall provide a sufficient level of resource throughout the duration of the Contract in order to consistently deliver a quality service.

## The Supplier’s staff assigned to the Contract shall have the relevant qualifications and experience to deliver the Contract to the required standard.

## The Supplier shall ensure that staff understand the Commission’s vision and objectives and will provide excellent customer service to the Commission throughout the duration of the Contract.

# SERVICE LEVELS AND PERFORMANCE

## The Commission will measure the quality of the Supplier’s delivery by:

| ## KPI/SLA | ## Service Area | ## KPI/SLA description | ## Target |
| --- | --- | --- | --- |
| ## 1 | ## Delivery of project outputs | ## Project outputs delivered according to the timescales set out in the deliverables table in Section 7. | ## 98% |
| ## 2 | ## Quality Assurance | ## Project outputs to be peer reviewed and follow an approval process (with clear quality assurance steps) before submission, to ensure accuracy of information, elimination of reporting bias and high levels of confidence in the outputs. | ## 98% |
| ## 3 | ## Response time | ## Responding to the questions and queries from the Geospatial Commission within 48 hours (Monday-Friday). | ## 95% |
| ## 4 | ## Project Management | ## Weekly project updates (format to be agreed upon contract commencement). | ## 98% |

## The contract will be terminated if the quality of the interim outputs is not of the expected quality and does not cover the deliverables agreed between the Geospatial Commission and the Supplier. The quality of the interim outputs will be assessed during the Gateway Points, as presented in the deliverables tables, under paragraph 7.2.

# SECURITY AND CONFIDENTIALITY REQUIREMENTS

## When meetings are held at the Geospatial Commission location (100 Parliament Street, London, SW1A 2BQ) the Supplier will need to be escorted to/from meetings and around the building due to security restrictions.

## The results/deliverables of the Contract should not be shared wider than the Supplier’s project team without explicit approval from the Geospatial Commission.

## The resulting outputs shall be the intellectual property of the Geospatial Commission. The analysis, and the interim and final reports, shall be the property of the Geospatial Commission. The Supplier shall not disclose the report (either in part or in full) to any third parties prior to publication by the Geospatial Commission, unless the Geospatial Commission gives expressed written consent to do so.

## All data security processes must be compliant with the General Data Protection Regulation (GDPR).

## The Supplier will be required to sign a Non-Disclosure Agreement (NDA) to cover the information the Commission will be sharing with them for the purposes of this contract.

# CONTRACT MANAGEMENT

## Attendance at Contract Review meetings shall be at the Supplier’s own expense. These will be held in accordance with the deliverables table, under paragraph 7.2

## Progress reporting should be provided to the Geospatial Commission at least weekly. The format and detail covered within these updates is to be agreed at the project inception meeting.

## The successful Supplier will be notified of details of the Programme Delivery Manager upon award.

# LOCATION

## The location of the Services will be carried out at the Supplier’s own offices for the majority of the time. The Geospatial Commission is based at 100 Parliament Street, London, SW1A 2BQ. The Supplier will be expected to attend regular progress checks at the location of the Commission as the research and analysis is being carried out, as well as contract reviews. All meetings might be organised as online video calls, in line with Government guidelines on the Covid-19 response.

Annex B

Supplier Proposal

REDACTED

  - Contract Terms

Attached as Separate Document

  - Supplier Costings

REDACTED

Rate Card

REDACTED