National Institute for Health and Care Excellence (NICE)

Invitation to tender

Requirements Specification for Reputation Research Survey 2018

Contract duration:   1 October 2018 to 31st March 2019

- Introduction

NICE, the National Institute for Health and Care Excellence, is an independent organisation responsible for providing evidence-based guidance on health and social care. NICE guidance, standards and other resources help health, public health and social care professionals deliver the best possible care within the resources available.

The NICE charter contains detailed information about who we are, what we do and the principles we work to. Details of our work programmes and examples of the guidelines can be found on the NICE website (www.nice.org.uk).

NICE is seeking bids through this invitation to tender to deliver a stakeholder reputation research project.

- Summary

NICE are procuring services to enable us to appoint a supplier for our stakeholder reputation research work, to include an online survey and qualitative research (interviews or focus groups as appropriate). The supplier will plan and produce all aspects of the NICE reputation research project, from October 2018. The intention is to repeat the project every 2 years.

The supplier will work closely with NICE to develop and deliver a high quality stakeholder reputation research project.

The contract will start in October 2018, and end in March 2019.

3.0	The NICE Stakeholder Reputation Research

Since 2015 NICE has been tracking public perception on a biannual basis, subscribing to reports from the Reputation Institute. In 2017 NICE was selected by the Cabinet Office to receive pro bono consultancy from the Reputation Institute to pilot a stakeholder reputation survey using the Reputation Institute’s RepTrak® model. The model provides an approach to measuring reputation, which is used globally across the private sector and nationally across the public sector to benchmark perceptions. The model is structured around four core themes and seven reputation dimensions and together these elements explain an organisation’s reputation.

NICE developed a survey that incorporated questions from the RepTrak® model, as well as including questions specific to NICE and ones that had been asked in previous studies to enable some comparison over time. The survey was delivered by NICE’s audience insight team, achieving 825 responses.

NICE would now like to combine the public and stakeholder perception surveys and outsource delivery to an external agency, who would work closely with NICE’s audience insight team. The audience insight team will be able to provide detail and feedback on previous studies and feed into and advise on the design and fieldwork elements of the project.

NICE does not require there to be direct comparison with the RepTrak® model, but it is expected that the survey will include some questions that have been asked in previous surveys to enable comparisons to be made over time.

In addition, we would like to undertake some qualitative research with some of our stakeholder partners to explore and understand their perspectives in more depth. We envisage this would be as a series of interviews with selected stakeholders, but are open to suggestions.

The primary objectives of the reputation research are to:

Measure stakeholder perceptions of NICE that shape its overall reputation.

Understand how stakeholder audiences interact with the organisation.

Understand how NICE performs against stakeholders' expectations.

Understand how NICE performs against selected benchmark organisations in relation to several key indicators (to be agreed).

NICE’s stakeholder groups are many and varied and the reputation survey will need to be distributed through different channels to reach them. Examples of our stakeholders (and groups we would expect to see represented in the distribution plan) include but are not limited to:

NICE’s sponsor department and other public sector partners, including the Department of Health and Social Care (sponsor department), NHS England, Public Health England, Department of Education, NHS Choices (contact details will be provided).

Practitioners, such as doctors, GPs, nurses, midwiferies, allied health professionals, pharmacists/medicines management, service managers, commissioners, public health and social care professionals and students.

General public, patients, service users and carers

Voluntary and community organisations

Pharmaceutical industries

Opinion formers, including MPs and journalists

NICE has an Insight Community of around 1,600 contacts who have agreed to be contacted for research purposes. Suppliers will be able to use this list as a means of distributing the survey. We would also be happy to promote the survey through our existing communication channels, including our monthly newsletters and social media. Submissions should include a detailed distribution plan and sampling method to show clearly how the survey will be sent to stakeholder groups to ensure that all are given the opportunity to respond.

- Essential Skills and Service Requirements

Specifically, the essential skills and service requirements that should be demonstrated in the tender response are as follows:

- Essential skills

  - Evidence of a successful track record of delivery of stakeholder surveys and research

  - Evidence of working collaboratively with clients

  - Ability to produce well designed surveys

  - Ability to conduct high quality qualitative research

  - Ability to produce insightful and actionable reports

  - Ability to produce findings in an engaging format

  - Ability to present findings to senior managers and board members

  - Evidence of working under a contract with Service Level Agreements (SLAs) and Key Performance Indicators (KPIs) monitoring and review tools.

- Service requirements

  - Detail of project management process, with clearly defined team responsibilities

  - Clearly defined timescale for delivery, including milestones

  - Collaborative working with the NICE audience insight team on the design of the stakeholder survey questions and discussion guides, so that some questions from historical surveys continue to be asked and comparisons can be made with previous results.

  - An approach that ensures that results can be benchmarked against other public bodies and particularly those within the health and social care family, such as Public Health England and the Care Quality Commission.

  - Details of survey distribution channels to be offered to ensure all of our stakeholder groups are given equal opportunity to respond.

  - Production of findings in the form of an engaging and insightful report that provides an understanding of how stakeholders perceive NICE. The report shall include detailed analysis and breakdown of results, where appropriate, and recommendations for improving NICE’s reputation among stakeholders.

  - Provision of the raw data, including survey data and transcripts from the qualitative work

  - Presentation of the findings to NICE’s Senior Management team (SMT) (Manchester or London). A presentation may also be required to the NICE Board. Please provide these costings as an addition.

- Monitoring and Evaluation

The performance of the supplier will be monitored against delivery of the requirements as set out above and listed in Annex 2, Milestones” of the final contract document.

In addition, the contractor shall undertake the following monitoring and evaluation tasks:

  - Provide records of number of completed surveys, including regular updates during the stakeholder survey response window.

  - Regular catch ups with NICE’s audience insight team (based in Manchester). To include a project kick off and meeting/discussion prior to survey distribution and qualitative work – not all meetings need to be face to face.

  - Regular update reports provided to NICE on the progress of the project.

  - Reports provided on the extent to which SLAs and KPIs have been met.

- Standards and Quality Assurance

The standards and quality assurance of the supplier will be measured against the delivery of the stakeholder reputation project.

In addition the supplier should have effective internal processes to support their own quality assurance. The methodology of the supplier in terms of quality assurance is imperative for the stakeholder reputation survey. The systematic monitoring and evaluation of the various aspects of the process are necessary to ensure that high standards of quality are being met.

Data integrity is very important, the supplier must demonstrate to NICE how they intend to effectively maintain and ensure the accuracy and consistency of the data collected during the project.

In addition the supplier must evidence that the requirements of the General Data Protection Regulation will be met and the rights of data subjects protected.

7.0	Declaration of Interests

NICE has a wide range of stakeholders with an interest and involvement in its work, including the general public, patients and carers, healthcare professionals, industry, political audiences, academia and international audiences. It is important for potential bidders to indicate where they anticipate areas of conflict with their existing work base, and how they would handle issues of conflict of interest and confidentiality should they arise. (Please see the form in the tender pack titled “Competing Interests”).

NICE’s code of practice on declaring and dealing with conflicts of interest must be adhered to.

8.0	Transparency

In light of the government’s need for greater transparency, suppliers and those organisations looking to bid for public sector contracts should be aware that if they are awarded a contract for this work, the resulting contract between the supplier and NICE will be published in its entirety.

In some circumstances, limited redactions will be made to some contracts before they are published in order to comply with existing law and for the protection of national security. Suppliers are asked to complete the Redactions Request form in the tender pack.

Please note that the total value (bottom line) of the agreement is required to be published under current EU regulations and the UK government’s Transparency Agenda.  If you require clarity on this point, please contact us via the route stated in section 12.1 below.

9.0	Budget

NICE will accept tenders up to £40,000 exclusive of VAT. Submissions will be judged on their overall quality and value for money, together with their likely success in providing the data and insights needed within the agreed timeframe.

NICE is a public sector employer, which qualifies us for a public sector discount with many organisations. If this applies to your bid, please ensure that this is outlined clearly in your proposal and ensure that the final cost is inclusive of any public sector discount.

- Your proposal

Set out in the same order as below, with reference to the requirements in clauses 2 to 9 and applying the same ordering convention as below:

  - Experience and expertise:

    - Summary of expertise and experience / track record in this field, demonstrating how you have worked collaboratively with other organisations.  This should also include membership of specialist professional bodies or any associated accreditations achieved.

    - Provision of a detailed project plan, showing key milestones, activities and delivery dates.

    - Detail of how you will work with the audience insight team to ensure that there is comparability with previous research projects

    - Experience of producing findings in an engaging format, ensuring they are tailored for the audience and include detailed analysis and breakdown of results

    - Evidence of ability to provide presentations on key findings to the NICE Board and Senior Management Team (SMT).

  - Methodology

    - Detail of staff that will be involved in each stage of the process and what their specific roles will be.

    - Description of the proposed approach, including survey and discussion guide design, distribution of survey, recruitment for qualitative work, reporting and presentations.

    - Details of distribution channels to be used to ensure that all our stakeholder groups are given the opportunity to respond to the survey.

    - Confirmation that NICE will own the data at the end of the process.

  - Contract management:

    - Please provide a project timeline, detailing milestones.

    - Please identify the risks associated with this contract, stating whether you consider them to be of high, medium or low probability of occurring and provide a summary of how you would mitigate each risk.

    - Please list any areas of existing work undertaken by your organisation and its members that may conflict with the work of the Institute and processes that you have in place to deal with any such conflicts that could arise during the contract period.

    - Please provide details of your process for dealing with conflicts of interest.

    - Please detail how you would review the project throughout the period of the contract to ensure Service Level Agreements (SLAs) and Key Performance Indicators (KPIs) are being adhered to

    - Please detail your experience of working under a contract with Service Level Agreements (SLAs) and Key Performance Indicators (KPIs) in place.

  - Standards and Quality Assurance:

    - Please detail your procedure to provide quality assurance and quality control of your work, including accuracy of data.

    - Please demonstrate how you ensure that respondent confidentiality is maintained.

    - Please detail what happens when concerns or complaints arise.

    - Please provide evidence that the requirements of the General Data Protection Regulation will be met and the rights of data subjects are protected.

  - Costings

    - Please detail your charging basis for the stakeholder reputation research, all costs and expenses must be included within the pricing presented. The final cost must be inclusive of any public sector discount.

    - Please state the benefits of your proposal and where your proposal adds value for money.

    - A detailed cost breakdown for this work as follows:

    - Please provide a cost breakdown in GBP sterling, exclusive of Value Added Tax (VAT), of the budget necessary to deliver the service required.

    - Please complete the costing table in the format provided below as failure to do so may result in your offer being rejected. All travel and subsistence costs are to be included in the specification cost below.

    - Provide costs below, exclusive of VAT in the table below:

| Total stakeholder reputation survey Specification Cost | GBP Sterling |
| --- | --- |
| Total Cost | £………………… excl VAT |
| Additional costs if presentation to the Board is required | £………………… excl VAT |

  - Policies, Certifications and Financial Statements

As required by Public Sector regulations and in line with best practice, please provide one copy each of your organisation’s policies relating to the following:

  - Health and Safety

  - Environmental

  - Equal Opportunities and Diversity in the Work Place

  - Modern Slavery Act Compliance

We recognise that some SMEs (small, medium enterprises) (less than 50 people for a small enterprise and less than 250 for a medium enterprise) may not have formal policies available but still operate their businesses in a manner that is conducive to the above. If you are an SME and do not have formal policies in place, please submit with your response, a written statement on how your company operates in light of the above three areas of legislation and best practice.

In addition please provide the following:

- The last three years of audited accounts for your organisation. If your organisation is an SME and you do not have audited accounts, please provide 3 years of balance sheets.

- A declaration (if applicable) of all current projects with clients or partners that your department/ group/organisation is currently working with which could be seen as being detrimental or ethically opposed to the health aims promoted by NICE.

- If your organisation (whole organisation including parent, group or subsidiary) has a turnover of £36 million pounds or greater then please provide a Modern Slavery Act Transparency Statement: this should set out the steps you have taken to ensure there is no modern slavery in your own organisation/business and that of your supply chain. If your organisation has taken no steps to ensure there is no modern slavery in your own organisation, then your statement should say so. [Please note: a parent org/ group statement is acceptable, this is compliance with the Modern Slavery Act 2015.]

  - References

    - Supply the names and contact details of two recent clients who would be willing to provide a confidential reference in support of the proposal, where either the same or very similar work to that being requested here, has been undertaken within the last 3 years.

11.0	Timetable

| Issue tender | 21/06/2018 |
| --- | --- |
| Deadline for expressions of Interest | 5pm 9/07/2018 |
| Deadline for Tender Questions | 5pm 9/07/2018 |
| Answers to questions sent out by NICE | 5pm 10/07/2018 |
| Tender receipt deadline | 12 noon 30/07/2018 |
| Tender assessment | 31/07-17/08/2018 |
| Notify short list | 20/08/2018 |
| Interviews | 04/09/2018 |
| Award contract and issue debrief | 04/09/2018 |
| Alcatel period (standstill period) | 05-14/09/2018 |
| Contract start | 01/10/2018 |

12.0	Tender instructions

12.1	Interested parties must submit an expression of interest (EOI) no later than 17:00 on 9th July 2018 to Gillian.Watson@nice.org.uk.

12.2	Bidders who submit a proposal and have not sent an EOI by the above deadline date and time shall not be considered.

12.3	Tenders must be submitted electronically no later than 12 Noon UK time on 30th July 2018 to contract.bids@nice.org.uk.

12.4	All tender proposals and the supporting documents must be written in English.

12.5	Failure to comply with these instructions may result in your offer being rejected.

12.6	The proposal must be titled ‘Nice Reputation Research Survey Service” and the bidder must answer all questions as accurately and concisely as possible in the same order as the questions are presented.

12.7	Where a question is not relevant to the bidder’s organisation, this should be indicated, with an explanation.

12.8	The bidder must be explicit and comprehensive in their proposals as this will be the single source of information on which their response will be evaluated.

12.9	The bidder is advised neither to make any assumptions about their past or current bidder relationships with NICE nor to assume that such prior business relationships will be taken into account in the evaluation procedure.

12.10	All offers must be submitted in GBP sterling and must be exclusive of Value Added Tax (VAT)

12.11	The Form of Offer must be submitted in hard copy only to arrive by 12 noon on 30th July 2018, addressed to:

Gillian Watson

Senior Procurement Officer

National Institute for Health and Care Excellence

Level 1a, City Tower

Piccadilly Plaza

Manchester

M1 4BT
Please note - The envelope must not identify the name of your company.

12.12	Before any documentation is submitted, those wishing to tender may have specific questions and queries regarding the process, the policy or the arrangements with NICE.  Under our procurement arrangements NICE has to ensure that all applicants receive equal treatment and we will share all information requests and responses with all applicants.  Consequently all questions and queries regarding this invitation to offer must be submitted by email to Gillian Watson (gillian.watson@nice.org.uk) no later than 17:00hrs 9th July 2018.

12.13	The questions and answers will be collated and distributed by email to all the potential tenderers by 17:00hrs 10th July 2018.  Please note that that there will be no telephone or informal or other kind of discussion between potential tenderers and officers or directors of NICE after this document is dispatched.

13.0	Selection Criteria

| Criteria | Weighting |
| --- | --- |
| - Policies, Certifications and Financial Statements (A bidder will be excluded from assessment if satisfactory policies and procedures, including their financial statements are not provided) | PASS/FAIL |
| Experience and Expertise / references - to include demonstrated experience and deliverable outcomes of similar processes. This will include the supply of 2 references. | 20 |
| Methodology - to include rationale for methodological approach, measurable outcomes and evaluations as well as identifying and resolving conflicts of interests. | 15 |
| Contract Management - to include an example time plan and staff allocation to tasks and identifying and mitigating risks. | 10 |
| Standards & Quality Assurance - to include evidence of quality standards, demonstrable process outcomes, risks, QA policy, Data Protection and Freedom of Information and Conflicts of Interest. | 5 |
| Project Cost & value for money (costings) | 50 |

- In light of the government’s drive for transparency, NICE is providing the formula that will be used for the cost evaluation aspect and the scoring guide. The cost will be evaluated using the following formula:

Lowest Bidder’s Price / Bidder’s Price 50

- 14.0 	Criteria and Scoring Guide

- Each evaluator will independently evaluate each tender submitted and use the following guide

- to score each criteria, the scores of all evaluators per criteria are then averaged and the criteria

- weighting is then applied to give an adjusted score.

| Score | Guide |
| --- | --- |
| -5 | The point is omitted |
| 0 | Not explained / repeat of specification |
| 1 | The point is not acceptable |
| 2 | The point is possibly acceptable |
| 3 | The point is acceptable |
| 4 | The point is well made and acceptable |
| 5 | Exceeds expectations / excellent |

15.0	Non-compliance

- NICE expressly reserves the right to reject any proposal that:

- Does not follow the instruction to tender guidelines

- Is incomplete, for example where answers are not provided to any questions, or a reasonable explanation is not given as to why an answer  has been omitted

- Refuses to adhere to, or makes significant unacceptable changes to the Terms and Conditions of Contract

- Has not responded to any mandatory elements, including failing to provide requested documents (i.e. the tender is non-compliant).