## Sheet1
CLARIFICATION LOG
Tender: | Design Tender - Roof Repair Works (MEND) - Royal Institution of Cornwall
Tender Reference: | 10/2023_(03)
Published Date:
Version number: | 0.4
Number | Clarification | Response | Reply date
1 | Are the site visits on the same day / time for all suppliers. | Yes. We have updated the Volume 1 - Timetable to afford the opportunity for Site Visits but these will be on set days / times – 13/10/2023 at 10:30 or 18/10/2023 at 13:00 Please contact Authorised Representative to arrange. | 2023-10-06
2 | How is the project being funded? | Funded by the Arts Council and Cornwall Council. | 2023-10-12
3 | Has a Principal Designer already been appointed up to RIBA Stage 3 and if so, will the information prepared to date be provided? | No. Scott& Co (details on drawings) were appointed to submit the Planning applications not to progress any project. There was no prior Principal Designer appointment. | 2023-10-12
4 | The Developed Design (RIBA Stage 3) already carried out, may introduce potential design liability issues. Any new designer would need to review the design undertaken to date. Is the client prepared to accept a design review and changes in design proposals to mitigate design liabilities, including potential delays in programme which may result? | It is understood that a design review will need to be undertaken. However, it is hoped that as planning has been approved, then there won't be many, if any, changes in the design proposals as time and budget are both restricted due to funding requirements. | 2023-10-12
5 | Are you requesting a Design Team to Complete Design, Tender and Contract Administration Task RIBA 4-6 inclusive or are you seeking a Design + Build Team to complete the design and implement the construction works? | Please see Appendices 1 and 5 which outline the duties that are required. We will require a PM to run the tender process, supervise the works to ensure compliance with their design and to advise the client. They will also be required to attend the site weekly and to maintain quality checks and raise defects as required. | 2023-10-12
6 | The requirement of minimum £10m Public Liability Insurance, is that required to be provided by the design team or could this be provided as a consortium Design + Build Team? | Just the design team. | 2023-10-12
7 | Do you expect there to be any input needed from a structural engineer as part of the works? | We do not believe that there is a need for a structural engineer. The project is for replacement roof coverings, no increased loadings are anticipated. | 2023-10-12
8 | Can you confirm the scope of the tender return please: - Do you require further information on top of the tender forms, and method statement? - Do you require CVs for the proposed team? - Do you require relevant case studies of similar completed work? | As detailed in Volume 2: Please provide CV and / or organisation biographies detailing all key members of your core team, either individuals or companies and the role which they would play in the delivery of the project. Where roles are not yet determined at time of tender then details should be provided around how you would select and appoint, to take into account assurances on high end quality outcomes, detail how you propose to meet that condition e.g. appoint another individual or organisation under your supervision with the specific experience, skill or knowledge required to meet the condition. Provide the name and contact details of sub contractors. To support your response, we would be seeking suitable case studies and references sites which Royal Institution of Cornwall may seek to contact as part of due diligence around evaluation. Your proposals should provide clear reference on how the experience you have would be utilised on this project to deliver meaningful quality outcomes. | 2023-10-12
9 | Reference Revised Heritage, Design and Access Statement: 4.03 Note: ‘possibly’ asbestos containing slates. Has there been a survey done yet? And if so, can this be provided please? Our query relating to Appendix 4 – Core Project Document Schedule below, also refers. If this has not yet been completed, we assume we are to allow for procuring a suitable survey prior to the commencement of construction works but can you please confirm? | Asbestos survey taking place November 6th. | 2023-10-25
10 | Grant of Listed Building Consent - 11 October 2022: Can any background information be provided as to why there are two separate listed building consents please? One for general roof works, then one for re-laying slates to specific areas. | The project expanded which needed another Lsted Building Approval. | 2023-10-25
11 | Appendix 1 – Brief Final: iii) refers to ‘bills of quantities’ - has the procurement method been agreed and fixed i.e. a traditional procurement route with the pricing document being a full bill of quantities? Or is procurement advice required? Additionally, is a schedule of works, or other similar (less detailed) pricing document more appropriate? | This is for the design team to recommend. The build element of the works would need to be in line with the public sector procurement Regulations. | 2023-10-25
12 | Appendix 1 – Brief Final: v) refers to “managing… quality of outcomes by the main contractor…” – elsewhere, the Construction phase role is described as ‘Client Agent’ and ‘Contract Administration’. We note the clarification (shown on Clarification Log v0.3)uploaded to the contracts finder portal referencing weekly site visits, but for the purposes of this proposal, is this a requirement for a ‘clerk of works’ role requiring weekly (written) reports please? | For the purposes of this tender, please allow for a clerk of works to undertake weekly site visits and to produce weekly reports to capture installation progress and any quality issues on behalf of the client. | 2023-10-25
13 | Appendix 2 – Key Contract Conditions: The terminology used appears to relate to an NEC standard form of agreement (for professional services) but in Volume 1 (paragraph 2.8) the Contract Conditions are noted as a JCT Consultancy Agreement (Public Sector). Can you clarify the proposed form of agreement and any revised Key Contract Conditions please? | JCT Consultancy Agreement (Public Sector) would be the preferred terms of contract. | 2023-10-25
14 | Appendix 2 – Key Contract Conditions: Refers to Asbestos Survey – ‘to follow’. Is this document available please? | Survey to be undertaken 6th November. Report will be issued to the succesful tenderer. | 2023-10-25
15 | Appendix 5 – Plan on a Page: Are you able to provide a schedule of meetings & meeting requirements please (Teams/in-person)? | Fortnightly online will typically suffice but will also expect face to face meetings at significant stages of the project. | 2023-10-25
16 | Design and Access Statement: There are two versions, one dated 12th August, one dated 9th October. Can you confirm which we are to base our proposal on please? | 9th October | 2023-10-25
17 | Volume 1 - Background, Instructions and Conditions of Tender - as amended by Clarification Log v0.3: We note from the Revised 'Volume 1' and clarifications posted on the contracts finder portal (Clarification Log v0.3 ) that dates for site visits were clarified on 6th October to be a) arranged on two dates for all tenderers and b) in the past (as this query is written). This is an update of paragraphs 3.10 & 3.11 of 'Volume 1 - Instructions' which advises tenderers can contact the museum at any time to arrange a visit. Due to annual leave it has not been possible to attend these 'communal' visits so we would request that we can contact the museum to arrange a site visit in accordance with the original tendering instructions on a date prior to the tender deadline please. | No - unfortunately due to the tight timescales of delivery this cannot be accommodated. | 2023-10-25
18 | Do we have as-built information | No | 2023-10-25
19 | Do we have any other roof details | No. But the team may need to recommend opening up /discovery activities to determine roof details. | 2023-10-25
20 | Do we have cctv surveys of the drain outlets | No | 2023-10-25
21 | Should the insulation be between rafters or below or horizontal on ceilings | This is for the design team to recommend. | 2023-10-25
22 | Can the roof level be raised? | This is not covered by the Listed Building Consent but the design team could apply if there is programme time, budget and advantage. | 2023-10-25
23 | Are there access improvements included? | Yes. Others might be proposed subject to further approvals or liaison with the LPA, eg permanent access down from the main flat roof to the Barham Room flat roof. | 2023-10-25
24 | During inspections of 18th October it had been indicated that photographs taken within voids could be made-available. Can these be circulated? | Please see attached images plus Quinquennial Inspection report - Additional photos. | 2023-10-25
25 | Is there any word count for this Tender? | Yes. 4000 words in total. We will accept complimentary and relevant documents as appendices - but these will not be used as part of the scoring process. | 2023-10-25
Clarifications will be published against the Contract Notice on Contracts Finder.
If interested in tendering for this project please ensure you add a "watch this notice" for alerts as from time to time additional information or clarifications may be published related to this tender.
It will be the responsibility of Bidders to ensure they are aware of all published clarifications and ensure that their bid has taken these into account.
In the event of any queries please contact: