## Sheet1
CLARIFICATION LOG
Tender: | Surface Water Drainage Work, Draceana Avenue, Falmouth
Tender Reference: | ITQ 01(01)
Published Date: | 2024-02-02
Version number: | 0.2
Number | Clarification | Response | Reply date
1 | Are we able to lose the arisings from the drainage and soakaway on site? | That is the case, there’s no material to take away from site, the initial top layer of compacted material can be set aside in a bund to be used in the skatepark construction and the deeper material can be used on site at a later date for landscaping. | 2024-01-24
2 | We would like to express our interest in the above opportunity. Could we please get guidance in finding the full tender documents as well as the works/pricing schedule? | Details around the tender process and the design and materials are specified on the PWS drawing attached to the tender; via the Contracts Finder Link - see here: https://www.contractsfinder.service.gov.uk/Notice/1de85549-fa5f-4c20-a65e-4d52744c5924 | 2024-01-24
3 | Regarding the 1nr. hydro slide chamber with penstock gate valve on inlet - Can you kindly advise the design head and flow for the Hydro-Slide. | The flow rate for the Hydro-slide is 5 litres / second. | 2024-02-02
4 | Are we to install the pipe system for the Silt traps and can you confirm the pipe diameter size please? | The skatepark contractors will run the pipe in 110mm from the park to the silt traps, the drainage contractor should install the system up to and including the silt traps the pipe size from the traps is 150mm. | 2024-02-02
5 | Can you confirm around licenced element of works by SWW? | The connection element of the drainage to the existing public sewer requires to be made by qualified and approved to carry out a connection to their network or excavate within 3m of a main. As an alternative to having new mains and service connections installed by South West Water, developers can arrange for the work to be carried out by qualified contractors.” ” The work must be carried out by a company that is accredited with the https://www.lrqa.com/en-gb/utilities/wirs-wirsae/wirs-accreditation/ which is administered by Lloyds Register.” Requirements to be met by persons carrying out works near to water mains and sewers: 1. The precise position of water mains and sewers must be ascertained by hand digging trial holes after first contacting South West Water, who will give such information as is available regarding the general location of the mains and sewer in the area. No liability is accepted for the accuracy of any information given as to the position or existence of water mains and sewers . In particular, service pipes and drainage connection are not generally shown on mains records, but their presence should be anticipated and precautions taken to avoid damage. 2. Notices of intent must be given to South West Water before any works are carried out in the vicinity, except in cases of emergency when our Operations Centre should be contacted as soon as possible. 3. Unless prior written approval has been obtained, mechanical excavation may not be permitted around, or within, 3 meters of the water main or sewer. Excavation may be necessary by hand. 4. Concrete haunches or surrounds to sewer s must not be disturbed without prior written consent from South West Water. 5. Before backfilling, the mains and sewer s will be inspected and any flaws or damage to the pipe or wrapping, if found, will be repaired by South West Water . All such flaws or damage must be immediately reported to the Company as soon as they are discovered. The carrying out of such repair s by South West Water shall not affect the question of liability, should any damage found to have resulted from the acts of those undertaking the works, their contractors, servants or agents. 6. Approved backfill will be used immediately around or over the ma ins and sewer s to a minimum cover of 300mm and the remainder of the backfill shall be to the appropriate Highways Authority Specification for the Reinstatement of Openings in Highways. 7. Both the existing main or sewer and the new works shall be suitably supported to prevent future settlement and any subsequent damage to equipment. 8. Ground adjacent to concrete thrust blocks supporting the main(s) and sewer(s) must not be disturbed. 9. Adequate support must be given to all water mains and sewers where these are likely to be undermined, and to all trenches in the vicinity of these, during the process of the works. 10. No apparatus shall be laid on or over any land within 300mm measured horizontally from any part of a water main or sewer or other apparatus belonging to the Company. Provided always that this cause shall not prevent any pipe, cable or conducting medium being laid at an angle of between 45 and 90 degrees across the line of the Company’s apparatus, with a vertical clearance in excess of 300mm. In exceptional circumstances this clause may be varied or deleted with the prior written consent from South West Water. 11. South West Water must be consulted before any work representing an increased risk to the integrity of the mains or sewers (e.g., piling, using explosives, thrust boring, pipe bursting etc.) is carried out. 12. Facilities for inspecting all work carried out shall be given to South West Water with adequate notice | 2024-02-02
6 | Are subcontractors permitted | Yes, as long as they are acredited for any of the works that required the consent of South West Water
Clarifications will be published against the Contract Notice on Contracts Finder.
If interested in tendering for this project please ensure you add a "watch this notice" for alerts as from time to time additional information or clarifications may be published related to this tender.
It will be the responsibility of Bidders to ensure they are aware of all published clarifications and ensure that their bid has taken these into account.
In the event of any queries please contact: