## Sheet1
CLARIFICATION LOG
Tender: | 0036 Development of Health and Well-being Hub
Tender Reference: | 0036
Published Date:
Version number: | 7
Number | Clarification | Response | Reply date
1 | We are aware that the University has a framework in place, can you clarify that this opportunity is not being procured through the framework and if this is the case what is the reasoning for this being procured out with the framework? | The University does not have a suitable Framework in place and is therefore using this Open Procedure for the appointment of the necessary consultants to undertake the commission in question. | 2023-02-14
2 | The Scope of Services being tendered do not include for an NEC Project Manager, should we include for this service as part of our offering, or is there an incumbent organisation providing this service? | The role of Project Manager under NEC4, or its equivalent under other forms of Works Contract, is to be included within the Scope of Service for this commission. | 2023-02-16
3 | The pricing document makes allowance for the Tenderer to cost for Clerk of Works (CoW) services, but under the NEC FoC there is a named entity called the Supervisor who carries out much of the same services as the CoW - should we include for Supervisor services as part of our bid instead of CoW? | The role of Supervisor under NEC4, or its equivalent under other forms of Works Contract, is to be included within the Scope of Service for this commission. The employment of a Clerk of Works is in addition to the Supervisor role and the Price Schedule is to be completed accordingly. | 2023-02-16
4 | Regarding the requirement for the key parties to provide examples of similar project experience / technical ability can you clarify what you mean by Lead Consultant – is the organisation leading the bid / will be contracting with the client entity? | The Lead Consultant is the entity which the Client will enter into contract with. | 2023-02-16
5 | Also on the same subject, would it be possible for tenderers to provide details of experience / technical ability for projects that are virtually complete (i.e. PC within weeks), rather than post-Completion? | Projects which are not completed will not be assessed. For clarity, the date on the PC certifate, or equivalent, must be no later than the closing date for return of tenders for this commission | 2023-02-16
6 | We are bidding as a Lead Consultant and have Sub-Consultants (other organisations) to carry some of the other services. You state the other Sub-Consultants (other organisations) supporting us as Lead are required to complete the self-declaration in Part 1 and 2 of Volume 2. Are you asking for each organisation to also complete all sections contained with part 1 and 2 eg. Supplier information, grounds for mandatory exclusion and economic standing? | Yes. All organisations making up a Team must complete Parts 1 and 2. | 2023-02-17
7 | It is noted that within Appendix D of the tender ‘NEC4 Contract Conditions’ the Contract Data states Delay damages for completion of the whole of the service are set as £1,000 per day. Could the University of St Mark and St John clarify whether this is intended to be the case and if so how the Damages would be enforced? | The delay damages will be enforced in line with the terms of the contract | 2023-02-17
8 | The Price Schedule has lump sums against each activity stage. Do you require this as a whole team lump sum or would you like for us to add separate columns for other team disciplines which makes up the overall lump sum? | The only figures required are the total (lump sum) figures for each Stage. | 2023-02-17
9 | With respect to 3,500 character limit with spaces. Does this mean 3,500 character limit including spaces or spaces cane be on top? Also, are we able to increase the character limit please as the questions are very detailed for us to answer? | The limit is 3500 characters including spaces. Information provided beyond that limit will not be assessed | 2023-02-17
10 | With respect to 3,500 character limit with spaces. Are we permitted to include as many diagrams as we want to? Also, would you like separate CV’s as an appendix on top of the 3,500 character limit? | Diagrams are not permitted and if included, will not be assessed. Additional documents must not be sent and will not be assessed | 2023-02-17
11 | Access to view the Premises during the tender period | To minimise disruption to the tenants, bidders wishing to view the premises will be limited to 4 people, permitted a maximum of 1 hour inside the building and will not be permitted to enter occupied rooms | 2023-02-17
12 | The design deliverable identified in the Scope Of Service has been defined as follows: STAGE A - Initial Design and preparation of brief and concept design: STAGE B - Developed Outline Design, Detailed Design and tendering; STAGE C - Construction Contract; STAGE D - Commissioning and Handover | The end of Stage B aligns with the end of RIBA Stage 4. By completion of Stage B designs should be in a prescriptive format. Contractor design elements are to be kept to a minimum. | 2023-02-21
These deliverables do not align directly with the BSRIA BG6 deliverables for an MEP consultant, we are assuming that the MEP design at Stage B will be acceptable at RIBA 4i and the services contractor will be responsible for the RIBA 4iii & 5 stages duties.
13 | Please provide a copy of the Universities Net Carbon Zero and sustainability policy as we would like to understand the target defined as Zero Carbon. | Marjon Zero ¦ Plymouth Marjon University | 2023-02-21
14 | Your answer to your clarification 7 (clarification log v.05) for delay damages to the design team of £1000 per day will be enforced. Can you please clarify how this will be enforced without the availability of a detailed programme from yourselves and how delays will be evaluated? Also, what happens if the delays are caused by 3rd parties outside of our control and how will this be assessed? We have a number of team members pulling out of this tender because these damages are over and above any contract agreement seen before and insurers are not willing to accept this. | Any delays to the contract will be assessed in line with the terms of the contract, in particular clause 60.1, compensation events. A programme is to be provided by the appointed consultant, as per clause 31.1 | 2023-02-24
15 | Within your HWB consult tender schedule 1 Price FINAL, you state fees won’t be paid until satisfactory completion of the stated Activity at Stages A and B. This could potentially equate to 3/4 months per stage and fees will not be paid until the end of such time. This a large risk on the designers and under normal circumstances, fees are paid on a monthly basis against a %age completion of design/work. Can this please be considered for Stages A and B? | At the discretion of the University, interim payments may be made during Stages A and B. | 2023-02-24
16 | Further to the response to Clarification Q2: regarding provision of Project Management services as part of the commission, should we provide relevant experience and contract examples for this additional team member as per Section 6.1? | If the lead consultant is not acting as Project Manager then the entity providing the Project Manager service is to submit relevant experience an contract examples (Section 6.1) | 2023-03-01
17 | With reference to: Volume 2 - Applicants offer: Section 2 Note 5, Part1 1.2(b) - (ii) - states you may ask them to complete this form (clarified as actually asking each to complete form per Clarification Log). Clarifications Log line 6 question requests clarification of sections required to be completed, not fully addressed by the response provided. Volume 2 - Applicants offer: Sections 2 Notes 5 states part 1 and part 2 must be completed by every organisation that is being relied on. We understand this to mean: Section 2 Part 1 "potential supplier information" - Section 1 (of part1) "potential supplier information" points 1.1(a) to 1.1(p) | All sub-consultants must complete the following questions: 1.1(a) - 1.1(p) 1.2(a)(i) - 1.2(a)(ii) 2.1(a) - 2.3(b) 4.1 - 4.2 5.1 - 5.3 | 2023-03-01
18 | Part 2 Exclusions grounds 2.1(a) to 2.3(b) and that the following are NOT required for completion by all organisations - only the tendering entity. 1.2(a) - (i) to 1.2(b) - (ii) ..approach to ..procurement" 1.3(a) to 1.3(h) "contact details and declaration" section 4 Economic and Financial Standing and Section 5.. "Wider group" Kindly confirm or clarify | See clarification 17 | 2023-03-01
19 | Is a BoQ required or a contract sum analysis (CSA) sufficient? | As stated in the Scope of Service the options for the procurement strategy are to be discussed with the Client | 2023-03-01
20 | Will the building be fully decanted for works or will it be partially occupied and phased? | The building will remain occupied until at least 31 October 2023, with the potential that it will be occupied until 29 february 2024. From 1 March 2024 it will be unoccupied | 2023-03-01
21 | How fixed is the current budget given the extent of work and remodelling? | The upper limit of the budget is fixed at £3.5m | 2023-03-01
22 | Can we include a phasing plan and project programme in the bid submission? | The submission of a phasing plan and project programme do not form part of the tender assessment process. See clarification 10 | 2023-03-01
23 | Is the building Post 2000 construction? | Planning consent for the premises was received in July 2004. The building was completed in late 2005 | 2023-03-01
24 | Will interior design input be required as part of the bid? | The works include significant alteration to the interior of the building. It is for the bidder to decide what disciplines are required to complete the commission | 2023-03-01
25 | Will Marjons be using in-house fire engineering for the fire strategy i.e is it excluded from the scope? | The development of the Fire Strategy for the operation of the completed building will be the responsibility of the Client | 2023-03-01
26 | Will the fit out of healthcare areas need to comply with current HBN’s and HTM’s ? | The Public facing spaces need to comply with the Health Building Notes and Health Technical Memoranda relevant to the proposed works | 2023-03-01
27 | Further to your response to clarification Nr.6, we note that all sub consultants that make up the team will need to complete part 1 & 2 of SQ, can you provide further clarity on question 6.1 examples whether our specialist services consultants (asbestos, SE etc) will need to complete? We will be acting as the Lead Consultant with sub consultants appointed by us on a back to back agreement. | See clarifications 17 and 18 | 2023-03-01
28 | Can you please confirm if it’s a typo error on Page 2 of Appendix D – Retention is stated as “Twelve Years” | The retention period is Twelve years | 2023-03-01
29 | Regarding the £1,000 per day delay damages, some of the supply chain partners are unwilling to bid for the project on this basis. Will this clause remain in the bid ? | Yes. See clarifications 7 and 14 | 2023-03-01
30 | Can you please advise that we are to complete the word template issued (0036 HWB consult tender Volume 2 - Applicants Offer FINAL 020223) along with commercial excel spreadsheet (0036 HWB consult tender Schedule 1 - Price FINAL) only with our submission response? | Yes. See also clarifications 17 and 18 | 2023-03-01
31 | As per the document, 0036 HWB consult tender Appendix A - Scope of Service FINAL 020223, scope b.xxiii please can you confirm whether it is intended that you require bills of quantities. scope as follows: Prepare all drawings, specifications, schedules, bills of quantities and other documents necessary for the obtaining of tenders. Ensure the documentation integrates and co-ordinates where necessary for any Client supplied equipment. Please confirm that bills of quantities will not be required | See clarification 19 | 2023-03-01
32 | Further to clarification 7 and In relation to X7 delay damages at £1,000 a day for completion of the whole services, the contract states that completion date for the whole of the service is "The date of issue of the Making good defects certificate of the construction works contract". In the absence of any respective date in contract data part 1, please can the client outline the process and date for applying delay damages with acknowledgment that it will be the contractor's responsibility for delivering the construction element of this project and therefore not strictly under control of the consultant. | See clarification 14 | 2023-03-01
33 | With regards to payment, could we please clarify the wording around "Fees will be paid upon satisfactory completion of the stated Activity at Stages A and B", i.e is this monthly in line with the contract or at completion of Activity, A, B, C and D? | Please discard the response to clarification 15. Fees will be paid in line with the Contract Data Part 1 (section 5 Payment) | 2023-03-01
34 | Appendix A – Scope of Service – Activity: Stage B, b.xxi - mentions life cycle costings, could we suggst that all tenderers put in a provisional sum of £5k within the summary table, until further detail is adapted? It’s difficult to understand the fee needed for LCC activities without the design detail being rather robust | A provisional sum will not be accepted | 2023-03-01
35 | Schedule 1 – Price. F. Fees will be paid upon satisfactory completion of activity at stages A and B – what does satisfactory mean, client approval (if so, what are the approval parameters), or completion of design team report? Who decides satisfactory completion? H. 80% of stage D fee will be paid upon issue of agreed final account. The remaining 20% will be paid upon issue of the certificate of making goods defects at the end of the defect period – If the construction contract was in dispute, it would prolongate fees being paid, potentially for a considerable time, could this be negotiated?. In addition, 20% retention, is this something that can be negotiated? | F - see clarification 33 H - No. Please note the 20% refers to the percentage of the Stage D fee. | 2023-03-01
36 | Would you mind clarifying for me please the following to ensure I complete correctly/provide the required information. Provision of data is referred to elsewhere but if it's actually to be completed at time of Contract Award and you don't require completion at present as part of Tender kindly advise. Could I also clarify that non or partial completion is not seen as a failure to provide requisite information, I could find no clarification on yes/no compliance or scoring for the document. | Where a question is subject of a Pass/Fail assessment non or partial completion will result in a Fail being given for the question | 2023-03-01
37 | with reference to: NEC4 Contract Conditions, Part 2 Data Provided by the Consultant 1 General - A) "The fee percentage is" - there is a range of expected construction cost for the project (Volume 1 2.1.11) Do you want two percentages stated for £3m and £3.5m? For the fees: Schedule 1 we should use figure from cell G33 (excluding VAT) as above figure is Excluding VAT Please also confirm which takes precedence - details taken from the Schedule 1 response to Tender or NEC4 Contract Conditions? | One percentage fee is to be provided. Cell G33 will automatically adjust in line with the figures inserted in cells F30 and G26 - 29 inclusive. See clarification 33 | 2023-03-01
38 | Please can you confirm the definitive list of roles required for the Development of Health and Well-being hub? | Bidders are to assess the tender documents and decide which disciplines are required to complete the commission. | 2023-03-01
39 | Appendix D Contract Data Part 1, 3 Time, The Starting Date is | The date is to be adjusted to be 30 March 2023 | 2023-03-01
Clarifications will be published against the Contract Notice on Find a Tender and Contracts Finder.
If interested in tendering for this project please ensure you add a "watch this notice" for alerts as from time to time additional information or clarifications may be published related to this tender.
It will be the responsibility of Bidders to ensure they are aware of all published clarifications and ensure that their bid has taken these into account.
In the event of any queries please contact: tenders@marjon.ac.uk