RTMC

Technology Key Performance Indicator Handbook

V1.0

Table of Contents

Document Control	2

TKPI 1: Rectification of Hard Faults	2

TKPI 2: Maintenance programme implementation	2

TKPI 3: Budget Management	2

TKPI 4: Employee Safety	2

TKPI 5: Time and Cost Predictability	2

TKPI 6: Data Management	2

TKPI 8: Quality Management	2

TKPI 9: Availability of Traffic Technology Systems	2

TKPI 11: Asset Condition	2

TKPI 12: Fault Analysis	2

TKPI 13: Internal customer satisfaction.	2

APPENDIX 1- Time and Cost Phases for TKPI 5	2

Document Control

| Document Title | RTMC Technology Key Performance Indicator Handbook |
| --- | --- |
| Author(s) | John Beavis (extracted from TechMAC MST) |
| Owner | Tod Wood |
| Distribution | Members of Performance Management Advisory Group, TechMAC and RTMC managers |
| Document Status | Live |

- Revision History

| Version | Date | Description | Author |
| --- | --- | --- | --- |
| 1.0 | 16/7/2012 | 1st version, extracted from TechMAC MST | John Beavis |

- Approvals

| Name | Document Version | Approval Date |
| --- | --- | --- |
| Tod Wood | 1.0 | 16/7/2012 |

| Indicator Ref. & Title | TKPI 1: Rectification of Hard Faults |
| --- | --- |
| Measure | Maximise availability of Traffic Technology Systems |
| Purpose / Description | To measure the efficiency and effectiveness of the Provider’s fault rectification service. The Provider should rectify faults on the Area Network as quickly and effectively as possible in order to minimise any danger, disruption or delay to the public, or damage to the Area Network and / or local environment. |
| Indicators |  |
| TKPI 1A | Number of category A, B and P faults where service is restored within the Restore Service times stated in Annex SI 13, as a percentage of the total number of such faults. |
| TKPI 1B | Number of category C, D and E faults where service is restored within the Restore Service times stated in Annex SI 13, as a percentage of the total number of such faults. |
| Definitions |  |
| Fault | A disruption or potential hazard to the operation, safety and/or integrity of the Area Network (or adjacent land) that requires an immediate response by the Provider. The fault has to have existed in HALOGEN for a duration longer than 20 minutes. |
| Category | See Annex SI 13 Performance Requirements. |
| Data Source | Provider’s FLOG (fault logging) database, HALOGEN |

Data Input                            Frequency / Reporting Period: Calendar month

| Fields | Total Number of category A faults. | (A) |
| --- | --- | --- |
|  | Total Number of category B faults. | (B) |
|  | Total Number of category P faults. | (P) |
|  | Total Number of category C faults. | (C) |
|  | Total Number of category D faults. | (D) |
|  | Total Number of category E faults. | (E) |
|  | Number of category A, B and P faults where Service is restored within the Restore Service times. | (F) |
|  | Number of category C, D and E faults where Service is restored within the Restore Service times. | (G) |

Calculations (Individual Monthly Performance)

| Measure | Calculation | Type | Decimals | Report |
| --- | --- | --- | --- | --- |
| TKPI 1A (M) | (F/(A+B+P))*100 | Percentage | 1 | G + T |
| TKPI 1B (M) | (G/(C+D+E))*100 | Percentage | 1 | G + T |

Calculations (Rolling 12 Month Performance) i.e. current month + preceding 11 months

| Measure | Calculation | Type | Decimals | Report |
| --- | --- | --- | --- | --- |
| TKPI 1A (A) | (F/(A + B + P)) *100 | Percentage | 1 | T |
| TKPI 1B (A) | (G/(C + D + E)) *100 | Percentage | 1 | T |

Note:   = the aggregation of input data for the current month and the preceding 11 months.

(M) Monthly indicator  (A) Annual indicator

| Indicator Ref. & Title | TKPI 2: Maintenance programme implementation |
| --- | --- |
| Measure | Provide Accurate Programme Information |
| Purpose / Description | To measure the Provider’s ability to schedule its works so as to be consistent with programmed schedules. The Provider should manage its resources to ensure all planned works are completed as programmed at the start of the year. |
| Indicators |  |
| TKPI 2A | Number of Planned Maintenance activities, excluding electrical activities, completed in the year to date, as a percentage of the total Planned Maintenance activities, excluding electrical activities, in the Planned Maintenance Programme. |
| TKPI 2B | Number of Planned Maintenance electrical activities completed in the year to date, as a percentage of the total Planned Maintenance electrical activities in the Planned Maintenance Programme. |
| Definitions |  |
| Planned Maintenance | Routine activities that are frequently repeated and continuously ongoing throughout the year. These include inspections, cleaning and electrical testing. |
| Completed | Work can only be considered to be completed when the entire scheme or activity has been carried out and the assets involved have been put into service. |
| Planned Maintenance Programme | Defines what routine maintenance activities are to be carried out in the year, and when these should be performed. |
| Data Source | Programme, work records |

Data Input                            Frequency / Reporting Period: Calendar month

| Fields | Number of planned maintenance activities, excluding electrical activities, completed in the current year to date. | (A) |
| --- | --- | --- |
|  | Number of maintenance activities, excluding electrical activities, planned to have been completed in the current year to date | (B) |
|  | Number of planned maintenance electrical activities completed in the current year to date. | (C) |
|  | Number of maintenance electrical activities planned to have been completed in the current year to date | (D) |

Calculations (Year to Date Monthly Performance)

| Measure | Calculation | Type | Decimals | Report |
| --- | --- | --- | --- | --- |
| TKPI 2A (M) | (A/B)*100 | Percentage | 1 | G + T |
| TKPI 2B (M) | (C/D)*100 | Percentage | 1 | G + T |

Note: (M) Monthly indicator  (A) Annual indicator

| Indicator Ref. & Title | TKPI 3: Budget Management |
| --- | --- |
| Purpose | Provide Accurate Financial Management |
| Description | To measure the predictability of the Provider’s financial forecasting with respect to the monthly accruals and annual budget allocation for the overall area portfolio. Relates to the requirements of the Resource Accounting Manual to demonstrate the `proper handling and reporting of public money’. |
| Indicators |  |
| TKPI 3A | Percentage variance between the actual and forecast value of work completed in the month (overall portfolio). (Value of all work excluding lump sum). |
| TKPI 3B | Percentage variance between the actual and forecast value of work completed in the financial year (overall portfolio). (Value of all work excluding lump sum). |
| Definitions |  |
| Forecast value | A disruption or potential hazard to the operation, safety and/or integrity of the Area Network (or adjacent land) that requires an immediate response by the Provider. The fault has to have existed in HALOGEN for a duration longer than 20 minutes. |
| Actual value | See Annex SI 13 Performance Requirements. |
| Data Source | HAMIS / SfM and / or Provider’s records |

Data Input                            Frequency / Reporting Period: Calendar month

| Fields | Forecast value of work planned to be completed in month (overall portfolio) | (A) |
| --- | --- | --- |
|  | Actual value of work completed in month (overall portfolio) | (B) |
|  | Forecast value of work planned to be completed in the financial year (overall portfolio) | (C) |
|  | Actual value of work completed in financial year (overall portfolio) | (D) |

Calculations (Individual Monthly Performance)

| Measure | Calculation | Type | Decimals | Report |
| --- | --- | --- | --- | --- |
| TKPI 3A (M) | (B-A)/A*100 | Percentage | 1 | G + T |

Calculations (Financial Year to Date)

| Measure | Calculation | Type | Decimals | Report |
| --- | --- | --- | --- | --- |
| TKPI 3B (A) | (D-C)/C)*100 | Percentage | 1 | G + T |

Note:   = the aggregation of input data for the current month and the preceding months to and including April.

(M) Monthly indicator  (A) Annual indicator

| Indicator Ref. & Title | TKPI 4: Employee Safety |
| --- | --- |
| Measure | Ensure Safe Operations on the Network |
| Purpose / Description | To measure the effectiveness of the Provider’s safety processes by monitoring all accidents reportable under RIDDOR and all other recorded injuries within the Provider’s organisation. |
| Indicators |  |
| TKPI 4A | Area RIDDOR Frequency Rate, based on all accidents reportable under RIDDOR. |
| TKPI 4B | Area Accident Frequency Rate, based on the total number of 4A and all other recorded injuries. |
| Definitions |  |
| RIDDOR | Reporting of Injuries, Diseases and Dangerous Occurrences Regulations. |
| Recorded Injuries | All injuries recorded in Accident Books (or databases) covering the Agency's Area Maintenance contract (TechMAC). |
| Data Source | Provider’s Accident Books / databases including RIDDOR forms. |

Data Input                            Frequency / Reporting Period: Calendar month

| Fields | Total number of hours worked in the month | (A) |
| --- | --- | --- |
|  | Total number of all accidents reportable under RIDDOR in the month | (B) |
|  | Total number of recorded injuries in the month (Non-RIDDOR) | (C) |
|  | Total of all accidents reportable under RIDDOR and all recorded injuries in the month | (D) = (B) + (C) |

Calculations (Rolling 12 Month Performance) i.e. current month + preceding 11 months

| Measure | Calculation | Type | Decimals | Report |
| --- | --- | --- | --- | --- |
| TKPI 4A (A) | B/A*100,000 | Integer | 2 | G + T |
| TKPI 4B (A) | D/A*100,000 | Integer | 2 | G + T |

Note:   = the aggregation of input data for the current month and the preceding 11 months.

(M) Monthly indicator  (A) Annual indicator

| Indicator Ref. & Title | TKPI 5: Time and Cost Predictability |
| --- | --- |
| Measure | Provide accurate financial and programme management |
| Purpose / Description | This PI measures the accuracy of time and cost predictions, initially only on eligible schemes exceeding £100K in value. The indicators are designed to reflect the impact on customers and the HA of changes in predictions during the different phases of design and construction of these schemes. The PI is a measure on the whole of the delivery team including HA, TechMAC and the Supply Chain. |
| Milestones | A series of milestones throughout the Scheme are identified as defined in “Time and Cost Phases for PI 5”, see Appendix 1. 1. Commitment to detailed design 2. Completion of detailed design 3. Agreement of Cost 4. Agreement of predicted start & finish dates 5. Actual start of Construction 6. Actual completion of Construction 7. Agreement of final account at first valuation after completion |
| Indicators |  |
| TKPI 5A | Variance between actual date at 2, compared to date at 2 as predicted at 1. |
| TKPI 5B | Variance between duration 5 to 6 as predicted at 4, compared to duration predicted at 1. |
| TKPI 5C | Variance between duration 5 to 6 as predicted at 4, compared to actual duration 5– 6. |
| TKPI 5D | Variance between duration 5 to 6 as predicted at 1, compared to actual duration 5– 6. |
| TKPI 5E | Variance between the sum of costs at milestone 3 compared to those costs predicted at milestone 1, as a percentage of costs predicted at milestone 1. |
| TKPI 5F | Variance between the sum of costs at milestone 7 compared to those costs predicted at milestone 3, as a percentage of costs predicted at milestone 3. |
| TKPI 5G | Variance between the sum of costs at milestone 7 compared to those costs predicted at milestone 1, as a percentage of costs predicted at milestone 1. |
|  | NB: All measures only for Live Schemes where data is less than 365 days old. |
| Definitions |  |
| “Live” Scheme | A Live scheme is determined by the age of the second of the two milestones that constitute the PI. This should be 365 days old or less to qualify as Live data. |
| Scheme Cost | The sum of all money managed by the Provider on behalf of the HA – including design, construction, statutory undertakers etc. This will not include land costs. |
| Eligible Scheme | Scheme currently approved by HA, with an estimated scheme cost over £100K at milestone 1. |
| Measure Period | Rolling 12 months [current month + preceding 11 months] (or year to date if less than 12 months data exists). |
| All Parties | HA, Designer/Project Manager, Constructor(s), TechMAC and Supply Chain. |
| Milestones | All milestones are defined in Appendix 1, “Time and Cost Phases for PI 5”. |
| Data Source | Provider’s records, HA records and Contractor’s records if applicable. |
| Methodology | Scheme Data Flow As part of preparing the annual programme, covering works funded for each financial year, a record for each Scheme is produced and relevant details recorded, including the predicted date for completion of detailed design, predicted construction start and finish dates, and prediction of final cost (milestone 1). When detailed design is completed relevant details are recorded and the variation from the prediction is calculated and recorded (milestone 2). When all parties agree the construction costs (milestone 3), the Provider records the revised predicted final scheme cost and the date of this entry, against the project record. Similarly, when all parties agree the construction dates – (during milestone 4) – the revised predictions for the start date for construction and completion date for construction, and therefore the construction duration are recorded. The actual dates for Start and End of Construction are promptly recorded as they occur and at the End of Construction the construction duration is calculated and entered into the records (milestone 5 & 6) Finally, the Provider records the projected final scheme cost, at the first valuation after the End of Construction (milestone 7) and the date of this entry, against the project record. TKPI Calculation Individual scheme data is then summarised to calculate the PIs. Only Live data is considered for each of the PIs. Each month, each PI is considered independently, so that data for a scheme may be eligible for inclusion in the calculation of some or all PIs. [NB As soon as completion of detailed design data is recorded for a scheme, that data is included in the subsequent calculation of 5A, at the end of the month. once this data is more than 365 days old (i.e. 12 months old) it is removed from the calculation of 5A, even though data from the same scheme may still be eligible for the calculation of 5B, 5C and 5D that month.] [NB As soon as cost data at milestone 3 is recorded for a scheme that data is included in the subsequent calculation of 5E, at the end of the month. Once this data is more than 365 days old (i.e. 12 months old) it is removed from the calculation of 5E, even though data from the same scheme may still be eligible for the calculation of 5F + 5G that month] For all Time Predictability PIs only positive variations (late completions) are added to the cumulative total, which is divided by the number of eligible schemes in the measure period to calculate the indicators. As all deviations from predictions are undesirable for budgetary control, the Cost Predictability PIs consider the absolute value of cost variances as a percentage of the sum of the initial predictions. This avoids the potential for negative and positive differences, in separate schemes, to have a compensatory effect on the indicators. Compensation events will affect the actual recorded dates / scheme cost but the predicted dates / cost will not be amended to reflect compensation events. i.e. compensation events which affect the duration and overall cost of a scheme will have a negative effect on the result. Until data is available for 12 months, the indicators are reported as Year to Date (YTD). |

Data Input                            Frequency / Reporting Period: Calendar month

| Fields |  |  |  |
| --- | --- | --- | --- |
|  | Predicted date for completion of detailed design as made at milestone 1. | (A) |  |
|  | Predicted date for start of construction as made at milestone 1. | (B) |  |
|  | Predicted date for completion of construction as made at milestone 1. | (C) |  |
|  | Predicted scheme cost as made at milestone 1. | (D) |  |
|  | Actual date for completion of detailed design (milestone 2) | (E) |  |
|  | Predicted scheme cost as made at milestone 3 | (F) |  |
|  | Date Milestone 3 was reached | (G) |  |
|  | Predicted date for start of construction as made at milestone 4. | (H) |  |
|  | Predicted date for completion of construction as made at milestone 4. | (I) |  |
|  | Date Milestone 4 was reached | (J) |  |
|  | Actual date for start of construction (milestone 5). | (K) |  |
|  | Actual date for completion of construction (milestone 6). | (L) |  |
|  | Predicted scheme cost as made at milestone 7. | (M) |  |
|  | Date Milestone 7 was reached | (N) |  |
|  | Variance calculation for 5E | (O) | (F) – (D) |
|  | Variance calculation for 5F | (P) | (M) – (F) |
|  | Variance calculation for G | (Q) | (M) – (D) |
|  | Live data for 5E | (R) | =IF[(TODAY –(G)) >365,0,1] |
|  | Live data for 5F and 5G | (S) | =IF[(TODAY –(N)) >365,0,1] |
|  | Live data for 5A | (T) | =IF[(TODAY –(E)) >365,0,1] |
|  | Live data for 5B | (U) | =IF[(TODAY –(J)) >365,0,1] |
|  | Live data for 5C and 5D | (V) | =IF[(TODAY –(L)) >365,0,1] |
|  | Predicted length of construction at Milestone 1 | (W) | (C) – (B) |
|  | Predicted length of construction at Milestone 4 | (X) | (I) – (H) |
|  | Actual length of construction | (Y) | (L) – (K) |
|  | Number of days variance for 5A | (Z) | (E) – (A) |
|  | Number of days variance for 5B | (AA) | (X) – (W) |
|  | Number of days variance for 5C | (AB) | (Y) – (X) |
|  | Number of days variance for 5D | (AC) | (Y) – (W) |

Calculations (Individual Monthly Performance)

| Measure | Calculation | Type | Decimals | Report |
| --- | --- | --- | --- | --- |
| TKPI 5A (A) | IF(T=1),THEN((Z>0))/(T) | Integer | 0 | G + T |
| TKPI 5B (A) | IF(U=1),THEN((AA>0))/(U) | Integer | 0 | G + T |
| TKPI 5C (A) | IF(V=1),THEN((AB>0))/(V) | Integer | 0 | G + T |
| TKPI 5D (A) | IF(V=1),THEN((AC>0))/(V) | Integer | 0 | G + T |
| TKPI 5E (A) | for all Schemes where R=1 [(O)/D]*100 | Percentage | 0 | G + T |
| TKPI 5F (A) | for all Schemes where S=1 [(P)/F]*100 | Percentage | 0 | G + T |
| TKPI 5G (A) | for all Schemes where S=1 [(Q)/D]*100 | Percentage | 0 | G + T |

Note:   = the aggregation of input data for the current month and the preceding 11 months. This data is deleted after 12 months inclusion in the results, see definition of live data.

(M) Monthly indicator  (A) Annual indicator

| Indicator Ref. & Title | TKPI 6: Data Management |
| --- | --- |
| Measure | Maintain accurate data and inventory records |
| Purpose / Description | To ensure that all assets maintained by the Provider, as well as all fault data, are recorded in the TPMS asset database. This allows the Provider to calculate and monitor asset availability, condition, faults and residual life, and so be better equipped to manage the assets under its control. |
| Indicators |  |
| TKPI 6A | Percentage of TPMS populated |
| Definitions |  |
| TPMS | Technology Performance Management System. |
| Data Source | Scheme data, TPMS, HALOGEN |

Data Input                            Frequency / Reporting Period: Calendar month

| Fields | To be agreed | (A) |
| --- | --- | --- |
|  |  | (B) |
|  |  | (C) |

Calculations (Individual Monthly Performance)

| Measure | Calculation | Type | Decimals | Report |
| --- | --- | --- | --- | --- |
| TKPI 6A (M) | TBA | Percentage | 1 | G + T |

Calculations (Rolling 12 Month Performance) i.e. current month + preceding 11 months

| Measure | Calculation | Type | Decimals | Report |
| --- | --- | --- | --- | --- |
| TKPI 6A (A) | TBA | Percentage | 1 | G + T |

Note:   = the aggregation of input data for the current month and the preceding 11 months.

(M) Monthly indicator  (A) Annual indicator

| Indicator Ref. & Title | TKPI 8: Quality Management |
| --- | --- |
| Measure | Ensure effective business processes and resource management systems |
| Purpose / Description | To assess how closely the Provider is complying with its contractual requirements, and how effectively it deals with instances of non-conformance. |
| Indicators |  |
| TKPI 8A | Number of Quality Management Points at start of the month. |
| TKPI 8B | Number of Quality Management Points cleared in the month. |
| TKPI 8C | Number of Quality Management Points accrued in the month. |
| TKPI 8D | Number of Non-conformities overdue (cumulative) at end of the month. |
| Definitions |  |
| Quality Management Points | Awarded to the Provider in accordance with the Quality Table in the Contract Data. |
| Non-conformity | Can occur without management points being awarded, so long as the necessary reports are raised to correct these, hence why these are measured as well as the number of management points awarded. |
| Data Source | Provider’s register of Quality Management Points, Quality Management System, Non-Conformity Reports |

Data Input                            Frequency / Reporting Period: Calendar month

| Fields | Number of Quality Management Points at start of the month. | (A) |
| --- | --- | --- |
|  | Number of Quality Management Points cleared in the month. | (B) |
|  | Number of Quality Management Points accrued in the month. | (C) |
|  | Number of Non-conformities overdue (cumulative) at end of the month. | (D) |

Calculations (Individual Monthly Performance)

| Measure | Calculation | Type | Decimals | Report |
| --- | --- | --- | --- | --- |
| TKPI 8A (M) | (A) | Integer | 0 | G + T |
| TKPI 8B (M) | (B) | Integer | 0 | G + T |
| TKPI 8C (M) | (C) | Integer | 0 | G + T |
| TKPI 8D (M) | (D) | Integer | 0 | G + T |

Note:  (M) Monthly indicator  (A) Annual indicator

| Indicator Ref. & Title | TKPI 9: Availability of Traffic Technology Systems |
| --- | --- |
| Measure | Maximise availability of Traffic Technology Systems |
| Purpose / Description | To provide a measure of the proportion of Technology Assets maintained by the Provider that are available for providing a service to the road user. |
| Indicators |  |
| TKPI 9A | Actual Operational Availability of technology system. |
| TKPI 9B | Contract Operational Availability of technology system. |
| Definitions |  |
| Technology system | The above measures are calculated for each of the following technology systems maintained by the Provider:- Emergency Roadside Telephones Signs Signals CCTV Midas |
| Actual Availability | All faults, irrespective of responsible party, are included in calculating this measure of availability. |
| Contract Availability | Only faults attributed to Provider responsibility are included in calculating this measure of availability. |
| Operational Availability | Lost hours of service are deducted from potential total hours of asset availability in order to calculate available hours. Degraded hours of service are not deducted. For definitions of “lost” and “degraded”, see MCH1867B, Table A4. |
| Data Source | To be agreed |

Data Input                            Frequency / Reporting Period: Calendar month

| Fields | Technology system Actual Operational Availability. | (A) |
| --- | --- | --- |
|  | Technology system Contract Operational Availability. | (B) |

Calculations (Individual Monthly Performance)

| Measure | Calculation | Type | Decimals | Report |
| --- | --- | --- | --- | --- |
| TKPI 9A (M) | (A) | Percentage | 2 | G + T |
| TKPI 9B (M) | (B) | Percentage | 2 | G + T |

Note:  (M) Monthly indicator  (A) Annual indicator

| Indicator Ref. & Title | TKPI 11: Asset Condition |
| --- | --- |
| Measure | Maximise availability of Traffic Technology Systems |
| Purpose / Description | A measure allowing the technology area team to monitor and manage long-term asset performance so as to maintain a satisfactory level of service provided to the road user. |
| Indicators |  |
| TKPI 11A | Percentage of technology assets registered within TPMS with an RDL below 2 years. |
| TKPI 11B | Percentage of technology assets registered within TPMS with an APIC score below 3. |
| Definitions |  |
| Technology system | The above measures are calculated for each of the following technology systems maintained by the Provider:- Emergency Roadside Telephones Signs Signals MIDAS CCTV. |
| TPMS | Technology Performance Management System. |
| RDL | Residual Design Life. Number of years left before an asset should be replaced (according to the manufacturer) without taking into consideration that asset’s past performance or current condition. |
| APIC | Asset Performance Indicator Classification. One of the technology Key Performance Indicators calculated within TPMS. A score for each asset of 0-10 is calculated, made up of the following weighted components:- Asset Condition Rating Residual Design Life Reliability (How frequently an asset develops faults) Maintainability (Time required to repair an asset’s faults) Obsolescence |
| Methodology | A high score for 11B would indicate that the condition of technology systems is in need of review, and suggest that renewal investment and planning is required. A high score for 11A should prompt the Provider to closely monitor APIC scores, but would not necessarily mean a high score for 11B. |
| Data Source | TPMS |

Data Input                            Frequency / Reporting Period: Calendar month

| Fields | Total number of technology system assets registered within TPMS | (A) |
| --- | --- | --- |
|  | Number of technology system assets of (A) with an input RDL | (B) |
|  | Number of technology system assets, of (B), with an RDL < 2 years | (C) |
|  | Number of technology system assets, of (A), with a calculated APIC | (D) |
|  | Number of technology system assets, of (D), with an APIC < 3 | (E) |

Calculations (Individual Monthly Performance)

| Measure | Calculation | Type | Decimals | Report |
| --- | --- | --- | --- | --- |
| TKPI 11A (M) | (C/A)*100 | Percentage | 1 | G + T |
| TKPI 11B (M) | (E/A)*100 | Percentage | 1 | G + T |

Note: (M) Monthly indicator  (A) Annual indicator

| Indicator Ref. & Title | TKPI 12: Fault Analysis |
| --- | --- |
| Measure | Maximise availability of Traffic Technology Systems |
| Purpose / Description | To assess the quality and reliability of technology infrastructure, and the Provider’s efforts to improve this performance. To assess the effectiveness and efficiency of the Provider’s fault rectification. |
| Indicators |  |
| TKPI 12A | Number of category A, B and P faults where service is restored within the Restore Service times stated in Annex SI 13, as a percentage of the total number of such faults. |
| Definitions |  |
| Technology Infrastructure | Encompasses NMCS2, COBS, and sub-systems such as MIDAS and CCTV |
| NMCS2 | 2nd generation National Motorway Communications System. Provides facilities for Regional Control Centres to operate motorway devices. |
| COBS | Control Office Based System. A computer system sitting within Regional Control Centres allowing the operation of all roadside equipment. |
| Hard Fault | A disruption or potential hazard to the operation, safety and/or integrity of the Area Network (or adjacent land) that requires an immediate response by the Provider. The fault has to have existed in HALOGEN for a duration longer than 20 minutes. |
| 2nd Response | Effort to fix a re-occurring fault that has the same symptoms as the original fault initially thought to have been rectified. |
| Data Source | HALOGEN fault logs, TPMS |

Data Input                            Frequency / Reporting Period: Calendar month

| Fields | Number of responses to hard faults | (A) |
| --- | --- | --- |
|  | Number of 2ndresponses to hard faults initially occurring no more than 1 calendar month beforehand | (B) |

Calculations (Individual Monthly Performance)

| Measure | Calculation | Type | Decimals | Report |
| --- | --- | --- | --- | --- |
| TKPI 12A (M) | (B/A)*100 | Percentage | 0 | G + T |

Note: (M) Monthly indicator  (A) Annual indicator

| Indicator Ref. & Title | TKPI 13: Internal customer satisfaction. |
| --- | --- |
| Measure | Operate as an integrated team |
| Purpose / Description | To ascertain how well the Provider is meeting the needs of its internal customers, and therefore the needs of road users. |
| Indicators |  |
| TKPI 13A | Average of satisfaction scores awarded to the Provider by its internal customers. |
| Definitions |  |
| Internal Customers | Organisations that the Provider works with and behalf of. These include: Managing Agent Contractors (MAC) Regional Control Centres (RCC) National Traffic Control Centre (NTCC) National Roads Telecommunications Services (NRTS) An internal customer is likely to express dissatisfaction when it receives negative feedback from road users. In this way, internal customer satisfaction can be seen to be an indirect measure of road user satisfaction. |
| Satisfaction Score | Awarded by respondents to a short questionnaire undertaken quarterly that is used by the Provider to find out how it is perceived by its internal customers. |
| Methodology | 13A will be calculated quarterly, as opinions are unlikely to change significantly from month-to-month, and form filling on a monthly basis could be overly burdensome on respondents. The questionnaire will try to establish how well the Provider has listened to, communicated with and understood the customer, the quality and promptness of the Provider’s work, and any specific problems that the customer has with the Provider. |
| Data Source | Customer satisfaction forms |

Data Input                            Frequency/Reporting Period: Quarterly

| Fields | Total of questionnaire scores awarded to Provider in last quarter | (A) |
| --- | --- | --- |
|  | Number of questionnaires completed and returned to Provider in last quarter (B) | (B) |

Calculations (Individual Monthly Performance)

| Measure | Calculation | Type | Decimals | Report |
| --- | --- | --- | --- | --- |
| TKPI 13A (Q) | A/B | Integer | 2 | G + T |

Note: (Q) Quarterly indicator

APPENDIX 1- Time and Cost Phases for TKPI 5

Time →

| Design Phase |  |  | Possible delay between completion of works info and start of pricing | Pricing Phase |  | Agreement of predicted start and finish dates | Possible delay between agreement of target price and start of construction | Construction Phase |  |  | Agreement of final account at first Valuation after completion |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Commitment to detailed design | Design | Completion of detailed design |  | Pricing | Agreement of cost |  |  | Actual start of Construction | Construction | Actual completion of Construction |  |
| 1 |  | 2 |  |  | 3 | 4 |  | 5 |  | 6 | 7 |

Milestone

Milestone Definitions

Design Phase

1. Commitment, after final VM, to completion dates and initial scheme cost. These dates are

drawn from a programme covering works funded for a financial year, to be compiled and

agreed by 31st March, for all eligible schemes. For schemes issued after 31st March the

earliest possible dates and scheme cost are to be agreed within the team.

2. Completion of detailed design as evidenced by the availability of a COMPLETE design

package (this may not coincide with the issue of the design package, subject to

programme and unforeseen delays in starting pricing).

Any issue of additional information would put back the end of the design stage. If the HA

request a hold on pricing then the end of the design stage is the stage at which the

complete package is ready for issue.

Pricing Phase

3. Agreement of Cost (e.g. Target Cost, Derived Price, Task Order Agreement and Tender

price agreement)

Construction Phase

4. Point at which an agreed construction programme is published. This will normally

coincide with milestone 3.

5. Actual start of works on site including any traffic management.

6. Completion as defined under the Contract and including removal of all traffic

management.

7. Agreement of final account at first valuation after completion.