1. Name of Programme Team:

Climate Change Team – WWF-UK

2. Name of Project:

Exploring the impacts of a potential UK carbon tax.

3. Purpose of project:

This project seeks to investigate the implications of a potential carbon tax on the food system and what implementing it could mean for delivering a Just Transition – policy solutions for managing and mitigating impacts on consumers and producers.

4. Background

Our world is under greater pressure than at any point in human history, and humanity faces some truly daunting challenges. We need to feed a growing population, we must limit global temperature rise and improve resilience and bring climate change under control, and we need halt and reverse the loss of nature. We refer to this as the Triple Challenge and it is the basis for our work in many areas.

For this project we are looking at the implications of action on one of these challenges on another. One of proposed ways to limit greenhouse gas emissions and improve on the issue of climate change is to introduce a carbon tax on companies. Under a carbon tax, the government sets a price that emitters must pay for each ton of greenhouse gas emissions they emit. This however will have a knock-on effect on the food system and how we provide affordable food for all.

To this end, WWF wishes to contract a party that can co-ordinate a research paper that assesses the potential implications of a carbon tax on the food value chain in the UK and begin to explore policy and implementation solutions to ensure a just transition.

5. Project Scope

The project should be able to answer question around the carbon tax.

- At what point in the supply chain are these costs likely to be felt?

- What are the areas of the value chain that will be most affected by this?

- What could it look like for consumers, depending on decisions taken by producers and retailers?

- What factors and policy/implementation solutions could help ensure that there are no negative implications on supply chain and consumers?

It is also critical to ensure that, as the UK manages its transition to a net-zero economy, it does not lead to inequalities and undesirable environmental and social outcomes.

We therefore want this project to consider the potential positive and negative knock-on effects to social inequality, sustainable development and environmental degradation.

6. Outputs

WWF expects this project to be delivered in the form of a written report (MS Word Document and pdf) and summary presentation (PowerPoint presentation). The summary report should contain a scenario analysis and quantifiable modelling. We also require all data and modelling is shared with WWF.

We may opt to publish the content of the report in full, and/or to produce separately branded materials highlighting the report's key conclusions. WWF will set up an expert review panel to cover key sector areas.

7. Budget/Costs

We invite respondents to indicate their budget requirements for this project within their proposal, WWF’s normal process is to make 100% of payment upon delivery of the requested products, but alternative payment schedules could be considered.

8. Submission of Proposal

The co-ordinating contractor shall submit their proposal by email by end of play on Friday 29th January 2020 to Seán Mallon.  The proposal must contain:

- In their bid, consultants should set out and support with evidence where necessary their proposed approach and methodology, their relevant experience, an outline project plan and full costs and expenses.

- Indicative timeline of work carried out and proposed delivery date.

9. Contact details

The nominated officer for this contract will be - Seán Mallon, Climate Change Specialist, WWF-UK

smallon@wwf.org.uk