## CDM1 Pre-Construction Info
CDM1 PRE-CONSTRUCTION STAGE INFORMATION
In accordance with regulation 4 of the Construction (Design & Management) Regulations 2015 The following information covering the planned works, site and environment is made available to prospective contractors to assist in the health and safety planning and management aspect of the tender process. This document will form the basis for the Construction Phase Plan and associated health and safety file that will be developed throughout the works.
POLICY OBJECTIVE STATEMENT
The Employer takes its obligations under environmental and health and safety legislation seriously and requires that its contractors and agents do likewise. This project will be designed and constructed as far as is reasonably practicable such that it is safe and without risk to the health or safety of the public, the people who will construct it or the subsequent users and other people affected by the completed project.
(1) Project information
Project Title | Area 7 - Concrete Portal Frame Beam Testing
Project Reference
Designer | Highways England
Employer | Highways England
Principal Designer | Highways England
(2) PLANNING AND MANAGEMENT OF THE PROJECT
(a) LOCATION OF THE PLANNED WORKS O.S Grid Reference. Road Number, River crossing etc. Nearest Settlement. Approach roads/Hazards. Post code if available | There are two (2) structures that require testing; 1) Cosby-Countesthorpe Road, Leicestershire, OSGR (E/N): 455320 / 294730. This road carries the M1 motorway over the local authority road Countesthorpe Road. Nearest postcode is LE8 6LD. 2) Coalville-Leicester Railway (Disused), Leicestershire, OSGR (E/N): 452310 / 305590. This road carries the M1 motorway over a disused rail track, which is now used as a public access pathway. Nearest postcode is LE6 0HL, Taverner Drive.
(b) CONTRACTOR DESIGN Extent of their design. Temporary works design. Specific elements design. Refer to further details included in the contract | The Contractor will be responsible for the provision of temporary access equipment to allow access to the structures (e.g. MEWP or scaffold tower). The type of access equipment is to be determined by the Contractor to ensure that it best suits their needs and the access restrictions.
(c) Arrangements for ensuring cooperation between duty holders and work is coordinated
(3) Client Brief
(a) NATURE & DESCRIPTION OF THE PLANNED WORKS Purpose of the works including main function and operational requirements of the finished project Main elements of the works and what they comprise | A portal frame structures study was conducted on the portal frame structures within the East Midlands to determine their current condition. As a result of this study, the two structures listed for this testing work have been identified as high-risk structures - and a variety of tests are to be undertaken at three (3) main areas of each structure to determine the condition of the concrete across the structures.
(b) PROGRAMME (TIMEFRAME AND BUDGET) Start date. (provisional or set), Contract period, budget. Restrictions imposed at certain times of year. | Mobilisation to begin 10th February 2020. Provisional end date for the project is currently 29th May 2020.
(c) CLIENT Main point of contact | Client: Highways England, Stirling House, Lakeside Court, Osier Drive, Sherwood Business Park, Nottingham, NG15 0DS.
(d) SIGNIFICANT HAZARDS & PRECAUTIONS IDENTIFIED AT THE DESIGN STAGE Reference should be made to the designer’s hazard identification to provide greater depth and detail and suggested precautions. Utilising wherever possible drawings and schedules. Refer contractor to specific appendices in the contract for risks at different stages of construction. Eg. Traffic Management. Site hoarding, pedestrian routes, underground and overhead services. | Both structures have had an asbestos action plan and will require a checklist to be completed for any instance where asbestos is found on site. It is not anticipated that these works will disturb any asbestos. Please note that: 1) For Cosby-Countesthorpe Road, asbestos is presumed. It was confirmed in 2008 to be present to the joints between structural walls, however has not been confirmed since this date. It must be assumed that it may still be there as there are no records of works having been carried out to remove. 2) For Coalville-Leicester Railway (Disused), asbestos is confirmed. Crocidolite asbestos has been confirmed to the weep pipes. It should be noted that Chrysotile asbestos has been previously confirmed on the ground at this site, however it is not anticipated to be there.
(e) SIGNIFICANT HAZARDS & PRECAUTIONS IDENTIFIED AT THE CONSTRUCTION STAGE Include what steps the design team should reasonably take to ensure their designs help manage foreseeable risks during the construction phase and when maintaining, cleaning or demolishing a structure Compliance with Specification. Contamination. Risk associated with storage of materials.
(f) HIGH RISK OR COMPLEX HAZARDS (IF APPLICABLE SEE SCHEDULE 3) Include expected standards of health and safety, including safe working practices, and how these standards will be maintained throughout.
(4) Existing Information Relevant to the Project
(a) STRUCTURAL DRAWINGS AND SURVEYS Include any existing drawings or surveys e.g. Asbestos | The following documents contain information relevant to the works: Testing Location Drawing for each structure Asbestos Action Plans for each structure Location Plans for each structure
(b) THE HEALTH AND SAFETY FILE Include any relevant information from an existing health and safety file. | Not Applicable