## Sheet1
CLARIFICATION LOG
Tender: | Riverbank repairs, Henley on Thames
Tender Reference:
Clarification deadline: | 3rd January 2025
Published Date: | 6th January 2025
Version number: | 1
Number | Clarification | Response | Reply date
1 | Is the contractor required to make good any damage to the grass and footpath as a result of anchoring the piles? | Yes | 2024-11-26
2 | Regarding 4.4.5 site security. The contractor must demonstrate in their construction phase plan how they will ensure that all areas where work is being carried are separated from areas remaining available to the general public. Marsh Bank Slip states road pins and tape is acceptable, New Street Slip says heras fencing. Please confirm that Heras fencing is not required to the bank slip and road pins, tape and crowd barrier fencing is acceptable | The contractor is responsible for site security and for risk assessing and providing the most appropriate option. If road pins, tape and crowd barrier fencing has proven sufficient for previous works then we are happy to accept this option. However, should it prove that more robust measures, such as heras fencing, are needed, then the contractor should allow for this. | 2024-11-26
3 | Please can you confirm that the new piles will be at least 6mm thick as per the requirement of a medium duty pile. | Yes | 2024-11-26
4 | Please can you confirm that the new anchor piles have to be at least 1m long driven piles and they cannot be flat plate, steel angle or suchlike. | Yes | 2024-11-26
5 | Please can you confirm whether the tropical marine hardwood rubbing boards can be 50mm thick and 150mm wide and that the capping pieces can be 50mm thick and 250mm wide. | Yes | 2024-11-26
6 | Regarding 4.9.2 Please confirm that we are to still price in CDM Welfare facilities and that the use of facilties does not negate this requirement | It is the contractors responsibility to provide any necessary welfare facilities. The public toilets should be accessible and open during the working hours. However, these should not necessarily be relied upon. | 2024-11-26
7 | 5.2.1 Services, will we be required to apply for a stat service pack? Because 5.11.2 says "All known services information will be supplied at time of bid". | We are not aware of any existing services in either location, but it is the responsibility of the contractor to check services. | 2024-11-26
8 | 5.3.5 States repairs to grass. It says "5.3.4 Any damage caused to grass is to be rectified by seeding the affected area as described in the attached Specification, at the Contractor’s own expense". We have not been provided with a copy of the specification. | The 'affected area' refers to the areas on which the works are being carried out. There are no exact specifications for the seeding, but it should be carried out to the Council's satisfaction. | 2024-11-26
9 | Occupancy of adjacent moorings, i.e. passed chaniage 100. Please can you confirm that no veseels will be moored there and that all boats will be removed prior to mobilisation. | The Council will ensure all boats are moved prior to mobilisation. This will include reasonable allowances for space adjacent to the moorings, to be agreed with the successful contractor. | 2024-11-26
10
11
12
13
In the event of queries please contact: Sheridan Jacklin-Edward, clerk@henleytowncouncil.gov.uk / 07595 608577.