## 3. Introduction
SPECIFICATION DOCUMENT
Osney Lock House
INTRODUCTION
Ref. | Description | £ | p
3.1 | INTRODUCTION
3.1.1 | The contractor is to note that the proposed works forming this schedule are for internal repair and refurbishment to various areas of the building forming Osney Lock House.
3.1.2 | The location of Osney Lock House is shown in the Google Maps image below, as well as in more detail in Appendix A.
3.1.3 | Location of works: Osney Lock House, Bridge Street, Osney, Oxfordshire, OX2 0AX.
3.1.4 | The Client will be: Environment Agency Address: Kings Meadow House, Kings Meadow Road, Reading, Berkshire, RH1 8DG.
3.1.5 | The Client Representative will be: Ridge & Partners LLP Address: Beaumont House, 59 High Street, Theale, Reading, Berkshire, RG7 5AL.
3.1.6 | The contractor is to note that existing layout drawings and a general site location drawing are provided in Appendix C.
3.2 | GENERAL
3.2.1 | The schedule has been prepared in order for a detailed cost breakdown to be provided, to aid the assessment of the works and to assist with progress and payments.
3.2.2 | The contractor is to take responsibility for the schedule and is to ensure its completeness with regards to the proposed scope of works. No costs incurred by the contractor during the pricing of these works will be accepted by the Employer.
3.2.3 | The contractor should note that all items of work contained within this schedule have been described in reasonable detail, but the contractor shall consider them in conjunction with material manufacturers recommendations, and actual work on site. The contractor shall include in his price for everything that is necessary in order to allow him to carry out the works in the best manner whether specifically mentioned or not. If and where approximate quantities are stated, these are for guidance only and the contractor is to make their own assessment of the actual quantities required by visiting site prior to submitting their costed return.
3.2.4 | The contractor is responsible for checking all dimensions on site. Any alterations or amendments to those detailed in this document are to be confirmed in writing by Ridge & Partners LLP.
3.2.5 | Should there be any items of work which the contractor is unclear as to what is required, then the query should be raised to Ridge & Partners LLP for clarification, during the tender process.
3.2.6 | The contractor is to price the schedule boldly in black ink, or typed to facilitate the photocopying of priced copies.
3.2.7 | The contractor is to allow to price for each item individually where ever possible. Items should not be grouped together quoting lump sums prices.
3.2.8 | No qualifications or alterations of any kind are to be made by the contractor to this schedule of works without the written agreement by the CA (Ridge & Partners LLP) or Environment Agency.
3.2.9 | The contractor is to refer to the Preliminaries section of this document for all applicable standards of all products and materials described below. Strict adherence to the requirements are required at all times.
3.2.10 | The contractor must examine this specification document, to ascertain all local conditions and restrictions, accessibility and visit site to ensure they have allowed for all necessary works (all labour, materials and equipment). No claims arising from the failure to do so, will be considered. The client will not be held responsible for any additional works claims which are deemed to be reasonably foreseeable which the contractor should have included for.
3.2.11 | The contractor's attention is also drawn to the Appendices detailing additional information required to complete the works. The contractor must strictly adhere to the requirements of these sections at all times while completing the works.
3.2.12 | The contractor must notify Ridge & Partners LLP upon the discovery of any discrepancies, errors or omissions within the specification documents or the works required immediately.
3.2.13 | The contractor shall be responsible for ensuring all employees including sub-contractors fully understand and work in accordance with the site’s rules and procedures. All contractors must wear company clothing, ID badges and have the correct PPE provisions.
3.2.14 | Allow to submit a detailed and site specific Pre-start Health & Safety Plan for the proposed works to Ridge & Partners LLP for comment and approval.
3.2.15 | The contractor is to allow for regularly removing waste materials from site (noting that there is limited access to the property, due to its location on an island in the River Thames. Where items are to be set aside, allow to record their condition and for safe and secure storage.
3.2.16 | The contractor is to leave the working areas clean and tidy upon at the end of the each working day.
3.2.17 | The contractor is to price for all works to be undertaken during "normal working hours" unless otherwise stated. Exact timings: to be confirmed, prior to works starting on site. No weekend or Bank Holiday works is permitted. No noisy works are permitted before 8.30am.
3.2.18 | Access to the site is only permitted for working on the proposed works.
3.2.19 | The contractor shall carry out the works without undue inconvenience and nuisance and without danger to building owners, occupants and visitors.
3.2.20 | When undertaking the specified works, they are to be in accordance with manufacturer's recommendations and guidelines.
3.3 | WORKS PROGRAMMING/ PHASING
3.3.1 | The works are to be undertaken in an unoccupied residential property.
3.3.2 | The contractor is to outline their proposals for programming the works below. A project programme must be provided with the tender.
3.3.3 | Prior to commencing works on site, the contractor must produce detailed plans for means of access, storage facilities, means of escape and evacuation routes from the building during the course of the works. This is to be issued to Ridge & Partners LLP and the Environment Agency for approval a minimum of two weeks prior to the commencement of works.
3.3.4 | The works are to be undertaken in strict accordance with all Statutory Consents and Conditions required by the local Building Control and Planning Department where necessary. The contractor shall be responsible for ensuring all works undertaken comply with current regulations and byelaws.
3.3.5 | The successful contractor is to undertake the works utilising trades persons and operatives who have the relevant experience, competence and technical skills required to achieve the applicable standards of all works, products and materials described below.
3.3.6 | The contractor is to make a reasonable allowance for the inspection, instruction and agreement of any works by Ridge & Partners LLP during the works as necessary to complete the works to the reasonable satisfaction of Ridge & Partners LLP.
3.3.7 | The contractor is to note that all electrical works that are required to be undertaken to the property, are to be carried out by the Environment Agency's Term Electrical Contractor, such as light fittings, sockets, wiring, extraction etc. As a result, no electrical works have been allowed for in this Schedule of Works. However, where required, the contractor is to allow to liaise with the electrical company and the Environment Agency accordingly. Include to make good affected surfaces (walls, floors, ceilings, joinery etc.), if and where required.
3.4 | CONSTRUCTION (DESIGN AND MANAGEMENT REGULATIONS) 2015
3.4.1 | The Construction (Design & Management) Regulations 2015 apply in full to these works. The contractor must comply with these regulations and ensure all required information is provided.
3.4.2 | Even though the building is unoccupied, the contractor must maintain safe access routes for all residents, visitors, deliveries and own workforce. This includes the public footpath and towpath.
3.5 | REFURBISHMENT AND DEMOLITION ASBESTOS SURVEY
3.5.1 | The Environment Agency has provided an Asbestos Survey Report (dated 9 November 2016) by CWE Services Limited within Appendix D of this report. The report provides R&D information relating to the internal and external areas of the property. Should any asbestos containing materials be found, the contractor is to allow for the safe removal and disposal of all asbestos containing materials as detailed within the report that are identified within the proposed works area.
3.5.2 | The contractor is to note that the asbestos containing materials that were found in the external undercloaking board to the roof (as stated in the report in Appendix D).
3.5.3 | Prior to the commencement of any works on site (including any site set up etc.), the contractor is to fully review the extent of Asbestos identified in the Survey Report provided within the Appendices. Where required as part of any works detailed in this specification, the contractor is to employ a UKAS accredited Asbestos Surveying Specialist to undertake full Refurbishment and Demolition (R&D) inspection and survey the areas of the building not included in the Survey Report provided. This is to include for full testing of samples where applicable. Allow for all necessary asbestos air sampling, fibre identification, bulk sampling and bulk sample identification as required.
3.5.4 | The contractor is responsible for ensuring that all asbestos containing materials are correctly removed (if any are found to be present within the proposed working area), upon advice from the CA) from site by a UKAS accredited company with an approved Waste Carriers Licence and disposed of in accordance with current HSE and regulatory guidelines. Copies of disposal certificates are to be issued to Ridge & Partners LLP & the Environment Agency.
3.5.5 | During the works the contractor is to give notice immediately of suspected asbestos-containing materials if discovered during the Works and avoid disturbing such materials. Statutory risk assessments and details of proposed methods for its safe removal are to be undertaken and submitted by the contractor.
3.5.6 | The contractor is to note that all work to be carried out in accordance with Health & Safety Executive (HSE) guidelines, including The Analysts' Guide (HSG248), Asbestos: The Survey Guide (HSG264) and the Control of Asbestos Regulations 2012.
3.6 | SITE MANAGEMENT & WELFARE
3.6.1 | The contractor is to submit proposals for site set up, site accommodation and welfare facilities which will be discussed and agreed at the pre-commencement meeting. The contractor is able to use the existing toilet facilities at the property (if required).
3.6.2 | The contractor is to note that there is no available parking within the lock house demise. There is however a designated parking area for Osney Lock House within the Osney Hydro Compound, which is located off Bridge Street. There is then a short walk along the towpath to the lock house.
3.6.3 | The contractor is to provide all necessary barriers; safety signage and site security required to carry out the works. This must include adequate 1800mm timber hoarding and or "Heras" type fencing, double clipped, around any external works areas and site compounds (if required). The property must remain secure at all times and once works are complete at the end of each day. All necessary lighting, warning and prohibition signs must be provided. The contractor is to ensure that no unauthorised access is permitted within the curtilage of the site or beyond the building secured entrances.
3.6.4 | The contractor is to provide all necessary facilities for the duration of the works. The contractor is to ensure that these are well maintained for the duration of the works. The contractor must ensure that all existing service covers, footpaths and other surfaces are adequately protected from damage from the use of site facilities during the works.
3.6.5 | The contractor shall provide and maintain all necessary mechanical equipment, plant etc. of all descriptions required for the satisfactory completion of the works and remove all, as and when required, or when directed by Ridge & Partners LLP.
3.6.6 | Due to the nature of the site all operatives must respect the surrounding area and be respectful to neighbours and members of the public.
3.6.7 | The contractor is to allow for removal and safe disposal of all waste from site (including hazardous waste material) in accordance with current Control of Asbestos Regulations 2012 and all Health & Safety legislation.
3.6.8 | The contractor is to allow for regularly removing waste materials from site. Due to the location of the property the use of skips may be restricting / not possible.
3.6.9 | The contractor shall be responsible for obtaining any required permission from the Local Authority, Client or other bodies for the positioning of any temporary facilities or structures outside the premises required for completing the works and ensuring all works undertaken comply with current regulations and byelaws.
3.6.10 | The contractor is to allow for all necessary protection to prevent surfaces and areas adjacent to the works from being damaged by the proposed works.
3.6.11 | The use of any electrical equipment is to be strictly controlled and steps are to be taken to ensure that leads are not long enough to touch the water. All equipment should be connected to lines to prevent their accidental dropping into water causing possible electric shocks etc.
3.7 | EXISTING SERVICES
3.7.1 | No disruption of services to the building shall be allowed without written consent from Ridge & Partners LLP or the Environment Agency and without adequate notice of the disruption being provided.
3.7.2 | Adequate protection of the existing services to the building will be required and any damage shall be made good to the satisfaction of Ridge & Partners LLP, the Environment Agency and the appropriate Statutory Authority, with the minimum of delay at the contractor's expense.
3.7.3 | The contractor is to ascertain for themselves the location of all services (which shall include gas, water, electricity, telecommunications services, fibre optic, drains (foul and surface), ducts, tubes, tunnels and the like, on and adjacent to the Site (underground and over ground)), that may be affected by the carrying out of the works and is to allow for all costs in connection with upholding, protecting and, if necessary, temporarily and / or permanently diverting and reinstating these services. All costs associated with works undertaken by Statutory / Service Utility Companies, including builder's work in connection, are to be allowed for by the contractor.
3.7.4 | All chambers, manholes, draw pits, plant and the like shall be adequately protected and any damage shall be made good at the contractor's expense.
3.8 | ACCESS & SCAFFOLDING
3.8.1 | The contractor is to provide all necessary access equipment required for completing the specified works. Any scaffolding and access equipment that is used must be installed/ erected and maintained to current national standards. Where this is permitted the contractor is responsible for maintaining the access routes and providing all necessary barriers, signage etc. to maintain safe working routes for the occupants, visitors and site operatives. Upon completion all access routes to be thoroughly cleaned and reinstated to match the existing standard.
3.8.2 | If used all scaffolding must be installed / erected and maintained to current Building Regulations, NASCC and national standards.
3.8.3 | The contractor is to allow for safe access in order to carry out all elements of the works. The contractor is deemed to have allowed for all alterations and amendments to the scaffold design to allow works by different trades and operatives needed to complete the works.
3.8.4 | Any damage to existing structures arising as a result of scaffold assembly and the works will be made good at the expense of the contractor.
3.8.5 | The contractor is to ensure that at all times, scaffolding / access provisions to undertake the works in no way reduces the security of the property. The contractor is to ensure that the scaffolding is suitably secured and protected from all persons, including any potential intruders at all times. All ladders are to be locked away at second lift level or above at the end of each working day.
3.8.6 | The contractor is to submit proposals for all high level access measures including risk assessments and method statements along with details of proposed specialist sub contractor. Risk assessments and method statement are to be reviewed and discussed with Ridge & Partners LLP prior to the works commencing on site. Any reasonably requested amendments to the submitted documents are to be made and subsequently included within the documents prior to works commencing.
3.8.7 | It should be noted that, due to the location of Osney Lock House, there is no vehicle access to the property, pedestrian access only via the towpath (see Appendix A). This may limit the type of plant and equipment etc. that can be carried to the property. The contractor is to visit site prior to works starting.
3.8.8 | The contractor is to familiarise themselves with the Environment Agency, Constructing a Better Environment - Safety, Health, Environment and Wellbeing, Code of Practice prior to works starting on site. This document provides guidance on working methods around the water. This is provided within Appendix E.
3.8.9 | When working near or over the water, the contractor must undertake works in accordance with the rules and requirement stated by the Environment Agency, including buoyancy aid, of a tested and approved pattern, is to be worn by all personnel working over water.
SECTION 3 - COSTED TOTAL (Excl VAT) £