Introduction Purpose HQ 51 Infantry Brigade & HQ Scotland require the services of a Production Company to support the planning, programme creation and delivery of Army at The Fringe which is part of the Edinburgh Fringe Festival. This is a 3-year package from 2023-2025.

Background Army @ The Fringe (armyatthefringe.org) Army@TheFringe (A@TF) is held during the Edinburgh Fringe Festival (EFF) during August for a period between 3-4 weeks, it involves transforming an Army Reserve Centre close to Edinburgh town centre into a Fringe venue and hosting a range of performing arts productions and engagement events. All productions have a direct military theme. Performances are augmented by break-out forums and panel discussions involving mixed panels of Army personnel, performers and external speakers. Army@TheFringe began in 2017 and was run in conjunction with Summerhall who are a local arts organisation. The event originally was all planned and delivered by the Army staff, however due to the success of the event it was decided that the event would continue however due to significant workload of creating a programme the need for a producer was identified in 2018 for the 2019 event and provided to be a success in expanding the reach and widening the number of events that were delivered in the venue. In order to deliver an event for 2020 during COVID the event was ran virtually which lead to a hybrid event being delivered in 2021. Due to Summerhall having scaled back operations in 2021 they were unable to support A@TF further. Additional production activities had therefore to be taken on the by the Production Company which included additional technical and marketing staff to deliver this event which resulted in these assets being supplied through the Producers company. In order to secure a long-term plan for this event we are now sourcing a Production Company for a period of 3 years to deliver the event each year whilst working with artists to develop future content for future programmes.

Objectives The Objective for the Production Company are to: - Enable generation of arts engagement content which supports Army engagement themes over a period of 3 years in order to ensure the sustainability and quality of Army@TheFringe going forward. - Increase the engagement impact of the event, in terms of audience involvement and media coverage both local and nationally by ensuring an earlier more professional marketing campaign each year. Successful procurement will mean: - Engagement with artists to commence 12 months in advance to develop new content, although for the 2023 event the Army will commence engagement prior to onboarding of a Production Company. - Opportunities to become embedded with Army units to research and develop content which will reflect the modern Army. - Exploitation by HQ Regional Command Arts engagement across the UK. - Army@TheFringe becoming less of a staff burden to Army in Scotland Engagement Branch.

Scope The scope for the Production Company is: - Attend planning meetings monthly during the planning phase via Skype/ Redford Barracks and/ or East Claremont Street and physical presence at East Claremont Street during the duration of Army@TheFringe. - Provide the Army with 3 quotes for the staging and lighting requirements inline with production requirements. - Complete licensing paperwork in order to create and run a Fringe venue. - Assist in the physical set-up of the venue, rehearsals and the performances. - Deliver an annual event for a period of up to 4 weeks during August. - Supply and payment of staff to deliver the media and production services. - Manage the callout to artists and development funding initiatives approved by the Army. - Create a plan and design for marketing material and posters which will be produced by the Army. - Manage the delivery milestones of artists and production companies. - Support the Army in Scotland aim in exploiting the engagement effect by: - Using up to five of the spaces in East Claremont St venue and neighbouring gardens to increase the number of shows and seats available. - Raising the profile of the venue though improved marketing across the city to increase awareness and an earlier start to ticket sales. Optional features are: - Support in the wider British Army national Arts programme. - Support to Army in Scotland for further Arts engagement events. Excluded features are: - Managing the operation of the venue. - Supplying personnel to support the setup and running of the venue, other than technical and production staff. - Payment of licences, staging and lighting. - Approve and finance the marketing plan. All programme and marketing material will be approved by Army Media and Communications to ensure that they comply with Army Engagement objectives and Army branding. The production company may have to work with Lowland Reserve Forces and Cadets Association who own the building and their associated contractors. Procurement fits within the HQ Scotland Engagement, Communications & Outreach strategy which positions Army@TheFringe as one of the key ways of demonstrating the Army’s contribution to Scotland’s culture, sense of identity and prosperity.

Requirements - Work with the Director of Army at the Fringe (SO1 Engagement, Communications and Outreach, HQ 51 Infantry Brigade & HQ Scotland) to develop a programme which supports the Army’s engagement objectives. The programme will include performing arts, spoken word events and activities conducted in up to 5 spaces at 89 E. Claremont St, outside areas including Clement Crescent Gardens, and other potential remote sites. The programme is to be finalised by the end of March. - Develop a callout and pitching competition approach as directed around October – January to ensure there is a stream of content in development for future years. For the 2023 Fringe, this will be completed on successful onboarding of a Production Company in early 2023. - Liaise with artists selected to deliver Army@TheFringe through a contract which is owned and managed by the production company. - Appoint and manage supporting production and technical staff as required in agreement with the director. - Develop requirements for staging and technical production for events at Army@TheFringe, if no MOD supplier can provide then provide the Army with 3 quotes for staffing and payment inline with the identified requirement of the programme. - Oversee the transformation of 89 East Claremont St into a successful venue for Army@TheFringe in line with a plan approved by the director and supported by the Army delivery team each August. - Completed licensing and production registration paperwork that is required by the Edinburgh Fringe Society and supporting organisations and submit to the Army to process and pay the necessary fees. - Manage all arrangements for box office and ticketing with a plan agreed by the director. - Ensure smooth running of technical rehearsals and production schedules, ensuring the needs of the artists are met as long as they are in balance with the Army’s objectives. - Provide training as necessary for all venue front of house staff and stage crew the week prior to the event. - Assist with creation and management of a bar, reception, and catering area in line with the plan approved by the director and supporting army staff. - Provide an impact assessment based on media, social media and other factors as directed by the director within two weeks of event completion. - Liaise with the Claremont Crescent Gardens Association over use of the garden for Army@TheFringe if the venue is required to be used. - Support the creation and management of army engagement events at the venue as directed in association with the army team. - Develop a marketing plan for the venue and provide options, costs and recommendations to the director for the Army to implement as appropriate. - Generate a successful media campaign to promote the venue on the productions is hosting in order to maximise footfall. This is to include launch events, outputs in media and social media, quick support Army objectives. This will include working with Army Media and Communications teams. - Provide the Army with a weekly update from the box office on ticket sales from the point that tickets go on sale. - Provide a Post Activity Report by mid-September capturing lessons learned and best practice. Payment will be made at agreed intervals on delivery of packages of work for Army@TheFringe. Measurable outputs: - Quality of acts delivering shows with a military theme delivered at Army@TheFringe - Media Coverage - Audience numbers We are procuring the services of a Production Company.

Outputs/deliverables/milestones - Confirm the intent for future years by October, for the 2023 event this will occur at onboarding of a Production Company in early 2023. - Agree deliverables and milestones for Production Company. - Planning and callouts – October-December, for the 2023 event this has already taken place. - Coord with artists and confirmation of acts – February - Secure programme – April - Confirm staging requirements, Programme launch, media products, licencing requirements – April/ May - Confirm staffing requirements, delivery of venue – July/ August - Delivery, Post event report Media analysis, ticketing close-down – September/ October - Regular attendance at monthly planning meetings via Skype/ Redford Barracks and East Claremont Street. - Creation of a budget forecast in conjunction with the Army meeting the funding approved on the Business Case. - Calling notice to potential acts for future involvement and engagement with interested parties. - Screening with Army to confirm acts suitable for the programme. - Commence media advertising and Social Media portals for A@TF in April. - Creation of a programme for a physical and online audience for a period of up to 4 weeks with a minimum of 3 different acts over a 6-day period delivering a diverse programme with a military theme. - Submission of Fringe programme for the Fringe brochure subject to Fringe Society deadlines. - Production of advertising material no later than end of May for the Army to clear the design work and arrange for printing, posters and leaflets. - 3 quotes and confirmation of staging and lighting requirements provided to the Army by June. - Completion of Fringe Society paperwork by July to enable the Army to submit. - Training to supporting military venue staff (Officer Cadets) during the rehearsals prior to the start of the event in August. - Coordination of rehearsals and venue space in the week prior to the event. - Conduct a Media Day prior to the event including calls to local and Scottish print and radio media. - Attendance at the venue as agreed with the Director during the live productions. - Support to Engagement events as identified by the Army through the programme. - Coordination of after-show discussions for selected performances. - A Media report produced within 14 days of the event. - Completion of a Lessons Identified document by end September. - All suppliers to be agreed with the Army before confirming any works and 3 quotes are to be provided, the Army will make any payments that are required for the running costs of the event inline with the costs approved on the Business Case. - This contract only covers the services of staff through the Production Company to support the delivery of Army@TheFringe.

Intellectual Property (IP) Rights (Known as IPR) NOT REQUIRED

Government Furnished Supplies Nothing will be provided to supplier.

Approach (optional and only in exceptional circumstances)

Payment Payment will be made via CP&F with agreed deliverables and milestones for Production Company. - Planning and callouts – October-December - Coord with artists and confirmation of acts – February - Secure programme – April - Confirm staging requirements, Programme launch, media products, licencing requirements – June - Confirm staffing requirements, delivery of venue – August - Delivery, PXR, Media analysis, ticketing close-down – October

Contract management arrangements - Planning meetings will be held monthly between the supplier and the Army to identify progress and identify any potential risks, these will increase to weekly from June with wider Army supporting staff brought in to ensure coordination between all stakeholders. These can be in person at Redford, East Claremont Street or via Skype. - Progress reports are required by the Army on a basis. KPIs will include: - Meeting licensing requirements - Delivery of a quality programme - Extent of the overall Media Reach - Total event physical and online ticket sales

End of contract/Exit strategy A review will be held annually as part of the Post Event Report on the feasibility and success of the event to decide future iterations, At the end of the contract it is agreed that a handover period and reports are provided detailing lessons identified and future collaboration works with artists that are in place.

Final Reminders