## Cover
Schedule of Works
Summer Works Projects 2023
for
Heart of Yorkshire Education Group
RIBA Stage | 3 | Date: | 12.05.2023
Revision:
Project Nr: | 38086
Prepared by: | John Clay, Rob Bursnoll & Harry Fong
Approved by: | Alex Bolton
Signed:
Mace Limited
42 Fountain Street
M2 2BE

## Construction Summary
Construction Summary |  | Wakefield College |  |  |  |  | Castleford Campus |  |  | Selby College |  | Total
|  | Area A - Digital Media Laboratory | Area B - Science Laboratories | Area C - Ventilation | Area D - Emergency Exit/ Refectory Exit | Area E - Animal care staff room | Area A - Student central | Area B - Construction Corridor | Area C - Transient offices | Area A - Decarbonisation Labs | Area B - Engineering Labs
BCIS Ref | Element | £ | £ | £ | £ | £ | £ | £ | £ | £ | £ | £
0.1 | Toxic / Hazardous Material Removal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
7.1 | Minor demolition and alteration works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
2.7 | Internal walls and partitions | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
2.8 | Internal doors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
3.1 | Wall finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
3.2 | Floor finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
3.3 | Ceiling finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
4.1 | FF&E | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
5 | Services | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
9 | Main Contractor's Preliminaries | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | Main Contractor's OH&P (linked to % below) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | Main Contractor's Design Fees | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Main Contractor's Risk (linked to % below) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| State Main Contractor's OH&P percentage: | 0%
| State Main Contractor's Risk percentage: | 0%
Pricing Notes:
1 | When you submit a price for the entire works (all schemes within Wakefield College, Castleford College & Selby College), please can you state your % cost saving to apply against your tender.
2 | Please submit your tender in accordance with the itemised pricing document i.e. quantity, unit & rate. Submitting only a 'total' cost against line items is unacceptable, breakdown is required.
3 | Furthermore to pricing note 2, the only exception is Section 5 'Services' where you are allowed to enter lump sum costs for each building services element listed inclusive of design. A quantified breakdown is required to be submitted with your tender submission to support the 'Services' total for each scheme.
4 | Items that are 'grey' are not applicable to that scheme and do not require pricing.
5 | Please note, there is no detailed schedule of works for Selby 'Area B - Engineering Labs'. For this scheme, please refer to the drawings and add in elemental totals on this tab.
6 | Please note, there is no detailed schedule of works for Castleford 'Area B - Construction Corridor'. For this scheme, please refer to the drawings and add in elemental totals on this tab.
Note on L4: Brennan, Mark: Element totals to be added in by Contractor (no breakdown for this scheme)
Note on L5: Brennan, Mark: Element totals to be added in by Contractor (no breakdown for this scheme)
Note on L6: Brennan, Mark: Element totals to be added in by Contractor (no breakdown for this scheme)
Note on L7: Brennan, Mark: Element totals to be added in by Contractor (no breakdown for this scheme)
Note on L8: Brennan, Mark: Element totals to be added in by Contractor (no breakdown for this scheme)
Note on L9: Brennan, Mark: Element totals to be added in by Contractor (no breakdown for this scheme)
Note on L10: Brennan, Mark: Element totals to be added in by Contractor (no breakdown for this scheme)
Note on L11: Brennan, Mark: Element totals to be added in by Contractor (no breakdown for this scheme)
Note on L12: Brennan, Mark: Element totals to be added in by Contractor (no breakdown for this scheme)

## Wakefield College
Section 1 - Wakefield College |  | Area A - Digital Media Laboratory |  |  |  | Area B - Science Laboratories |  |  |  | Area C - Level 3 Ventilation |  |  |  | Area D - Emergency Exit/ Refectory Exit |  |  |  | Area E - Animal care staff room
|  | Quantity | Unit | Rate | Total | Quantity | Unit | Rate | Total | Quantity | Unit | Rate | Total | Quantity | Unit | Rate | Total | Quantity | Unit | Rate | Total
Ref | Element | £ |  |  |  | £ |  |  |  | £ |  |  |  | £ |  |  |  | £
0.1 | Toxic / Hazardous Material Removal |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
a | Undertake an Asbestos Refurbishment & Demolition survey of all areas affected by the works. | [19 empty] | 0
b | Note: PS allowance will be made for asbestos removal where required. | [19 empty] | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
| Other toxic / hazardous material removal items |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
| Include below for any items required to complete the works which are not specified above: |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
i | add description where needed |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
ii | add description where needed |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
iii | add description where needed |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
7.1 | Minor demolition and alteration works |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
a | Produce a schedule of condition to record the current condition of the areas indirectly affected by the works including and not limited to access to the area of works, external areas used for storage etc. The schedule of condition will need to be issued to the Project Manager prior to commencement of works. | 1 | item |  | 0 | 1 | item |  | 0 | 1 | item |  | 0 | 1 | item |  | 0 | 1 | item |  | 0
b | Include for disposal of all items within the schedule unless otherwise stated. | 1 | item |  | 0 | 1 | item |  | 0 | 1 | item |  | 0 | 1 | item |  | 0 | 1 | item |  | 0
c | Protect all retained surfaces and items in areas affected by the works as reasonably necessary. Where the lift is to be used, this should be protected and its weight limit not exceeded. Repair of any damage occurring during the works will be the responsibility of the contractor and will be made good at the contractor’s expense to the reasonable satisfaction of the Project Manager. | 1 | item |  | 0 | 1 | item |  | 0 | 1 | item |  | 0 | 1 | item |  | 0 | 1 | item |  | 0
d | Remove all chattels, fixed furniture and fittings that remain within the area including but not limited to chairs, tables, worktops, shelving, counters etc. Make good existing finishes to match. Extent to be retained or disposed of to be confirmed by Wakefield College. | 1 | item |  | 0 | 1 | item |  | 0 | 1 | item |  | 0 | 1 | item |  | 0 | 1 | item |  | 0
e | Remove the suspended ceiling grid, tiles and associated fixtures and fittings. Suspended ceiling tiles will need to be retained to replace damaged tiles retained in other areas. |  | m2 |  | 0 |  | m2 |  | 0 |  | m2 |  | 0 |  | m2 |  | 0 |  | m2 |  | 0
f | The existing suspended ceiling to these areas will be retained allow to protect the existing suspended grid and ceiling tiles throughout the entirety of the works. Any damaged sections of grid or tile will need to be replaced to match existing. |  | m2 |  | 0 |  | m2 |  | 0 |  | m2 |  | 0 |  | m2 |  | 0 |  | m2 |  | 0
g | Remove all existing carpet and vinyl floor finishes including associated fixtures and fittings. Clean off all adhesives and prepare for new floor covering. |  | m2 |  | 0 |  | m2 |  | 0 |  | m2 |  | 0 |  | m2 |  | 0 |  | m2 |  | 0
h | Remove section of low level wall to make way for the new stairs as shown on 10Architect Drawing No. A-2200-P1- Existing and Proposed Plans. |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  | m2 |  | 0 |  |  |  | 0
i | Allow for minor alteration works to move back the line of the soil retaining wall to allow the stair to come past the line of the new stairs. Please refer to 10Architect Drawing No. A-2200-P1- Existing and Proposed Plans for the location. |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  | m2 |  | 0 |  |  |  | 0
j | Remove the section of curtain walling and cladding panels. The zone of curtain walling and cladding to be removed is shown on Drawing No. A-2221-P1 - Existing and Proposed Elevations. Re-install Panel B in the place of Panel A to avoid a small section of cladding being required adjacent to the new door. Please refer to H11 - Curtain Walling of the Preambles document for the specification of the curtain walling system. |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  | m2 |  | 0 |  |  |  | 0
k | Remove walls, partitions, glazed partitions and door sets as indicated on Drawing Area B - Science Laboratories - Enabling Drawings. Ensure the walls that are to remain are made secure. Make good damage to existing finishes to match in preparation for fit-out works. |  |  |  | 0 |  | m2 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
l | Remove walls, partitions, glazed partitions and door sets as indicated on Mace Drawing - Media Laboratory Enabling Works May 2023. Ensure the walls that are to remain are made secure. Make good damage to existing finishes to match in preparation for fit-out works. |  | m2 |  | 0 |  |  |  | 0
m | Remove walls, partitions, glazed partitions and door sets as indicated on Mace Drawing - Animal Care Enabling Works - May 2023. Ensure the walls that are to remain are made secure. Make good damage to existing finishes to match in preparation for fit-out works. |  |  |  | 0 | [13 empty] | m2 |  | 0
n | Following the removal of the two existing internal wall partitions (as shown on Mace Drawing - Animal Care Enabling Works - May 2023), allow for installing two ceiling mounted bulkheads to the locations shown on Mace Drawing - Animal Care Proposed Works May 2023. The new bulkheads should match any existing bulkheads and be constructed from one layer of Gyproc Wallboard 12.5mm each side. Cut back and utilise the existing frame as the stud to form the bulkheads. Include for any adjustments, removal and remedial works to the frames to achieve the proposed layout. | [17 empty] | m2 |  | 0
o | All new and existing openings in fire rated partitions and compartment floors and walls are to be fully smoke and fire sealed to match the fire rated value of the surrounding structure. |  | m2 |  | 0 |  | m2 |  | 0 |  | m2 |  | 0 |  | m2 |  | 0 |  | m2 |  | 0
p | Install new double door set to provide fire escape as per 10Architect's Drawing No. A-2221-P1 - Existing and Proposed Elevations. No external ironmongery to be installed. Please refer to Section 435 of the Preambles document for the product specification of the new fire escape double doors. |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 1 | item |  | 0 |  |  |  | 0
q | The Contractor will be responsible for preparing the design for the new foundations for the new staircase. The design and installation of the new concrete foundations will form part of the Contractor's Design Portion. |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 1 | item |  | 0 |  |  |  | 0
r | Provide and install a purpose made platform and fire escape stairs on steel posts. The design should consist of a hot-dipped galvanised frame. Typically this would be a perimeter steel plate and internal bracing structure with balusters bolter to the site of the perimeter frame with a continuous handrail on top. The landing and treads would consist of punched and perforated galvanised steel planks. Stair to have 155mm rise and 250mm going. Nosing's to be rounded and tread to have same punched plate finish as the platform. Galvanised balustrade to be fixed to the side of the structural frame. Please refer to the 10Architects Drawing No. A2200-P1 - Existing and Proposed Plans, and Sections L30 and Z11 of the Preambles document for the specification of the new staircase. |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 1 | item |  | 0 |  |  |  | 0
| Other demolition / alteration items |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
| Include below for any items required to complete the works which are not specified above: |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
i | add description where needed |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
ii | add description where needed |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
iii | add description where needed |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
2.7 | Internal walls and partitions |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
a | Type 1 internal walls; full height partition. Two layers of Gyproc Wallboard 12.5mm each side of Gypframe 70 S 50 'C' Studs at 600mm centres. For heights up to 4200mm. |  |  |  | 0 |  | m2 |  | 0 | [7 empty] | 0 |  | m2 |  | 0
b | Type 2 internal walls; full height partition 60 min fire rated. Two layers of Gyproc Wallboard 15mm each side of Gypframe 70 S 50 'C' Studs at 600mm centres. For heights up to 4200mm. |  | m2 |  | 0 |  | m2 |  | 0 | [7 empty] | 0 |  |  |  | 0
c | Utilise the existing internal glazing timber frame as the stud to form the partition. Include for any adjustments, removal and remedial works to the frames to achieve the proposed layout. |  |  |  | 0 |  | m2 |  | 0 | [7 empty] | 0 |  |  |  | 0
d | Following the removal of the existing single door and frame to the Animal Care Staff Room (as shown on Mace Drawing - Animal Care Enabling Works - May 2023), allow to infill the door opening, finish with plaster skim and decorate. | [7 empty] | 0 |  |  |  | 0 | [5 empty] | m2 |  | 0
e | Extra over for forming single door opening in new partition | 1 | item |  | 0 | 4 | item |  | 0 | [7 empty] | 0 | 1 | item |  | 0
f | All newly formed partitions are to be tape, jointed and finished with a plaster skim. |  | m2 |  | 0 |  | m2 |  | 0 | [7 empty] | 0 |  | m2 |  | 0
g | Install internal glazing to areas indicated on the Works Plan. Contractor to provide a system proposal that meets the required fire rating. |  |  |  | 0 |  | m2 |  | 0 | [7 empty] | 0 |  |  |  | 0
h | Install new fire line board with plaster skim and paint finish to provide 30 minutes fire integrity in the area show on 10Architects Drawing No. A-2221-P1 - Existing and Proposed Elevations. |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  | m2 |  | 0 |  |  |  | 0
i | Install new fire line board with plaster skim and paint finish to provide 30 minutes fire integrity in the area show on Drawing Area B - Science Laboratories - Enabling Drawings. |  |  |  | 0 |  | m2 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
| Other internal walls and partitions items |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
| Include below for any items required to complete the works which are not specified above: |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
i | add description where needed |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
ii | add description where needed |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
iii | add description where needed |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
2.8 | Internal doors |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
a | Door Type 1: supply and install 44mm thick single swing door leaf with laminate finish; vision panel; and 30 min Fire rated smoke seals. Include allowance for the works to be completed in conjunction with access control installation which covered in the MEP section. |  |  |  | 0 |  |  |  | 0 | [7 empty] | 0 | 1 | item |  | 0
b | Door Type 1: supply and install 44mm thick single swing door leaf with laminate finish; vision panel; and 30 min Fire rated smoke seals. Include allowance for the works to be completed in conjunction with access control installation which covered in the MEP section. |  |  |  | 0 | 3 | item | [5 empty] | 0 |  |  |  | 0 |  |  |  | 0
c | Allow to re-install the single door to the newly formed wall partition to Room WU102 as shown on Drawing Area B - Science Laboratories - Enabling Drawings. |  |  |  |  | 1 | item
d | Allow to remove the existing single door to Room U203 - IT Laboratory, and re-install the single door to the new location to Room U203 as shown on Mace Drawing - Media Laboratory Proposed Works May 2023. | 1 | item | [5 empty] | 0
e | Install the previously removed double doors to the newly formed wall partition to Room WU101 as shown on Drawing Area B - Science Laboratories - Enabling Drawings. Include allowance for the works to be completed in conjunction with access control installation which is covered in the MEP section. |  |  |  | 0 | 1 | item |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
f | Door Type 3: Supply and install a 60min fire curtain such as Firesafe60 or similar approved. The proposed system must be subjected to a fire-resistance test achieving a performance level of 60 minutes to BS 476-22:1987 in accordance with BS 476-20:1987. |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
g | Allow to remove and carefully store the existing two single doors to the Animal Care Staff Room and the Exam Office as shown on Mace Drawing - Animal Care Enabling Works- May 2023. | [11 empty] | 0 |  |  |  | 0 | 2 | item |  | 0
h | Install the previously removed single door to the newly formed wall partition to the Exam Office as shown on Mace Drawing - Animal Care Proposed Works - May 2023. Include allowance for the works to be completed in conjunction with access control installation which is covered in the MEP section. | [16 empty] | 1 | item |  | 0
i | Install timber architraves to new doors including decoration finish to match existing. | 1 | item |  | 0 | 5 | item |  | 0 |  |  |  |  | 1 | item |  | 0 | 2 | item |  | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
| Other internal doors items |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
| Include below for any items required to complete the works which are not specified above: |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
i | add description where needed |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
ii | add description where needed |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
iii | add description where needed |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
2.8 | Windows |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
a | Install new opening light to the left-hand side of the new double door set as indicated on 10Architects Drawing No. A-2221-P1 - Existing and Proposed Elevations. The opening light will be side hung as per the specification. Please refer to Section 435A of the Preambles document for the product specification of the casement window. |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 1 | item |  | 0 |  |  |  | 0
b | Install new mullion and frame fixed up to the existing frame and connected with a narrow insulated cladding infill to ensure continuity of the curtain walling system. Refer to 10Architects Drawing No. A-2221-P1 - Existing and Proposed Elevations. |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 1 | item |  | 0 |  |  |  | 0
3.1 | Wall finishes |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
a | Make good areas of damage to existing walls where walls have been removed. |  | m2 |  | 0 |  | m2 |  | 0 |  | m2 |  | 0 |  | m2 |  | 0 |  | m2 |  | 0
b | Make good areas of damaged plasterwork to existing walls prior to decoration, including any damage or where fixings to services have been removed. |  | m2 |  | 0 |  | m2 |  | 0 |  | m2 |  | 0 |  | m2 |  | 0 |  | m2 |  | 0
c | Clean and prepare existing walls prior to decoration. |  | m2 |  | 0 |  | m2 |  | 0 |  | m2 |  | 0 |  | m2 |  | 0 |  | m2 |  | 0
d | Decorate newly plastered walls; 1 mist coat and 2 full coats Dulux Trade Emulsion Colour: to be confirmed by the Client. |  | m2 |  | 0 |  | m2 |  | 0 |  | m2 |  | 0 |  |  |  | 0 |  | m2 |  | 0
e | Decorate newly plastered walls to the new Green Room; 1 mist coat and 2 full coats of Rosco Chroma Key Green emulsion paint or similar Client approved paint colour. |  | m2 |  | 0 |  |  |  | 0 |  |  |  | 0 | [5 empty] | m2 |  | 0
f | Decorate retained plaster walls; 2 full coats Dulux Trade emulsion Colour TBC. |  | m2 |  | 0 |  | m2 |  | 0 |  | m2 |  | 0 |  | m2 |  | 0 |  | m2 |  | 0
g | Decorate existing window boards with 2 full coats of white gloss. |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
h | Install Altro Whiterock Hygienic Wall Cladding; floor to ceiling fully bonded to the wall partition. Include for any adhesive or fixings associated in the installation of the system. |  |  |  | 0 |  |  |  | 0 |  | m2 |  | 0 |  |  |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
| Other wall finishes items |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
| Include below for any items required to complete the works which are not specified above: |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
i | add description where needed |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
ii | add description where needed |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
iii | add description where needed |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
3.2 | Floor finishes |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
a | Make good areas of damage to existing floors / sub-floors where walls have been removed to ensure a level and smooth surface is provided for the new floor finish. |  | m2 |  | 0 |  | m2 |  | 0 |  |  |  | 0 |  | m2 |  | 0 |  | m2 |  | 0
b | Clean existing floors and prepare for new coverings. |  | m2 |  | 0 |  | m2 |  | 0 |  |  |  | 0 |  | m2 |  | 0 |  | m2 |  | 0
d | Altro Zodiak vinyl with cove and capped skirting. Laid on prepared floors made good, Smooth and level with prescribed smoothing and levelling compound to specification under section M50 /130. |  |  |  | 0 |  | m2 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
e | Timber skirting; to new partitions with carpet flooring; 100mm high 18mm thick with 9mm chamfer; finish to match existing. |  | lm |  | 0 |  | lm |  | 0 |  |  |  | 0 |  | lm |  | 0 |  | lm |  | 0
f | Install suitable thresholds to change of floor surfaces. | 1 | item |  | 0 | 5 | item |  | 0 |  |  |  | 0 |  | item |  | 0 |  | item |  | 0
g | 1.3mm Rosa Chroma Key vinyl flooring or similar Client approved product. To be fitted in accordance with the Manufacturer's instructions. Laid on prepared floors made good, Smooth and level with prescribed smoothing and levelling compound to specification under section M50 /130. |  | m2 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
h | Burmatex Academy Carpet Tile. Laid on prepared floors made good, Smooth and level with prescribed smoothing and levelling compound to specification under section M50 /130. |  | m2 |  | 0 |  |  |  | 0 |  | m2 |  | 0 |  |  |  | 0 |  | m2 |  | 0
i | Joseph Hamilton Seaton - Sprit Carpet Tile, 77 Porpoise. Laid on prepared floors made good. Smooth and level with prescribed smoothing and levelling compound to specification under section M50 /130. Install carpet tiles to the locations shown on Mace Drawing - Animal Care Proposed Flooring Layout Plan - May 2023. |  |  |  | 0 | [7 empty] | 0 | [5 empty] | m2 |  | 0
j | New floor finish to be welded to the existing to provide a continuous finish from stairs to the escape door. Altro Zodiak vinyl with cove and capped skirting. Laid on prepared floors made good, Smooth and level with prescribed smoothing and levelling compound to specification under section M50 /130. |  |  |  | 0 |  | m2 |  | 0 |  | m2 |  | 0 |  | m2 |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
| Other floor finishes items |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
| Include below for any items required to complete the works which are not specified above: |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
i | add description where needed |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
ii | add description where needed |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
iii | add description where needed | [7 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
3.3 | Ceiling finishes |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
a | Install a suspended ceiling to all newly formed areas. Install at a height similar to what has been previously removed, include for any access equipment, mechanical fixings associated with installing exposed white steel grid and 600 x 600 acoustic ceiling tiles (Armstrong or similar). Include for accommodating the ventilation ductwork, and other building systems (e.g. sprinkler system, lighting, etc.) for each office and usable area in accordance with the proposed plans. The proposed setting out of the grid needs to ensure no perimeter tiles are less than half a tile in thickness. For Area A: Please refer to Mace Drawing - Media Laboratory Ceiling Works May 2023 for the exact location of the proposed works. |  | m2 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
b | Allow to make good any areas of suspended ceiling that have been affected throughout the works to be in keeping with the original installation. Allow for decoration of the perimeter shadow battens to the suspended ceiling system. Ensure to include for any access equipment, mechanical fixings, gird and ceiling tiles associated in these works. |  | m2 |  | 0 |  | m2 |  | 0 |  |  |  | 0 |  | m2 |  | 0 |  | m2 |  | 0
c | Install British Gypsum Casoline MF ceiling or similar to match the existing and form perimeter edging detail; please refer to Mace Drawing - Media Laboratory Ceiling Works May 2023 for the exact location of the proposed works. |  | m2 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
| Other ceiling finishes items |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
| Include below for any items required to complete the works which are not specified above: |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
i | add description where needed |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
ii | add description where needed |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
iii | add description where needed |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
4.1 | FF&E |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
4.1.1 | Generally |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
| NOTE: All FF&E are a client direct item |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
| Other FF&E items |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
| Include below for any items required to complete the works which are not specified above: |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
i | add description where needed |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
ii | add description where needed |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
iii | add description where needed |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
5 | Services |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
a | See MEP Performance Specification and Drawings. |  | item |  | 0 |  | item |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
b | The main contractor is responsible for ensuring new mechanical and electrical service installations are coordinated with the new construction works and comply with the prescribed fire strategy. |  | item |  | 0 |  | item |  | 0 |  |  |  | 0 |  | item |  | 0 |  |  |  | 0
c | Any new builders work openings, chasing and drilling in new or existing structures are to be undertaken in compliance with NBS Section P31. |  | item |  | 0 |  | item |  | 0 |  |  |  | 0 |  | item |  | 0 |  | item |  | 0
d | The main contractor will be responsible for coordinated Builders work in connection with new mechanical & electrical services installations and shall ensure compliance with Specification Section P31. |  | item |  | 0 |  | item |  | 0 |  |  |  | 0 |  | item |  | 0 |  | item |  | 0
e | Where new drillings or openings are required through the precast floor planks. The main contractor shall set out the locations and opening dimensions and shall seek approval from the Project Manager prior to the start of any drilling or cutting works whatsoever. |  | item |  | 0 |  | item |  | 0 |  |  |  | 0 |  | item |  | 0 |  | item |  | 0
5.1 | Sanitary installations |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
5.2 | Disposal Installations |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
5.3 | Water Installations |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
5.4 | Space Heating and Air Conditioning |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
5.5 | Ventilation Systems |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
5.6 | Electrical Installations |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
a | Install new bulkhead lighting fixture above the new double doors as per 10 Architects Drawing No. A-2221-P1 Existing and Proposed Elevations. |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 1 | item |  | 0 |  |  |  | 0
b | Install new illuminated fire escape running person sign to internal location above the new double door set. |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 1 | item |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
5.7 | Fire Protection |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
5.8 | Communication, Security and Control Installations |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
5.9 | Builder's Work in Connection with Services |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
| Other services items |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
| Include below for any items required to complete the works which are not specified above: |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
I | add description where needed |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
ii | add description where needed |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
| Sub-totals |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0

## Castleford College
Section 2 - Castleford College |  | Area A - Create new student central |  |  |  | Area B - Construction Corridor |  |  |  | Area C - Create two transient offices
|  | Quantity | Unit | Rate | Total | Quantity | Unit | Rate | Total | Quantity | Unit | Rate | Total
Ref | Element | £ |  |  |  | £ |  |  |  | £
0.1 | Toxic / Hazardous Material Removal |  | 0 |  |  |  | 0 |  |  |  | 0
a | Undertake an Asbestos Refurbishment & Demolition survey of all areas affected by the works. |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
b | Note: PS allowance will be made for asbestos removal where required. |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0
| Other toxic / hazardous material removal items |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
| Include below for any items required to complete the works which are not specified above: |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
i | add description where needed |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
ii | add description where needed |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
iii | add description where needed |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
7.1 | Minor demolition and alteration works |  | 0 |  |  |  | 0 |  |  |  | 0
a | Produce a schedule of condition to record the current condition of the areas indirectly affected by the works including and not limited to access to the area of works, external areas used for storage etc. The schedule of condition will need to be issued to the Project Manager prior to commencement of works. | 1 | item |  | 0 |  |  |  | 0 | 1 | item |  | 0
b | Include for disposal of all items within the schedule unless otherwise stated. | 1 | item |  | 0 |  |  |  | 0 | 1 | item |  | 0
c | Protect all retained surfaces and items in areas affected by the works as reasonably necessary. Where the lift is to be used, this should be protected and its weight limit not exceeded. Repair of any damage occurring during the works will be the responsibility of the contractor and will be made good at the contractor’s expense to the reasonable satisfaction of the Project Manager. | 1 | item |  | 0 |  |  |  | 0 | 1 | item |  | 0
d | Remove all chattels, fixed furniture and fittings that remain within the area including but not limited to chairs, tables, worktops, shelving, counters etc. Make good existing finishes to match. Extent to be retained or disposed of to be confirmed by Wakefield College. | 1 | item |  | 0 |  |  |  | 0 | 1 | item |  | 0
e | Remove the suspended ceiling grid, tiles and associated fixtures and fittings. Suspended ceiling tiles will need to be retained to replace damaged tiles retained in other areas. | [7 empty] | 0 |  |  |  | 0
f | The existing suspended ceiling to these areas will be retained allow to protect the existing suspended grid and ceiling tiles throughout the entirety of the works. Any damaged sections of grid or tile will need to be replaced to match existing. | [7 empty] | 0 |  |  |  | 0
g | Remove all existing carpet and vinyl floor finishes including associated fixtures and fittings. Clean off all adhesives and prepare for new floor covering. | [7 empty] | 0
h | Remove wall to form new door opening as indicated on Transient Office B Drawings. Ensure that walls that are to remain are made secure. Make good damage to existing finishes to match in preparation for fit-out works. | [7 empty] | 0 |  |  |  | 0
i | All new openings in fire rated partitions and compartment floors and walls are to be fully smoke and fire sealed to match the fire rated value of the surrounding structure. | [7 empty] | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0
| Other demolition / alteration items |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
| Include below for any items required to complete the works which are not specified above: |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
i | add description where needed |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
ii | add description where needed |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
iii | add description where needed |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
2.7 | Internal walls and partitions |  | 0 |  |  |  | 0 |  |  |  | 0
a | Type 1 internal walls; full height partition. Two layers of Gyproc Wallboard 12.5mm each side of Gypframe 70 S 50 'C' Studs at 600mm centres. For heights up to 4200mm. | [7 empty] | 0 |  |  |  | 0
b | Type 2 internal walls; full height partition 60 min fire rated. Two layers of Gyproc Wallboard 15mm each side of Gypframe 70 S 50 'C' Studs at 600mm centres. For heights up to 4200mm. | [7 empty] | 0
c | Curved Acoustic Wall: Utilising GypWall Curve or similar. Two layers of Gyproc Sound Block 12.5mm each side of Gypframe 70 S 50 'C' Studs at 300mm centres. Gypframe 72 EDC 80 CurveLyner Channel to top and bottom rail. Include 25mm Isover Acoustic Roll in the cavity |  | m2 |  | 0 |  |  |  | 0
d | Utilise the existing internal glazing timber frame as the stud to form the partition. Include for any adjustments, removal and remedial works to the frames to achieve the proposed layout. | [7 empty] | 0 |  |  |  | 0
e | Extra over for forming single door opening in new partition |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
f | All newly formed partitions are to be tape, jointed and finished with a plaster skim. |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
g | Install internal glazing to areas indicated on the Works Plan. Contractor to provide a system proposal that meets the required fire rating. | #REF! | [6 empty] | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0
| Other internal walls and partitions items |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
| Include below for any items required to complete the works which are not specified above: |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
i | add description where needed |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
ii | add description where needed |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
iii | add description where needed |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
2.8 | Internal doors |  | 0 |  |  |  | 0 |  |  |  | 0
a | Door Type 1: supply and install 44mm thick single swing door leaf with laminate finish; vision panel; and 30 min Fire rated smoke seals. Include allowance for the works to be completed in conjunction with access control installation which covered in the MEP section. | [7 empty] | 0 |  |  |  | 0
b | Door Type 2: supply and install 44mm thick single swing double door leaf with painted finish; vision panel; and 30 min Fire rated smoke seals. Include allowance for the works to be completed in conjunction with access control installation which covered in the MEP section. |  |  |  | 0 |  |  |  | 0
c | Door Type 3: Supply and install a 60min fire curtain such as Firesafe60 or similar approved. The proposed system must be subjected to a fire-resistance test achieving a performance level of 60 minutes to BS 476-22:1987 in accordance with BS 476-20:1987. | [7 empty] | 0
d | Install timber architraves to new doors including decoration finish to match existing. |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0
| Other internal doors items |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
| Include below for any items required to complete the works which are not specified above: |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
i | add description where needed |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
ii | add description where needed |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
iii | add description where needed |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
3.1 | Wall finishes |  | 0 |  |  |  | 0 |  |  |  | 0
a | Make good areas of damage to existing walls where walls have been removed. | [7 empty] | 0 |  |  |  | 0
b | Make good areas of damaged plasterwork to existing walls prior to decoration, including any damage or where fixings to services have been removed. |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
c | Clean and prepare existing walls prior to decoration. |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
d | Decorate newly plastered walls; 1 mist coat and 2 full coats Dulux Trade emulsion Colour TBC. |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
e | Decorate retained plaster walls; 2 full coats Dulux Trade emulsion Colour TBC. |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
f | Decorate existing window boards with 2 full coats of white gloss. | [7 empty] | 0
g | Install Altro Whiterock Hygienic Wall Cladding; floor to ceiling fully bonded to the wall partition. Include for any adhesive or fixings associated in the installation of the system. | [7 empty] | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0
| Other wall finishes items |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
| Include below for any items required to complete the works which are not specified above: |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
i | add description where needed |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
ii | add description where needed |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
iii | add description where needed |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
[9 empty] | 0 |  |  |  | 0
3.2 | Floor finishes |  | 0 |  |  |  | 0 |  |  |  | 0
a | Make good areas of damage to existing floors / sub-floors where walls have been removed to ensure a level and smooth surface is provided for the new floor finish. | [7 empty] | 0 |  |  |  | 0
b | Clean existing floors and prepare for new coverings. | [7 empty] | 0 |  |  |  | 0
c | Burmatex Academy Carpet Tile. Laid on prepared floors made good, Smooth and level with prescribed smoothing and levelling compound to specification under section M50 /130. | [7 empty] | 0 |  |  |  | 0
d | Altro Zodiak vinyl with cove and capped skirting. Laid on prepared floors made good, Smooth and level with prescribed smoothing and levelling compound to specification under section M50 /130. | [7 empty] | 0
e | Timber skirting; to new partitions with carpet flooring; 100mm high 18mm thick with 9mm chamfer; finish to match existing. |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
f | Install suitable thresholds to change of floor surfaces. | [7 empty] | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0
| Other floor finishes items |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
| Include below for any items required to complete the works which are not specified above: |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
i | add description where needed |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
ii | add description where needed |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
iii | add description where needed | [7 empty] | 0 |  |  |  | 0
3.3 | Ceiling finishes |  | 0 |  |  |  | 0 |  |  |  | 0
a | Install a suspended ceiling to all newly formed areas. Install at a height similar to what has been previously removed, include for any access equipment, mechanical fixings associated with installing exposed white steel grid and 600 x 600 acoustic ceiling tiles (Armstrong or similar). Include for accommodating the ventilation ductwork, and other building systems (e.g. sprinkler system, lighting, etc.) for each office and usable area in accordance with the proposed plans. The proposed setting out of the grid needs to ensure no perimeter tiles are less than half a tile in thickness. | [7 empty] | 0 |  |  |  | 0
b | Allow to make good any areas of suspended ceiling that have been affected throughout the works to be in keeping with the original installation. Ensure to include for any access equipment, mechanical fixings, gird and ceiling tiles associated in these works. | [7 empty] | 0 |  |  |  | 0
| Ceiling to be made up from GypCeiling MF or similar suspended ceiling fixed to existing bridge cross members to give a cavity and lined with two layers of Gyproc SoundBloc 12.5mm with 100mm Isover Spacesaver Ready-Cut in the cavity. |  |  |  | 0 |  |  |  | 0
| All newly formed ceilings are to be tape, jointed and finished with a plaster skim. |  |  |  | 0 |  |  |  | 0
| Decorate newly plastered ceilings; 1 mist coat and 2 full coats Dulux Trade emulsion Colour TBC. | [7 empty] | 0
| Other ceiling finishes items |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
| Include below for any items required to complete the works which are not specified above: |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
i | add description where needed |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
ii | add description where needed |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
iii | add description where needed |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
4.1 | FF&E |  | 0 |  |  |  | 0 |  |  |  | 0
4.1.1 | Generally
NOTE: All FF&E are a client direct item
Other FF&E items
| Include below for any items required to complete the works which are not specified above: |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
i | add description where needed |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
ii | add description where needed |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
iii | add description where needed |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
5 | Services |  | 0 |  |  |  | 0 |  |  |  | 0
a | See MEP Performance Specification and Drawings |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
b | The main contractor is responsible for ensuring new mechanical and electrical service installations are coordinated with the new construction and comply with the prescribed fire strategy. |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
c | Any new builders work openings, chasing and drilling in new or existing structures are to be undertaken in compliance with NBS Section P31. |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
d | The main contractor Shall be responsible for coordinated Builders work in connection with new mechanical & electrical services installations and shall ensure compliance with Specification Section P31. |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
e | Where new drillings or openings are required through the precast floor planks. The main contractor shall set out the locations and opening dimensions and shall seek approval from the Project Manager prior to the start of any drilling or cutting works whatsoever. |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
5.1 | Sanitary installations |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0
5.2 | Disposal Installations |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0
5.3 | Water Installations |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0
5.4 | Space Heating and Air Conditioning |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0
5.5 | Ventilation Systems |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0
5.6 | Electrical Installations |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
a | Optional |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0
5.7 | Fire Protection |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0
5.8 | Communication, Security and Control Installations |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0
5.9 | Builder's Work in Connection with Services |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0
| Other services items |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
| Include below for any items required to complete the works which are not specified above: |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
ii | add description where needed |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
| Sub-totals |  |  | 0 |  |  |  | 0 |  |  |  | 0

## Selby College
Section 3 - Selby College |  | Area A - Decarbonisation Labs |  |  |  | Area B - Engineering Labs
|  | Quantity | Unit | Rate | Total | Quantity | Unit | Rate | Total
Ref | Element | £ |  |  |  | £
0.1 | Toxic / Hazardous Material Removal |  | 0 |  |  |  | 0
a | Undertake an Asbestos Refurbishment & Demolition survey of all areas affected by the works.
b | Note: PS allowance will be made for asbestos removal where required. | 1 |  |  | 0
[5 empty] | 0 |  |  |  | 0
| Other toxic / hazardous material removal items |  |  |  | 0 |  |  |  | 0
| Include below for any items required to complete the works which are not specified above: [Contractor to complete section] |  |  |  | 0 |  |  |  | 0
i | add description where needed |  |  |  | 0 |  |  |  | 0
ii | add description where needed |  |  |  | 0 |  |  |  | 0
iii | add description where needed |  |  |  | 0 |  |  |  | 0
7.1 | Minor demolition and alteration works |  | 0 |  |  |  | 0
a | Produce a photographic schedule of condition to record the current condition of the areas indirectly affected by the works including and not limited to access to the area of works, external areas used for storage etc. The schedule of condition will need to be issued to the Project Manager prior to commencement of works. | 1 |  |  | 0
b | Include for disposal of all items contained within this schedule in addition to those reference within section 1 of [Drawing: SCCC-10A-V3-XX-DR-A-3120-T1] or [Drawing: SCCC-10A-V3-XX-DR-A-3120-T1] where appropriate unless otherwise stated. |  |  |  | 0 |  |  |  | 0
c | Protect all retained surfaces and items in areas affected by the works as reasonably necessary. Where the lift is to be used, this should be protected and its weight limit not exceeded. Repair of any damage occurring during the works will be the responsibility of the contractor and will be made good at the contractor’s expense to the reasonable satisfaction of the Project Manager. |  |  |  | 0 |  |  |  | 0
d | Remove all chattels, fixed furniture and fittings that remain within the area including but not limited to chairs, tables, worktops, shelving, counters etc. Make good existing finishes to match. Extent to be retained or disposed of to be confirmed by HoYEG. |  |  |  | 0 |  |  |  | 0
e | Remove the suspended ceiling grid, tiles and associated fixtures and fittings. Suspended ceiling tiles will need to be retained to replace damaged tiles retained in other areas. |  |  |  | 0 |  |  |  | 0
f | The existing suspended ceiling to these areas will be retained allow to protect the existing suspended grid and ceiling tiles throughout the entirety of the works. Any damaged sections of grid or tile will need to be replaced to match existing. |  |  |  | 0 |  |  |  | 0
g | Remove all existing carpet and vinyl floor finishes including associated fixtures and fittings. Clean off all adhesives and prepare for new floor covering. |  |  |  | 0 |  |  |  | 0
h | Blockwork to be demolished up to u/s of existing steel beam Width to be maximised with returns retained to minimise disruption to existing M&E fixtures as located on Decarbonation Lab (Drawing: SCCC-10A-V3-XX-DR-A-3120-T1) |  |  |  | 0 |  |  |  | 0
i | Remove walls, partitions, glazed partitions and door sets as indicated on (Drawing: SCCC-10A-V3-XX-DR-A-3120-T1). Make good damage to existing finishes to match in preparation for fit-out works. |  |  |  | 0 |  |  |  | 0
j | Protect the boarded up windows as indicated on (Drawing: SCCC-10A-V3-XX-DR-A-3120-T1) |  |  |  | 0 |  |  |  | 0
k | All new and existing openings in fire rated partitions and compartment floors and walls are to be fully smoke and fire sealed to match the fire rated value of the surrounding structure. (Needs to be removed) |  |  |  | 0 |  |  |  | 0
l | All other M&E fixtures suspended at high level to be retained and require protecting throughout demolition and construction works to prevent accidental damage. |  |  |  | 0 |  |  |  | 0
m | skirting coverings to be removed with exposed surfaces made good. If required, floors to receive self-levelling compound to ensure a level and consistent surface is achieved.
n | Allow to either remove and store at a suitable location or extensively protect in-situ and the existing retractable acoustic wall.
| Add description where needed |  |  |  | 0 |  |  |  | 0
| Include below for any items required to complete the works which are not specified above: |  |  |  | 0 |  |  |  | 0
i | add description where needed |  |  |  | 0 |  |  |  | 0
ii | add description where needed |  |  |  | 0 |  |  |  | 0
iii | add description where needed |  |  |  | 0 |  |  |  | 0
2.7 | Internal walls and partitions |  | 0 |  |  |  | 0
a | Existing wall Type P1 (Light blue) As referenced in Sections 2 and 3 of Drawing: SCCC-10A-V3-XX-DR-A-3120-T1. All walls to Decarbonisation Workshops to be lined with pvc hygienic wall cladding - Altro Whiterock or equal and equivalent. Blockwork walls to be dot and dab lined with plasterboard to provide level surface for affixing cladding. Linings to extend full height to level of new ceilings. |  |  |  | 0 |  |  |  | 0
b | Existing wall Type 2 (Red) As referenced in Sections 2 and 3 of Drawing: SCCC-10A-V3-XX-DR-A-3120-T1. All walls to Decarbonisation Store and other reference areas of retained Blockwork walls to be dot and dab lined with plasterboard to provide level surface for application of skimmed plaster and emulsion paint finish. |  |  |  | 0 |  |  |  | 0
c | Wall Type P1 (Turquoise line) full height partition. Two layers of Gyproc WallBoard 12.5mm each side of Gypframe 70 S 50 'C' Studs at 600mm centres. For heights in accordance with section 3 of Drawing: SCCC-10A-V3-XX-DR-A-3120-T1.
d | Boxing in around existing beam is to be undertaken in conjunction with sections 6 and 7 of Drawing: SCCC-10A-V3-XX-DR-A-3120-T1. 2x15 Soundbloc on studs Acoustic lagging are to be used throughout.
e | Utilise the existing internal glazing timber frame as the stud to form the partition. Include for any adjustments, removal and remedial works to the frames to achieve the proposed layout. |  |  |  | 0 |  |  |  | 0
f | Extra over for forming single door opening in new partition |  |  |  | 0 |  |  |  | 0
g | All newly formed partitions are to be tape, jointed and finished with a plaster skim. |  |  |  | 0 |  |  |  | 0
h | Install internal glazing to areas indicated on the Works Plan. Contractor to provide a system proposal that meets the required fire rating. |  |  |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
| Other internal walls and partitions items |  |  |  | 0 |  |  |  | 0
| Include below for any items required to complete the works which are not specified above: |  |  |  | 0 |  |  |  | 0
i | add description where needed |  |  |  | 0 |  |  |  | 0
ii | add description where needed |  |  |  | 0 |  |  |  | 0
iii | add description where needed |  |  |  | 0 |  |  |  | 0
2.8 | Internal doors |  | 0 |  |  |  | 0
a | Door Type 1: supply and install 44mm thick single swing door leaf with laminate finish; vision panel; and 30 min Fire rated smoke seals. Include allowance for the works to be completed in conjunction with access control installation which covered in the MEP section. |  |  |  | 0 |  |  |  | 0
b | Door Type 2: supply and install 44mm thick single swing double door leaf with laminate finish; vision panel; and 30 min Fire rated smoke seals. Include allowance for the works to be completed in conjunction with access control installation which covered in the MEP section. |  |  |  | 0 |  |  |  | 0
c | Door Type 3: Supply and install a 60min fire curtain such as Firesafe60 or similar approved. The proposed system must be subjected to a fire-resistance test achieving a performance level of 60 minutes to BS 476-22:1987 in accordance with BS 476-20:1987. |  |  |  | 0 |  |  |  | 0
d | Install timber architraves to new doors including decoration finish to match existing. |  |  |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
| Other internal doors items |  |  |  | 0 |  |  |  | 0
| Include below for any items required to complete the works which are not specified above: |  |  |  | 0 |  |  |  | 0
i | add description where needed |  |  |  | 0 |  |  |  | 0
ii | add description where needed |  |  |  | 0 |  |  |  | 0
iii | add description where needed |  |  |  | 0 |  |  |  | 0
3.1 | Wall finishes |  | 0 |  |  |  | 0
a | Make good areas of damage to existing walls where walls have been removed. |  |  |  | 0 |  |  |  | 0
b | Make good areas of damaged plasterwork to existing walls prior to decoration, including any damage or where fixings to services have been removed. |  |  |  | 0 |  |  |  | 0
c | Clean and prepare existing walls prior to decoration. |  |  |  | 0 |  |  |  | 0
d | Decorate newly plastered walls; 1 mist coat and 2 full coats Dulux Trade emulsion Colour TBC. |  |  |  | 0 |  |  |  | 0
e | Decorate retained plaster walls; 2 full coats Dulux Trade emulsion Colour TBC. |  |  |  | 0 |  |  |  | 0
f | Install Altro Whiterock Hygienic Wall Cladding; floor to ceiling fully bonded to the wall partition. Include for any adhesive or fixings associated in the installation of the system. |  |  |  | 0 |  |  |  | 0
g | To all door architraves, prepare and decorate new joinery in RAL 7012 (steel grey gloss) paint, allow for knot-stop, priming, undercoats and finishing coats as recommended by manufacturer. |  |  |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
| Other wall finishes items |  |  |  | 0 |  |  |  | 0
| Include below for any items required to complete the works which are not specified above: |  |  |  | 0 |  |  |  | 0
i | add description where needed |  |  |  | 0 |  |  |  | 0
ii | add description where needed |  |  |  | 0 |  |  |  | 0
iii | add description where needed |  |  |  | 0 |  |  |  | 0
3.2 | Floor finishes |  | 0 |  |  |  | 0
a | Allowances should be made for levelling screeds to achieve a suitable standard for the laying of new vinyl floor. This specification for types of screed should be in conjunction with vinyl manufacture's guidance. |  |  |  | 0 |  |  |  | 0
b | Make good areas of damage to existing floors / sub-floors where walls have been removed to ensure a level and smooth surface is provided for the new floor finish.
c | Clean existing floors and prepare for new coverings. |  |  |  | 0 |  |  |  | 0
d | Non slip vinyl flooring with cove and capped skirting. Laid on prepared floors made good, Smooth and level with prescribed smoothing and levelling compound to specification under section M50 /130. Area in conjunction with section 1 of the Drawing: SCCC-10A-V3-XX-DR-A-3121-T1. Colour: Trout subject to client approval. |  |  |  | 0 |  |  |  | 0
e | Install suitable thresholds to change of floor surfaces. |  |  |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
| Other floor finishes items |  |  |  | 0 |  |  |  | 0
| Include below for any items required to complete the works which are not specified above: |  |  |  | 0 |  |  |  | 0
i | add description where needed |  |  |  | 0 |  |  |  | 0
ii | add description where needed |  |  |  | 0 |  |  |  | 0
iii | add description where needed
3.3 | Ceiling finishes |  | 0 |  |  |  | 0
a | Ceiling Type B- Install a suspended ceiling to all newly formed areas. Install at a height, expressed at Section 5 of Drawing: SCCC-10A-V3-XX-DR-A-3120-T1, include for any access equipment, mechanical fixings associated with installing 600 x 600 Hygienic Ceiling Tile. British Gypsum Casoline Quick-Lock Grid T24 with Gyprex Satinspar. Include for accommodating the ventilation ductwork, and other building systems (e.g. sprinkler system, lighting, etc.) for each laboratory in accordance with the proposed plans. The proposed setting out of the grid needs to ensure no perimeter tiles are less than half a tile in thickness. |  |  |  | 0 |  |  |  | 0
b | Ceiling Type J- Install a suspended ceiling to all newly formed areas. Install at a height, expressed at Section 5 of Drawing: SCCC-10A-V3-XX-DR-A-3120-T1, include for any access equipment, mechanical fixings associated with installing Plasterboard and painted. British Gypsum Casoline MF ceiling with plasterboard and painted finish. Include for accommodating the ventilation ductwork, and other building systems (e.g. sprinkler system, lighting, etc.) for each laboratory in accordance with the proposed plans. The proposed setting out of the grid needs to ensure no perimeter tiles are less than half a tile in thickness.
c | Ceiling type K- Ceiling tiles to be replaced with Gyprex SatinSpar. Allow to make good any areas of suspended ceiling that have been affected throughout the works to be in keeping with the original installation. Ensure to include for any access equipment, mechanical fixings, gird and ceiling tiles associated in these works. |  |  |  | 0 |  |  |  | 0
| Rooflights Existing rooflights at high level Rooflights to be checked for leaks and sealed, insulated and boarded. Actuators to be disconnected. Refer Section 4 of the Drawing: SCCC-10A-V3-XX-DR-A-3120-T1. |  |  |  | 0 |  |  |  | 0
Bulkhead Existing plasterboard bulkhead should be retained, and made good when necessary and subject to a painted finish.
| Other ceiling finishes items |  |  |  | 0 |  |  |  | 0
| Include below for any items required to complete the works which are not specified above: |  |  |  | 0 |  |  |  | 0
i | add description where needed |  |  |  | 0 |  |  |  | 0
ii | add description where needed |  |  |  | 0 |  |  |  | 0
iii | add description where needed |  |  |  | 0 |  |  |  | 0
4.1 | FF&E |  | 0 |  |  |  | 0
4.1.1 | Generally
NOTE: All FF&E are a client direct item
Other FF&E items
| Include below for any items required to complete the works which are not specified above: |  |  |  | 0 |  |  |  | 0
i | add description where needed |  |  |  | 0 |  |  |  | 0
ii | add description where needed |  |  |  | 0 |  |  |  | 0
iii | add description where needed |  |  |  | 0 |  |  |  | 0
5 | Services |  | 0 |  |  |  | 0
a | See MEP Performance Specification and Drawings |  |  |  | 0 |  |  |  | 0
b | The main contractor is responsible for ensuring new mechanical and electrical service installations are coordinated with the new construction and comply with the prescribed fire strategy. |  |  |  | 0 |  |  |  | 0
c | Any new builders work openings, chasing and drilling in new or existing structures are to be undertaken in compliance with NBS Section P31. |  |  |  | 0 |  |  |  | 0
d | The main contractor Shall be responsible for coordinated Builders work in connection with new mechanical & electrical services installations and shall ensure compliance with Specification Section P31. |  |  |  | 0 |  |  |  | 0
e | Where new drillings or openings are required through the precast floor planks. The main contractor shall set out the locations and opening dimensions and shall seek approval from the Project Manager prior to the start of any drilling or cutting works whatsoever. |  |  |  | 0 |  |  |  | 0
5.1 | Sanitary installations |  |  |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
5.2 | Disposal Installations |  |  |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
5.3 | Water Installations |  |  |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
5.4 | Space Heating and Air Conditioning |  |  |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
5.5 | Ventilation Systems |  |  |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
5.6 | Electrical Installations |  |  |  | 0 |  |  |  | 0
a | Optional |  |  |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
5.7 | Fire Protection |  |  |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
5.8 | Communication, Security and Control Installations |  |  |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
5.9 | Builder's Work in Connection with Services |  |  |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
| Other services items |  |  |  | 0 |  |  |  | 0
| Include below for any items required to complete the works which are not specified above: |  |  |  | 0 |  |  |  | 0
ii | add description where needed |  |  |  | 0 |  |  |  | 0
| Sub-totals |  |  | 0 |  |  |  | 0

## 9 Preliminaries
9 | Main Contractor's Preliminaries | Wakefield College | [9 empty] | Castleford Campus | [5 empty] | Selby College |  |  |  | Total
|  | Area A - Digital Media Laboratory |  | Area B - Science Laboratories |  | Area C - Ventilation |  | Area D - Emergency Exit/ Refectory Exit |  | Area E - Animal care staff room |  | Area A - Create new student central |  | Area B - Construction Corridor |  | Area C - Create two transient offices |  | Area A - Decarbonisation labs |  | Area B - Engineering Labs
|  | Fixed | Time Related | Fixed | Time Related | Fixed | Time Related | Fixed | Time Related | Fixed | Time Related | Fixed | Time Related | Fixed | Time Related | Fixed | Time Related | Fixed | Time Related | Fixed | Time Related | Fixed | Time Related
9.1 | Employer's Requirements | [20 empty] | 0 | 0
9.1.1 | Site Accommodation | [20 empty] | 0 | 0
9.1.2 | Site Records | [20 empty] | 0 | 0
9.1.3 | Completion and post completion requirements | [20 empty] | 0 | 0
[22 empty] | 0 | 0
9.2 | Main Contractor's Cost Items | [20 empty] | 0 | 0
9.2.1 | Management & Staff | [20 empty] | 0 | 0
9.2.2 | Site Establishment | [20 empty] | 0 | 0
9.2.3 | Temporary Services | [20 empty] | 0 | 0
9.2.4 | Security | [20 empty] | 0 | 0
9.2.5 | Safety & Environmental Protection | [20 empty] | 0 | 0
9.2.6 | Control & Protection | [20 empty] | 0 | 0
9.2.7 | Mechanical plant | [20 empty] | 0 | 0
9.2.8 | Temporary Works | [20 empty] | 0 | 0
9.2.9 | Site Records | [20 empty] | 0 | 0
9.2.10 | Completion & post completion requirements | [20 empty] | 0 | 0
9.2.11 | Cleaning | [20 empty] | 0 | 0
9.2.12 | Fees & charges | [20 empty] | 0 | 0
9.2.13 | Site Services | [20 empty] | 0 | 0
9.2.14 | Insurance, bonds, guarantees & warranties | [20 empty] | 0 | 0
[22 empty] | 0 | 0
| Other Items | [20 empty] | 0 | 0
| Include below for any items required to complete the works which are not specified above: | [20 empty] | 0 | 0
i | add description where needed | [20 empty] | 0 | 0
ii | add description where needed | [20 empty] | 0 | 0
iii | add description where needed | [20 empty] | 0 | 0
iv | add description where needed | [20 empty] | 0 | 0
v | add description where needed | [20 empty] | 0 | 0
[22 empty] | 0 | 0
| Sub-totals | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0

## 11 Design Fees
11 | Design Fees | Wakefield College |  |  |  |  | Castleford Campus |  |  | Selby College
|  | Area A - Digital Media Laboratory | Area B - Science Laboratories | Area C - Ventilation | Area D - Emergency Exit/ Refectory Exit | Area E - Animal care staff room | Area A - Create new student central | Area B - Construction Corridor | Area C - Create two transient offices | Area A - Decarbonisation Labs | Area B - Engineering Labs
11.3 | Main Contractor's Design Fees | £ | £ | £ | £ | £ | £ | £ | £ | £ | £
11.3.1 | Temporary works Design fees
11.3.2 | Mechanical & Electrical Design fees
11.3.3 | Structural fees | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
Other Items
Include below for any items required to complete the works which are not specified above:
i | add description where needed
ii | add description where needed
iii | add description where needed
iv | add description where needed
v | add description where needed
| Sub-totals | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
The schemes are to be procured traditionally with the only Contractor Design Portion (CDP) to be as follows:
- MEP services
- Structural (Refectory Fire Exit at Wakefield College and the Decarbonisation Labs at Selby College)