## Design Team Release Schedule
Document Revision |  | P01
Project Stage |  | Stage 4
RFI | NO | Request for Information | Information Required | Designer | Building | Design Information Required Date | Status | Received | Notes | Response
4872-ME- | 001 | Provide frozen Arch layouts incl assocaited dwg GA's | Layout Drawing | Arch | Decarb Workshops & Advanced Engineering Labs | 2023-04-07 | Open |  |  | Frozen architectural layouts issued 06/04/23 - 10architect 11/04/23
4872-ME- | 002 | Please confirm proposed occupancy levels for each space, and intended usage hours | Schedules | Client / Architect | Decarb Workshops & Advanced Engineering Labs | 2023-04-07 | Open |  |  | Client to confirm - 10architect 11/04/23
4872-ME- | 003 | Provide latest FF&E layouts detailing water supplies, drainage, any specialist power and data e.g commando outlets | Layout Drawing | Client / Architect | Decarb Workshops & Advanced Engineering Labs | 2023-04-07 | Open |  |  | Indicative FFE layout included on plans for Advanced Engineering Labs. Client to confirm any comments and provide layout for Decarbonisation Workshops. - 10 architect 11/04/23
4872-ME- | 004 | Please confirm current heating flow & return temperatures from existing heating system | Confirmation | Client | Decarb Workshops & Advanced Engineering Labs | 2023-04-07 | Open
4872-ME- | 005 | Please provide building fabric construction materials build-up and the resulting U-Value for: External Walls Ground Floor Roof Glazing (Including G-Value) | Confirmation | Client / Architect | Decarb Workshops & Advanced Engineering Labs | 2023-04-07 | Open |  |  | We do not have a record of the U-values and G-value. Are you able to proceed based upon the limiting standards within the Building Regulations at the time? - 10architect 11/04/23
4872-ME- | 006 | It is understood that soldering will be undertaken within the Labs, please advise if a room mounted, local recirculation LEV system is suitable (e.g. RS-E0342 Fume extraction unit) in lieu of a fixed LEV service installation | Confirmation | Client | Advanced Engineering Labs | 2023-04-07 | Open
4872-ME- | 007 | Please confirm quantity and location of compressed air outlets; please advise flow rate required at each outlet | Confirmation | Client | Decarb Workshops & Advanced Engineering Labs | 2023-04-07 | Open
4872-ME- | 008 | What grade of compressed air is required for the carbon capture machines, and flow rate required | Confirmation | Client | Decarb Workshops | 2023-04-07 | Open
4872-ME- | 009 | Please confirm power and data requirements for each room | Confirmation | Client | Decarb Workshops & Advanced Engineering Labs | 2023-04-07 | Open
4872-ME- | 010 | Please confirm where data cab can be located at ground floor level. Can we use decarb store SE0:08 | Confirmation | Client | Decarb Workshops | 2023-04-07 | Open
4872-ME- | 011 | Please confim any security requirements to the spaces I.e CCTV / access control | Confirmation | Client | Decarb Workshops & Advanced Engineering Labs | 2023-04-07 | Open
4872-ME- | 012 | It is assumed that no high risk activity will be undertaken in the workshops and no high risk emergency lighting will be installed. Please confirm | Confirmation | Client | Decarb Workshops & Advanced Engineering Labs | 2023-04-07 | Open
4872-ME- | 013 | Please confirm the form of lighting control required in the spaces - we assume manual control as per current provision | Confirmation | Client | Decarb Workshops & Advanced Engineering Labs | 2023-04-07 | Open
4872-ME- | 014 | Please confirm the kind of activities that wil be carried out in the workshops. It is assumed that IP 40 luminaires will be suitable for the use of the space | Confirmation | Client | Decarb Workshops | 2023-04-07 | Open
4872-ME- | 015 | Please provide most recent electrical testing and inspection certificates - to confirm the current installation is in satisfactory condition for extension | Confirmation | Client | Decarb Workshops & Advanced Engineering Labs | 2023-04-07 | Open
4872-ME- | 016 | Please confirm requirements and location for 3 phase power outlets within the Engineering Labs. Understanding is 110V power is no longer required. | Confirmation | Client | Advanced Engineering Labs | 2023-04-07 | Open
4872-ME- | 017
4872-ME- | 018
4872-ME- | 019
4872-ME- | 020
4872-ME- | 021
4872-ME- | 022
4872-ME- | 023
4872-ME- | 024
4872-ME- | 025
4872-ME- | 026
4872-ME- | 027
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-

## Lists
Buildings | Team Members | Information Required
Decarb Workshops & Advanced Engineering Labs | Client | Layout Drawing
Decarb Workshops | Arch | Particular Specification
Advanced Engineering Labs | Struc/Civils | Schedules
| Ramboll MEP | Construction Details
| Contractor | Connection requirements and Layout Drawings
| Client / Architect | Data Sheets
Report
As Built records
Sign off
Revit Model
Tech sub c/w Revit families
Dates
Tech Sub
Instruction
Confirmation
-