Public Health England HR Review

# Project outline

The main deliverable included within this tender specification is to provide independent expert support to help ready our HR function to support PHE through the next phase of its development, delivering the best possible service to a national organisation operating first and foremost through a network of local PHE Centres and our scientific campuses at Chilton, Colindale and Porton.

- Background

PHE is the expert national public health agency that fulfils the Secretary of State for Health's statutory duty to protect health and address inequalities, and discharges his power to promote the health and wellbeing of the nation. PHE has operational autonomy and its freedoms and obligations are described in the Framework Agreement with the Department of Health.  PHE acts globally and nationally where it is uniquely places to do so, and supports local priorities through its network of Centres. It employs 5,500 staff and has a net operating budget of £302m.  More information on PHE’s role and functions can be found at Annex A and background on PHE’s HR department and priorities at Annex B.

- Context

Our HR team operates in a complex and ever evolving landscape, made more challenging by the fact that we operate three different sets of terms and conditions: Civil Service, legacy (mostly NHS Agenda for Change) and, for those in the clinical ringfence, Medical and Dental.

In common with ALBs elsewhere in government, we are periodically subject to the Tailored Review process overseen by the Cabinet Office and, in the case of health-related ALBs, the Department of Health. The recent review recognised the good progress we made early on in developing our organizational capability, particularly on integrating a workforce of over 5,000 scientists, data specialists, healthcare professionals and civil servants from over 100 organizations into one, whilst at the same ensuring delivery of core functions as set out in the annual remit letter from Ministers (https://www.gov.uk/government/publications/phe-remit-letter-2016-to-2017). This early work was followed by an in-house strategic review leading to a significant organizational change programme, Securing our Future.

Approximately 500 staff will have left PHE during 2016/17 through either voluntary exit, voluntary redundancy or compulsory redundancy in the past year and the demand on HR has therefore been considerable. The most significant element of Securing Our Future will take place in 2017/18, namely the planned restructure associated with the National Infection Service, where over half of our staff work. This is a key development ahead of the planned move to PHE Harlow in the early 2020s.

.

- Aims and objectives

The overall aim is to future proof the HR service for at least the next three to five years, identifying and maximising the benefits of digital technology wherever possible. The review should consider and make specific recommendations on the structure, function,

performance, and resourcing of PHE’s HR function, with particular reference to the following:

- HR business systems and processes, including an assessment of how they could be improved through using the latest digital technology and associated opportunities with respect to HR analytics, insight and reporting;

- the HR business partnering model (including geographical distribution and quality control) and wider employee relations (e.g. grievances, performance management, disciplinary and other HR casework)

- the level and nature of HR support required for the move to PHE Harlow and associated workforce planning requirements

- Recruitment, payroll and pensions

- Learning and development, including links to staff appraisal and mandatory training

As set out in section 8 below, bidders are invited to submit an outline project plan and methodology.  We anticipate that, as a minimum, this should:

- identify current strengths and areas for improvement, taking into account the current skills and capabilities in the team any wider learning from experience since PHE’s establishment

- identify and prioritise the actions that will support PHE during the next phase of

development, particularly in the context of the full roll-out of the National Infection Service and future move to Harlow

- make recommendations for future leadership and management arrangements for HR

- identify potential metrics and benchmarks against which success could be measured, both in terms of operational performance and value add to the organization and delivery of its mission

- in delivering the above, propose an action plan with timescales for

implementation and an informed assessment on the associated resourcing implications.

Engagement with key stakeholders will be key, and we suggest that the review team engages with:

- Internal PHE staff to include a range of Directors, Centre Directors, Senior Managers and HR staff

- Trade union representatives

- External stakeholders:

- Rupert McNeil, Chief People Officer, Civil Service

- Kate Tilley, Director - People and Capability, Department of Health

- SBS (external payroll provider)

- ESR national team

- Standard information for applicants

  - The sections below provide standard information on different aspects of the project and will contain details relevant to your application.

  - Governance Issues

    - Day-to-day management of the estimate production will be by an identified project lead within the provider organisation.

    - The successful provider must adhere to the Data Protection Act (1998) and the Freedom of Information Act (2000). Effective security management, and ensuring personal information and assessment data are kept secure, will be essential.

  - Risk Issues and Management

    - Applicants should submit, as part of their application, a summary explaining what they believe will be the key risks to delivering this project, and what contingencies they will put in place to deal with them.

    - A risk is defined as any factor which may delay, disrupt or prevent the full achievement of a project objective. All risks should be identified. The summary should include an assessment of each risk, together with a rating of the risks likelihood and its impact on a project objective (using a high, medium or low classification for both). The risk assessment should also identify appropriate actions that would reduce or eliminate each risk, or its impact.

- Dissemination

Any items published on gov.uk are crown copyright.

Intellectual Property

Background Intellectual Property” means any Intellectual Property and Intellectual Property Rights, other than Foreground Intellectual Property, that is used in connection with any part of the Services. “Foreground Intellectual Property” means any Intellectual Property and Intellectual Property Rights that arises or is obtained or developed by, or by the Contractor on behalf of, either party in the course of or in connection with the performance of the Services.

All Foreground Intellectual Property shall vest in and be owned absolutely by the Agency and the Contractor agrees to execute all documents and assignments and do all such things as may be necessary to perfect the Agency’s title to the Intellectual Property or to register the Agency as owner of registrable rights.

All Background Intellectual Property owned by either Party shall remain the property of that Party but the Contractor shall, where it has the right to do so, grant the Agency and any Beneficiary a non-exclusive, perpetual, royalty free, global license to use any Background Intellectual Property to the extent necessary for the purpose of the Services and for the use or exploitation of any Foreground Intellectual Property.

The Agency shall be entitled to negotiate and agree provisions for the ownership of Intellectual Property Rights which deviate from the above to the extent that such other provisions, in the authority’s opinion, are more suitable for the services under that Order.

- Budget and Timescale

  - The project has a provisional budget of up to £70,000 excluding VAT

  - The project will conclude by no later than 31 March 2017

- Application Process

  - Applications should be submitted electronically through the Bravo portal and include the following documentation:

- Supporting statement setting out establishing suitability to undertake the project.

- Outline project plan & methodology

- Risk statement

- Budget

- Project team CVs

  - Applications will be reviewed by an internal PHE panel and candidates will be informed electronically of the result.

  - Shortlisted candidates will be invited to present their proposal to the panel on Wednesday 25 January.

- Selection Criteria

Criteria used by members of the review panel to assess applications for funding from the project will include:

- RELEVANCE of the proposed plan and methodology to the aims and objectives of the project

- QUALITY of the work plan and proposed management arrangements

- STRENGTH and EXPERIENCE of the project team

- VALUE for money (justification of the proposed costs)

- INVOLVEMENT of key stakeholders

The scoring methodology will be:

Unacceptable = 0 marks

Weak = 5 marks

Satisfactory = 10 marks

Good = 15 marks

Excellent = 20 marks

Timetable

It is anticipated that commissioning of this project will occur to the following timetable:

- Issue of invitation to tender – Wednesday 19th January 2017.

- Deadline for receipt of applications: Thursday 2nd February 2017.

- Notification to shortlisted bidders: Friday 3rd February 2017.

- Presentations and Panel Decision: Tuesday 7th February 2017.

- Award of contract: Wednesday 8th February 2017.

- Mobilisation: w/c 13th February 2017.

- Project completion: Early April 2017.

- Report Issue: Mid April 2017.

- Contacts

  - Questions regarding this tender can be directed via the Bravo platform.

ANNEX A

The Minister for Public Health and Innovation sets out the government's requirements of PHE in an annual remit letter and strategic priorities.  PHE is responsible for four critical functions:

- To fulfil the Secretary of State’s duty to protect the public’s health from infectious diseases and other public health hazards, working with the NHS, local government and other key partners in England but also working with the Devolved Administrations and globally where appropriate. This means providing the national infrastructure for health protection including: an integrated surveillance system; providing specialist services, such as diagnostic and reference microbiology, and developing the application of genomic technologies; investigation and management of outbreaks of infectious diseases and environmental hazards; ensuring effective emergency preparedness, resilience and response for health emergencies, including global health security and work on antimicrobial resistance; acting as the focal point for the UK on the International Health Regulations; evaluating the effectiveness of the immunisation programme and procuring and supplying vaccines.

- To secure improvements to the public’s health, including supporting the system to reduce health inequalities and to deliver From Evidence into Action and the Five Year Forward View commitments to a radical upgrade in prevention. It should do this through its own actions and by supporting Government, local government, the NHS and the public to secure the greatest gains in physical and mental health. PHE will promote healthy lifestyles, provide evidence-based, professional, scientific and delivery expertise and advice, develop data, information resources and tools (particularly on return on investment and value for money) and support the system to meet legal duties to improve the public’s health and reduce health inequalities.

- PHE has a key role in improving population health through sustainable health and care services through, for example: promoting the evidence on public health interventions and analysing future demand to help shape future services; working with NHS England on effective preventative strategies and early diagnosis; providing national co-ordination and quality assurance of screening programmes, the introduction of new programmes and the extension of existing programmes; running national data collections for a range of conditions, including cancer and rare diseases; and providing data analyses which support the NHS in improving services and outcomes.

- Ensure the public health system maintains the capability and capacity to tackle today’s public health challenges and is prepared for the emerging challenges of the future, both nationally and internationally. This will mean: undertaking, contributing to, and supporting research and development; supporting and developing a skilled public health workforce; supporting local government to improve the performance of its functions; providing the professional advice, expertise and public health evidence to support the development of public policies to have the best impact on improving health and reducing health inequalities; and collecting, quality assuring and publishing timely, user friendly high quality information on important public health topics and public health outcomes.

More information can be found in PHE’s Strategic Plan and most recent Annual Report and Accounts:

https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/516985/ PHE_Strategic_plan_2016.pdf

https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/539768/ PHE_annual_report_2015_2016_web.pdf

ANNEX B

On 1 April 2013, 50 HR staff from the former Health Protection Agency, who were previously

providing a HR, payroll and pensions and occupational health service to approximately 3,600 staff, along with five HR staff from smaller predecessor organisations, merged to establish PHE’s HR directorate. The service is now supporting a staffing establishment of c5,300 across 74 sites. Workforce information transferred to the Finance and Commercial Dirctorate from 1 April 2015.

Leadership, team occupational development interventions and staff engagement have increasingly become the responsibility of the Organisational and Workforce directorate, working closely with HR on a number of joint initiatives. There is currently one learning and development specialist post in HR.

The current HR to staff ratio is 1:126, based on 49 HR staff, minus seven payroll and pensions staff. The ratio is amongst the highest in the Civil Service, where the average is now 1:112.

The PHE HR directorate deals with arguably the most complex set of mixed terms and conditions in the Civil Service: c2,700 staff on Civil Service terms and conditions; c1,860 staff on legacy terms and conditions; and c700 staff on NHS terms and conditions.

PHE continues to use the legacy payroll and workforce information system, Electronic Staff Record (ESR). This is an NHS platform which is not designed to support a Civil Service organisation. It is, however, currently free of charge.

There are typically between 400-500 live recruitment campaigns at any time across PHE. These consist of a mixture of internal, Civil Service wide, national and rapid recruitment campaigns.

HR has reduced its established budget by 20% since 1 April 2015 at a time of unparalleled

organisational change. Additional fixed term budgeted support has been provided from the

National Infections Service, Centres and Regions and corporate budgets.

Fixed term funding for interim pensions staff to develop the Compendia interface between ESR and MyCSP, due to go live in late 2016, and for the transfer of staff on legacy terms to the Civil Service pension scheme on 31 March 2015 and the consequent GAD choice exercise, has also been received.

Increasingly, HR is involved with national diversity and staff health and wellbeing initiatives and is receiving requests to support other organisations on these important areas.

In line with the Civil Service workforce plan, HR’s key priorities are as follows:

• Streamlined, consistent, efficient and measured HR Operations by introducing further

digitalisation, quality control and integration of payroll, pensions, recruitment and ESR, or

an alternative system.

• The forthcoming NIS reorganisation and integral cultural change project in preparation for

Science Hub.

• Diversity, inclusion and staff wellbeing established as core business by initiatives such as

Project SEARCH, MOSAIC, ex-military personnel wounded in service, tackling pay

inequalities, unconscious bias and recruiting from new labour markets (including 120

apprentices). Monitored through diversity dashboards and aiming to create a level playing

field across PHE as an exemplar to the country.

• Establishing a clear link between effective diversity and staff inclusion and staff health and

wellbeing outcomes and promulgating this across all employers.

• Making PHE’s 1,350 managers more resilient and effective people managers,

supported by our major cohort of 400 plus internal volunteers, whose effectiveness and

contribution we wish to further explore.

• Supporting PHE people managers in developing and caring for their staff during ongoing

organisational change, with business partners increasingly integrated into management

teams, supported by tailored interventions for teams with low staff engagement scores.

• Workforce planning fully integrated with finance and business planning and including the above comprehensive apprenticeship programme.