RFQ FY20-02

LaunchPad Initiative 2019 Open Call

COASTAL APPLICATIONS COMPETITION

CONDITIONS TO TENDER AND MANAGEMENT REQUIREMENTS

Contents

INTRODUCTION	2

I. CONDITIONS TO TENDER	3

1. Participation in the Tender	3

2. Presentation and Submission	4

3. Content of the Project Submission Form	4

4. Tender Evaluation Process	5

5. Budget and non-refundable grant	6

II. MANAGEMENT REQUIREMENTS	6

1. Scope of work and project logic	6

2. Contractual milestones and review meetings	6

3. Deliverables - Documents and items to be produced/delivered	7

4. Management	8

5. Reporting	8

ANNEX A – DETAILS ON DELIVERABLES	9

ANNEX B – COST ELIGIBILITY LIMITS AND CONDITIONS	13

# INTRODUCTION

The LaunchPad Initiative Open Call 2019 is competition launched by the Satellite Applications Catapult and the UK Ambassador Platform for ESA Business Applications (https://business.esa.int).  call.  Users and customers for services identified through this open call may be located anywhere globally.

The overall objective of the call is to stimulate the submission of new ideas for commercially viable and sustainable services that show innovative utilisation of space services and technologies such as: Satellite Communications, Satellite Navigation, Earth Observation or Human Spaceflight technologies within non-space markets.  The LaunchPad Initiative Open Call 2019 specifically seeks proposals that concern services and markets related to coastal applications.  No other thematic areas are considered eligible.

The specific objectives of the call are:

- to determine the economic viability and technical feasibility of integrated service(s) and the associated system(s) able to meet the needs and conditions of relevant customers, users and other stakeholders;

- to secure the buy-in and involvement of important customers, users and other stakeholders; and

- to prepare the implementation of sustainable service(s) via potential follow-on projects within the ESA Business Applications programme elements.

To meet its goals, this call supports the generation of new or the improvement of existing user-driven applications and services that employ at least one space asset such as Satellite Communications, Satellite Navigation, Earth Observation, Human Spaceflight technologies, etc. and that are conceived to become sustainable in the short to medium term. These ideas will be implemented as projects with a maximum duration of 6 months where the funding granted is limited to 25.000 Euro per project on a co-funding basis of 50% (e.g. a project with total cost of 50.000 Euro may be granted a maximum of 25.000 Euro).

For activities where good economic viability and technical feasibility can be proven, the bidders will have the opportunity to propose further development and implementation of their idea up to a pre-operational level via a follow-on Feasibility Study or Demonstration Project within the ESA Business Applications framework (https://business.esa.int).

The purpose of this document is to present the conditions to bid for the LaunchPad Initiative

Open Call and to present the Management Requirements to be considered by the bidder.

# I. CONDITIONS TO TENDER

## 1. Participation in the Tender

Bidders are invited to submit their projects considering the launch and evaluation dates and the eligibility requirements below announced in the call at the following address: procurement@sa.catapult.org.uk

Eligibility Requirements:

Domain of activity

In order to be eligible, bidders must fulfil at least one of the following requirements:

a) Entities listed in either the 2016 UK Space Directory or the KTN Space & Satellite Applications UK Landscape (https://space.ktnlandscapes.com/);

b) Other UK Entities involved in satellite applications (Earth Observation, Human Spaceflight, Launchers, Navigation, Space Science, Space Engineering, Operations, Technology, Telecommunication);

c) Space and non-space newcomer entities in the UK holding ideas for innovative utilisation of space assets to develop non-space services.

Legal requirements

In order to be eligible for contract award, bidders must fulfil all the requirements below:

a) To be a legal entity (a public law company / a private law company / an association / a foundation)

registered under the laws of the United Kingdom;

b) To be headquartered in the United Kingdom;

c) To be fully compliant with the United Kingdom tax and social security obligations;

d) To observe the remaining requirements stated in this document;

e) When acting in collaboration with other national or foreign entities, the Bidder is the sole contractor and will be fully responsible for managing the grant.

The Satellite Applications Catapult, which hosts the ESA Business Applications UK Ambassador Platform will help coordinate the competition call, the receipt and evaluation of submissions. Consequently, the Satellite Applications Catapult is not eligible to bid to the competition. Satellite Applications Centres of Excellence and their respective host institutions are eligible to apply for the competition

Entities with multiple proposals

During the LaunchPad Initiative, funding is limited to one contract per entity per year.

Exceptionally, following a notification in the initiative website, entities with a contract may be allowed one additional contract in the same year.

Eligible costs

In order to be eligible, besides observing the dispositions in “Annex B - Cost eligibility limits and conditions”, all project costs must be:

• Necessary to the execution of the project;

• Incurred by the beneficiary and recorded in its accounts;

• Incurred during the contract term;

• Indicated in the cost planning in the proposal;

• Without VAT, interest owned, or duties.

Expenses incurred in the preparation and dispatch of the proposal will not be reimbursed.

## 2. Presentation and Submission

General Standards of Presentation

The Project Submission Form and all correspondence relating to it shall be in the English language. The Cover Letter and the Executive Summary shall not exceed 1 page each. Sections 1, 2, 3, 4 and 5 of the Proposal (part C of the Project Submission Form) shall not exceed 10 pages in total.

All sections shall be filled in and the proposal shall have enough substance to perform the evaluation.

Formal conditions, commitments, undertakings

Projects may be submitted at any given time before the submission date but there will be only one evaluation after the submission date. The submission and evaluation dates are set out in the Letter of Invitation to Tender and  to the following address:

procurement@sa.catapuilt.org.uk

In the Cover Letter the bidder shall explicitly state compliance with and acceptance of the LaunchPad Initiative Conditions to Tender and Management Requirements and Draft Contract.

Omission of this statement leads to rejecting the proposal.

Conditions relating to Intellectual Property Rights (IPR)

i) Bidders’ IPR: LaunchPad Initiative bidders will hold full and unconditional IPR on any proprietary assets to be used in their project. The project submission does not grant to Catapult, ESA, and/or UKSA any Intellectual Property Right, license, or option on any technology contained in the said project.

ii) Proprietary Assets: In case a bidder intends to explore, perform, develop and/or by any means use

proprietary assets in his/her LaunchPad Initiative Applications project, the entity is obliged to submit and annex with the Project Submission Form a formal written document (e.g. agreement, license, comfort letter) signed by the legal representative of the assets owner expressly granting the right to explore, perform, develop and/or by any means use those assets. The lack of that document leads to the rejection of the project.

Dispatch and receipt conditions

All Project Submission Forms shall be submitted to Catapult in .pdf format only and in a single e-mail to the address: procurement@sa.catapult.org.uk  until the closing date and time.

Enquiries and requests for clarification may be directed to the person responsible identified in the letter of invitation to tender. The deadline for submitting enquiries and clarifications is 16/05/2019. The responses to enquiries and clarifications received by this date, with the exception of confidential matters specific to individual potential bidders, will be notified to all interested parties via the competition website by 21/05/19.

## 3. Content of the Project Submission Form

The content required for the Project Submission Form is detailed in a dedicated document and shall comprise the following elements:

A. Cover Letter

B. Executive Summary

C. Proposal

## 4. Tender Evaluation Process

Tender Opening Board

The Tender Opening Board (TOB) is carried out by Catapult, Business Applications UK Ambassador Platform and ESA and assesses the admissibility of the project and checks all formal requirements, ensuring the project does not show prima facie evidence of a major noncompliance with the call requirements that would impair the fairness or transparency of the competition.

Specifically the TOB will assess:

i. Cover Letter

ii. Executive summary

iii. Compliance with Eligibility Requirements

iv. Compliance with Presentation and Submission

A project is only admitted for evaluation by the Tender Evaluation Board (TEB) if all formal requirements are met. Where any formal requirements are not met, the project will be rejected.

Tender Evaluation Board

The Tender Evaluation Board (TEB) is responsible for the evaluation of Proposals based on defined evaluation criteria. The TEB is composed of ESA, UKSA, Catapult, Business Applications UK Ambassador Platform and, if the case may be, non-voting experts. The information provided in the Project Submission Form will be dealt with in strict confidence.

The Proposal evaluation is based on the way the criteria below have been addressed in the Project Submission Form to the TEB. The Project Submission Form provides guidance on the expected content for evaluation against these criteria.

Evaluation Criteria

1. Background and experience ( Maximum score available 20)

- Team composition and partnerships

- Background of entities involved

- Vision

2. Business Case ( Maximum score available 30)

- Value proposition and objectives

- Commercial viability

- Targeted non-space market

- Customers/users and stakeholders

- Value chain current situation

- User/customer needs

3. Proposed Technical Solution ( Maximum score available 30)

- Solution description

- Justified involvement of a minimum of one eligible space asset

- Maturity of technologies required for integration

- Potential feasibility of application/service concept

- Access to technologies/space assets/know-how

- Added value

- Value chain and positioning

- Viability

- Risks

4. Activity Proposal (Maximum score available 20)

- Study logic and content

- Work breakdown

- Milestones and Cost Planning

- Management

All bidders will be notified by e-mail about the TEB decision within 30 days after the Evaluation Date.

Winning projects will be awarded a contract. The period between the notification of the TEB decision and the placement of the contract is in principle no longer than 30 days. In the event of an unsuccessful outcome of the evaluation, the bidder may submit a new project in any potential future open calls.

## 5. Budget and non-refundable grant

The total available budget for the implementation of the LaunchPad Initiative Open Call is 100,000 Euro. The available grant per winning project is up to 25,000 Euro. All projects should consider a

co-funding basis of up to 50% of the total project cost (e.g.:for a total project cost of 50.000 Euro, the maximum grant is 25,000 Euro; if the total project cost is above 50,000 Euro, the maximum grant remains 25.000 Euro). At all times, the TEB has the prerogative to approve projects considering a co-funding rate below 50%. Catapult is the sole responsible for the payment of grants to the winning entities.

The total price is to be exclusive of profit and based on a total cost of in Euro (€). Please note that this should be the potential/proposed cost, which includes both, company contribution and grant value in EURO.

# II. MANAGEMENT REQUIREMENTS

## 1. Scope of work and project logic

Within the activities to be developed under a LaunchPad Initiative Applications project, the bidder shall propose to perform the preparatory work and establish the key documents for the development of an application/service involving one or multiple space assets in order to fulfil the requirements of the relevant user community. The programme of work of the project shall

be composed by commercial and technical activities and, if economic viability and technical feasibility are proven, it shall involve the preparation of an implementation approach and of a pilot service. The project shall be organised in a way that supports the generation of the deliverables defined in section 3. Documents and items to be produced/delivered”.

## 2. Contractual milestones and review meetings

The contract term is fixed to a maximum of 6 months, during which the project must be executed and all deliverables submitted.

The following table represents the sequence of events to be taken into account in establishing the logical organisation of the work for LaunchPad Inititiative projects. Contractual Milestones

are the Kick-Off Meeting, the Mid-Term Review and the Final Review. Progress Meetings (if needed) are not foreseen as physical meetings but via tele-/videoconference; additional meetings may be requested either by Catapult or the Contractor; each of these meetings will take place in the United Kingdom and will be attended by representatives of the project team, Catapult, Business Applications UK Ambassador Platform and possibly ESA and UKSA. The documentation supporting each meeting shall be delivered to Catapult five (5) working days before the meeting takes place.

| Milestone | Months after contract signature | Meetings | Purpose of the meeting |
| --- | --- | --- | --- |
| Kick-Off | 0 | Kick-off | Clarification of outstanding issues; Overview of milestones payment plan and deliverables. |
| Mid-Term | 3 | Mid-Term | Presentation by the Contractor and review of the progress of the work including the status of due deliverables and the financial execution |
| Final | 6 | Final | Final presentation by the Contractor and review of the progress of the work including the status of due deliverables and the financial execution |

## 3. Deliverables - Documents and items to be produced/delivered

Contractors shall follow the structure of deliverables presented here and detailed in Annex A.

A single study report document containing the due deliverables shall be provided at mid-term and final project stages.

Due by

| Deliverables | Mid-Term | Final |
| --- | --- | --- |
| D1.1. Customer/User/Stakeholder Analysis | Draft only |  |
| D1.2. Value Preposition | Draft only |  |
| D2.1. Service/System Definition | Draft only |  |
| D2.2. Technical Feasibility Analysis | Draft only |  |
| D3.1. Business Model(s) | Draft only |  |
| D3.2. Business Plan | Draft only |  |
| D3.3. Viability Analysis | Draft only |  |
| D3.4. Socio Economic Impact Analysis | Draft only |  |
| If applicable: |  |  |
| D4.1. Proof of Concept |  |  |
| If continuation is foreseen via ESA Business Applications framework |  |  |
| D5.1. Draft Activity Pitch Questionnaire (APQ) |  |  |
| If continuation is foreseen outside the ESA Business Applications framework |  |  |
| D5.2. Business roadmap |  |  |

## 4. Management

Project Manager

The Contractor shall implement effective and economical management for the project. The nominated Project Manager shall be responsible for the management and execution of the work and for the coordination and control of the work within the consortium (when applicable). The Project Manager will be the official point of contact with Catapult during the execution of the work, and shall be identified in the Cover Letter.

Project Name/Acronym

The Contractor shall give the project a name. It is required to select a name not already used within the community of the former or existing ARTES and/or Business Applications projects, and to indicate the project name and acronym in the Cover Letter.

Access

During the course of the Contract Catapult and ESA shall be afforded free access to any plan, procedure, specification or other documentation relevant to the programme of work.

## 5. Reporting

Minutes of Meetings (MoM)

Formal written MoM attended by Catapult shall normally be agreed and made available by the Contractor within the next day of the meeting. The MoM shall clearly identify all agreements made including agreed action items.

Mid-Term Report

The Contractor shall deliver, not later than five (5) working days before the Mid-Term Review Meeting, the Mid-Term Report, on which Catapult will provide comments at the Mid-Term Review Meeting. The Mid-Term Report shall be self-standing, not requiring to be read in conjunction with other documents issued within the project. It shall present the status of all deliverables agreed and include an attached .pdf with the deliverables due at that time. Within one week after the Mid-Term Review Meeting the finalised version of the Mid-Term Report shall be delivered in one single document in .pdf format.

Final Report and public Executive Summary

The Contractor shall deliver, not later than five (5) working days before the Final Review Meeting, a Draft Final Report, on which Catapult will provide comments at the Final Review Meeting. The Final Report is to be written in a concise form and shall describe the major accomplishments of the project in an introductory part, and have attached all the deliverables due. It shall be self-standing, not requiring to be read in conjunction with other documents issued within the project.

The Contractor shall attend a LaunchPad Initiative Final Review workshop.

For the purpose of disseminating Catapult and ESA activities, a public Executive Summary of the project, not containing proprietary information, shall be provided at this stage. Within one week after the Final Review Meeting the finalised version of the Final Report and the public Executive Summary shall be delivered in single documents in .pdf format.

Problem Notification

The Contractor shall immediately notify Catapult of any problem likely to have a major effect on the time schedule of the work, or to have significantly impact the scope of the work to be performed (due to e.g. procurement problems, unavailability of facilities or resources, etc.), or to require any budget changes (e.g. allocation of budget from one cost category to another; impossibility to spend the total grant amount).

# ANNEX A – DETAILS ON DELIVERABLES

Within the activities to be developed under a LaunchPad Initiative Applications project, the Contractor shall propose to perform the preparatory work and establish the key documents for the development of application/service involving one or multiple space assets in order to fulfil the requirements of the relevant user community, and define the roadmap for its future implementation. The following deliverables shall be provided:

D1.1 Customer/User/Stakeholder Analysis (suggested length: 4 pages)

The contents of this section shall include:

- An identification of the stakeholders in the project, distinguishing between customers (who pay), users (who uses), service providers and other stakeholders (regulators, relevant authorities).

- Presentation of customers interested in and willing to pay for the planned application/service, and evidence of contact.

- Identification, quantification and validation of relevant needs, constrains and Key Performance Indicators (KPIs) which paying customers, users and other relevant stakeholders will use to evaluate the impact of the proposed application/service in their operational environment.

- A high level assessment of the benefits (e.g. financial, societal) resulting from the use of the system/service that will affect the key stakeholders.

To further detail the Customer/User/Stakeholder Engagement, the Bidder may also present:

- Overview of the engagement activities with the customers/users/stakeholders.

- Depending on the subject and when considered necessary or helpful, the organisation of a customer/user workshop might be considered. If such a workshop is carried out, the related workshop report compiling all information, i.e. participants, programme, hand-outs, presentations, results, conclusions, shall be included.

D1.2. Value Preposition (suggested length: 1 pages)

The contents of this section shall include:

- Definition and validation of the value proposition(s) that the planned application/service will bring to the customers/users/stakeholders addressing their needs and KPIs.

D2.1. Service/System Definition (suggested length: 4 pages)

The contents of this section shall include:

- Definition of the service concepts towards paying customers, users and other relevant stakeholders

- aligned with the needs and KPI identified, and taking into account any performance, quality and mode of delivery, integration with and interfaces to operational processes and procedures.

- Definition of the end-to-end service value chain, including key resources, key activities and key partners involved, their roles, and the interactions amongst them, and taking into account existing tools and services of paying customers, users and other relevant stakeholders to interface with.

- A description of the space assets involved including the justification for the use of them (i.e. Satellite Telecommunication, Satellite Earth Observation, Satellite Navigation, Human Space Flight).

- Definition of the system architectures providing the defined service concepts, taking into account any existing infrastructure of paying customers and other relevant stakeholders.

- Visualisation of the system architecture in terms of main building blocks and interfaces to external systems and services identifying key technologies required and their maturity status (existing, commercial-off-the-shelf, to be developed, market readiness, etc.).

- Presentation and justification of the role of the space asset(s) (Earth observation, satellite navigation, satellite communication, human spaceflight, etc.) which are subject for integration.

Suggested aid: a high level block diagram with your system/service showing the key attributes and key building blocks and the main interfaces (internal and external).

D2.2. Technical Feasibility Analysis (suggested length: 2 page)

The contents of this section shall include:

- Justification of the final service concept and its underlying system and validation of the service concept with the engaged customers, users and other relevant stakeholders.

- Identification of critical elements and risks related to development, implementation, and operation of the service and system from a developer perspective as well as from the the perspective of paying customers, users and other relevant stakeholders, and presentation of mitigation strategies and measures.

- Assessment of the overall technical feasibility of the proposed service and system concept.

D3.1 Business Model(s) (suggested length: 1 page)

The contents of this section shall include:

- Definition of business model(s) based on the value proposition(s) and service concept(s) addressing as a minimum customer relationships, paths to market, key resources, key activities, key partnerships, revenue streams and cost structure.

- Presentation of the validation activities of the business assumptions with the engaged customers, users and other relevant stakeholders.

Suggested aid: this deliverable shall be prepared and elaborated making use of the Business Canvas template available under (https://business.esa.int/documents or https://strategyzer.com/canvas).

D3.2 Business Plan (suggested length: 4 pages)

The contents of this section shall include:

- Presentation of the quantitative market analysis for the envisaged services including the size and attractiveness of the market/customer segment(s).

- Presentation of the competitive environment and of the main competitors including information on their services and value propositions.

- Presentation of the financial plan and financial projections for development and sales, including key financial indicators such as CAPEX, OPEX, Break Even Point, Net Present Value, financial projections for the next 5 years.

- A discussion of your market penetration projections (i.e. percentage of market share, etc.), including key assumptions. This part should be put in relation with the competitive positioning described in point 4 and stakeholders’ benefits described.

- Presentation of the team, competences and capabilities required to implement and deliver the service.

In case of missing competences and capabilities, presentation of the intended strategy to acquire them.

D3.3 Viability Analysis (suggested length: 3 pages)

The contents of this section shall include:

- Identification of critical elements and aspects related to the business model(s) and business plan and their robustness, by addressing aspects such as market barriers, cost/benefit ratios, competitive positioning, key differentiators, growth potential, etc., and presentation of mitigation strategies and measures.

- Identification of critical elements and aspects related to non-economic aspects (e.g. liability, regulation, public acceptability, etc.) and presentation of mitigation strategies and measures.

- Assessment of the overall commercial viability of the proposed service and system concept.

D3.4 Socio Economic Impact Analysis (suggested length: 2 pages)

The contents of this section shall include:

- Assessment of the potential socio-economic impact of resulting operational services regarding expected revenues, job creation across the value chain, export opportunities, establishment of new markets, investment leverage, and societal benefits.

D4.1. Proof of concept (suggested length: 1-2 pages)

The contents of this section shall include:

- Definition of the most critical technical, operational, commercial elements which shall be validated within the PoC, including hypotheses, validation methods, and quantifiable success criteria.

- Presentation of the PoC outline, including objectives for the PoC, scope, schedule, approach, necessary training and communication material, and involvement of the customers, users and other relevant stakeholders (where necessary).

- Presentation of the results, including assessment of the outcome on the most critical elements and validation of the results with the involved customers, users and other relevant stakeholders (where necessary).

Suggested aid: The PoC might consist of a mock-up, simulations, etc. which is compiled on a minimum effort base, i.e. major development efforts shall be avoided.

D5.1. Activity Pitch Questionnaire (APQ) (suggested length: 7 pages)

For activities where good economic viability and technical feasibility can be proven, the bidders will have the opportunity to propose further development and implementation of their idea up to a pre-operational level via a follow-on Feasibility Study or Demonstration Project within the ESA Business Applications framework (https://business.esa.int).  The first step in this process is the completion of an Activity Pitch Questionnaire (APQ).

The contents of this section shall include:

- A completed APQ template document, the template is available here: https://business.esa.int/documents

By providing this questionnaire, you allow ESA to quickly take informed decisions on next steps, pointing you to the most appropriate activity stream (e.g. additional preparatory work, training, teaming up with some other partners, go ahead targeting a feasibility study, or a demonstration project in a single or a two phases approach). Please note that ESA may provide this Activity Pitch Questionnaire to and discuss it with the National Delegations of the countries of your consortium.

D5.2. Business Roadmap (suggested length: 2 page)

For activities where good economic viability and technical feasibility can be proven, the bidders will have the opportunity to propose further development and implementation of their idea outside the ESA Business Applications framework.

The contents of this section shall include:

- Presentation of the conclusion concerning the feasibility and viability of the specified application/service and associated system, and wrap up of the critical success factors and risks for the implementation of the solution,

- Definition of the next steps for service implementation, taking into account potential success factors and showstoppers (e.g., technology maturity, lack of service provision history, capital requirements, etc.) and identification of critical milestones.

- In the case the decision is to go ahead outside the ESA Business Applications framework, describe in detail what the next step shall be, highlighting any support required from the Agency.

# ANNEX B – COST ELIGIBILITY LIMITS AND CONDITIONS

1. Direct Costs

The project may consider the following direct costs, to be presented in EURO (€):

| Cost Category | Cost ( EURO €) |
| --- | --- |
| Staff |  |
| Subcontracting Cost |  |
| Access to data sources |  |
| Travel, subsistence and accommodation expenses (including % of manpower cost) |  |
| Equipment |  |
| Awareness raising / promotion Costs |  |
| External Services |  |
| Miscellaneous |  |
| Indirect Cost |  |
| Total Activity Cost |  |
| Company contribution (50%) |  |
| LaunchPad Initiative Contract Price (50%, up to €25,000) |  |
| Total Project Cost: |  |

[Please provide additionally the following information]

- Exchange Rate (if not in Euros)

- Average Hourly Rate

- Total Number of hours

[Travel expenses can be up to 8% of the manpower cost without need for a travel plan to be provided. Should it exceed 8%, please provide a detailed travel plan.

If external services are used, please indicate the company and its geographical location

Please confirm that any marketing or promotional costs do not exceed 3% of the total activity cost.]

2. Indirect Costs

Indirect costs are all those eligible costs which cannot be identified by the participant as being directly attributed to the project. They may not include any direct costs. A specific flat rate of 10% of the staff costs is to be used to calculate the indirect costs.

2 In order to check if the candidate project name is already in use by another ARTES or Business Applications project, it is suggested to perform a search for that name under: http://artes-apps.esa.int/projects (for ARTES Applications programme elements) and http://artes.esa.int/projects (for any other ARTES programme element) and https://business.esa.int/projects for Business Applications

3 For the preparation of the deliverables, the interactive Outline Proposal tools may provide support:

https://business.esa.int/documents

Support on completing an APQ can be provided by the UK Regional Ambassador Platform network

https://business.esa.int/ambassador-platforms/ap-uk