# SUPPORT TO DEVELOP SPECIALISED COMMISSIONING POLICIES AND SERVICE SPECIFICATIONS FOR 2016/17 TO 2018/19

Final Version: 1.0

Date: 10.10 2016

Authors: Ahmed Syed & Donna Hakes

# Specification of Requirements

## Background to the requirements

### Introduction

#### This is an invitation for bids from the NHS England Lead Provider Framework (LPF) Agreement – Lot 1 End to End Commissioning Support Services to provide support to develop specialised clinical commissioning policies and service specifications for 2016/17 to 2018/19.

#### Call-Off Contracts will be established with selected Providers from Lot 1 of the LPF Agreement to deliver the requirements outlined within this specification document.

#### The NHS England may award up to three (3) Providers with Call-Off Contracts to deliver these requirements. The rationale in appointing more than one provider is to mitigate possible risks and issues in delivery of the work related such as provider capacity, conflicts of interests and likely impact of unforeseen delays. The resulting awarded Call-Off Contracts are expected to operate as follows:

#### The top ranking Provider from the resulting Further Competition process will be appointed as a Preferred Provider. The Preferred Provider appointed a Call-Off Contract, would be automatically granted the right to deliver the requirements as outlined in this document, in the first instance.

#### Where the Preferred Provider cannot deliver the requirements during the term of the Call-Off Contract due to capacity or conflict of interest issues, then the Second Ranking Provider awarded a Call-Off contract following the conclusion of the Further Competition, would be granted the right to deliver the requirements.

#### Where the Second Ranking Provider cannot deliver the requirements during the term of the Call-Off Contract due to capacity or conflict of interest issues, then the Third Ranking Provider awarded a Call-Off contract following the conclusion of the Further Competition, would be granted the right to deliver the requirements .

### Background and context

#### NHS England has held the direct commissioning responsibility for prescribed specialised services since April 2013. As part of these duties, NHS England is responsible for programme management of the development, testing and adoption of a range of clinical commissioning policies and service specifications.  These set out the nationally consistent commissioning position for specific treatments, technologies and services to ensure equal access for defined groups of patients, for which NHS England has legislative responsibility for.

#### The programme of clinical evidence reviews, which are based on treatment topics, are agreed on an annual basis (ongoing) with the flexibility to add new topics should they be considered clinically necessary through horizon scanning systems. The nature of this programme planning makes it essential that there is in place long term contractual relationship with specialist Providers who can deliver this element of our programme requirement.

#### Specialised Services have a single operating model which applies equally across the population of England.

#### Specialised services clinical commissioning policies form a critical part of NHS contracts, helping to ensure equitable access to evidence-based and cost-effective treatments and health technologies and providing clarity on whether or not treatments are routinely commissioned. Similarly, service specifications are important in clearly defining the standards of care expected from organisations funded by NHS England to provide specialised care. This approach promotes fairness and transparency in access to services ensuring whilst high quality care for patients

#### In order to support funding decisions and ensure high standards of care, development of clinical commissioning policies and service specifications is informed by clinical evidence reviews. In addition to clinical evidence reviews, activity, service and financial impact are undertaken to establish impact of any proposed changes on services delivering care and the associated budget impact.  These elements form part of the formal public consultation for clinical commissioning policy and service specification proposals.

#### All specialised services are grouped into six national programmes of care (NPoCs) - Internal Medicine, Cancer, Blood and infection, Mental Health, Trauma and Women and Children. Each NPoC has several Clinical Reference Groups (CRGs) to provide clinical advice and leadership.

#### The programme of work for 2015/16 undertook the consideration of circa 100 clinical commissioning policies and service specifications. Approximately 100 developed into documents for consideration through the governance process to recommended commissioning position. The following clinical commissioning policy development arrangements were in place in 2015/16:

#### A ‘turnkey’ solution was provided by Deloitte to support the development of clinical commissioning policies. In addition to undertaking clinical evidence reviews, this provided an effective PMO function to oversee the significant clinical commissioning policy pipeline process, direct support to the work with clinicians and other stakeholders to draft, develop and test policy proposals, and an objective review of the development process to capture ‘lessons learned’ to inform process going forward.

- Solutions for Public Health (SPH), a team within Arden and Greater East Midlands Commissioning Support Unit (AGCSU), undertook a number of independent evidence reviews for specialised commissioning ‘in-house’ clinical commissioning policy developments.

- NICE supported NHS England policy production by undertaking and publishing Rapid Evidence Reviews.

- United Kingdom Medicines Information (UKMi): NHS England had access to medicine reviews undertaken by the United Kingdom Medicines Information (UKMi) service which is part of NHS England’s Specialised Pharmacy Services (SPS)

- Public Health England undertook some clinical evidence reviews to support NHS England as part of a Heads of Agreement.

#### Service specifications were developed in-house by NHS England in 2015/16.

### Clinical evidence reviews 2016/17 onwards:

#### From 2016/17 onwards, NHS England plans to have the following arrangements in place for clinical evidence reviews to support its specialised services clinical commissioning policy and service specification development:

#### NICE to undertake complete clinical commissioning policy development for licensed drugs in the form of Commissioning Support Documents (CSDs) (25 per annum) and clinical evidence reviews (8 per annum).

#### UK Medicines information service (UKMi) which is part of NHS England’s Specialised Pharmacy Services (SPS) to undertake 9 clinical evidence reviews for cancer drug off label indications.

#### Public Health England to deliver up to 12 clinical evidence reviews per annum as part of a Heads of Agreement in place between NHS England and Public Health England.

#### External Providers will deliver a maximum of 60 clinical evidence reviews per annum.

#### In 2016/17, clinical commissioning policy and service specification will include the following phases of development:

#### Phase A: Clinical Build - the starting point of the clinical build phase is the potential inclusion of a proposal on to the clinical policy or service specification development work programme and concludes following a recommendation, made through a gateway managed by the Clinical Panel, to the National Programme of Care Board (NPoC) for prioritisation. If included, a clinical evidence review is undertaken in order to develop the proposition for clinical policy and maybe required for a service specification. Phase A is lead and assured by the Clinical Effectiveness Team (CET).

#### Phase B: Impact Analysis - the second phase involves further development of the proposition which requires the undertaking of operational and financial impact assessments, initial stakeholder testing and formal public consultation. Any discrepancies or queries related to the clinical evidence review undertaken may be raised in this Phase. This phase is managed by the NPoC and concludes through a gateway at NPoC Board level.

#### Phase C: Governance - the third and final phase is the recommendation process through the Clinical Priorities Advisory Group (CPAG), and the decision through Specialised Commissioning Oversight Group (SCOG) and Specialised Services Commissioning Committee (SSCC). Following decisions being made, all clinical commissioning policies and service specification will be progressed through NHS England Gateway and published on NHS England website.

### Scope of the Procurement

### The aims and objectives of this procurement are broadly the same as those presented at the Provider briefing call held on 23rd June 2016. The slide pack presented at this session can be found as Appendix 1.

### Aims and Objectives

#### The aim of this work is to provide professional services to support NHS England in developing clinical commissioning policies and services specifications for a period of 3 years.

### Objectives

#### The objective of the professional services will be to undertake clinical-effectiveness, safety and cost effectiveness (where information is available) reviews of published peer reviewed clinical evidence to support clinical commissioning policy and service specification in accordance with the guidance provided (Appendix 2).

#### To undertake the clinical evidence reviews using validated methodological approaches to ensure they are robust and of high quality as well as legally appropriate.

#### The support required will be for up to 60 evidence reviews across the six NPoCs.

#### To support development of proposals in a timely manner to ensure they are completed to meet deadlines for consideration as part of NHS England’s annual prioritisation, or through the In Year Service Development route if clinical urgency or no financial impact is determined.

### Contract timeframes

#### The appointed Providers are required to begin work as soon as the Call Off Contract(s) have been awarded.

#### The Duration of the Call-Off Contracts is 3 years, currently anticipated to run from 19th December 2016 until 18th December 2019.

### Constraints and Dependencies

#### The professional services will be required to develop a maximum of 60 proposals per year. An initial batch of proposals will be agreed on an annual basis. Further new proposals will be added on an ad-hoc basis as they are identified during the year. Each clinical evidence review will need to be completed in ten weeks following agreement and sign off of the PICO – Eight weeks to produce the evidence report plus one week for NHS England to review and feedback and one week for provider to make amendments if necessary.

#### Appointed Providers will be required to work with the Specialised Commissioning Policy Working Groups (PWGs) (See Appendix 3 for PWG terms of reference) when undertaking clinical evidence reviews and following public consultation to take into account feedback relevant to the reviews.

#### Appointed Providers will require access to library resources to search and download peer reviewed and published evidence.

## Requirements

### Mandatory and Minimum Requirements

#### Providers must have the following skills and expertise to deliver the outputs:

#### expertise in research methods particularly in undertaking clinical evidence reviews;

#### expertise in knowledge and information management with access to clinical library resources;

#### expertise in applied epidemiology;

#### expertise in analysis and interpretation of clinical research evidence to provide the evidence summary, what it means, and then translate this not only into technical documents but also interpret what the key factors of the studies means for the public;

#### project management skills to ensure the work is delivered in a timely and robust manner; and

#### independence from the subject matter, industry expertise.

#### A minimum of 3 years’ experience of undertaking evidence reviews on health technologies to support the NHS and/or third sector organisation is required.

#### Providers must undertake clinical evidence reviews in accordance with NHS England’s clinical evidence review guidance document (See Appendix 2).

#### Providers must use the methodology defined by NHS England to evaluate the evidence.

#### Providers must follow all steps defined and notes provided in the guidance document (Appendix 2) in completing the clinical evidence review template (including the tables).

#### Providers must complete the patient’s benefit section of the CPAG summary report.

#### Providers must be able to provide an audit of undertaking the clinical evidence review if required by NHS England and support in its response to comments and feedback received on the evidence review during public consultation that may challenge the review. Audit information requested must be provided to NHS England within 5 working days.

### Deliverables

#### Deliverable 1 – Completed clinical evidence review template (all sections including tables) in accordance with the guidance provided (Appendix 2) for each proposal.

#### Deliverable 2 – Audit information related to clinical evidence reviews where requested.

#### Deliverable 3 – Completed ‘The Benefits of the Proposition’ and ‘Other health metrics determined by the evidence review’ sections in the CPAG summary report (Appendix 4) in plain using information from table 9 of Appendix 2.

### Timescales & Implementation

#### Each clinical evidence review must be completed in ten weeks from the date a completed and signed off ‘Population Intervention Comparator and Outcome’ template for the proposal is sent to the appointed Provider.

#### Providers must share the final version of the clinical evidence review with the PWG for one week to give them an opportunity to feedback and provide any comments. The provider is required to make the amendments and return the final evidence review within one week.

### Location

#### It is expected that the appointed Providers would be able to undertake the outlined work remotely on their own premises and communicate with NHS England through means such as emails, phone calls, WebEx etc.

#### On rare circumstances the appointed Providers may be required to physically attend meetings.

### Roles and Responsibilities

#### As outlined in the clinical evidence review guidance document, Providers will be required to:

#### Scope the proposal with NHS England’s PWGs;

#### Extract data from published literature and assess the quality of evidence; and

#### Submit clinical evidence reviews to the PWG to draft a proposition for consideration by NHS England governance.

#### The Clinical Effectiveness Team will oversee and coordinate the work with the appointed Providers.

### Management Information & Governance

#### The Clinical Effectiveness Team will report progress on a monthly basis to the Specialised Commissioning Programme of Care Programme Oversight Group.

#### These meetings are attended by the Specialised Commissioning National Clinical and Deputy Clinical Directors, Clinical Effectiveness Team members, National Programme of Care Managers, Head of Acute Programmes, Mental Health Programme of Care lead.

#### Monthly meetings/webinars will be held with the appointed Providers to oversee progress and performance.

#### Project progress reports will be required on a weekly basis (every Friday) from appointed Providers. Reports should as a minimum include the following information – NHS unique reference number (URN), topic name, date PICO agreed, delivery date of final report, current status, invoicing information. See example in Appendix 5 All information shared with the appointed Providers by NHS England must be treated confidentially

#### NHS England will own intellectual property rights to the clinical evidence reviews.

### Performance and Measurement

#### The structure of performance measurement is described in the table below:

| Key Performance Indicator (KPI) | Measurement | Target |
| --- | --- | --- |
| Deliverable 1 Delivery Timescale | The provider must submit the completed clinical evidence review templates within the agreed timescales– | Submitted within the timescales specified: Completed and finalised in ten weeks from date a completed and signed off PICO template is submitted to the provider. - Eight weeks to complete the evidence review - One week for PWG to provide feedback - One week to make any amendments necessary |
| Deliverable 1 - Adherence to evidence review process guidelines | The provider must reassure NHS England that all steps outlined in the evidence review guidance. This includes: - Developing the search strategy - Screening steps 1 & 2 - Data extraction - Assessment of the quality of evidence - Reporting the findings of the assessment - Sharing the draft clinical evidence review with the PWG for comment - Making any amendments based on PWG feedback Include summary of steps followed in the methodology section of the clinical evidence review template |  |
| Deliverable 1- Quality of evidence review report content | The provider must complete the clinical evidence review template (all sections including the tables) in a standardised manner using the notes provided Reports which are: - Well formatted and structured - Written in clear and understand able language |  |
| #### Deliverable 2 - Audit information related to evidence reviews where requested | #### The provider must submit the audit information within the agreed timescales. | Submitted within the timescales specified: 5 working days from date requested. |
| #### Deliverable 3 – Completion of the CPAG summary report | #### The provider must complete ‘The Benefits of the Proposition’ and ‘Other health metrics determined by the evidence review’ sections of the CPAG summary report in plain language | As per deliverable 1 |

### Contract Term

#### The contract term is set at 3 years i.e. 36 months from the date of award.

#### NHS England reserves the right to extend the Call-Off Contract for a maximum period of up to 12 months, subject to appropriate budget approvals being in place.

#### NHS England may elect to extend or request additional deliverables beyond those captured in the original Call-Off Contract provided that:

#### The value of the extended or additional work does not exceed more than 10% of the original contract value;

#### The extended and/or additional deliverables are within the statement of requirements scope outlined in section 3 of this document;

#### The extended and/or additional deliverables are delivered by the appointed Providers in accordance with the agreed Fixed Price Rate Cards (including any Discounts) negotiated as part of this procurement process that resulted in the agreed final Call-Off Contract; and

#### Appropriate NHS England approvals have been sought and confirmed ahead of the extended deliverables and/or additional works have been commissioned by the NHS England Contract Manager.

### Pricing

#### Pricing will be based on the following:

#### Base day rate per specialist role; and

#### Fixed discount rates against the base day rate/specialist role based on the following bandings:

#### Band 1: 1-20 Proposals per 12 month period;

#### Band 2: 21-40 Proposals per 12 month period;

#### Band 3: 41-60 Proposals per 12 month period; and

#### Band 4: Single Provider Rate.

#### All Pricing negotiated as part of the process that resulted in the agreed Final Call-Off Contract (including Fixed Day Rates and any Discounts) will remain fixed during the Contract Term and for any extension agreed between NHS England and the appointed Providers.

#### Whilst it is anticipated that NHS England will commission up to 60 evidence reviews for specifications/policies during a 12-month period, payment to the appointed Providers will be on a case-by-case basis upon completion of the evidence review and in accordance with the fixed budget in place for these requirements (which is not being disclosed to the Providers).

## Appendices

### Appendix 1: LPF Briefing – 23rd June 2016:

### Appendix 2: Evidence review guidance

### Appendix 3: PWG terms of reference

### Appendix 4: CPAG Summary Report

### Appendix 5: Progress Report