## Sheet1
Highways England Confirmation of Task Order Redactions made under FOIA 2000 exemptions sec 40: personal info and sec 43: commercial.
Supplier: | AECOM | Fee Request for this CTO |  | 13967.9
Project Title: | A46 Newark Bypass RIS scheme options
Contract Ref. | 114/2/1391/2 | CPA No.: | Redacted | BPA No.: | Redacted
PIN Description: | Studies | Sub Pin: | Redacted | PIN No.: | Redacted
HE Reference: | EM 5 16/17 | Start and End Date : |  | 08/04/2016 - 04/05/2016
Task Overview and Expected Outcomes
The AECOM SPA team has recently been assisting NDD to progress A46 Newark Bypass RIS scheme option development. Work in Feb/March under CTO EM 46.01 has built on the work completed under PCF Stage 0 under the Major Project framework. This work developed a Recommended Solution for an A46 dualling scheme with a combination of ‘At Grade’ and ‘Grade Separated’ junctions. This work has been reviewed, further option assessment has taken place, and an interim report produced. The interim report has developed a phased solution of the scheme in order to meet current budget constraints and develop a solution that will address capacity and safety issues at the Cattle Market and A1 junctions. This task order is intended to take forward the key actions and conclusions of the interim report, in order to further progress the development of the A46 dualling scheme during April 2016 up to 4/5/2016.
Task Objectives and Milestones
This task includes for the following elements of work: 1. Project Management 2. Strategic Modelling Review The modelling strategy proposed in the Appraisal Specification Report (Feb 2016) will be reviewed, and consideration given to how the WYG VISUM model may form part of the initial scheme assessment process going forward and the strategic modelling best way forward to ultimately support a scheme business case. 3. Development of Junction designs Develop the recommended options from the Interim report and carryout further testing of the designs at Cattle Market and the A46 bypass options of the A46. Test junctions with WYG future year flows to determine robustness of design. Development of Appraisal summary Table for by-pass scheme Refine Cost estimate for all options being taken forward. 4. Network Rail Undertake an assessment of engineering feasibility of A46 on-line dualling once the parameters from Network Rail are received, develop the engineering feasibility design of the two parallel schemes. (Note: This may not be complete by 4/5/2016 owing to requirement for third party information. 5. VISSIM model Review A46 VISSIM model status and develop CTO for extending model to cover Farndon and Winthorpe junctions and associated revalidation as a post 4/5/2016 task. 6. Reporting The current A46 interim report will be updated following the conclusion to the above work, with recommendations for further actions to take the scheme forward to PCF Stage 1.
Expected Project Outcomes
The following elements will be produced; • Strategic modelling assessment and recommendations for business case modelling • Junction designs for Cattle Market and A1 bypass scheme • VISSIM model review and proposal for further mode development • Updated A46 report Interim Report.
Project Risk and Management
The task will be managed by Sarah Guest, in conjunction with Graham Fry. The largest risk to this work, is proceeding without contact with Major Projects and TAME to obtain their advice and guidance on developing an A46 major scheme that will fit within their parameters for funding. We recommend once the outcome of this element of the study is concluded and the outcome of the HESPA contract is known that consultation with Major projects is undertaken. Note: Preparation for and attendance at the A46 working Group Meeting in Nottingham (SG and GF) to present to ongoing work and conclusions draw so far is subject to some uncertainty so this will be covered under the Area Planning support CTO.
HE Project Sponsor | Sign: |  | Print Name: |  | Date:
Management Approver: | Sign: |  | Print Name: |  | Date:
Contractual Approval: | Sign: |  | Print Name: |  | Date: