## Sheet1
It is expected that Traffic management will be typically booked every Monday, Tuesday, Wednesday and Thursday nights starting on the 13th January 2020 - 12th March 2020. Each block of structures is envisaged to be 1 weeks work. Traffic management dates will be subject to roadspace availability. Nb. no inspections programmed w/c 17th Feb to ensure there is sufficient time to arrange TTROs for subsequent inspections.
Structure Key | Structure Name | Road | Km | Anticipated TM Layout | Provisional Date | Expected Dates of Shifts Involving TM shown in bold:
22774 | Welsh Lane Overbridge | A43 | 35.7 | NB: Lane 1 closure. SB: Lane 2 closure. | 2020-01-13
22775 | Biddlesden Road Overbridge | A43 | 36.5 |  |  | January
22774 | Welsh Lane Overbridge | A43 | 35.7 | NB: Lane 2 closure. SB: Lane 1 closure. | 2020-01-14 | Mo | Tu | We | Th | Fr | Sa | Su
22775 | Biddlesden Road Overbridge | A43 | 36.5 |  |  |  |  | 1 | 2 | 3 | 4 | 5
22778 | Dadford Road Overbridge | A43 | 40.6 | NB: Lane 1 closure. SB: Lane 2 closure. | 2020-01-15 | 6 | 7 | 8 | 9 | 10 | 11 | 12
22779 | Winterhills Road Overbridge | A43 | 41.1 |  |  | 13 | 14 | 15 | 16 | 17 | 18 | 19
22778 | Dadford Road Overbridge | A43 | 40.6 | NB: Lane 2 closure. SB: Lane 1 closure. | 2020-01-16 | 20 | 21 | 22 | 23 | 24 | 25 | 26
22779 | Winterhills Road Overbridge | A43 | 41.1 |  |  | 27 | 28 | 29 | 30 | 31
4741 | A5070 Interchange South | M69 | 114.3 | NB: Lane 1 + 2 SB: Lane 3 + 2 | 2020-01-20 | 6 13 20: February
4742 | A5070 Interchange North | M69 | 114.5 |  |  | Mo | Tu | We | Th | Fr | Sa | Su
4761 | A5 Interchange South | M69 | 110.1 |  |  | 11 18 25: 1; 12 19 26: 2
4762 | A5 Interchange North | M69 | 110.3 |  |  | 3 | 4 | 5 | 6 | 7 | 8 | 9
4741 | A5070 Interchange South | M69 | 114.3 | NB: Lane 3 + 2 SB: Lane 1 + 2 | 2020-01-21 | 10 | 11 | 12 | 13 | 14 | 15 | 16
4742 | A5070 Interchange North | M69 | 114.5 |  |  | 17 | 18 | 19 | 20 | 21 | 22 | 23
4761 | A5 Interchange South | M69 | 110.1 |  |  | 24 | 25 | 26 | 27 | 28 | 29
4762 | A5 Interchange North | M69 | 110.3
1966 | Newton Lane | M6 | 135.7 | Lane 1 + 2 both carriageways. | 2020-01-22 | 3 10 17 24: March
28039 | MS3 @ 135/6 | M6 | 135.6 |  |  | Mo | Tu | We | Th | Fr | Sa | Su
21212 | Vms Gantry No.44 (M6/0/2/S) | M6 | 134.9 | [8 empty] | 1
21213 | Vms Gantry No.43 (M6/0/1/S) | M6 | 135.7 |  |  | 2 | 3 | 4 | 5 | 6 | 7 | 8
1966 | Newton Lane | M6 | 135.7 | Lane 3 + 2 both carriageways. | 2020-01-23 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[6 empty] | 16 | 17 | 18 | 19 | 20 | 21 | 22
16935 | Nene Viaduct | A14 | 47.7 | Lane 1 closures A14 Local authority closures for some spans | 2020-01-27 | 23 | 24 | 25 | 26 | 27 | 28 | 29
16935 | Nene Viaduct | A14 | 47.7 |  | 2020-01-28 | 2 9 16 23: 30; 3 10 17 24: 31
16935 | Nene Viaduct | A14 | 47.7 |  | 2020-01-29
16935 | Nene Viaduct | A14 | 47.7 |  | 2020-01-30
22540 | River Nene No.2 | A45 | 192.3 | EB Lane 1 + slip | 2020-02-03
22539 | River Nene No.1 | A45 | 192.3 | WB Lane 1 + slip | 2020-02-04
7833 | Derwent | A38 | 449.7 | EB Lane 1 | 2020-02-05
7833 | Derwent | A38 | 449.7 | WB Lane 1 | 2020-02-06
11991 | Kirby Muxloe Interchange North | A46 | 176.6 | NB: Lane 1 + Layby Closure SB: Lane 2 | 2020-02-10
11992 | Kirby Muxloe Interchange South | A46 | 176.6
11993 | M1 Confirmatory Sign Gty | A46 | 176.8
11991 | Kirby Muxloe Interchange North | A46 | 176.6 | NB: Lane 2 SB: Lane 1 + Layby Closure | 2020-02-11
11992 | Kirby Muxloe Interchange South | A46 | 176.6
11993 | M1 Confirmatory Sign Gty | A46 | 176.8
26030 | VMS MS3 No. 5 | A38 | 439.2 | Lane 1 both directions. | 2020-02-12
7808 | Staker Lane North | A38 | 440.2
7807 | Staker Lane South | A38 | 440.1
7808 | Staker Lane North | A38 | 440.2 | Lane 2 both directions. | 2020-02-13
7807 | Staker Lane South | A38 | 440.1
7811 | Sign Gantry No 1 | A38 | 442.3 | NB: Lane 1 + A516 Exit Slip SB: Lane 2 | 2020-02-24
7812 | Sign Gantry No 2 | A38 | 442.9
7813 | Sign Gantry No 3 | A38 | 443
7815 | Sign Gantry | A38 | 443.3
7811 | Sign Gantry No 1 | A38 | 442.3 | NB: Lane 2 + 3 SB: Lane 2 + 3 | 2020-02-25
7812 | Sign Gantry No 2 | A38 | 442.9
7813 | Sign Gantry No 3 | A38 | 443
7815 | Sign Gantry | A38 | 443.3
5376 | A46 Crossing | A1 | 204.8 | NB: Lane 1 + Exit Slip SB: Lane 2 | 2020-02-26
26038 | A1/A17/A46 Slip Road Footbridge | A1 | 204.7
5376 | A46 Crossing | A1 | 204.8 | NB: Lane 2 SB: Lane 1 + Exit & Entry Slips | 2020-02-27
26038 | A1/A17/A46 Slip Road Footbridge | A1 | 204.7
22573 | Nene Wharf | A45 | 176.5 | NB: Lane 1 + Entry Slip | 2020-03-02
22573 | Nene Wharf | A45 | 176.5 | SB: Lane 1 + Exit Slip | 2020-03-03
18335 | Nether Lock Viaduct | A46 | 238.2 | Full closure | 2020-03-04
18335 | Nether Lock Viaduct | A46 | 238.2 | Full closure | 2020-03-05
2972 | Allestree West R/W | A38 | 448.5 | Carriageway and lane closures with switches | 2020-03-09
2973 | Allestree East R/W | A38 | 448.5
16600 | Allestree Junction North | A38 | 448.6
16601 | Allestree Junction South | A38 | 448.5
16600 | Allestree Junction North | A38 | 448.6 | Carriageway and lane closures with switches | 2020-03-10
16601 | Allestree Junction South | A38 | 448.5
16602 | Ferrers Way | A38 | 448
22571 | Turnells Mill I/C | A45 | 176.7 | Full closure underneath | 2020-03-11
22574 | London Road | A45 | 176.3 | Full closure underneath | 2020-03-12