Invitation to Tender

# NATIONAL INSTITUTE FOR HEALTH AND CARE EXCELLENCE

# Invitation to recruit and facilitate focus groups to inform the development of NICE guidance on Social, emotional and mental wellbeing in primary and secondary education

Tender Submission
Instructions and Guidance

and

Specification

- Contents

1.	Contents	2

2.	Introduction	3

3.	Contract Details	3

4.	Invitation to Tender Pack	3

5.	Instructions and Guidance	3

6.	Suppliers Instructions	4

7.	Queries about the Procurement	7

8.	NICE’s Named Point of Contact	7

9.	Suppliers Named Point of Contact	7

10.	Additional Information	8

11.	Freedom of Information	8

12.	Tender Evaluation and Selection Criteria	8

13.	Specification of requirements	11

- Introduction

  - The Centre for Guidelines at the National Institute for Health and Care Excellence (NICE) is inviting contractors to respond to the following invitation to tender.

- Contract Details

Contract: 		Recruit and facilitate focus groups to inform the development of NICE guidance on Social, emotional and mental wellbeing in primary and secondary education

Contract Duration:	8 months

Contract commences:	19th October 2020

Budget:	£20,500 excl. VAT is the maximum budget allocated to this work, bids over this amount will not be considered

- Invitation to Tender Pack

  - The following documents are included in the Invitation to Tender pack:

Tender Submission Instructions and Guidance (this document)

Provides the Supplier with instructions to tendering, submission guidance and evaluation procedures

Statement of Requirements and appendices (this document)

Outlines the requirements of NICE for the provision of the Service

Terms and Conditions of Contract

The terms on which this contract will be awarded and the service provided throughout the full life cycle of the contract

- Instructions and Guidance

  - Supplier Invitation to Tender

    - Submission of final offers to this ITT shall be in accordance with Section 14 and 15.

    - On receipt of final offers from Suppliers in response to this ITT, NICE will evaluate each response using the Evaluation Methodology set out in section 12.

  - Interview

    - As part of the evaluation process, Suppliers may be required to attend an interview. The interview will be determined by the evaluation procedure, applying the criteria as described in section 12 of this document. Suppliers must ensure they are available to attend the interviews on the dates stated below.

    - The evaluation methodology applied to such interviews is detailed in section 12.

    - Supplier must ensure they are available on the following date and times.

| DAY | DATE | TIME | LOCATION |
| --- | --- | --- | --- |
| Wednesday & Thursday | 9th & 10th September 2020 | All Day | Zoom |

  - Procurement Timetable

    - The estimated timetable for the remainder of this procurement is as follows:

| Stage | Date |
| --- | --- |
| Issue final ITT documentation | 24th July 2020 |
| Deadline for Expression of Interest | 31st July 2020 |
| Deadline for bidder questions | 4th August 2020 |
| NICE final response to questions deadline | 7th August 2020 |
| Tender Responses | 14th August 2020 |
| Tender Evaluation | 17th – 28th August 2020 |
| Interviews | 9th & 10th September 2020 |
| Preferred Bidder Notice and Losing Suppliers Debriefed | 15th September 2020 |
| Alcatel Period (10 working days) | 15th – 25th September 2020 |
| Contract Award | 26th September 2020 |
| Contract drafting and signing | 26th – as soon as possible |
| Contract Commences | 19th October 2020 |

- Suppliers Instructions

  - This section sets out the general instructions for the submission of the tender / final offer from the Suppliers in response to this ITT. These instructions must be followed and adhered to. Any deviation from these instructions may result in your tender being rejected.

  - Expressions of Interest must be emailed to Irene.walker@nice.org.uk no later than 17:00 (5.00pm) UK time on 31st July 2020.

  - Questions on any aspect of the brief, by email to Irene.Walker@nice.org.uk by 17:00 (5.00pm) UK time on 4th August 2020.

  - Responses to questions will be sent to all interested parties by 17:00 (5.00pm) UK time on 7th August 2020.

  - The tender submission offer must be returned no later than 12:00 (12.00pm) UK time on 14th August 2020

  - All forms requiring signature including the Form of Offer, must be signed, scanned and included in your bid which must be received by NICE no later 12:00 (12.00pm) UK time on 14th August 2020

  - All tender submission and final offers must be written in English and to be submitted electronically by email in a Microsoft word format to: contract.bids@nice.org.uk. Please use as the subject title: NICE SEW [company name]

  - All other forms requiring signatures must be scanned in PDF format and included in your tender submission as stated in 6.6 above.

  - The package must bear no sign / brand of any other form of identification of the sender.

  - All responses must be referenced as detailed in the final ITT for ease of evaluation.

  - All offers must be submitted in GBP sterling and must be exclusive of Value Added Tax (VAT).

  - Suppliers should answer all questions as accurately and concisely as possible in the same order as the questions are presented. Where a question is not relevant to the Supplier, this should be indicated, with an explanation.

  - Suppliers must be explicit and comprehensive in their responses to this ITT as this will be the single source of information on which responses will be scored and ranked.  Suppliers are advised neither to make any assumptions about their past or current supplier relationships with NICE, nor to assume that such prior business relationships will be taken into account in the evaluation procedure.

  - NICE reserves the right at any time:

    - to issue amendments or modifications to the documents contained in the Invitation to Tender pack during the tender;

    - to not bind itself to accept the lowest or any offer and reserves the right to accept an offer either in whole or in part, each item being for this purpose treated as offered separately;

    - to purchase the most cost effective and economically advantageous offer from this tender and does not bind itself to the cheapest price or the overall winner of the scoring evaluation that may result from this procurement;

    - to terminate this procurement at any time;

    - to require Suppliers to provide additional information supplementing or clarifying any of the information provided in response to the requests set out in this ITT. NICE may seek independent financial and market advice to validate information declared, or to assist in the evaluation.

  - NICE will not be liable for any cost incurred in relation to any part of this procurement activity throughout its lifecycle to close, including any costs or expenses incurred by any Supplier or the Supplier's Team or any other person in resource time, preparation of responses, attendance of meeting, or any other cost that the Supplier may incur.

  - Costs shall be fixed for the duration of the contract and not subject to change, unless agreed in writing by both NICE and the Contractor.

  - The costing spreadsheet of your offer must be transparent to NICE and not be password protected or have any part of the model hidden. All costs breakdowns must be shown within your response and provided in GBP sterling.

  - Non-Compliance and/or disqualification

    - NICE expressly reserves the right to reject any proposal that:

- does not submit an Expression of Interest by the deadline date and time

- does not meet any minimum requirement in the tender;

- does not follow the instruction to tender guidance;

- is incomplete, or does not provide either an answer to any question or a reasonable explanation of why an answer to any question has been omitted;

- refuses to adhere to the Terms and Conditions of Contract.

- Queries about the Procurement

  - All requests for clarification or further information in respect of this procurement should be addressed to NICE’s named contact point (section 8) or discussed during the relevant dialogue meeting with the representatives of NICE. No approach of any kind in connection with this procurement should be made to any other person within, or associated with, NICE.

  - NICE will ensure that all applicants receive equal treatment during this procurement and we will share all information requests and responses with all applicants.

  - Any questions and answers will be collated and distributed by email to all the Suppliers throughout the tender period.

  - Please note that that there will be no telephone or any informal or other kind of discussion between Suppliers and officers or directors of NICE after this document is dispatched other than the representative of NICE named in section 8.

  - If NICE considers any question or request for clarification to be of material significance, both the question and the response will be communicated, in a suitably anonymous form to all Suppliers.

  - All responses received and any communication from Suppliers will be treated in confidence but will be subject to paragraph 7.5.

- NICE’s Named Point of Contact

  - NICE’s named point of contact for this procurement is:

Irene Walker

National Institute for Health and Care Excellence
Level 1A City Tower
Piccadilly Plaza
Manchester
M1 4BD

# Tel: 0161 870 3198 Email: irene.walker@nice.org.uk

- Suppliers Named Point of Contact

  - Suppliers are asked to include a single point of contact in their organisation.  NICE will not be responsible for contacting the Supplier through any route other than the nominated contact.  The Supplier must therefore undertake to notify any changes relating to the contact promptly.

- Additional Information

  - NICE expressly reserves the right to require a Supplier to provide additional information supplementing or clarifying any of the information provided in response to the requests set out in the final ITT. NICE may seek independent financial and market advice to validate information declared, or to assist in the evaluation.

- Freedom of Information

  - In accordance with the obligations and duties placed upon public authorities by the Freedom of Information Act 2000 (“the FoIA”), all information submitted to NICE may be disclosed in response to a request made pursuant to the FoIA.

  - In respect of any information submitted by a Potential Supplier that it considers to be commercially sensitive the Potential Supplier should:

- clearly identify such information as commercially sensitive;

- explain the potential implications of disclosure of such information; and

- provide an estimate of the period of time during which the Potential Supplier believes that such information will remain commercially sensitive.

  - Please submit responses to 11.2 as an Annex with the completed tender offer.

  - Where a Potential Supplier identifies information as commercially sensitive, NICE will endeavour to maintain confidentiality. Suppliers should note, however, that, even where information is identified as commercially sensitive, NICE might be required to disclose such information in accordance with the FoIA. Accordingly, NICE cannot guarantee that any information marked ‘commercially sensitive’ will not be disclosed.

- Tender Evaluation and Selection Criteria

  - Evaluation

    - NICE will review all tenders to ensure they are fully compliant with these instructions. Any non-compliant bid may be rejected (see 6.15).

    - The underlying principle of ITT evaluation will be based on the Most Economically Advantageous Tender that meets NICE’s requirements.

    - The Evaluation Methodology set out in this section will be used to evaluate the Suppliers’ submission/offer to this Invitation to Tender (ITT).

    - Each evaluator will independently evaluate each tender submitted and use the following guide to score each criterion. The scores of all evaluators per criterion will then be averaged and weighting applied to give an adjusted score. All clarifications required by NICE will be incorporated into the final evaluation.

    - Bidders should note that cost is a factor in this procurement and represents 50% of the overall score.

| Score | Guide |
| --- | --- |
| -5 | The point is omitted |
| 0 | The point repeats the specification |
| 1 | The point is not acceptable |
| 2 | The point is possibly acceptable |
| 3 | The point is acceptable |
| 4 | The point is well made and acceptable |
| 5 | Exceeds Expectations / Best |

| Criteria | Weighting |
| --- | --- |
| Methodological experience and expertise including planning, preparing, facilitating, analysing and writing up focus groups with children and young people | 10 |
| Relevant experience of conducting research with children and young people including plans for recruitment | 10 |
| Plans for engagement and support of children and young people – including ability to recruit based on the following: - Geographical representation (at least 3 locations) - Urban & rural representation - Primary & secondary education representation - Children who are ‘seldom heard’ (see Specification Context and Background for definition) - Age ranges - Diverse membership (taking into account equalities duties) and those groups identified as requiring special consideration | 10 |
| Proven ability to meet the NICE timeline and provide effective communication with Public Health Internal Guideline Development Team | 2.5 |
| Plans for appropriate ethical and research governance processes | 5 |
| Plans for ensuring a safe environment, including safeguarding, for children and young people to engage virtually | 2.5 |
| Plans for collation, synthesis and reporting of focus group outputs, including a description of the planned methodology | 7.5 |
| Plans for , risk identification and management, including contingency plans for further COVID-19 lockdowns and the closure of schools | 2.5 |
| GDPR compliance | PASS / FAIL |
| Cost | 50 |

  - Cost Evaluation

    - The cost will be evaluated using the following formula:

Lowest Price / Suppliers Price X 50 (the weighting)

  - Interview and Evaluation

    - NICE may choose to shortlist a bidder or Suppliers to present to the evaluation panel and clarify any outstanding areas or their proposal where NICE may have concerns or further questions. However, if no further concerns or questions are raised, NICE reserves the right to proceed to Contract Award.

    - Each bidder interviewed will be re-scored independently of the tender response, based on their responses in the interview alone and re-ranked against each of the others bidders that were shortlisted for interview. This evaluation will have no bearing on the evaluation that resulted in the bidder being shortlisted to interview or not. Suppliers not invited to interview will be notified at the same time as shortlisted Suppliers.

    - The scoring guide and criteria in 12.1 above will be used to score the interviewed bidder, however the weightings will not be applied, the composite score of the interview panel will form the basis of award. The interview will be in direct relation to the outstanding areas of the Suppliers proposal.

    - Shortlisted Suppliers will be notified of the evaluation process on invitation to interview.

- Specification of requirements

Introduction

The Centre for Guidelines at the National Institute for Health and Care Excellence (NICE) is inviting contractors to respond to the following invitation to tender. Please see Part 2 on how to complete your proposal.

You must return your proposal by 12pm on 14th August 2020 (please see contact details in Part 2). If you have any questions or wish to seek clarification, please email your query to contract.bids@nice.org.uk

This document is presented in 2 parts:

Part 1 – provides background information and presents the specification of the work, which you should take into account when drafting your proposal.

Part 2 – how to complete your proposal.

Following receipt of tender responses, the selection process will involve:

- Short listing of eligible bidders

- Notification of shortlisted bidders by 5pm on 4th September 2020

- An interview for the shortlisted bidders on the 9th & 10th September 2020 to discuss their application, methods and to ask questions

- Write to all bidders by 5pm on 15th September 2020 to notify selection outcomes.

Please note that all tender responses will be treated with absolute confidentiality.

Thank you for your interest in this work.

Part 1: Specification

Context and Background

The National Institute for Health and Care Excellence (NICE) has been asked by the Department of Health and Social Care in England to update public health guidance on Social and emotion wellbeing in primary and secondary education (PH12 & PH20)  The guidance covers how educational and other professionals can provide a supportive environment, universal education and targeted interventions to promote good social and emotional wellbeing in children and young people in primary and secondary education. Both guidelines aim to help children and young people reach their full potential and maximise their opportunities.

The guidance will focus on children and young people in all educational settings and cover the following key areas:

- Whole-school approach including the identification of those with, or at risk of, poor social and emotional wellbeing

- Universal education

- Targeted approaches

- Targeted mental health support

- Transition

The detailed scope for this guidance can be found here and is also appended to this document (see Appendix A).

To help us find the best available evidence, review questions will be used to guide a series of systematic reviews of the literature. Draft review questions are listed in the scope. They will also be used to consider how the outcomes that are important to children and young people can be improved. Equalities issues will be considered within the review questions. We will also take into account cost-effectiveness when making recommendations involving a choice between alternative interventions or services. Appropriate economic review questions will be identified.

Developing the guideline

The development work for this guideline will be undertaken by the Public Health - Internal Guideline Development team at NICE. More information on the guideline development process is available in Developing NICE guidelines: the manual. To assist in the development of this guideline, a Public Health Advisory Committee (PHAC) has been appointed to review the evidence, draft recommendations, identify dissemination and implementation issues and act as a champion for the guideline after publication. The group includes health and social care practitioners, service providers and researchers, as well as lay and carer members. All members of the PHAC have equal status, which reflects the relevance and importance of their different expertise and experience. The development phase of the guideline work began in August 2019 and will run until June 2021. Over this period the PHAC will meet at regular intervals to review the evidence and draft recommendations. There will be a public consultation on the draft guideline.

The guidance is aimed at teachers, school support staff, school governors and others working with children and young people in primary and secondary education, local authorities, the NHS and voluntary and community sectors.

Draft recommendations will be informed by the reviews of evidence that have been undertaken for the development of the guidance.

Proposals are invited to conduct focus group work using methods that ensure government mandated social distancing are observed such as using virtual meetings. The aim of the focus group work is to discuss both the identified evidence and the committees interpretation of it with children and young people in primary and secondary education, including ‘seldom heard’ children and young people, so that their perspectives can be incorporated into the work of the PHAC. This group could include representation from

- children and young people who are young carer’s, who have been excluded (Permanently and Multi-Fixed) or who are home-schooled because there is no other appropriate alternative option available

- children and young people with SEND, with ACE’s (including traumatised children, criminally exploited children or who have chronic physical illnesses)

Aim of this work

The aim of this work is to recruit and facilitate focus groups of children and young people  (ages 5-18) in primary and secondary education (Key Stage 1 to Post-16 education) including ‘seldom heard’ children and young people so that their perspectives can be incorporated into the work of the PHAC.

The Public Health - Internal Guideline Development team and NICE acknowledge that any involvement needs to occur within an ethical framework in which young people’s voices are valued, and their participation adequately supported. More information is available in The NICE Patient and Public Involvement Policy. The focus groups will add important value by bringing the perspectives of children and young people to the work of the PHAC, including providing up-to-date insight on issues of importance to them.

We would like the children and young people on the focus groups to provide insight about their perspectives on the evidence, relevance and impact of potential recommendations and any specific issues identified by the PHAC.

Tasks required:

While we would seek to be guided by the contractor about the specific details of the work, based on their expertise, the key elements are to:

- Identify and recruit focus groups of

  - children in primary and secondary education (Key stage 1 to Post-16 education) who represent a diverse range of backgrounds and experiences, ideally with a geographical spread across England.

  - ‘seldom heard’ children and young people who may be underrepresented in the evidence base. This group could include representation from

    - children and young people who are young carer’s, who have been excluded (Permanently and Multi-Fixed) or who are home-schooled because there is no other appropriate alternative option available

    - children and young people with SEND, with ACE’s (including traumatised children, criminally exploited children) or who have chronic physical illnesses

The scope of the guideline notes that specific consideration will be given to children:

  - with SEND

  - who may be absent from lessons regularly (for example, those with long term physical conditions)

  - who are excluded (on a permanent or temporary basis)

- The number of children to participate is not specified and would let this be guided by your experience and expertise.

Detailed tasks

- The Contractor to organise day, time and appropriate forum for the focus groups (for example, virtual meetings). Ensure that

  - meetings will be convenient for children and young people,

  - the forum used will be safe and secure for children and young people and facilitates their full engagement, and

  - children and young people have an environment that ensures privacy where appropriate,

- Plan, prepare and facilitate focus group meetings covering each population group above detailing how the groups will be stratified by age / key stage.

- Groups to be facilitated by the contractor

- Contractor/facilitator to structure the focus groups in an age-appropriate and sensitive way and ensure the groups are supportive, using age-appropriate material

- Contractor to provide a detailed methodology that would be used to recruit and conduct the focus group. To note, the methodology will need to be agreed and quality assured by NICE. The methodology will be published as part of the appendices of the guideline

- Contractor to seek advice on ethical approval and where necessary to obtain the relevant ethical approval from a recognised ethics committee

- Provide the results in a report that can be presented to the guideline committee and added into the final guideline as an appendix.

- Ensure that all facilitators have current DBS checks.

- Ensure that arrangements are in place for children who may require additional support, including support for the potential emotional impact of participation.

- Contractor/facilitator to arrange appropriate payments for participation to children (if appropriate).

- Contractor/facilitator to consider and support how children might benefit from taking part in the focus group, for example learning new skills through their participation.

- Contractor/facilitator to arrange to feedback the results to the focus group participants.

- Contractor to virtually attend PHAC meetings (approximately 2-3) and provide a brief presentation of the focus group themes and discussions.

- Attendance at project meetings with NICE, which will be held on Zoom.

- Contractor to ensure adherence to NICE’s confidentiality requirements.

- Contractor to comply with NICE’s policy on Declaring and Managing Interests for Advisory Committees. A standard form will be supplied.

- Any publications based on the focus group findings to be authorised by NICE

The work would need to be completed by,28th May 2021 to fit into the Guideline timeline.

Outputs:

These should include a written report, with a draft supplied by April 2021 and a final draft by June 2021

Final report to include:

- aims of the project and issues addressed

- methodology including the methods used to recruit participants, the running of the groups, the programme of activities, methods used for identifying and recording issues raised and discussed, basic demographic information about participants (including age, gender, ethnicity and geographic area)

- findings and conclusion.

Part 2: Completing your proposal

Please provide your responses to the questions below. You may use diagrams, tables and images as appropriate.

- Please describe the methodological experience and expertise you have which demonstrates your organisation's suitability to deliver this contract. Please include two examples of previous work that demonstrate your experience and ability to provide this work to a high standard.

- Please outline your proposals for the following areas:

  - How you would recruit and run focus groups of children and young people under 16 purposely for this work that maintains the requirement for social distancing such as virtual meetings. How would you minimise the potential for bias in certain groups being under or over represented. How would you generalise the findings given any limitations/biases in recruitment?

  - How you would plan, prepare and facilitate the focus groups within the specified timeline

  - The methods for the focus groups, including the collation and synthesis of the focus group outputs

    - How you would involve children and young people and children who are’ seldom heard’

    - How you would ensure a safe and secure environment for all children and young people, and in particular, those who may be especially vulnerable.

  - How you would address ethical considerations, including

    - safeguarding protocols with DBS checks of all relevant staff including those involved in organising and hosting virtual groups

    - informed consent from participants and their care givers/parents/guardians and

    - support to the children and young people involved throughout the process and their care givers/parents/guardians

  - How you would feedback the results to all participants and what additional steps would you take to feedback to ‘seldom heard’ or vulnerable children

  - How you would feedback to the PHAC at a committee meeting

  - Write up of the focus groups discussions and a report for the final guideline.

  - A timeline for the project completion

3. Please outline details of staff who would facilitate the groups, and details of their skills and experience in this area. Please also include what contingencies are in place to cover staff absence.

4. How you would approach and manage communications with the Public Health Internal Guideline Development Team.

5. What you see as key risks for your work and how will you mitigate them including any contingencies for future lockdowns including the closure of schools.

6. Please provide a breakdown of your costs. These should be indicated by task, member of staff and time needed. Please indicate where VAT will apply. Please note that the budget for this work is up to £20,500 excl. VAT.

| Task | Number and grade of staff involved | Time/ cost of staff | Total cost |
| --- | --- | --- | --- |
| Clarification of focus group content |  |  |  |
| Recruitment of participants |  |  |  |
| Admin to arrange virtual sessions, etc |  |  |  |
| Facilitation of groups, including appropriate materials, tools etc |  |  |  |
| Data analysis and report writing |  |  |  |
| For other costs add rows |  |  |  |

Data Protection Act 2018 and GDPR

- This contract involves the processing of personal data, the successful bidder will be expected to demonstrate compliance with data protection legislation. In particular GDPR Article 30.

- Your tender response must include a statement of compliance to the GDPR and Data Protection Act 2018 and acknowledgement and agreement to provide if requested all the items detailed in 4 below.

- Non-compliance – should the winning bidder fail to provide any GDPR evidence as request by NICE or fails the GDPR assessment, NICE retains the right to revoke the contract offer and offer the contract to the next ranked bidder or close the procurement and re-tender at its discretion.

- The winning bidder will be required as a minimum (on request from NICE) to provide details of the technical facilities and measures (including systems and processes) you have in place, to ensure compliance with the General Data Protection Regulation and to ensure the protection of the rights of data subjects. Your response must include, but should not be limited to facilities and measures:

- to ensure ongoing confidentiality, integrity, availability and resilience of processing systems and services;

- to comply with the rights of data subjects in respect of receiving privacy information, and access, rectification, deletion and portability of personal data;

- to ensure that any consent based processing meets standards of active, informed consent, and that such consents are recorded and auditable;

- to ensure legal safeguards are in place to legitimise transfers of personal data outside the EU (if such transfers will take place);

- to maintain records of personal data processing activities; and

- to regularly test, assess and evaluate the effectiveness of the above measures

Appendix A

NATIONAL INSTITUTE FOR HEALTH AND CARE EXCELLENCE

Guideline scope

Social, emotional and mental wellbeing in primary and secondary education

This guideline will update and replace NICE guidelines on social and emotional wellbeing in primary education (PH12) and social and emotional wellbeing in secondary education (PH20).

NICE worked with Public Health England to develop this scope.

The guideline will be developed using the methods and processes outlined in developing NICE guidelines: the manual.

- Why the update is needed

New evidence that could affect the recommendations was identified through the surveillance process. NICE decided to combine the guidelines so that commonalities and differences between interventions for children and young people at different ages and life stages (for example at puberty) can be addressed. Full details are set out in the surveillance review decision.

Social and emotional learning includes interrelated cognitive, communication, emotional and behavioural skills. These can be associated with better health and mental wellbeing outcomes and educational achievement.

Mental health is a dynamic state of mental wellbeing, in which a person is able to develop their potential, work productively and creatively, build strong and positive relationships with others and contribute to their community. It encompasses psychological, social and emotional wellbeing.

Primary and secondary schools help children and young people learn social and emotional skills through both the taught and wider curriculum (such as activities outside the classroom). Schools can provide the supportive, caring and nurturing environment that supports positive social, emotional and mental wellbeing. They are also key settings in which to identify and provide early intervention for children and young people at increased risk of mental ill health.

### Key facts and figures

#### General wellbeing

In an average class of 30 15-year-old students: 10 are likely to have separated parents, 7 to have been bullied, 6 to be self-harming and 1 to have experienced the death of a parent (Promoting children and young people’s emotional health and wellbeing, Public Health England).

Adverse childhood experiences increase the risk of difficulties learning and engaging with others and poorer physical and mental health in later life.

18% of students aged 11 to 15 years report having experienced bullying online (Cyberbullying: an analysis of data from the Health Behaviour in School-aged Children survey for England, 2014, Public Health England). Being bullied is associated with lower achievement in both primary and secondary education.

Children with special educational needs and disabilities (SEND) are at greater risk of bullying, exclusion, school absences and emotional difficulties.

#### Mental health

Between 1999 and 2017 the prevalence of mental disorders in children and young people age 5 to 15 increased from 9.7% to 11.2%, and emotional disorders increased from 4.3% to 5.8% (Mental health of children and young people in England, NHS Digital).

Around half of all mental health problems are established by the age of 14 (The five year forward view for mental health, NHS England).

The number of referrals by schools in England seeking mental health treatment increased significantly between 2014 and 2018, with 56% coming from primary schools (School referrals for mental health treatment rise by over a third, NSPCC).

### Current practice

Schools have statutory duties to establish environments where children and young people are supported and can fully engage. These duties encourage schools to support personal development, mental health and wellbeing.

Many schools follow a whole-school approach to social, emotional and mental wellbeing (Supporting mental health in schools and colleges, Department for Education). This approach goes beyond learning and teaching to include school culture, ethos and environment. It involves engaging with children and young people, their parents and carers, teacher and school leaders and outside agencies.

Social, emotional and mental wellbeing may be promoted in curriculum subjects such as personal, social, health and economic education (PSHE) and be embedded more broadly through a school's commitment to the spiritual, moral, social and cultural development (SMSC) of their pupils.

Key challenges for schools include:

knowing what approaches improve student outcomes in a specific school setting

accommodating effective teaching of social, emotional and mental wellbeing in a crowded curriculum.

Schools also may not have the time or resources to assess the effectiveness of programmes they use or provide quality assurance of interventions.

Schools use various methods to identify children that may benefit from targeted interventions to support their approach to social, emotional and mental wellbeing. This may include information from other professionals such as a speech and language therapist or SEND coordinator.

### Policy, legislation, regulation and commissioning

This guideline will complement legislation such as the Department for Education's Keeping children safe in education and Supporting pupils with medical conditions at school, and their guidance on Preventing and tackling bullying, Mental health and behaviour in schools and Relationships education, relationships and sex education (RSE) and health education.

The government is incentivising and supporting all schools and colleges to identify and train a designated senior lead for mental health who will oversee implementation of a whole-school approach (see Transforming children and young people’s mental health provision: a green paper and the government response to the public consultation on this paper).

Mental health support teams are being rolled out targeting support for school age children experiencing low to medium level mental health problems (Children and young people’s mental health – policy, services, funding and education, House of Commons Library).

The Ofsted Education inspection framework has been updated since the previous NICE guidelines were published. Ofsted has also proposed a new judgement on personal development, behaviour and attitudes and schools' leadership and management.

- Who the guideline is for

This guideline is for:

teachers, school support staff and others working in schools with – or responsible for – children and young people

school leadership teams, including governors and leadership teams of multi-academy trusts

practitioners with a health or social care remit (including public health, mental health and social workers) working in the NHS or local authorities

commissioners and providers of interventions and services for child social, emotional and mental wellbeing

the wider public, private, voluntary and community sectors working with children and young people.

It may also be relevant for:

children, young people, and their parents and carers

researchers and policy makers

people providing or receiving home schooling

organisations with a responsibility for inspection.

NICE guidelines cover health and care in England. Decisions on how they apply in other UK countries are made by ministers in the Welsh Government, Scottish Government, and Northern Ireland Executive.

## Equality considerations

NICE has carried out an equality impact assessment during scoping. The assessment:

lists equality issues identified, and how they have been addressed

explains why any groups are excluded from the scope.

- What the guideline will cover

  - Who is the focus?

### Groups that will be covered

Children and young people in primary or secondary education, key stages 1 to 5, and people with SEND up to and including 25 years old in further education colleges.

Specific consideration will be given to:

Children and young people who have been absent from school for extended or regular periods of time, for example those with a long-term condition.

Children and young people who have been excluded from school on a temporary or permanent basis.

Where evidence allows, groups of children and young people vulnerable to poorer outcomes, such as those listed in the equality impact assessment.

### Groups that will not be covered

Children receiving early years foundation stage (EYFS) educational curriculum (typically children aged 4 to 5).

Young people not in education.

Young people with SEND in higher education.

  - Settings

### Settings that will be covered

Schools providing primary and secondary education including maintained schools, schools with a sixth form, academies, free schools, independent schools, non-maintained schools, and alternative provision including pupil referral units (see Department for Education's Types of school).

Special schools.

Further education colleges for young people, generally between the ages of 16 and 18.

Young offender institutions.

Secure children's homes.

Secure training centres.

Secure schools.

### Settings that will not be covered

Higher education institutions such as universities.

Private homes.

  - Activities, services or aspects of care

### Key areas that will be covered

We will look at evidence in the areas below when developing the guideline, but it may not be possible to make recommendations in all the areas.

Whole-school approaches

        - The whole-school approach is an integrated approach that includes and goes beyond teaching and learning in the classroom to all aspects of the life of a school including culture, ethos and  environment, as well as partnerships with parents or carers and families, outside agencies, and the wider community (see Public Health England’s Promoting children and young people’s emotional health and wellbeing).

        - Identifying vulnerable children and young people as part of the whole-school approach.

Universal approaches

        - Curriculum content and classroom-based interventions focused on social, emotional and mental wellbeing. This includes lessons on resilience, self-esteem, coping skills (such as dealing with bereavement or adverse childhood events), mental health awareness, managing social relationships (to avoid bullying, including online bullying) and the appropriate and safe use of the internet and social media.

Targeted approaches

        - Targeted social or emotional support such as individual or small group interventions for areas such as self-esteem, resilience or coping skills for children and young people who need extra support in developing social and emotional skills.

        - Targeted mental health support such as individual or small group interventions for children and young people at risk of depression, anxiety or stress.

Transition

        - Support during periods of transition (for example developmental transitions such as puberty, life transitions such as family break-ups or bereavement, and educational transitions such as moving from primary to secondary school).

#### Areas that will not be covered

        - Interventions aimed at treating depression, anxiety or other mental health diagnoses.

        - Management of disruptive or violent behaviour.

        - Strategies focused on preventing self-harm or suicide. These are covered in the NICE guidelines on preventing suicide, self-harm in over 8s and self-harm: short-term management and secondary prevention in primary and secondary care.

### Related NICE guidance

#### Published

Depression in children and young people: identification and management in primary, community and secondary care (2019) NICE guideline NG134

Preventing suicide in community and custodial settings (2018) NICE guideline NG105

Attention deficit hyperactivity disorder: diagnosis and management (2018) NICE guideline NG87

Challenging behaviour and learning disabilities: prevention and interventions for people with learning disabilities whose behaviour challenges (2015) NICE guideline NG11

Social and emotional wellbeing: early years (2014) NICE guideline PH40

Looked-after children and young people. (2015) NICE guidance PH28

Antisocial behaviour and conduct disorders in children and young people: recognition and management (2013) NICE guideline CG158

Psychosis and schizophrenia in children and young people: recognition and management (2013) NICE guideline CG155

Social anxiety disorder: recognition, assessment and treatment (2013) NICE guideline CG159

Self-harm in over 8s: long-term management. (2011) NICE guideline CG133

#### In development

Alcohol interventions in secondary and further education. Publication expected August 2019

Children and young people with disabilities and severe complex needs: integrated health and social care support and service guidance. Publication expected February 2021

Looked after children and young people. Publication expected April 2021

#### NICE guidance that will be updated by this guideline

Social and emotional wellbeing in secondary education (2009) NICE public health guideline PH20

Social and emotional wellbeing in primary education (2008) NICE public health guideline PH12

  - Economic aspects

We will take economic aspects into account when making recommendations. We will develop an economic plan that states for each review question (or key area in the scope) whether economic considerations are relevant, and if so whether this is an area that should be prioritised for economic modelling and analysis. We will review the economic evidence and carry out economic analyses, using NHS and personal social services (PPS), public sector and local authority perspective, as appropriate.

  - Key issues and draft questions

While writing this scope, we have identified the following key issues and draft questions related to them:

        - Whole-school approach:

1.1 What principles or combination of principles of the whole-school approaches to promote social, emotional and wellbeing in children and young people in primary and secondary education, and young people with SEND in further education, are effective and cost-effective?

1.2 What are children and young people's experiences of the whole-school approach in promoting social, emotional and mental wellbeing?

1.3 What are the barriers and facilitators to using the whole-school approach to promote social, emotional and mental wellbeing in children and young people?

        - Identifying vulnerable children and young people as part of the whole-school approach:

2.1 What are the risk factors associated with poor social, emotional and mental wellbeing?

2.2 What are the barriers and facilitators to identifying children and young people at risk of poor social, emotional and mental wellbeing?

2.3 What is the usefulness of assessment tools to identify children and young people with poor social, emotional and mental wellbeing?

        - Universal classroom-based interventions:

3.1 What universal classroom-based interventions to promote social, emotional and mental wellbeing in children and young people in primary and secondary education, and young people with SEND in further education, are effective and cost effective?

3.2 Are universal classroom-based interventions acceptable to the children and young people receiving them and to those delivering them?

3.3 What are the barriers and facilitators to using universal classroom-based interventions to promote social, emotional and mental wellbeing in children and young people?

        - Targeted social or emotional support

4.1 What targeted approaches to promote social, emotional and mental wellbeing in children and young people in primary and secondary education, and young people with SEND in further education, are effective and cost effective?

4.2 Are targeted approaches to promote social, emotional and mental wellbeing acceptable to those receiving them and to those delivering them?

4.3 What are the barriers and facilitators to using targeted approaches to promote social, emotional and mental wellbeing in children and young people?

        - Targeted mental health support:

5.1 What targeted mental health support approaches for children and young people in primary and secondary education, and young people with SEND in further education, are effective and cost effective?

5.2 Are targeted mental health support approaches acceptable to the children and young people receiving them and to those delivering them?

5.3 What are the barriers and facilitators to using targeted mental health support?

6	Support during periods of transition:

6.1 What are effective and cost-effective interventions to support the emotional and social wellbeing of children during periods of transition (such as between schools, life stages or due to traumatic events)?

6.2 Are interventions to support the emotional and social wellbeing of children and young people during periods of transition (such as between schools, life stages or due to traumatic events) acceptable to children and young people?

6.3 What are the barriers and facilitators to supporting the emotional and social wellbeing of children and young people during periods of transition?

The key issues and draft questions will be used to develop more detailed review questions, which guide the systematic review of the literature.

  - Main outcomes

The main outcomes that may be considered when searching for and assessing the evidence for interventions are:

Social, emotional and mental wellbeing outcomes (subjective or objective) such as:

communication skills

confidence or self-esteem

planning and problem-solving skills

relationships skills, cooperating with others and negotiating conflict

resilience and determination

managing feelings

engagement, belonging or connectedness.

School-related and academic outcomes such as:

educational attainment (for example reading, maths and science)

absenteeism

exclusion

school environment.

Other outcomes:

quality of life

unintended consequences

economic outcomes.

Acceptability of interventions:

satisfaction

adherence.

Barriers and facilitators of interventions:

physical environment (including time)

staffing (including staff numbers, training and skills)

attitudes (such as those of teachers, parents, carers and pupils).

The main outcomes that may be considered when searching for and assessing the evidence for risk factors are:

Identification of vulnerable children and young people:

individual factors

familial factors

school factors

peer factors.

- NICE quality standards and NICE Pathways

  - NICE quality standards

### NICE quality standards that may need to be revised or updated when this guideline is published

School based interventions. Publication date to be confirmed.

  - NICE Pathways

When this guideline is published, we will update the NICE Pathway on social and emotional wellbeing for children and young people, which brings together everything we have said on social and emotional wellbeing for children and young people in an interactive flowchart.

- Further information

This is the final scope, which takes into account comments from registered stakeholders during consultation. The guideline is expected to be published in August 2021. You can follow progress of the guideline. Our website has information about how NICE guidelines are developed.

© NICE 2019. All rights reserved. Subject to Notice of rights.