## 1. Instructions
Defence Infrastructure Organisation Digital Plan of Work INFORMATION DELIVERY PLAN
Description
The IDP is a 360 schedule of information deliverables for a project or contract confirming the specific employer information deliverable requirements and delivery party. The main IDP sheet should be completed at least prior to each stage to support any procurement activity by adding the delivery role type to each stage deliverable to be included. The information deliverables should be profiled from all parties including internal teams and stakeholders to meet the Plain Language Questions for each stage.
Instructions
The IDP sheet will be completed and maintained by the appointed Employer Information Manager
The sheet shall be included with all tender invitations with roles assigned to the tendered deliverables and confirmed with each supplier proposal `
At appointment the appointed party will be confirmed in each assigned deliverable and stage to confirm the contracted information deliverables
Entry fields are highlighted in yellow
IDP
1 | The plain language project_title shall be entered in the [project_title] field
2 | The assigned (z9 code) project_ref shall be entered in the [project_ref] field. Note this is used as the project_ref component of BS1192/ISP19650 file names
3 | Each stage header shall be assigned the latest delivery data information will be accepted by. Note this will replicated into each assigned deliverable but can be indevidually overwritten. This is related to but is not the project program
4 | For each deliverable:
a) review the default
b) N/F Native Format files required - if the authored often propratory file is required to be delivered
c) Ass Assurance item - Yes files should only be delivered if requested by the EIM, N files should be delivered, S files should be Shared for Information only - non contractural.
d) O/F Open File format required
e) 3DMF 3D Model Federation - required as part of an additioanal federated deliverable

## 2. PIR
EIR Ref No. | Defence Infrastructure Organisation PROJECT INFORMATION REQUIREMENTS
| To be completed only by Suppliers as part of their Tender Response Proposal. |  | Notes
Supplier Name:
Contract Reference Number:
Supplier's Framework BEP Doc Ref:
| Supplier Framework BEP clarification. Doc Ref or None: | None | If None - Framework BEP to apply in full by default
| Supplier Project IDP capability clarification. Doc Ref or None: | None | If None - Supplier confirms capability to deliver IDP (sheet 3) in full by default
| Project Startup |  | By | Stage | Notes
Project Reference (Code)
Project Name
Project Description
| Programme Reference (if any) | Generated by Glider
Programme Description
Project Location (Site Description)
PCF Number
5.2 | Appointments
Client Project Manager
Client Requirements Manager
Client Information Manager
Site Reference
Establishment Land Parcel Reference
Land Parcel Description(s)
Project Requirements (in addition to those specified within the EIR)
5.4 | Naming Convention additional information:
| a) Originators (added to Picklists) | No
| b) Volumes (added to Picklists) | No
| c) Locations (added to Picklists) | No
5.5 | Specific Security Requirements. Doc Ref or None: | None
5.6 | Specific Requirements for Coordination and Clash Detection. Doc Ref or None: | None
5.11 | Specific Training Requirements. Doc Ref or None: | None
6.2 | Specific software / platform information requirements. Doc Ref or None: | None
6.3 | Uniclass 2015 NBS Version:
6.4 | Co-ordinates
| a) Intersection of grids XX and YY | xxxxxx.xxxE xxxxxx.xxxN
| b) Intersection of grids AA and BB | xxxxxx.xxxE xxxxxx.xxxN
| c) Ground Floor FFL | xxx.xxx
d) Origin Rotation
e) Offsets
f) Datum
g) Specific Units

## 3. IDP
Defence Infrastructure Organisation INFORMATION DELIVERY PLAN | [5 empty] | Click for PLQ |  |  | Defines the owner’s business case for the project, including required outcomes and other core considerations. |  |  |  | Develops project objectives, including project outcomes and required performance for the asset/facility. |  |  |  | Prepares the concept design, including outline proposals for the structural design and building services engineering systems. |  |  |  | Develops the design, including coordinated and updated proposals for structural design and building services engineering systems. |  |  |  | Prepares technical design, including all architectural, structural and building services engineering information, cost and detailed operational data. |  |  |  | Plans, organizes and coordinates offsite manufacturing with onsite construction, including assembly, testing and commissioning. |  |  |  | Training of the operations team and selected end-users, handover of the asset/facility to the operator and start-up of operations. |  |  |  | Steady-state operation, aftercare, post-occupancy evaluation of performance, fine tuning, benchmarking and feedback.
Project Name
ProjRef
EIM | [Employer_information_manager] | DIO Stage Code | [7 empty] | DI0 |  |  |  | DI1 |  |  |  | DI2 |  |  |  | DI3 |  |  |  | DI4 |  |  |  | DI5 |  |  |  | DI6 |  |  |  | DI7
[7 empty] | Info by date: |  |  |  | Info by date: |  |  |  | Info by date: |  |  |  | Info by date: |  |  |  | Info by date: |  |  |  | Info by date: |  |  |  | Info by date: |  |  |  | Info by date:
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40
Ref | Deliverable | N/F | Ass | Cap | O/F | 3DMF | Role | LOD | LOI | By Date | Role | LOD | LOI | By Date | Role | LOD | LOI | By Date | Role | LOD | LOI | By Date | Role | LOD | LOI | By Date | Role | LOD | LOI | By Date | Role | LOD | LOI | By Date | Role | LOD | LOI | By Date | Deliverables | Stages
A0000 | Client Requirements
A00100 | CIS Requirement Parts A and B | Y | N |  | .pdf | N | [33 empty] | 0
A00200 | Security Requirement (OR1) | Y | N |  | .pdf | N
A00300 | User Requirement Document | Y | N |  | .pdf | N | [33 empty] | 0
A00400 | System Requiements Document | Y | N |  | .pdf | N
A00500 | ITEAP | Y | N |  | .pdf | N
A00600 | Scope | Y | N |  | .pdf | N
B0000 | Site Discovery
B00100 | Archaeological | Y | N |  | .pdf | N | [33 empty] | 0
B00200 | Asbestos | Y | N |  | .pdf | N | [33 empty] | 0
B00300 | Condition | Y | N |  | .pdf | N | [33 empty] | 0
B00400 | Dimensional | Y | N |  | .pdf | N | [33 empty] | 0
B00600 | Geotechnical | Y | N |  | .pdf | N | [33 empty] | 0
B00700 | Ground Investigation | Y | N |  | .pdf | N | [33 empty] | 0
B00800 | Hazardous Substances | Y | N |  | .pdf | N | [33 empty] | 0
B00900 | Land Quality Assessment | Y | N |  | .pdf | N | [33 empty] | 0
B01000 | Surveys | Y | N |  | .pdf | N | [33 empty] | 0
B01100 | Topographical | Y | N |  | .pdf | N | [33 empty] | 0
B01200 | Unexploded Ordnance | Y | N |  | .pdf | N | [33 empty] | 0
C0000 | Project & Info Man
C00100 | 4D Programme Federated Model(s) | Y | N |  | .pdf | N | [33 empty] | 0
C00200 | 5D Cost Federated Model(s) | Y | N |  | .pdf | N | [33 empty] | 0
C00300 | 6D Handover Sequence Federated Model(s) | Y | N |  | .pdf | N | [33 empty] | 0
C00400 | Benefits Realisation Plan | Y | N |  | .pdf | N | [33 empty] | 0
C00500 | BIM Execution Plans (Post) (See CDDL item 55) | Y | N |  | .pdf | N | [33 empty] | 0
C00600 | BIM Execution Plans (Pre) (See CDDL item 55) | Y | N |  | .pdf | N | [33 empty] | 0
C00700 | BIM Maturity Assessment Tool (BMAT) | Y | N |  | .pdf | N | [33 empty] | 0
C00800 | Case Study | Y | N |  | .pdf | N | [33 empty] | 0
C00900 | Clash Detection Resolution Report | Y | N |  | .pdf | N | [33 empty] | 0
C01000 | COBie Federated Data (output) | Y | N |  | .pdf | N | [33 empty] | 0
C01100 | COBie Demand Matrix (Input) | Y | N |  | .pdf | N | [33 empty] | 0
C01200 | Construction Phase Plan (See CDDL part 2 item 14) | Y | N |  | .pdf | N
C01300 | Room/Asset Data Sheets | Y | N |  | .pdf | N | [33 empty] | 0
C01400 | Communications Plan | Y | N |  | .pdf | N | [33 empty] | 0
C01500 | Construction Environmental Management Plan (See CDDL item 31) | Y | N |  | .pdf | N | [33 empty] | 0
C01600 | Construction Risk Review | Y | N |  | .pdf | N | [33 empty] | 0
C01680 | Construction Traffic Management Plan ((See CDDL Part 2 item 13) | Y | N |  | .pdf | N
C01650 | Design Lifecycle Plan (See CDDL item 60) | Y | N |  | .pdf | N
C01700 | Discipline Models & Drawings (Task Teams) | Y | N |  | .pdf | N | [33 empty] | 0
C01900 | Earned Value Management reporting (See CDDL item 11) | Y | N |  | .pdf | N | [33 empty] | 0
C02000 | Employers Information Requirements | Y | N |  | .pdf | N | [33 empty] | 0
C02100 | Governement Soft Landing Plan (See CDDL item 32) | Y | N |  | .pdf | N
C02200 | Interface Management Plan (See CDDL item 34) | Y | N |  | .pdf | N | [33 empty] | 0
C02300 | Federated Coordination Models | Y | N |  | .pdf | N | [33 empty] | 0
C02400 | Finance and Programme reporting | Y | N |  | .pdf | N | [33 empty] | 0
C02500 | Information Delivery Plans (IDP) | Y | N |  | .pdf | N | [33 empty] | 0
C02600 | Information Delivery Plans Master (MIDP) (See CDDL item 56) | Y | N |  | .pdf | N | [33 empty] | 0
C02700 | Information Delivery Plans Task (TIDP) | Y | N |  | .pdf | N | [33 empty] | 0
C02800 | Lessons Learned | Y | N |  | .pdf | N | [33 empty] | 0
C02900 | LFE Record | Y | N |  | .pdf | N | [33 empty] | 0
C02950 | Outline Specification (See CDDL item 59) | Y | N |  | .pdf | N
C03000 | Photorealistic Visualisation Model(s) | Y | N |  | .pdf | N | [33 empty] | 0
C03100 | PM Tasking | Y | N |  | .pdf | N | [33 empty] | 0
C03200 | Pre-Tender Estimate | Y | N |  | .pdf | N | [33 empty] | 0
C03300 | Project Execution Plan (See CDDL item 30) | Y | N |  | .pdf | N
C03350 | Project Management Plan (See CDDL item 2) | Y | N |  | .pdf | N
C03400 | Risk Adjusted Schedule (10/50/90 % confidence) | Y | N |  | .pdf | N | [33 empty] | 0
C03500 | Risk and Opportunities Management Plan (See CDDL item 5) | Y | N |  | .pdf | N | [33 empty] | 0
C03600 | Programme (See CDDL item 3) | Y | N |  | .pdf | N | [33 empty] | 0
C03700 | Stakeholder Management Plan (See CDDL item 1) | Y | N |  | .pdf | N | [33 empty] | 0
C03800 | Stakeholder Profiles | Y | N |  | .pdf | N
C04100 | Transition Management Plan (See CDDL part 2 item 12) | Y | N |  | .pdf | N
C04200 | Updated Through Life (Project) Management Plan (TLMP) (PMP) | Y | N |  | .pdf | N | [33 empty] | 0
C04250 | Waste Management Plan (See CDDL part 2 item 10) | Y | N |  | .pdf | N
C04300 | Whole Life Cost Model (CDEL and RDEL) | Y | N |  | .pdf | N | [33 empty] | 0
C04350 | Whole Life Carbon Assessment (See CDDL item 57) | Y | N |  | .pdf | N
C04400 | Project/Programme Minutes/Reports | Y | N |  | .pdf | N
C04500 | Plans & Programmes | Y | N |  | .pdf | N
C04600 | Risk Registers (See CDDL item 6) | Y | N |  | .pdf | N
D0000 | Cost Management
D00100 | Cost Management Template | Y | N |  | .pdf | N | [33 empty] | 0
D00200 | Future and Current Contract Tracker (FACCT) | Y | N |  | .pdf | N
D00300 | IPE Template | Y | N |  | .pdf | N
D00400 | Project Management Plan | Y | N |  | .pdf | N
E0000 | Procurement & Commercial Management
E00100 | [reserved] | [38 empty] | 0
G0000 | Design
G00100 | Accessibility Assessment Form | Y | N |  | .pdf | N
G00200 | Assessment Study Report | Y | N |  | .pdf | N | [33 empty] | 0
G00300 | Building Services | Y | N |  | .pdf | N | [33 empty] | 0
G00400 | Design Documents, including the design lifecyle plan | Y | N |  | .pdf | N | [33 empty] | 0
G00500 | Design Freeze | Y | N |  | .pdf | N | [33 empty] | 0
G00600 | Feasibility Study Report | Y | N |  | .pdf | N | [33 empty] | 0
G00800 | Noise/Acoustic | Y | N |  | .pdf | N | [33 empty] | 0
G00900 | Structural | Y | N |  | .pdf | N | [33 empty] | 0
H0000 | Environmental
H00100 | Environmental Impact Assessment | Y | N |  | .pdf | N | [33 empty] | 0
H00300 | Pre-construction habitat survey (See CDDL part 2 item 56) | Y | N |  | .pdf | N | [33 empty] | 0
H00500 | Sustainability and Environmental Management Plan (See CDDL item 53) | Y | N |  | .pdf | N | [33 empty] | 0
H00600 | Sustainability Appraisal | Y | N |  | .pdf | N | [33 empty] | 0
H00700 | Sustainability and Resilience Plan (See CDDL item 33) | Y | N |  | .pdf | N
H00800 | Sustainability and Environmental Appraisal Tools (SEAT) Management Plan (See CDDL item 53) | Y | N |  | .pdf | N
I0000 | H&S
I00100 | CDM Audit Template | Y | N |  | .pdf | N
I00200 | CDM15 Principal Contractor Appointment | Y | N |  | .pdf | N | [33 empty] | 0
I00300 | CDM15 Principal Designer Appointment | Y | N |  | .pdf | N | [33 empty] | 0
I00400 | Health and Safety File (See CDDL part 2 item 53) | Y | N |  | .pdf | N | [33 empty] | 0
J0000 | Contract Man
J00100 | Acceptance Criteria | Y | N |  | .pdf | N | [33 empty] | 0
J00200 | Assessment Study Task Directive | Y | N |  | .pdf | N | [33 empty] | 0
J00300 | C+E Acceptance Process Document | Y | N |  | .pdf | N
J00400 | Change Control Form (SD Injection) | Y | N |  | .pdf | N | [33 empty] | 0
J00500 | Change Management Strategy | Y | N |  | .pdf | N | [33 empty] | 0
J00600 | Commercial Compliance Report | Y | N |  | .pdf | N | [33 empty] | 0
J00700 | Construction Contract Financial Close | Y | N |  | .pdf | N | [33 empty] | 0
J00900 | Contracts closure | Y | N |  | .pdf | N | [33 empty] | 0
J01000 | Defects rectification report | Y | N |  | .pdf | N | [33 empty] | 0
J01100 | Delivery Risk Review (schedule) | Y | N |  | .pdf | N | [33 empty] | 0
J01200 | Evaluation Criteria | Y | N |  | .pdf | N | [33 empty] | 0
J01300 | Evaluation Tool (AWARD) | Y | N |  | .pdf | N | [33 empty] | 0
J01400 | Feasibility Study Task Directive | Y | N |  | .pdf | N | [33 empty] | 0
J01500 | Invitation to Negotiate | Y | N |  | .pdf | N | [33 empty] | 0
J01600 | Master Data Assumption List (MDAL) | Y | N |  | .pdf | N | [33 empty] | 0
J01700 | Milestone Payment Schedule | Y | N |  | .pdf | N | [33 empty] | 0
J01800 | Pre-Handover Plan | Y | N |  | .pdf | N | [33 empty] | 0
J01900 | Project Brief | Y | N |  | .pdf | N | [33 empty] | 0
J02000 | Project Completion Report | Y | N |  | .pdf | N | [33 empty] | 0
J02100 | PSP Contract Award | Y | N |  | .pdf | N | [33 empty] | 0
J02200 | PSP Contract Award (PSP Workstage 6,7 & 8) | Y | N |  | .pdf | N | [33 empty] | 0
J02300 | PSP Financial Close | Y | N |  | .pdf | N | [33 empty] | 0
J02400 | PSP Mini-Competition Evaluation Report | Y | N |  | .pdf | N | [33 empty] | 0
J02500 | PSP Mini-Competition Evaluation Report (if not earlier competed) | Y | N |  | .pdf | N | [33 empty] | 0
J02600 | PSP Project Brief (PSP Workstage 6,7 & 8) (if not earlier competed) | Y | N |  | .pdf | N | [33 empty] | 0
J02700 | PSP Tender (successful bid) | Y | N |  | .pdf | N | [33 empty] | 0
J02800 | Request for Contract Action (RCA) | Y | N |  | .pdf | N | [33 empty] | 0
J02900 | Requirements of Response | Y | N |  | .pdf | N | [33 empty] | 0
J03000 | Defect completion report | Y | N |  | .pdf | N | [33 empty] | 0
J03100 | Technical Statement of Requirement (TSOR) | Y | N |  | .pdf | N | [33 empty] | 0
J03400 | TSP Appointment | Y | N |  | .pdf | N
J03500 | TSP Assesment | Y | N |  | .pdf | N
J03600 | Works Information Site Information documents | Y | N |  | .pdf | N | [33 empty] | 0
K0000 | Construction
K00100 | [reserved] | [38 empty] | 0
L0000 | Asset Man/Handover
L00100 | Aquatrine Service Locations Drawings | Y | N |  | .pdf | N | [33 empty] | 0
L00200 | Asbestos Management Plan | Y | N |  | .pdf | N
L00300 | Asset Drawing Register | Y | N |  | .pdf | N
L00400 | Asset Drawings (CAD) | Y | N |  | .pdf | N
L00500 | Asset Drawings (other) | Y | N |  | .pdf | N
L00600 | Asset Drawings (pdf and tif) | Y | N |  | .pdf | N
L00700 | Asset Register - Built (level 2, L3 & L4) | Y | N |  | .pdf | N
L00800 | Asset Register - Infrastructure (Level 2, L3 & L4) | Y | N |  | .pdf | N
L00900 | Asset related preventative cyclic maintenance and associated certification. | Y | N |  | .pdf | N
L01000 | BREEAM Certification (Including DREAM) | Y | N |  | .pdf | N
L01050 | Building Manual (See CDDL part 2 item 62) | Y | N |  | .pdf | N
L01100 | Collateral Warranties | Y | N |  | .pdf | N
L01200 | Commissioning and Testing Records | Y | N |  | .pdf | N
L01300 | Confined Spaces Register | Y | N |  | .pdf | N
L01400 | Construction and Design Management (CDM) & H&S Files | Y | N |  | .pdf | N
L01500 | Contract Risk Registers | Y | N |  | .pdf | N
L01600 | COSHH / MSDS | Y | N |  | .pdf | N
L01700 | Data archive registers / policy | Y | N |  | .pdf | N
L01800 | Data Dictionaries / ERDs / data models (logical & physical) | Y | N |  | .pdf | N
L01900 | Data Management records (inc filenaming conventions) | Y | N |  | .pdf | N
L02000 | Deleterious materials | Y | N |  | .pdf | N
L02100 | DESAR | Y | N |  | .pdf | N
L02200 | Digital Certificates / Encryption Keys / System Admin Pwds | Y | N |  | .pdf | N
L02300 | Discharge Consent | Y | N |  | .pdf | N
L02400 | Electrical Operations Register | Y | N |  | .pdf | N
L02500 | Electrical Switching Schedule | Y | N |  | .pdf | N
L02600 | Energy Performance Certificates | Y | N |  | .pdf | N
L02700 | Environmental Management System | Y | N |  | .pdf | N
L02800 | Equipment Stores Account | Y | N |  | .pdf | N
L03000 | Establishment Layout Drawing | Y | N |  | .pdf | N
L03100 | Establishment Policies | Y | N |  | .pdf | N
L03200 | Establishment Specific Task Schedule (ESTS) | Y | N |  | .pdf | N
L03300 | Establishment Standing Orders | Y | N |  | .pdf | N
L03500 | External Communications | Y | N |  | .pdf | N
L03600 | Fileplans for loose electronic files | Y | N |  | .pdf | N
L03700 | Financial Accounting | Y | N |  | .pdf | N
L03800 | Fire Safety Information (See CDDL part 2 item 54) | Y | N |  | .pdf | N
L03900 | Forward Additional Services Plan (FASP) | Y | N |  | .pdf | N
L04000 | Forward Land Management Services Plan (FLMSP) | Y | N |  | .pdf | N
L04100 | Forward Maintenance Register | Y | N |  | .pdf | N
L04200 | Fuel & Lubricants Account | Y | N |  | .pdf | N
L04300 | Gas Safety Management Plan | Y | N |  | .pdf | N
L04400 | GFE Schedule | Y | N |  | .pdf | N
L04500 | Ground Condition Reports | Y | N |  | .pdf | N
L04600 | Grounds Maintenance Drawings | Y | N |  | .pdf | N
L04700 | Guidance & Training | Y | N |  | .pdf | N
L04800 | Hazard Register | Y | N |  | .pdf | N
L04900 | Hazardous Waste Registration | Y | N |  | .pdf | N
L05100 | Investment Appraisals / Option Studies | Y | N |  | .pdf | N
L05200 | IT System Documentation | Y | N |  | .pdf | N
L05300 | Key Registers & Key Safe Combinations | Y | N |  | .pdf | N
L05400 | Land Quality Assessments | Y | N |  | .pdf | N
L05500 | Legionella Management Plan | Y | N |  | .pdf | N
L05600 | Legionella Risk Assessments | Y | N |  | .pdf | N
L05700 | Licences | Y | N |  | .pdf | N
L05900 | Log book | Y | N |  | .pdf | N
L05950 | Manufacturing and construction information (See CDDL part 2 item 55) | Y | N |  | .pdf | N
L06100 | Master Programme of Works | Y | N |  | .pdf | N
L06200 | Mechanical Systems Operating Register | Y | N |  | .pdf | N
L06300 | Meter readings | Y | N |  | .pdf | N
L06400 | Method Statements | Y | N |  | .pdf | N
L06500 | Miscellaneous & Consumables Stores Account | Y | N |  | .pdf | N
L06700 | O&M Manuals | Y | N |  | .pdf | N
L06800 | Ozone Deleting Gas Register | Y | N |  | .pdf | N
L06900 | Pest Control records | Y | N |  | .pdf | N
L07000 | Plant & Equipment Inspection records | Y | N |  | .pdf | N
L07100 | Plant & Equipment Register | Y | N |  | .pdf | N
L07200 | Practical Completion Certificate | Y | N |  | .pdf | N
L07300 | Programme of Outstanding Work | Y | N |  | .pdf | N
L07400 | Quality Management Plans (See CDDL item 4) | Y | N |  | .pdf | N
L07500 | Records of Legionella Control Measures | Y | N |  | .pdf | N
L07600 | Register of Authorising Engineers / Authorised Persons | Y | N |  | .pdf | N
L07700 | Register of Hard Copy Manuals | Y | N |  | .pdf | N
L07800 | Register of Official Establishment Photographs | Y | N |  | .pdf | N
L07900 | Register of PAT Testing | Y | N |  | .pdf | N
L08000 | Register of Portable Appliances | Y | N |  | .pdf | N
L08100 | Register of Restricted High Places | Y | N |  | .pdf | N
L08200 | Risk Assessment to determine frequency of tests | Y | N |  | .pdf | N
L08300 | Risk Assessments to determine inspection frequencies | Y | N |  | .pdf | N
L08600 | Safe Systems of Work (SSoW) and site wide risk assessments. | Y | N |  | .pdf | N
L08700 | Site Coordination Installation Design Authority (SCIDA) drawings | Y | N |  | .pdf | N
L08800 | Security records | Y | N |  | .pdf | N
L08900 | Service Register | Y | N |  | .pdf | N
L09000 | Site-wide Infrastructure Drawings | Y | N |  | .pdf | N
L09400 | Statement of Known Hazards aka Buried Services Drawings | Y | N |  | .pdf | N
L09500 | Statutory Signage Log | Y | N |  | .pdf | N
L09600 | Stores Accounting | Y | N |  | .pdf | N
L09700 | Systems Architecture | Y | N |  | .pdf | N
L10000 | Test Certificates | Y | N |  | .pdf | N
L10100 | Training Records | Y | N |  | .pdf | N
L10200 | Tree Management Drawings | Y | N |  | .pdf | N
L10300 | Utilities management | Y | N |  | .pdf | N
L10400 | Waste transfer certificates | Y | N |  | .pdf | N
L10500 | Water Abstraction Licence | Y | N |  | .pdf | N
L10600 | WELL Certification | Y | N |  | .pdf | N
M0000 | Construction
M00100 | RFI | Y | N |  | .pdf | N | [33 empty] | 0
N0000 | Assurance
N00500 | Compliance documents and certification | Y | N |  | .pdf | N | [33 empty] | 0
N00700 | Design Compliance Review | Y | N |  | .pdf | N | [33 empty] | 0
N00900 | Fire Safety Acceptance Certificate | Y | N |  | .pdf | N | [33 empty] | 0
N01000 | Gateway Review | Y | N |  | .pdf | N | [33 empty] | 0
N01200 | Government Soft Landings requirements | Y | N |  | .pdf | N | [33 empty] | 0
N01800 | Post Operation Evaluation (1, 2 & 3 Years) | Y | N |  | .pdf | N | [33 empty] | 0
N01900 | Post Project Evaluation | Y | N |  | .pdf | N | [33 empty] | 0
N02200 | Risk Potential Assessment | Y | N |  | .pdf | N | [33 empty] | 0
N02300 | Security Policy | Y | N |  | .pdf | N | [33 empty] | 0
N02400 | Works Completion Certificates | Y | N |  | .pdf | N | [33 empty] | 0
14 sections & 228 rows
Note on H8: N/F Native Format files required - if the authored often propratory file is required to be delivered
Note on I8: Ass Assurance item - Yes files should only be delivered if requested by the EIM, N files should be delivered, S files should be Shared for Information only - non contractural.
Note on K8: O/F Open File format required
Note on L8: 3DMF 3D Model Federation - required as part of an additioanal federated deliverable

## 4. PLQ
Defence Infrastructure Organisation PLAIN LANGUAGE QUESTIONS
| Gway |  | Plain Language Questions | DelRefs | Comment | PLQ Answered
Gateway 0 | Gway 0 | G0:1
| Gway 0 | G0:2
| Gway 0 | G0:3
| Gway 0 | G0:4
| Gway 0 | G0:5
| Gway 0 | G0:6
| Gway 0 | G0:7
| Gway 0 | G0:8
| Gway 0 | G0:9
Gateway 1 | Gway 1 | G1:1
| Gway 1 | G1:2
| Gway 1 | G1:3
| Gway 1 | G1:4
| Gway 1 | G1:5
| Gway 1 | G1:6
| Gway 1 | G1:7
| Gway 1 | G1:8
| Gway 1 | G1:9
Gateway 2 | Gway 2 | G2:1 | Has the BIM Maturity Assessment Tool (BMAT) been refreshed since the last GWR and what is the current BMAT score? | Evidence that the BMAT has been completed.
| Gway 2 | G2:2 | Has the information from this phase been published into the Product Information Management Common Data Environment (PIM CDE) / Asset Information Management Common Data Environment (AIM CDE)? | Evidence of information being published and document the location here.
| Gway 2 | G2:3 | Has the Information Delivery Plan (IDP) (contained as an annex within the Employers Information Requirements (EIR)) been updated for the next project phase? | Evidence that the updated IDP is prepared for the next project stage.
| Gway 2 | G2:4 | Has a GSL Project Champion been regularly engaged? | Evidence of engagement with GSL Project Champion.
| Gway 2 | G2:5 | Has an Information Manager been engaged? | Evidence of engagement with an Information Manager
| Gway 2 | G2:6 | Has the architectural concept and associated outline specification been statisfactorily delivered? | Evidence of design progress
| Gway 2 | G2:7 | Has engagement with Stakeholders through working groups been staisfactory? Has the GSL concept been embraced? | Evidence that the GSL concept and the engagement of the Authority and its representatives has been acknowledged
| Gway 2 | G2:8 | Have all the planning documents been delivered and do they provide a suitable framework for the development of the Project? | Evidence of project planning and management of deliverables/time
| Gway 2 | G2:9 | Has evidence been presented supporting the level of building sustainability and resilience in the architectural concept? | Evidence of building resilience and carbon netzero
Gateway 3 | Gway 3 | G3:1 | Has the development of the Spatially Coordinated design from the Architectural concept been completed and accepted? | Evidence of progress and process
| Gway 3 | G3:2 | Has the outline specification been updated to reflect the Spatially Coordinated design? | Evidence of systematic approach
| Gway 3 | G3:3 | Have Change Control procedures been initiated? | Evidence of Config Control planning
| Gway 3 | G3:4 | Have sufficient design studies and engineering analysises been completed to test the design? | Evidence of process and development cycle
| Gway 3 | G3:5 | Has a fully costed proposal been received for RIBA stages 4, 5 and 6? | Evidence of system management and meeting delivery targets
| Gway 3 | G3:6 | Has performance to schedule been satisfactory? | Evidence of project management process and skills
| Gway 3 | G3:7 | Does the level of Project risk remain within acceptable tolerances? | Continued business justification
| Gway 3 | G3:8 | Has an LFE review been completed | Evidence of process and application of best practice
|  | G3.9 | Is the design aligned to government policy on carbon netzero and resilience? | Evidence of innovation leading to policy alignment
| Gway 3 | G3:10 | Has a strucural engineering certification been completed? | Evidence of the BRCS application
Gateway 4 | Gway 4 | G4:1 | Has a Construction Phase Plan been delivered? | Evidence of legal requirement met
| Gway 4 | G4:2 | Have the construction and manufacturing plans been finalised through design review? | Evidence pf good preparation
| Gway 4 | G4:3 | Have the final specifications been completed, including the OR2 and CIS Part C specifications? | Evidence of design input and finalisation with the Authority
| Gway 4 | G4:4 | Have the GSL working groups completed their input as part of the design process? | Evidence of GSL application and acceptance of the design by Stakeholders
| Gway 4 | G4:5 | Are plans for integration of the building systems complete? | Evidence of the comprehensive approach to project planning
| Gway 4 | G4:6 | Does the level of Project risk remain within acceptable tolerances? | Continued business justification
| Gway 4 | G4:7 | Have the management plans for construction been delivered and agreed? | Evidence of satisfactory project planning and assurance of construction process and planning
| Gway 4 | G4:8 | Has the PCIP been updated to reflect Project developments? | Health and Safety review of construction
| Gway 4 | G4:9
Gateway 5 | Gway 5 | G5:1 | Has the Building Manual including Health and Safety File and Fire Safety Information been delivered? | Legal requirement
| Gway 5 | G5:2 | Has the Practical Completion certificate been delivered with the associated Defect List? | Legal requirement
| Gway 5 | G5:3 | Has construction quality been properly assessed and was it satsifactory? | Evidence of the quality reporting process and level of quality
| Gway 5 | G5:4 | Has the required training been delivered to the FM organisation? | Evidence of the GSL process working correctly
| Gway 5 | G5:5 | Has the accpetance process planning and the TMP been delivered as required? | Evidence of transition management
| Gway 5 | G5:6 | Were the construction reports delivered as requested? | Evidence of project planning and information exchange
| Gway 5 | G5:7 | Have the building logistics been prepared as required by the contract? | Evidence of project planning and building supportability
| Gway 5 | G5:8 | Did any H&S issues arise during construction and were any residual issues identified to the Authority? | Evidence of construction management best practice
| Gway 5 | G5:9 | Was commissioning of the building system satisfactory? | Evidence of process and interface management
Gateway 6 | Gway 6 | G6:1 | Was defect identification, sentencing, rectification and sign-off completed as requried? | Evidence of the defect reporting process
| Gway 6 | G6:2 | Has the Final Completion certificate been accepted? | Evidence of process closure
| Gway 6 | G6:3 | Have any warranty issues been identified and how were they resolved? | Evidence of how the handover process is working
| Gway 6 | G6:4 | Have the FM teams been able to takeover the buidling and work without hindrance or issue? | Evidence of how the handover process is working
| Gway 6 | G6:5 | Has a POE been completed? | Evidence of best practice capture
| Gway 6 | G6:6 | Has an LFE review been completed? | Evidence of best practice capture
| Gway 6 | G6:7 | Has the Building design and construction contract closed? | Evidence of closure
| Gway 6 | G6:8
| Gway 6 | G6:9
Gateway 7 | Gway 7 | G7:1
| Gway 7 | G7:2
| Gway 7 | G7:3
| Gway 7 | G7:4
| Gway 7 | G7:5
| Gway 7 | G7:6
| Gway 7 | G7:7
| Gway 7 | G7:8
| Gway 7 | G7:9

## 5. MIDP
Defence Infrastructure Organisation SUPPLIER MASTER INFORMATION DELIVERY PLAN | [9 empty] | By: | [5 empty] | Files shall be referenced as below, including the IDP DelRef increment e.g. A00100_1 |  | DelRef increment calculations
Date:
Add project code to 2. PIR
Project Number | Originator | Volume | Location | Type | Role | Document Number | Status | Rev | IDP Del Ref | Stage | LOD | LOI | Title | File Extension | DelDate | COBie Document.Name | COBie Document.File | C1 | C2 | DelRef_#
[9 empty] | A00200 | [8 empty] | A00200 | 1 | A00200_1
Note; to add further rows, select rows> copy >insert copied cells
Note on M5: Del Refs need be assigned within 3. IDP before they can be selected
Note on T5: Cells will populate automatically once the Yellow fields are populated

## 6. PickList
Defence Infrastructure Organisation PICKLISTS
Roles [R] Organisations [O] |  | Volume / Location |  | Level |  | Type |  | Role(Discipline) |  | Status |  | Rev | DelRef | Stg | LOD | LOI | Delivery Formats
DIO | Project Manager [R] |  |  | 00 | Ground | AN | AN Announcement / Press release/Newsletter | A | Architect | A0 | Published Strategy | Manual | Dynamic | DI0 | D0 | L0 | .sup | sup Supplier Assigned
PSP | Principle Service Provider [R] | KE | Kitchen Extension | RF | Roof | AP | AP Application for payment / invoice | B | Building Surveyor | A1 | Published Brief | Entry | List | DI1 | D1 | L1 | .ags | ags Association of Geotechnical and Geoenvironmental Specialists AGS4 Addendum 3
PPD | RM [R] | OE | OPS Extension | FN | Foundation | AR | AR Assurance | C | Civil | A2 | Published Concept |  | based on | DI2 | D2 | L2 | .docx | doc doc/docx
PAG | BC Working Group [R] | SA | Sleeping Accommodation | XX | Omitted | AS | AS Assessment | D | Drainage & Pipelines | A3 | Published Definition |  | IDP | DI3 | D3 | L3 | .dwg | dwg dwg/dgn
CCONS | Cost Consultant [R] | SC | Storage Compound | ZZ | Multiple Locations | AU | AU Audit | E | Electrical | A4 | Published Design |  | selections | DI4 | D4 | L4 | .gml | gml OpenGIS Geography Markup Language Encoding Standard
CDM | CDMC [R] | VG | Vehicle Garage |  |  | AV | AV Animation video/audio | F | Facilities Management | A5 | Published Build |  |  | DI5 | D5 | L5 | .ifc | ifc Industry Foundation Class (ifc)
COM | Commercial [R] | XX | Omitted |  |  | BQ | BQ Bill of Quantities | G | Geographic & Land Surveyor | A6 | Published Handover |  |  | DI6 | D6 | L6 | .lml | lml LandXML www.landxml.org
CONS | Consultant [R] | ZZ | Multiple Locations |  |  | CA | CA Calculation(s) | H | Heating and Ventilation (HVAC) | A7 | Published Operation |  |  | DI7 | D7 | L7 | .ntv | ntv Native Format
CONT | Contractor [R] |  |  |  |  | CD | CD Contract | I | Interior Designer | B0 | Published Strategy | [5 empty] | .pdf | pdf ISO Portable Document Format
DFR | DFRMO [R] |  |  |  |  | CE | CE Compensation Event | J | Project Manager | B1 | Published Brief | [5 empty] | .rvt | Autodesk Revit file
EST | Estates Consultant [R] |  |  |  |  | CN | CN Change notice | K | Client | B2 | Published Concept | [5 empty] | .u3d | u3d PDF 3D Industry Forum
LEG | Legal Consultant [R] |  |  |  |  | CO | CO Correspondence | L | Landscape Architect | B3 | Published Definition | [5 empty] | .wml | wml OpenGIS WaterML
PMO | [R] |  |  |  |  | CP | CP Budget / Cost Plan | M | Mechanical | B4 | Published Design | [5 empty] | .xlsx | xls xls/xlsx
PAG | Project Assurance Group [R] |  |  |  |  | CR | CR Clash Rendition | N | Network Modelling | B5 | Published Build | [5 empty] | .shpx | ESRI shapefile and components
SICONT | Site Investigation Contractor [R] |  |  |  |  | CS | CS Conversation record / Telephone record | P | Public Health / Safety | B6 | Published Handover | [5 empty] | .gdb | ESRI Geodatabase File
STA | Statutory and Local Authority [R] |  |  |  |  | CT | CT Certificate | Q | Quantity Surveyor | B7 | Published Operation | [5 empty] | .mdb | ESRI Perosnal Geodatabase file
TFM | SD TFM [R] |  |  |  |  | CV | CV Curriculum Vitae | S | Structural | S1 | Shared for coordination
USR | End User Representative [R] |  |  |  |  | DA | DA Data sheet | T | Town and Country Planning | S2 | Shared for information
ACL | Acoustic Consultants [O] |  |  |  |  | DB | DB Database | W | Contractor | S3 | Shared for client review, comment and/or acceptance
AEC | AECOM [O] |  |  |  |  | DR | DR Drawing | X | Subcontractor | S4 | Shared for stage approval
ARU | ARUP [O] |  |  |  |  | DS | DS Design statement | Y | Specialist Designer
ATK | Atkins (O'Seas) [O] |  |  |  |  | DT | DT Document Transmittal Note | Z | General (non-disciplinary)
BAB | Babcock International Group [O] |  |  |  |  | ES | ES Estimate
BAE | BAE Systems [O] |  |  |  |  | EW | EW Early warning notice
BAL | Balfour Beatty [O] |  |  |  |  | FM | FM Federated Model
GAL | Galliford Try [O] |  |  |  |  | FN | FN File note
GLD | Gleeds [O] |  |  |  |  | GU | GU Guide
HEN | Henry Brothers [O] |  |  |  |  | HS | HS Health & Safety File
HYD | Hydrock [O] |  |  |  |  | IE | IE Information Exchange (COBie)
INT | Interserve [O] |  |  |  |  | IS | IS Instruction (inc site instructions etc)
JAC | Jacobs [O] |  |  |  |  | IT | IT Inspection and test plan
KIE | Kier [O] |  |  |  |  | JV | JV Job vacancy posting / Job description
LEN | Lendlease [O] |  |  |  |  | KP | KP Key performance indicators
MAC | Mace |  |  |  |  | LT | LT Letter
MOR | Morgan Sindall / Baker Hicks [O] |  |  |  |  | M1 | M1 Modelled Surveys (from point clouds etc) Reference
MMD | Mott MacDonald [O] |  |  |  |  | M2 | M2 2D Model
RAM | Ramboll [O] |  |  |  |  | M3 | M3 3D Model
RID | Ridge (O'Seas) [O] |  |  |  |  | M4 | M4 4D Model
TBC | Bush Consultancy [O] |  |  |  |  | M5 | M5 5D Model
VOL | Volker Fitzpatrick [O] |  |  |  |  | MA | MA Materials appraisal form
WAT | Wates [O] |  |  |  |  | MC | MC Charter / Mission statement
WDC | Willmott Dixon [O] |  |  |  |  | MD | MD Model (non-CAD)
WOO | Wood PLC [O] |  |  |  |  | MI | MI Minutes/Action notes
WYG | White Young Green [O] |  |  |  |  | MO | MO Memorandum
SBR | Scott Brownrigg |  |  |  |  | MP | MP Map
TPA | TPA |  |  |  |  | MR | MR Model Rendition
ADS | Amey Defence Services |  |  |  |  | MS | MS Method statement
ARC | Arcadis |  |  |  |  | MX | MX ESRI MDX
TTT | Tetratech |  |  |  |  | NC | NC Non-conformance report
[6 empty] | OC | OC Organisation chart
[6 empty] | OM | OM Operations & Maintenance (O&M)
[6 empty] | PC | PC Policy
[6 empty] | PG | PG Programme
[6 empty] | PH | PH Photograph(s any media)
[6 empty] | PL | PL Plan eg Execution Plan
[6 empty] | PO | PO Purchase order
[6 empty] | PP | PP Presentation
[6 empty] | PR | PR Progress Report
[6 empty] | PT | PT Permit
[6 empty] | QU | QU Quotation
[6 empty] | RA | RA Risk assessment
[6 empty] | RD | RD Room or Requirements Data Sheet
[6 empty] | RE | RE Register eg asset register
[6 empty] | RF | RF Request for information
[6 empty] | RP | RP Report
[6 empty] | RR | RR Risk Register
[6 empty] | RV | RV Review record
[6 empty] | SC | SC Schedule eg manhole schedule
[6 empty] | SE | SE Security
[6 empty] | SG | SG Strategy
[6 empty] | SI | SI Site Investigation
[6 empty] | SK | SK Sketch
[6 empty] | SL | SL Snagging List
[6 empty] | SN | SN Site Inspection
[6 empty] | SO | SO Scope of work
[6 empty] | SP | SP Specification
[6 empty] | ST | ST Standard
[6 empty] | SU | SU Survey
[6 empty] | TD | TD Tender document
[6 empty] | TN | TN Technical note
[6 empty] | TO | TO Task order
[6 empty] | TP | TP Template
[6 empty] | TQ | TQ Technical query
[6 empty] | VO | VO Variation Order
[6 empty] | VS | VS Visualisation
[6 empty] | WO | WO Work Order
|  | END - see notes below | [5 empty] | END - see notes below | [5 empty] | END - see notes below
Notes; | The Name lists extend to the highlighted (yellow) areas to extend the worksheet amend the lists accordindly [Formulas>Name Manager]
To review the Name list areas, select the Name from the Name Box as below

## 7. PickList (2) (hidden)
[18 empty] | Dynamic list for MIDP DelRef data validation list |  | #REF! | #REF! | 1
Defence Infrastructure Organisation Supplier Master Information Delivery Plan | [9 empty] | By: | [8 empty] | #REF! | #REF! | #REF!
[10 empty] | Date: | [8 empty] | #REF! | #REF! | #REF!
Add project code to 2. PIR | [18 empty] | #REF! | #REF! | #REF!
Ref | Org | Vol | Level | Typ | Rol | Number | Status | Rev | Del Ref | Stage | LOD | LOI | Doc Title | File Ext. | DelDate | COBie Document.Name | COBie Document.File |  | #REF! | #REF! | #REF!
| WDC | SA | XX | DR | W | 0001 | S2 | P01 | A00100 | DI1 | D0 | L1 | GA Plan | .pdf |  |  |  |  | #REF! | #REF! | #REF!
| WDC | SA | XX | M3 | W | 0008 | S2 | P03 |  | DI2 | D2 | L2 | MODEL | .lml | [5 empty] | #REF! | #REF!
| DIO | SC | FN | AP | A | 9000 | A5 | C01 |  | DI3 | [9 empty] | #REF! | #REF!
| DIO | [7 empty] | A00200 | [10 empty] | #REF! | #REF!
| DIO | [18 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[9 empty] | A00100 | [10 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[19 empty] | #REF! | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[19 empty] | #REF! | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[19 empty] | #REF! | #REF! | #REF!
[19 empty] | #REF! | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[19 empty] | #REF! | #REF! | #REF!
[19 empty] | #REF! | #REF! | #REF!
[19 empty] | #REF! | #REF! | #REF!
[19 empty] | #REF! | #REF! | #REF!
[19 empty] | #REF! | #REF! | #REF!
[19 empty] | #REF! | #REF! | #REF!
[19 empty] | #REF! | #REF! | #REF!
[19 empty] | #REF! | #REF! | #REF!
[19 empty] | #REF! | #REF! | #REF!
[19 empty] | #REF! | #REF! | #REF!
[19 empty] | #REF! | #REF! | #REF!
[19 empty] | #REF! | #REF! | #REF!
[19 empty] | #REF! | #REF! | #REF!
[19 empty] | #REF! | #REF! | #REF!
[19 empty] | #REF! | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[19 empty] | #REF! | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[19 empty] | #REF! | #REF! | #REF!
[20 empty] | #REF! | #REF!
[19 empty] | #REF! | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[19 empty] | #REF! | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[19 empty] | #REF! | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[19 empty] | #REF! | #REF! | #REF!
[19 empty] | #REF! | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[19 empty] | #REF! | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[19 empty] | #REF! | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[19 empty] | #REF! | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[19 empty] | #REF! | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[19 empty] | #REF! | #REF! | #REF!
[20 empty] | #REF! | #REF!
[19 empty] | #REF! | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[19 empty] | #REF! | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[19 empty] | #REF! | #REF! | #REF!
[19 empty] | #REF! | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[19 empty] | #REF! | #REF! | #REF!
[19 empty] | #REF! | #REF! | #REF!
[19 empty] | #REF! | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[19 empty] | #REF! | #REF! | #REF!
[19 empty] | #REF! | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[19 empty] | #REF! | #REF! | #REF!
[19 empty] | #REF! | #REF! | #REF!
[19 empty] | #REF! | #REF! | #REF!
[19 empty] | #REF! | #REF! | #REF!
[20 empty] | #REF! | #REF!
[19 empty] | #REF! | #REF! | #REF!
[20 empty] | #REF! | #REF!
[19 empty] | #REF! | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[19 empty] | #REF! | #REF! | #REF!
[20 empty] | #REF! | #REF!
[19 empty] | #REF! | #REF! | #REF!
[19 empty] | #REF! | #REF! | #REF!
[19 empty] | #REF! | #REF! | #REF!
[19 empty] | #REF! | #REF! | #REF!
[19 empty] | #REF! | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[19 empty] | #REF! | #REF! | #REF!
[19 empty] | #REF! | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!
[20 empty] | #REF! | #REF!