- SCHEDULE O

- EXIT PLAN

Exit Plan

The draft Exit Plan is contained at the Appendix to this Schedule O. It shall be agreed with the Authority within six (6) months of Agreement Commencement Date and reviewed on an annual basis.

The Equinox Consortium shall maintain the Exit Plan such that it, as a minimum, includes:

all the necessary information, assets, management arrangements and responsibilities required:

for a controlled Contract exit where there is no transfer of service provision to a replacement provider; and for the transition of Service provision to a replacement provider;

a commitment regarding the continued presence of Key Personnel as the Senior Responsible Owners of the Exit Plan;

a commitment to restrict movement of Engaged Personnel in the final six (6) Months of the Term to an absolute minimum; and

an obligations matrix that tracks Contractor obligations against the Agreement, inclusive of all continuing obligations.

Exit Strategy

The Equinox Exit Strategy is aligned to the Authority requirements. A summary of the strategy and Contractor Obligations on exit is given in the table at the end of this Schedule.

Equinox is focused to provide DE&S with a legacy of capability across the PM, PC and ILog Functions, across the Director, General Programmes area and in support of P3M and PMO best practice. This will influence our behaviour at each level of exit. Our approach towards exit and management of a legacy position will also be guided by the ‘Obligation to Assist’ principle irrespective of whether there is a transition of service to a replacement provider or not. This means that we will provide (where it is within our scope or control) all necessary information, assets, management arrangements and responsibilities required for a controlled Contract exit. Such information, assets, management arrangements and responsibilities will be agreed with the Authority on notice of an exit.

Once an Exit Date has been notified, Equinox will maintain the continued presence of our Key Personnel as the senior responsible owners of our exit plan during an agreed transition period or close down process. Equinox will also seek to restrict movement of Engaged Personnel in the final six (6) months of the Term to an absolute minimum. Our aim will be to accelerate learning in the event of a new provider and ensure that our lasting legacy is resilient and endures in the best interests of DE&S.

We will track our obligations against the Agreement through to exit, including any continuing obligations (e.g., Task Orders that are required to complete beyond the Exit Date) and detail the critical activities, learning, systems and processes necessary for the effective operation of the Programme in a ‘handover learning document’. We will work collaboratively with any new provider to ensure that they understand the content of the document and benefit from our learning during the transition period.

Managing a Legacy Position

The delivery of PDP results in an organisation that is required to grow rapidly to support the early kick-off of the Agreement, and then move to a position where DE&S owns and can control the knowledge, thus reducing the risk and reliance upon a third party. This is a normal position that those companies forming Equinox find themselves in on a global scale. It is, therefore, natural for us to want to leave our clients with a lasting legacy. The creation of a legacy position means:

We have created capability within DE&S that was not in place when the PDP commission started

We have created the ability for DE&S to build capacity as and when required in the future

We have consolidated the many routes to market and helped DE&S Director, General Programmes area simplify delivery of its services to its clients

We have complemented the DE&S ‘Ways of Working’; and have helped embed LFE and new

(external) best practices in the culture of providing Programme services to projects

We have a ready-made blue print for the future operation of a long-term PDP service contract. To assure that these legacy success factors are achieved, we have adopted an approach that defines and creates relationships that are:

      - Clear at the outset what the triggers are for any transition period.  As defined within ISO:44001 (collaboration), we will always maintain an agreed Exit Plan, with clear triggers and actions around de-mobilisation and exit so that all understand their obligations

      - Transparent in their structure to assess competence of the organisation to take on the roles when shifted across.

Exit of Individuals

We employ great people, and will use our Integrated Technical Competency Framework to ensure we have the right competency in the right position, motivated the right way to deliver excellent performance. We use communities of practice to connect our people together and to share knowledge so that DE&S will always be accessing the full combined knowledge of our consortium. It is recognised that there are numerous contractual paths that could lead to an engaged person’s exit from Equinox.  In general, our approach to supporting the exit of personnel will be:

Managing Churn.  Inevitably, there will be some churn of our people; we will work to manage this in the combined best interests of DE&S and our resource, aiming to achieve 90% resource retention (per annum) and avoid removing people from delivering services before their task is completed. We anticipate that our MOD experienced resource pool will continue to grow through the PDP service. We will seek to ensure that DE&S benefit from this experience by creating career paths for individuals within the PDP context that ensure they can progress, which in turn will reduce churn.

Bespoke/Key Positions.  Certain CDT roles (in particular, Key Personnel and specifically the Equinox SRO) and some resource roles (where the Authority may have requested a specific person) are considered key positions and exit of personnel will be managed with additional effort to minimise disruption to DE&S. We will ensure strong relationships and a consistency in delivery approach, that grows across DE&S over the duration of the contract. However also to prevent the risk of single-point-of-failure from having a single key individual, for every person in a key position, specific exit/succession plans will be agreed with the JPMO (and respective Authority Demanders where applicable) as soon as the need becomes apparent. Subject to programme/task duration there will be some churn, but the anticipation is that this will always be managed on a case-by-case basis with DE&S to ensure continuity of service.

Tasking Order Exit

For each Tasking Order, at the point of completion or termination, we will undertake a series of Task Reviews that will focus on continuous improvement, capturing and sharing lessons learned, developing case studies of best practice and benefits delivered and embedding a legacy of an enhanced capability within DE&S. It is recognised that there are numerous contractual paths that could lead to Task termination.

Our approach to Task Reviews and Close Out is outlined below:

Task Review: Equinox will capture learning from its team during Service delivery, through interviews and monthly reports. As agreed from time to time with DE&S we will also engage with Clients to gauge their opinion and understand how we are meeting requirements or could improve. Where improvements are identified (through our LFE process), they will be captured within our Continuous Service Delivery Improvement Plan and responsibility for action assigned and tracked within the JPMO according to the LFE/Continuous Improvement process.

Task Close Out: Prior to the end of each Task, Equinox will ensure a series of cessation activities are completed by our Personnel. This will be designed to ensure retention and transfer of knowledge to DE&S to ensure a lasting legacy. This will include the completion and filing and storing of information, post placement reviews and debriefing, all relevant knowledge and LFE captured and transferred to DE&S (including the deletion of DE&S information on any other medium or media) and confirmation in writing to DE&S that this has been completed. Similar to Task Review, where any opportunities for improvements are identified (through our LFE process), then they will be captured within our Continuous Service Delivery Improvement Plan and responsibility for action assigned and tracked within the JPMO according to the LFE / Continuous Improvement process.

Obligations

Upon award of contract, Equinox will establish an obligations matrix to track all obligations against the Agreement. A draft obligations matrix can be found at the end of this Appendix.  Our focus on this will flow through each Tasking Order and the emphasis will increase as they approach conclusion and/or we approach Exit. This is so that we leave a lasting legacy and to make certain that no benefits are lost. Our obligations matrix will include all continuing obligations, and be prepared for handover to DE&S upon Exit.

The obligations matrix will be owned by the Equinox SRO, with support from Equinox Contract Lead and Task Co-ordinator, reviewed quarterly.

Once generated, the obligations matrix will be included into the PgMP.

Benefits Tracking

Benefits will often be realised well beyond the closure of a particular Task. A summary of these will be developed for each individual Task. This will maintain and define the necessary, and associated, activities to achieve the release of benefits for all Approved Tasking Orders. These will be owned by the Task Co-ordinator, reviewed on a monthly basis and included formally with this PgMP.

Contract Close

Building upon Equinox’s approach to provide DE&S with a lasting legacy of capability, we will embrace fully our ‘Obligation to Assist’ during contract close to ensure a business as usual approach is maintained and ensure a smooth transition during our departure. This will ensure an orderly and efficient transition of all activities undertaken by Equinox to DE&S. We will maintain our Exit Plan to ensure that we can at all times satisfy our obligations, agreeing this Exit Plan with the Authority within 3 months of Contract Award and then formally reviewing this on an annual basis and updating this 12 months prior to the end of any potential Contract Term.

| Scenario | People | Information | Performance | Contract | Commercial |
| --- | --- | --- | --- | --- | --- |
| Tasking Order Completion | - Redeployment to new task. - Return to Equinox (bench resource) - Wider Replacement | - Document Transfer - State Deliverables - Key contacts - Equipment/software - IP register - Skills Transfer | - Deliverables Review - Performance Feedback - Shared Learning - Personal Feedback | - Tasking Order Deliverables - Milestone Review | - Close out financial payments in line with rate card - Close tasking Order - Audit as required |
| Contract/Exit Term | - Staff Communications - TUPE to DE&S or other - Redeployment to Equinox partners - Transition Plan | - Full record transfer - All deliverables - Key Contacts - Equipment/software - IP register - Skills Transfer | - KPI Assessment - Reflect exit targets - Commitment to restrict engaged | - 12 month notice period - Maintain obligations matrix | - Exit planning at contractor cost - Financial commitments and close out forecasts - Monthly fee reports - Exit payable - 6 month retention |
| Termination at Will - Contract | - Staff Communications - TUPE to DE&S or other - Redeployment to Equinox partners | - Full record transfer - All deliverables - Equipment/software - IP register - Align to objectives matrix | - Reconcile KPIs - Assessment for period/service completed | - 1 month notice period | - Payment of fees incurred and Travel and Subsistence costs - No loss of earning |
| Termination at Will - Tasking Order | - As per Tasking Order completion | - As per Tasking Order completion | - Reconcile KPIs - Assessment for period/service completed | - Resource: 1 day notice period - Tasking Order: 5 days’ notice period | - Payment of fees incurred and Travel and Subsistence costs - Driven by Tasking Order Deliverables |

PDP ITN Schedules H (Personnel) and O (Exit Plan).

As highlighted in the PDP ITN Schedule H.

As highlighted in the PDP ITN Schedule C.